## Proposal list
# | Proposal Title | Approval Status | IRB required? | Current activity Completion-Closure plan/timeline | Date Updated | PI Affiliation | Collaborators /Co-Investigators | Comment
1 | Viral limit of detection for diagnosis of chronic HCV infection | Approved | YES | Received NCDC IRB approval; has BUMC IRB approval. Data use agreement revised and sent back to the PI for endorsement. Data use agreement sent to the NCDC co-investigator to initiate procedures leading to the signing of the document. PI will gain access to the requested dataset only after Data Use agreement is signed | 2017-05-15 | Dr. J. Morgan Freiman, Boston University Medical Center | Irina Tskhomelidze, Tengiz Tsertsvadze, Nikoloz Chkhartishvili, George Kamkamidze, Maia Tsereteli, Mamuka Zakalashvili, CDC
2 | Assessment of the national hepatitis C elimination program: treatment outcomes and associated factors | Approved | NO | Manuscript draft is ready; modified data analysis conducted by CDC per request of the lead authors | 2017-05-15 | Dr. Tengiz Tsertsvadze, IDACIRC | Tengiz Tsertsvadze, Amiran Gamkrelidze, Akaki Abutidze, Nikoloz Chkhartishvili, George Kamkamidze, David Metreveli, Irina Tskhomelidze, Lia Gvinjilia, Muazzam Nasrullah, Francisco Averhoff
3 | High sustained viral response among HCV genotype 3 patients with advanced liver fibrosis - real-world data of HCV elimination program in Georgia | Approved | NO | Manuscript circulated among co-authors. Comments receveived. to be submitted to the journal of Virology | 2017-05-15 | Dr. Maia Butsashvili, Dr. George Kamkamidze, HRU/NeoLab | Maia Butsashvili, Lia Gvinjilia, George Kamkamidze, David Metreveli, Shorena Dvali, Tamar Rukhadze, Amiran Gamkrelidze, Muazzam Nasrullah, Juliette Morgan, Francisco Averhoff
4 | Long-term health outcome among HCV patients with advanced liver fibrosis treated through HCV Elimination Program in Georgia | Approved | YES | Revised proposal submitted to the CDC Foundation. NG initiated contract setup. Georgian IRB approval is in place. Submission to go to CDC IRB | 2017-05-15 | Dr. Maia Butsashvili, Dr. George Kamkamidze, HRU/NeoLab | Maia Butsashvili, George Kamkamidze, Representatives of US CDC (to be defined by CDC); Amiran Gamkrelidze, 1 researcher from each of the following clinics, 1 representative of MOH Hepa; ID hospital, Mrcheveli
5 | Genetic characteristic of hepatitis C virus in Georgia: implications for hepatitis C elimination program | N/A | N/A | Not Applicable | N/A | Dr. Tengiz Tsertsvadze, IDACIRC | N/A
6 | Defining the role of Ribavirin in treatment naive patients with chronic Hepatitis C recombinant genotype 2k/1b infections | N/A | N/A | Not Applicable | N/A | Dr. Jaba Zarkua, Clinic Mrcheveli | N/A
7 | Simplified diagnostics and monitoring of hepatitis C infected patients in rural primary care settings using newly approved pan-genotypic antiviral therapy—a pilot study in the country of Georgia | Approved | TBD | TBD | 2017-05-15 | Dr. Muazzam Nasrullah, CDC | Information to be provided by the PI
8 | Xpert HCV VL Performance Evaluation | Approved | YES | Contract between Cepheid and NCDC/OST site to be signed in near future. Devices to be shipped. NCDC IRB and Ge government approval in place. | 2017-05-15 | Dr. Maia Alkhazashvili, NCDC | Ekaterina Adamia, Akaki Abutidze, Marika Karchava, George Kamkamidze, Jaba Zarkua, Maia Alkhazashvili, Beth Skaggs, Jan Drobeniuc
9 | Effectiveness of ledipasvir/sofosbuvir based regimens in patients with hepatitis C virus genotype 1, 2, 3 and 4 infection and factors associated with treatment outcomes within Georgian national hepatitis C elimination program | Approved | NO | Filled original table shells provided to the PI in late Februrary, 2017. Data analysis should be modified to include 2 year dataset as stated in the proposal #24. Merged with the proposal #24. | 2017-05-15 | Dr. Tengiz Tsertsvadze, IDACIRC | Tengiz Tsertsvadze, Nikoloz Chkhartishvili, Lali Sharvadze, Akaki Abutidze, Vakhtang Kerashvili, Representative of NeoLab, Representative of Mrcheveli, Lia Gvinjilia, Muazzam Nasrullah, Amiran Gamkrelidze, Valeri Kvaratskhelia, Sanjeev Arora, Stefan Zeuzem, Nezam Afdhal, Francisco Averhoff
10 | Real-world effectiveness of sofosbuvir and ledipasvir/sofosbuvir based regimens in hepatitis C virus genotype 3 infection within national hepatitis C elimination program in the country of Georgia | Approved | NO | Filled table shells provided to the PI in late Februrary, 2017. Modified table shells provided back to the lead authors by the CDC analytical team. | 2017-05-15 | Dr. Tengiz Tsertsvadze, IDACIRC | Tengiz Tsertsvadze, Nikoloz Chkhartishvili, Lali Sharvadze, Akaki Abutidze, Vakhtang Kerashvili, Representative of NeoLab, Representative of Mrcheveli, Lia Gvinjilia, Muazzam Nasrullah, Amiran Gamkrelidze, Valeri Kvaratskhelia, Sanjeev Arora, Nezam Afdhal, Stefan Zeuzem, Francisco Averhoff.
11 | Gender differences in spontaneous and antiviral treatment-related clearance of HCV infection among participants of HCV elimination program Georgia | Approved | NO | The working group information will be provided by the PI | 2017-05-15 | Dr. Gia Kamkamidze, HRU/Neolab | TBD - NEOLAB/HRU group, CDC team, Others
12 | Hepatitis B (HBV) reactivation associated with DAA-based therapy for HCV infection: Retrospective Study | Proposals #12, 13, and 14 requested to be merged | N/A | Resubmitted to the SC for approval as a proposal #15 | 2017-05-15 | Dr. Lia Gvinjilia, CDC | N/A
13 | Risk of HBV reactivation among HCV infected patients treated with DAAs, Prospective cohort study | Proposals #12, 13, and 14 requested to be merged | N/A | Resubmitted to the SC for approval as a proposal #15 | 2017-05-15 | Dr. Maia Butsashvili, HRU/Neolab | N/A
14 | Defining the HBV reactivation rates among patients with HCV/HBV co-infection treated within Hepatitis C Elimination Project. | Proposals #12, 13, and 14 requested to be merged | N/A | Resubmitted to the SC for approval as a proposal #15 | 2017-05-15 | Dr. David Metreveli, Mrcheveli | N/A
15 | Risk of Hepatitis B (HBV) reactivation among HCV/HBV co-infected patients treated with DAAs within Hepatitis C Elimination project: Prospective cohort Study | Approved | YES | Co-investigators nominated. Potential funding source to be defined | 2017-05-15 | Dr. Lia Gvinjilia, CDC | Maia Butsashvili, David Metreveli, Jaba Zarkua, Tinatin Kuchuloria, Tengiz Tserstvadze, Lali Sharvadze, Davit Baliashvili, Aaron Harris, Jan Drobeniuc, Saleem Kamili, Muazzam Nasrullah, Juliette Morgan, Francisco Averhoff
16 | Estimating incidence of HCV infection in Georgia | Approved | YES | Was resubmitted as a proposal #21 | 2017-05-15 | Dr. Tengiz Tsertsvadze, IDACIRC | Tengiz Tsertsvadze, Representatives of CDC, Ministry of Health, NCDC, 4 clinical sites/hubs and other relevant site; invited SMEs
17 | The rate of HCC occurrence in chronic HCV patients with liver cirrhosis after treatment with DAAs. | Approved | YES | Was merged with the proposal #4 | 2017-05-15 | Dr. David Metreveli, Mrcheveli | David Metreveli, Jaba Zarkua, Mamuka Zakalashvili, Maia Zhamutashvili, members from scientific committee
18 | Access to care in Georgia’s hepatitis C Elimination Program | Approved | TBD | Co-investigators to be nominated. | 2017-05-15 | Dr. Shaun Sadaker, CDC | 1 author from each Tbilisi clinic; Authors from seroprevalence survey group
19 | Building of Next Generation Sequencing (NGS) Capacity for Hepatitis C Surveillance in Georgia | Approved | TBD | Proposal was submitted to the CDC foundation for funding. NG initiated contract setup. | 2017-03-02 | Drs. Adam Kotorashvili and Gvantsa Chanturia, NCDC | Molecular Epidemiology Laboratory, NCDC/Lugar Center
20 | Establishment of the system for archiving samples collected within the Hepatitis C Elimination Program in Georgia | Approved | TBD | Proposal was submitted to the CDC foundation for funding. NG initiated contract setup. | 2017-05-15 | Dr. Nazibrola Chitadze, NCDC | TBD
21 | Establishing Georgian PWID cohort study to estimate incidence of HCV infection | Approved | YES | Revised proposal submitted to the CDC Foundation. NG initiated contract setup. Protocol submitted to the local IRB. Data collection tools were revised based on Univ of Bristol comments | 2017-05-15 | Dr. Tengiz Tsertsvadze, IDACIRC/Hepa | Maka Gogia, Georgian Harm Reduction Network (GHRN); Nikoloz Chkhartishvili, IDACIRC; Akaki Abutidze, IDACIRC; Representatives of CDC, NCDC, NeoLab and Mrcheveli.
22 | Evaluation of integrated HCV treatment program in harm reduction centers of Georgia | Approved | YES | Revised proposal submitted to the CDC Foundation. NG initiated contract setup | 2017-05-15 | Dr. Maia Butsashvili, HRU | George Kamkamidze (Neolab), David Metreveli (Mrcheveli), Representative of NCDC (TBD), Representatives US CDC (TBD), Representative of New Vector (TBD
23 | Descriptive analysis of pediatric HCV cases in Georgia | Approved | YES | works will be initiated in June after FETP supervisor is back to Georgia | 2017-05-15 | Mariam Izoria, NCDC | Bryan Yeh, SC-FELTP, SCO
24 | 2-year treatment outcomes of the national hepatitis C elimination program in Georgia | Approved | NO | Data analysis will be conducted after June freeze of the treatment database | 2017-05-15 | Dr. Tengiz Tsertsvadze, IDACIRC | Tengiz Tsertsvadze, Nikoloz Chkhartishvili, Lali Sharvadze, Akaki Abutidze, Vakhtang Kerashvili, Representative of NeoLab, Representative of Mrcheveli, Lia Gvinjilia, Muazzam Nasrullah, Amiran Gamkrelidze, Valeri Kvaratskhelia, Sanjeev Arora, Stefan Zeuzem, Nezam Afdhal, Francisco Averhoff.
25 | Cost of HCV-related health care prior to DAA treatment | Approved | TBD | Table shells developed. Letter of data request to be submitted to the Ministry of Health | 2017-05-15 | Professor Peter Vickerman, University of Bristol | Peter Vickerman, Josephine Walker, Muazzam Nasrullah, Tatia Kuchuloria, to recruit others that are interested from NCDC and CDC, including a local MPH-level student
26 | Surveillance and Risk of Transmission of HCV and HBV in Renal Dialysis, Georgia | Approved | TBD | TBD | 2017-05-15 | Georgian Investigator TBD + Nancy Glass (CDC) | PI, Subject Matter Expert, Other contributors (may include members from the scientific committee). Must include at least one author from NCDC and CDC
27 | Risk factors for treatment discontinuation caused by adverse events in chronic HCV patients receiving sofosbuvir and ledipasvir/sofosbuvir based treatment within Georgian national hepatitis C elimination program | TBD | No | Submitted to the SC for approval | 2017-05-15 | Dr. Tengiz Tsertsvadze, IDACIRC | Tengiz Tsertsvadze, Nikoloz Chkhartishvili, Lali Sharvadze, Akaki Abutidze, Vakhtang Kerashvili, Representative of NeoLab, Representative of Mrcheveli, Representatives of ministry of health, Lia Gvinjilia, Muazzam Nasrullah, Amiran Gamkrelidze, Valeri Kvaratskhelia, Sanjeev Arora, Stefan Zeuzem, Nezam Afdhal, Francisco Averhoff
28 | Evaluation of the diagnostic performance of the Xpert® Fingerstick HCV Viral Load (VL) Assay | TBD | YES | Submitted to the SC for approval | 2017-05-15 | Dr. Francesco Marinucci, FIND | FIND co-investigators (Francesco Marinucci, Elena Ivanova, Violet Chihota), NCDC co-investigator (Maia Alkhazashvili)
29 | Feasibility, acceptability, effectiveness and cost-effectiveness of a decentralized and a centralized model of HCV viremia testing for confirmation and cure versus standard of care among harm reduction site attendees in Georgia | TBD | YES | Submitted to the SC for approval | 2017-05-15 | Dr. Maia Butsashvili, Neolab/HRU | FIND and Georgia co-investigators (to be confirmed)
30 | Prevalence of hepatitis C in pediatric population of Georgia | TBD | YES | Submitted to the SC for approval | 2017-05-15 | Dr. Davit Baliashvili,NCDC | Amiran Gamkrelidze, Khatuna Zakhashvili, Maia Tsereteli, Davit Baliashvili, Ana Aslanikashvili, Tsira Merabishvili, Ana Giguashvili, Representatives of CDC DVH and CDC SC office.

## EASL 2017 list
# | Presentation Title | Type | Presenting author | Date | Time | Comment
1 | Prevalence and genotype distribution of hepatitis C virus in Georgia: A 2015 nationwide population-based survey | Poster Presentation | Dr. Davit Baliashvili, NCDC | 2017-04-20 | 08:00-18:00 | Viral Hepatitis: Hepatitis C Clinical (Except Therapy), Abstract THU-203
2 | Treatment outcomes of hepatitis C virus recombinant form 2k/1b with sofosbuvir based regimens in Georgia | Poster Presentation | Dr. David Metreveli, MRCHEVELI | 2017-04-20 | 08:00-18:00 | Viral Hepatitis: Hepatitis C Clinical (Therapy), bstract THU-255
3 | Prevalence and risk factors for hepatitis B infection in the adult population of Georgia: a nationwide survey | Poster Presentation | Dr. Ana Kasradze, NCDC | 2017-04-21 | 08:00-18:00 | Viral hepatitis: Hepatitis A, B, D E - Clinical (except therapy), Abstract FRI-130
4 | Abbott HCV core Ag and HCV RNA comparison study in country of Georgia | Poster Presentation | Dr. Nazibrola Chitadze, NCDC | 2017-04-21 | 08:00-18:00 | Viral hepatitis: Hepatitis C - Clinical (except therapy), Abstract FRI-199
5 | Effectiveness of DAA-based treatment of HCV in active people who inject drugs living in middle income countries (MIC): the results of a prospective cohort study in Tbilisi, Georgia | Poster Presentation | Dr. Julie Bouscaillou, MDM in collaboration with NEOLAB/HRU | 2017-04-21 | 08:00-18:00 | EU and Public Health, Abstract FRI-467
6 | High sustained viral response among hepatitis C virus genotype 3 patients with advanced liver fibrosis - real-world data of HCV elimination program in Georgia | Poster Presentation | Dr. Maia Butsashvili, NEOLAB | 2017-04-22 | 08:00-18:00 | Viral hepatitis: Hepatitis C - Clinical (therapy), Abstract SAT-221
7 | Real-world effectiveness of sofosbuvir and ledipasvir/sofosbuvir based regimens in hepatitis C virus genotype 3 infection within national hepatitis C elimination program in the country of Georgia | Poster Presentation | Dr. Tengiz Tsertsvadze, IDACIRC | 2017-04-22 | 08:00-18:00 | Viral hepatitis: Hepatitis C - Clinical (therapy), Abstract SAT-283
8 | Treatment outcomes of patients with chronic hepatitis C receiving sofosbuvir-based combination therapy within national hepatitis C elimination program in the country of Georgia | Poster Presentation | Dr. Tengiz Tsertsvadze, IDACIRC | 2017-04-22 | 08:00-18:00 | Viral hepatitis: Hepatitis C - Clinical (therapy), Abstract SAT-284
9 | Projected impact and pathways to success of the hepatitis C virus elimination program in Georgia, 2015-2020 | Oral Presentation | Dr. Josephine G. Walker, University of Bristol | TBD | TBD | TBD

## AASLD 2017 submissions list
# | Presentation Title | Type | Presenting author | Date | Time | Comment
1 | Effectiveness of ledipasvir/sofosbuvir in hepatitis C virus genotype 1, 2 and 3 infection: real-world data from Georgian hepatitis C elimination program | Poster Presentation
2 | Real-world effectiveness of sofosbuvir and ledipasvir/sofosbuvir based regimens in hepatitis C virus genotype 3 infection within national hepatitis C elimination program in the country of Georgia | Poster Presentation
3 | Impact of hepatitis C virus recombinant form RF1_2k/1b on treatment outcomes within the Georgian national hepatitis C elimination program. | Poster Presentation
Note on B2: Author: First two - National data
Note on B4: Author: Data obtained from IDACIRC project