## Sheet1
Social Welfare Matrix - February 2018
|  | 2018 | 2019 | 2020
Objectives | Responsible Government Entity | Prior action(s) | Trigger action(s) | Trigger action(s) | Results (indicators, baseline, target) | Scope of TA
Pillar 1. To develop social support and solidarity system | MOLHSA
Improve support to person with disability by developing social model and strenghtening capacities |  | In the view to improve in the way disability is managed in the country, the government commissioned an external evaluation of the current system that includes a mapping of the institutions and benefits available, an analysis of the strengths and weaknesses of the system, and recommendations | Based on the assessment of the existing system, the government developed proposals in the form of a realistic action plan to improve the situation, conducted an assessment of existing human capacities to identify training needs and developed a training curricula for social workers. | Capacities of social workers to assess disability status and properly support persons with disabilities is provided in at least XXX districts. | Number of social workers receiving an advance training on disability assessment and support to persons with disabilities Baseline (2017): Target (2021):
Implement the second phase of deinstitutionalization |  | In the view to pursue the deinstitutionalization efforts, the government commissioned a study on the first phase of the process and developed a road-map for the second phase including clear proposals on how to support those population groups in need. | Pilot day care centres and/or home support programs are set-up and assessed with respect to their economic feasibility and adequacy to answer to the need of the populations that were previously placed in dedicated centres. | Based on the pilot, a permanent solution is adopted by the government and progressively rolled-out over the country. | Number of person in special centres Baseline (2017): Target (2021): Number of persons received support through a solution alternative to special centres Baseline (2017): Target (2021):
Establish new services for children in street situation |  | In the view of improving children protection, an study is conducted to identify main triggers , assess existing support mechanism that is provided to this vulnerable group and propose improvements based on recognised best practices and international experiences. | Based on the study, the government proposed and piloted a plan intended to (1) better protect children in their households and prevent their destitution, and (2) improve the support provided to street-children in the view of providing them with equal opportunities to other children. | The pilot is evaluated, and an adjusted national program is progressively rolled-out to better protect children and better support street-children. | Number of street-children registered Baseline (2017): Target (2021): Number of children that are successfully removed from the streets each year Baseline (2017): Target (2021):
Pillar 2. To ensure affordable and quality healthcare and promotion of healthy lifestyle | MOLHSA
Improve effectiveness and efficiency of universal healthcare and other programs |  | In the view of improving the effectiveness and efficiency of universal health care, the government has commissioned an evaluation that allow to clearly identity groups of population that are not properly covered and the main pitfalls of the existing health care system (e.g. geographical disparities, increasing costs, diverse quality of treatment, etc.) | Based on the evaluation, changes are proposed by the government in order to improve the effectiveness and efficiency of universal healthcare and other related health programs. Proposed improvements are subject to the development of roadmaps for their progressive realisation. | Proposed improvement are piloted and actions are taken to improve the effectiveness and efficiency of universal healthcare, with a particular attention not to worsen the situation for the poorest and most vulnerable groups of the population. | Utilisation rate of health services, disaggregated by sex and income quintile groups. Cost per capita of the universal healthcare program
Strengthen the system for postgraduate medical education and align it with EU standards |  | The government conducted an assessment of the current postgraduate medical education system in the country in a view to progressively align Georgia's practices with EU standards and other appropriate international standards | Based on the evaluation, a clear strategy has been formulated to improve the postgraduate medical education system and quick wins have been implemented | The postgraduate medical education system is progressively aligned with EU standards | Number of the PGME 161 basic standards that are met Number of the PGME 94 quality development standards that are met
Strengthen the Mental Health Services |  | A study commissioned by the government analyses current mental health services in Georgia with respect to international best practices and standards developed by international organisations, and proposes different scenario to improve the situation and provide better services to the population | A transformation plan is proposed by the government to provide better care to the people with mental illnesses and reduce the stigma on this group of the population | Changes are progressively implemented, the budget dedicated to mental health services in increased, and communication campaign are conducted to reduced the stigma on people with mental illnesses | Budget dedicated to mental illnesses Baseline (2017): Target (2021): Number of people receiving information on mental illnesses
Pillar 3. To optimize resources allocated to IDP needs | Ministry of refugees and displaced persons
IDP monthly allowance reform - shift from status to needs base (adjusted allowance to IDPs needs ; accelerate IDP accommodation pace and livelihoods) |  | The government proposed a reform of the IDP monthly allowance based on international best practices, aligned with international standards regarding the right of IDPs, that ensures protection for the poor and vulnerable households and increases equity of treatment between IDPs and general population | The proposed reform is piloted in at least XX districts and an external evaluation is commissioned to assess the impact of the reform on the IDP population | The reform is informed by the pilot evaluation, and adopted before its national roll-out | Number of IDPs Number of IDPs living in poverty (disaggregated by sex)