georgia HIV/AIDS NAtional Strategic Plan

2019 - 2022

List of Abbreviations	2

Background	3

1.	Situation Analysis	3

1.1	Legal Framework	3

1.2	Global Strategies	4

1.3	HIV/AIDS Epidemiological Update	4

Progress towards 90-90-90	6

Management of co-infections	6

2.	HIV/AIDS National Response – General Approach, Goal and Strategic Objectives	7

2.1	HIV Prevention and Detection: Achievements and Remaining Challenges	8

MSM	9

SW	9

Prisoners	10

2.2	HIV Treatment and Care: Achievements and Remaining Challenges	10

2.3	Governance and Leadership: Achievements and Remaining Challenges	12

3.	Funding Requirements for 2019 – 2022 NSP	14

I.	Current Funding Landscape	14

II.	Funding GAP	16

4.	2019 – 2022 NSP Implementation Timelines	16

Annexes	17

1.	Figures and Graphs	17

2.	2019 – 2022 NSP Detailed Budget	22

3.	2019 – 2022 NSP M&E Framework	23

References	38

1.	Figure 1 Health Expenditure as % of total government expenditure (Georgia VS Europe & Central Asia Regional Overage)	15

Figure 2 Number of new HIV case registered annually (2008 - 2017)	15

Figure 3 Main Routs of Transmission	15

Figure 4 HIV prevalence rates in 2007, 2010, 2012, 2015, Tbilisi based on non-weighted data (sample sizes 136, 271, 216 and 300 respectively)	16

Figure 5 Prevalence of injecting drug use in adult population in EECA region	16

Figure 6 PWID Population Size Estimations during 2011-2017	16

Figure 7 Prevalence among PWID (2009-2017)	17

Figure 8 HIV prevalence among Female Sex Workers in Tbilisi and Batumi (2002-2017)	17

Figure 9 HIV prevalence among prisoners in 2009, 2012, 2015 (sample sizes 211, 286 and 301, respectively)	17

Figure 10 Proportion of People with TB/HIV Receiving Treatment for Both Diseases	18

Figure 11 Progress towards 90-90-90 in Georgia, 2017	18

Figure 12 Coverage with preventive services (MSM population)	18

# List of Abbreviations

| AIDS | Acquired Immunodeficiency Syndrome |
| --- | --- |
| ART | Antiretroviral Therapy |
| Bio BSS | Bio-Behavioral Surveillance Survey |
| CI | Confidence Interval |
| EECA | Easter Europe and Central Asia |
| EMTCT | Elimination of Mother to Child Transmission |
| EU | European Union |
| FSW | Female Sex Worker |
| GoG | Government of Georgia |
| HCV | Hepatitis C Virus |
| HIV | Human Immunodeficiency Virus |
| HR | Harm Reduction |
| MoLHSA | Ministry of Labor, Health and Social Affairs |
| MSM | Men who have sex with men |
| NSP | Needle and Syringe Program |
| Ob/Gyn | Obstetrics and Gynecologist |
| OST | Opioid Substitution Therapy |
| PLHIV | People Leaving with HIV |
| PSE | Population Size Estimation |
| PWID | People who inject drugs |
| SW | Sex Worker |
| TB | Tuberculosis |
| TGF | The Global Fund |
| TP | Transition Plan |
| UNAIDS | Joint United Nations Program on HIV/AIDS |
| WHO | World Health Organization |

# Background

Government of Georgia has declared health of countries population as the priority when announced Universal Health Program in 2013 and approved 2014-2020 State Concept of Health Care System of Georgia for Universal Health Care and Quality Control for the Protection of Patient’s Rights in 2014. HIV/AIDS is acknowledged as one of the priority communicable diseases along with Hepatitis C, Tuberculosis and other vaccine preventable diseases. With introduction of Hep C elimination program in 2015, Georgia become the first country in WHO European Region to provide universal coverage with Hepatitis C treatment for entire population.

The spending for health in the general government budget varied from under 4% to over 6% during the last decade (see Figure 1). However, with the introduction of the Universal Health Care program, the state budget allocations have increased and the share of health spending in the general government budget has reached 8.8% in 2016. Nevertheless, this indicator can be used to indicate the government commitment to distribute fair share of the government budget to the health system, which is still relatively low compared with other countries in the European region.

Yet fragile economic situation in the country may limit government’s ability to further increase its investments in health, which will be required in order to meet the increased domestic commitments as the international financing for the health sector of Georgia shrinks. The recently manifested trend in devaluation of the national currency and increased external debt (19 billion GeL as of December 31, 2017)  may also present a further challenge.

According the Global Fund 2018 eligibility list, Georgia is still eligible for funding for the 2020-2022 funding cycle. Even thought, understanding the economic fluctuations and possible challenges with taking over funding from external sources, Georgia was among the first few countries in Eastern European and Central Asia region that has developed Transition and Sustainability Plan in 2016. The plan covers period of 2017-2021 and aims to ensure smooth transition from TGF funding towards fully national funding of HIV and TB national response by Year 2022.

The presented document is the fifth National Strategic Plan for HIV/AIDS since the 2003 and beyond analyses of achievements and challenges of national response, covers transition activities as well.

# Situation Analysis

## Legal Framework

Georgian citizens are entitled to equal and unlimited access to quality HIV preventive and treatment services. The right to access the adequate health services with full respect of human rights and patient dignity is pursued by the following legal acts:

- Constitution of Georgia;

- Georgia Law on Health Care;

- Georgia Law on Medical Activities;

- Georgia Law on Patients’ Rights;

The Georgia Law on HIV defines the responsibility of the GoG to ensure the implementation of effective interventions for HIV prevention and effective treatment. The Law determines the basic principles of HIV/AIDS response in Georgia, the rights and responsibilities of HIV/AIDS patients and health workers. The existing legislative framework provides protection of health, as well as state and public safety and the fulfillment of the requirements of the international treaties and agreements of Georgia in controlling the infectious diseases.

The Georgia Law on Public Health further emphasizes the role that GoG should play in creating a robust strategic framework for HIV national response and supporting its implementation.

The Georgia Law on State Budget defines annual allocative amount for HIV programs. These allocations cover HIV service delivery costs as well as some preventive activities.

Article 356 of the EU Georgia Association Agreement issued in June 2014 stipulates the commitment of Georgia to strengthen “epidemiological surveillance and control of communicable diseases, such as for example HIV/AIDS, viral hepatitis, tuberculosis as well as antimicrobial resistance, as well as increased preparedness for public health threats and emergencies.”

## Global Strategies

Main directions and activities proposed in new strategy are fully align with UN Sustainable Development Goal 3 and UNAIDS 90-90-90 Strategy

## HIV/AIDS Epidemiological Update

Georgia remains to be a low prevalence country with concentrated epidemics in several key population groups: people who inject drugs (PWIDs); sex workers (SWs), men who have sex with men (MSMs) and prisoners. Even prevalence remains low in general population, there is a risk that epidemic could worsen because of growing number of new cases  among key populations, especially PWID’s and MSM’s. Female partners of those groups (majority of MSM in Georgia also have female partners) might serve as a bridge to general population and deserve special attention as well.

The first case was detected in Georgia in 1989. Since then country has been actively monitoring the epidemic and has reached significate achievements, but HIV/AIDS remains as important public health issue. According the National AIDS center, estimated number of people leaving with HIV/AIDS for 14 May 2018 is 7012 and number of new cases registered for the same period is 250, in total in 2017 there were 631 new cases registered. Majority of infected are males (5248), within the age group of 29 - 40.  For the moment 3772 patients has developed AIDS, 1440 have died. The highest number of new cases, so far, has been registered in 2016 – 719.

UNAIDS estimates the number of people leaving with HIV as 12 000 and number of new cases registered during 2016, as 1 100. During the recent communications with UNAIDS, in the process of updating the SPECTRUM, it was agreed that estimated number of PLHIV is 10 500 and this is the number that was used in the process of Strategy development.

Main route of transmission is sexual intercourse, followed by injecting drug use (see Figure 3). Heterosexual and homo/bisexual contacts together are responsible for almost 56% of cases. Which is pretty alarming, especially knowing that HIV prevalence among MSM is rapidly growing, and according Bio BSS studies, majority of them have sexual contacts with female partners as well, what makes them a bridging population and increases the risk of spreading disease in general population.

Most recent Population Size Estimation (PSE) survey defined the size of MSM population as 17 200. HIV prevalence in this group has increased dramatically over last couple years: from 3.7% in 2007 up to 20.7% in 2015. Highest prevalence is in the capital Tbilisi and Batumi, port at Black Sea cost, that become a very popular resort not only in Georgia, but in the Region.

Based on the latest population size estimation (PSE) survey conducted among PWIDs in 7 cities of Georgia (2016-2017) the national prevalence estimates for injected drug use in adult population is 2.24% (2.13-2.39) which is the third highest estimate in the world and the second in EECA region (see Figure 5). The actual estimated figure based on the National Experts’ consensus is 52,500 (50,000-56,000) which indicates 5% increase of the population size since 2014. Although, increasing trend of PWID population is obvious, the percent-wise increase of the estimate was lower in 2016 than in 2014 when the increase from 2011 was 9% (see Figure 6). HIV prevalence in PWID has not changed since 2009, it varies between 2.4 (95% CI 1.56-3.46) and 2.3 (95% CI 1.63-3.12).

HIV infection rate among Female Sex Workers (FSW’s) remains low - less than 2% during the last 15 years (see Figure 7). The latest PSE survey conducted in 2014, and the latest Bio BSS – in 2017. The latter also provided some corrections of PSE for Tbilisi and Batumi. The estimated size of sex workers population for Georgia is 6525; for Tbilisi the estimated size is 600 and for Batumi - 700. Majority of the sex workers surveyed represent the age group 40+.

The peculiarity of Georgian sex business, in contrast to other post-soviet countries, stays the same over 15 years - sex work, at least, the low-level sex work - does not overlap with injecting drug use. One interesting new trend is increased use of non-injecting drugs (sedatives/sleeping pills in Tbilisi and marijuana – in Batumi) among FSWs in both cities. Bigger proportions reported having used non-injecting drug during the last 12 months in both cities, compared to 2014 survey (Tbilisi: 11% (2017) vs 6.3% (2014) and Batumi: 20% (2017) vs 5.8% (2014)). This increase is statistically significant.

The latest Bio BSS among prisoners was conducted in 2015. At the time, as of October, 2015, there were 10201 (9876 males, 325 - females) prisoners in Georgian penitentiary system, which included 15 establishments. The HIV prevalence found by the survey was 1.4 %. In the previous survey of 2012 the prevalence was 0.3%. The increasing tendency of HIV spread did not demonstrate statistically significant change.

### Progress towards 90-90-90

Analysis of national data on fast-track 90-90-90 targets shows that the major gap in the cascade of HIV care continuum is at the stage of HIV diagnosis with only 48% of estimated number of people living with HIV aware of their status.

While diagnosis remains the main challenge, country has made remarkable progress on the right side of the cascade from diagnosis through viral suppression. Georgia implemented treat all policy in 2015 and since then all HIV positive persons are offered antiretroviral therapy (ART) regardless of immune status or disease stage. Country is approaching fast-track targets for ART and viral suppression. Among diagnosed persons ART coverage increased from 62% in 2015 to 81% in 2017; viral suppression rates among those on treatment increased from 84% in 2015 to 89% in 2017.

Excellent results are achieved among children, but it also should be mentioned number of children living with HIV is very low in Georgia (estimated 45 children <15 years), indicating effectiveness of national effort towards elimination of mother to child transmission of HIV.

Nevertheless, significant gap in the diagnosis stage undermines accomplishments in treatment provision and on a population level only 35% of PLHIV are virally suppressed, which is not sufficient to derive maximum individual and public health benefits of ART.

### Management of co-infections

Important part of HIV treatment and care service delivery is the management of co-infections, particularly of tuberculosis and HCV infection, which are two major causes of death among PLHIV in Georgia.

There is strong collaboration between TB and HIV services ensuring effective implementation of collaborative HIV/TB activities, including HIV screening of all persons with active TB disease,  TB case finding among HIV positive persons and provision of treatment for both diseases. The prevalence of HIV among TB patients remained low – below 5% at all time points over the last decade. Prevalence of TB among newly diagnosed persons is around 5-7%, and in vast majority of cases TB is diagnosed first and then HIV is identified. Many of the TB/HIV co-infected patients already have deteriorated immune system and most likely TB co-infection is the result of late HIV diagnosis. That is why TB is major cause of death in HIV persons despite the universal availability of treatment for both diseases. Estimates of TB/HIV treatment coverage is over 90% and significantly exceed global and European coverage (Figure 10).

## HIV/AIDS National Response – General Approach, Goal and Strategic Objectives

Georgia has achieved significant progress in several directions in fight against HIV/ADS, especially in treatment outcomes, but timely detection and inclusion in treatment program remains a challenge. It is strategically important to increase the coverage by preventive services and scale up  testing among representatives of key population and their sexual partners. With decreasing financial support from TGF, it is important that Government gradually takes financial responsibility to cover activities previously funded by TGF. This will also require close collaboration with non-governmental actors that been implementing activities for two decades.

From the beginning of HIV epidemic in Georgia in 1989 the majority of HIV cases were attributed to injecting use of drugs, but from 2011 sexual route of transmission slowly became dominant.  This has to be taken into consideration, even majority of MSM in Georgia, also have the female sexual partners, and increasing prevalence of HIV in this particular group, might cause the spread of infection into general population, if not managed properly.

Despite of efforts, coverage with preventive services and testing uptake remains to be a serious challenge for HIV/AIDS National response in Georgia. According latest epidemiological data, MSM and PWID remain to be the most vulnerable groups with highest prevalence of HIV. Considering the situation with the late diagnosis in Georgia, as well as high HIV prevalence among MSM, testing uptake among this population shall increase dramatically in order to improve identification of cases.

HIV prevention among people who inject drugs (PWIDs) is one of the priority objectives of the National HIV Strategy which declares the importance of highly cost-effective evidence based Harm Reduction (HR) interventions, namely Needle and Syringe Program (NSP) and Opioid Substitution Treatment (OST) Program, to control HIV epidemic in Georgia. Implementation of harm reduction interventions started in 2005 and since then, despite of the strict anti-drug policy, the harm reduction services have been largely expanded in terms of the scope and the scale. Government fully took over the funding for OST program and co-financing requirements for beneficiaries of state program were removed. This will allow more beneficiaries to access the OST services.

According the programmatic data, coverage with preventive services among PWID has increased from 17% in 2012  to 57% in 2016. But the same coverage according Bio BSS was considerably lower and equaled to 23.3% in 2016. Such difference may be caused by the reporting system that actually allowed duplication of beneficiaries in the system. Reporting system has changed in 2017 and now clients can only be registered once in the system, using unique identifier. It is expected that two sources of information will become closer after above mentioned change and it will be easier to assess the situation in this group.

NGOs and CSO’s are providing preventive services since the first TGF grant in 2002. The last achievement in this term is the introduction of PrEP for MSM’s, that is implemented by community driven non-governmental organization. But uptake is still low and it has to be increased.

Transition Plan developed and approved by Country Coordination Mechanism in 2016, calls for scaled-up smooth transitioning from the Global Fund financing to full local financing of the National HIV/AIDS and TB Programs by 2022. This timing coincides with the time frame of new National Strategic Plan, that allows the integration of those two documents.

The overarching goal of 2019-2022 National Strategic Plan is to reverse the HIV epidemic in Georgia, through sustainable, targeted interventions for key populations and their sexual partners, improvement of the quality of the services and outcomes of the treatment.

To achieve this goal, NSP emphasizes  on following three strategic objectives:

- HIV Prevention and Detection: Scale up of preventive services to ensure timely detection and progression to care;

- HIV Treatment and Care: Improve HIV health outcomes through ensuring universal access to quality treatment, care and support;

- Governance and Policy development: Ensure sustainability of response to the epidemic through enhanced government commitment, enabling legislative and operational environment, and greater involvement of civil society.

Those objectives are the same as in previous National Plan, as well as majority of activities proposed, as the major challenge remains the same, timely detection and progression to care. The new activities proposed mainly aim to expand the coverage of KP’s with preventive services and testing and make services more attractive.

### HIV Prevention and Detection: Achievements and Remaining Challenges

To increase the coverage with preventive activities, 2019 – 2022 NSP proposes to make them more attractive through expansion of  services offered. For instance, adding vaccination/treatment of Hep C and Hep B to HIV case management protocol, gives opportunity to get the multiple services at one point, that will decrease the travel time and cost associated to it. As it was already mentioned Georgia is providing Hep C treatment program for entire population for free. This is a great opportunity to integrate HIV testing into existing program and expand HIV testing uptake. Currently, this approach is tested in several regions in country and most likely will prove to be effective, if that’s the case, integration will be expanded to entire country.

Level of knowledge concerning HIV infection among MSM is high and has further improved over the last years, but this has not influenced personal risk perception among MSM, as well as behaviour trends. They are characterized by risky sexual behavior with large number of different of partners, both male and female. More than half of surveyed MSM reported having a female partner during the last 12 months. They also report insufficient use of condoms, especially permanent partners (both male and female), as well as involvement in group sexual practices often without condoms. Awareness on places of condom and lubricants supply is high among MSM, still, unsafe behaviour is quite widespread. These tendencies are reflected in the HIV prevalence increase and, besides, raise concerns about the potential bridging role of MSM in HIV transmission to general population.

For last three years, there is a tendency of decreasing knowledge level in KP’s regarding HIV, this might be caused by “generation change”, younger ones have less information not only about the HIV, but also where to get the information and testing. This requires an attention from the NGO’s that are implementing preventive programs.

Said all that, NSP proposes to develop and launch effective behaviour change communication and counselling services for all KP’s. Introduction of self-testing and saliva testing might expand the testing uptake. Improvement of quality of VCT services provided might also contribute to the testing uptake. Obviously, Georgia has to implement the system of reporting in case of self-testing for reporting, so that positive cases are not lost to follow up and those who will decide to use the self-testing are protected in terms of confidentiality.

Provision of legal and psycho-social assistance, adding vaccination/treatment of Hep C/B to HIV case management protocol, adding HIV testing to Hep C screening standards all is envisioned to expand the coverage.

Strategic Plan calls for inclusion of mental health services in harm reduction programs.  Scaling up Opioid Substitution Therapy (OST) for PWIDs. Greater utilization of HIV prevention benefits offered by opioid substitution maintenance and other treatment and rehabilitation options will be achieved through gradual increase in the capacity of service delivery system, improvements in service quality (including revision of the current dosing and other regulations), targeted promotion of OST services, strengthened psychosocial support of OST patients, improved accessibility of services for disadvantaged patients, accommodating the needs of women, and introduction of long-term OST in penitentiary institutions. For women, adolescents and young people who inject drugs, reproductive health services also should be offered at service points.

Peer support programs prove to be effective long ago. In case of Georgia, it is envisioned that  peers might be effectively used to optimize the case finding. For this people who will be involved in program implementation will be incentivized for every positive case identified with their support and involvement.

Introduction of PrEP was piloted for MSM population in current TGF grant in Georgia. Update of services was still low at the moment of NSP development, but this was attributed to different processes ongoing in the country, but as implementers were presenting interest is high in MSM population. NSP actually calls for expansion of PrEP and PEP, not only for MSM, but PWID and SW as well. To expand the availability of PrEP and PEP, it is proposed to make them available at community level service points as well, not only at clinical settings.

| PWID | ### MSM |
| --- | --- |
| - Increase coverage with Preventive services - Behavior change communication and counseling services - VCT and saliva testing - TB screening questionnaire for TB diagnostics and referral for treatment - Legal Assistance - Psycho-social assistance - Expansion of OST services - Adding vaccination/treatment of Hep C/B to HIV case management protocol - Adding HIV testing to Hep C screening standards - Peer support programs - Optimized case finding – incentives provided for every new HIV positive - Prevention and treatment of over dose - Reproductive health programs, especial programs for adolescent and young people who inject drugs - Inclusion of mental health services in prevention/harm reduction programs - Implementation of Provider initiated testing at all health care facilities; - Introduction of PrEP | - Increase coverage of preventive services - Explore need for geographical expansion of preventive services - Increase testing coverage - Increase access to condoms and lubricants - Behavior change communication and counseling services (especial for those who are having sexual contact both with men and women, transgender population) - TB screening questionnaire for TB diagnostics and referral for treatment - Ensure access to existing services for migrants and those involved in commercial sex - Ensure integration of Hep C testing and Hepatitis B vaccination with MSM service package. - Activities against violence and improve referral services - Implementation of self-testing based on newly developed protocol according WHO recommendations - Improve access for MSM to Post Exposure Prophylaxis (make PEP available at community level / service points); - Improve access to mental health services - PrEP expansion (including prisons); |

| SW | Prisoners |
| --- | --- |
| - Increase coverage with Preventive services - Behavior change communication and counseling services - Increase VCT and saliva testing - TB screening questionnaire for TB diagnostics and referral for treatment - Increase access to condoms and lubricants - Add Reproductive health services to package (FP/safe abortion consultation and referral to Ob/Gyn) - Sustain STI diagnostic and treatment - Activities against violence and improve referral services - Improve access to mental health services - Improve access for SW to Post Exposure Prophylaxis (make PEP available at community level / service points); - PrEP introduction (make PEP available at community level / service points); | - Increase coverage with Preventive services - Behavior change communication and counseling services - Increase access to condoms and lubricants - Increase access to harm reduction services |

HIV detection efforts will include universal testing (PMTCT screening) of pregnant women; Provider initiated testing on clinical and behavioral indications; Promotion of VCT among the contacts of those who tested HIV positive.

Observance of essential human rights, confidentiality principles and voluntary acceptance of the offered services will be ensured in all settings. Patients who test positive for HIV will be offered support required for their timely progression to care and treatment.

Implementation of PIT will continue to focus on drug treatment facilities, STI and TB clinics, and antenatal care facilities, with intention to expand indicator disease guided HIV testing and counseling in health sector, including in primary health care. This activity will be supported by the State HIV/AIDS Program component “HIV/AIDS voluntary counselling and testing for risk groups”. HIV testing efforts will be expanded in people living with HCV through establishing linkages with national hepatitis C program. The developed PIT standards will be further reviewed, endorsed by the relevant state authorities and rolled-out through in-service training program involving personnel of the mentioned facilities.

### HIV Treatment and Care: Achievements and Remaining Challenges

While detection remains a challenge, country has achieved  a remarkable progress on right side of cascade: Georgia is approaching fast-track targets for ART and viral suppression. ART coverage among diagnosed persons increased from 62% in 2015 to 81% in 2017. Viral suppression rates among those on treatment increased from 84% in 2015 to 50 89% in 2017. Provider initiated HIV testing and counselling services cover patients with active TB and almost 93% of them has been tested for HIV during last two years. Country is on the path to meet 12 month ART retention target of 90% by end of 2018.

Stratification by age and gender shows that men have better detection rates, but women older than 15 years have already achieved fast track targets for ART and viral suppression – 93%  ART coverage of diagnosed persons and 91% of those on ART reaching viral suppression. While 89% of men on ART had viral suppression, only 77% of diagnosed men were on treatment. Excellent results are achieved among children, but it also should be mentioned number of children living with HIV is very low in Georgia (estimated 45 children <15 years), indicating effectiveness of national effort towards elimination of mother to child transmission of HIV.

Georgia was the first country in the region to ensure universal access to free hepatitis C treatment for HIV/HCV co-infected persons. It started in 2011 within the Global Fund supported program and from 2015 continued within the national hepatitis C program. From 2011 through 2017, a total of 1104 HIV/HCV co-infected persons were treated for HCV (420 persons with dual therapy in 2011-2015; 684 with direct acting antivirals in 2015-2017) representing 71% of co-infected population. Enrollment of PLHIV in HCV treatment program continues with an overall goal of curing HCV in all persons with known HIV/HCV co-infection.

Adherence support and promotion include clinic-based services provided to all persons picking-up antiretroviral drugs, as well as out-of-clinic/home support delivered by dedicated adherence mobile units. The latter service was established in 2008, providing services to persons registered with one of the AIDS centers in Tbilisi, Kutaisi, Batumi and Zugdidi. Mobile units provide adherence monitoring and support on average to 220 persons on a monthly basis.

The palliative care service provision for PLHIV in Georgia has been established in 2008 and since then has been led by the Georgian National Association of Palliative Care. The program delivers home-based services through operation of palliative care mobile units in Tbilisi, Kutaisi, Batumi and Zugdidi. Services provided include medical, psychological, social and spiritual support for chronically ill patients, and are implemented by health workers and non-health caregivers, including PLHIV. The program has been providing care to up to 35 patients on a monthly basis.

Community-based HIV self-support centers operate in Georgia since 2004 that provide psychosocial support through peer groups as well as through trained psychologist and hot-line services. The service is implemented by HIV/AIDS Patients Support Foundation. Up to 10,000 consultations are provided annually, including to PLHIV and their close ones/caregivers.

The main challenge is that all outpatient care and support activities are entirely supported by donor funding and includes adherence promotion and support services, home-based palliative care for chronically ill persons and community-based self-support services.

Nevertheless, significant gap in the diagnosis stage undermines accomplishments in treatment provision and on a population level only 35% of PLHIV are virally suppressed, which is not sufficient to derive maximum individual and public health benefits of ART.

The following is proposed:

- Expand HIV testing services (HTS) among key populations at risk

  - Refer to combination prevention services for key populations

- Expand provider initiated HIV testing services (HTS) in health care sector

  - Provide HTS in specialty clinics, including infectious diseases, tuberculosis, STI and viral hepatitis clinics

  - Provide HTS in emergency departments

  - Provide HTS to hospitalized persons

  - Provide HTS in primary healthcare clinics

  - Provide HTS to contacts of diagnosed PLHIV (contact tracing/investigation)

- Introduce HIV self-testing

- Provide essential clinical care services for all people living with HIV (PLHIV)

  - Out-patient medical care

  - In-patient medical care

  - Laboratory monitoring (CD4 cell count, viral load, drug resistance testing)

- Provide ART to all PLHIV in accordance with existing guidelines, including in the region of Abkhazia

- Procure first, second and third-line ARV drugs

- Provide clinic based adherence monitoring and support

- Provide home based adherence support

- Ensure effective program administration and quality of service delivery

- Ensure effective program delivery including in the region of Abkhazia

- Maintain operation of National AIDS Health Information System (HIV/AIDS database) and implement other M&E activities

- Implement operational research to inform service delivery

- Ensure quality of service delivery:

    - Update and develop clinical practice guidelines

    - Implement quality control/clinical audit for clinical care and ART

    - Implement quality control for laboratory services

    - Support human capacity strengthening through continued medical education, including participation in international meetings

- Ensure necessary investments in the infrastructure

- Develop adequate physical infrastructure of  the National AIDS Center, including building and equipment

- Reduce morbidity and mortality due to co-infections with TB and viral hepatitis

- Ensure provision of HIV/TB collaborative activities

- Provide treatment for hepatitis C

- Provide prevention and treatment for hepatitis B

- Provide care and support services for PLHIV

- Ensure operation of peer-support services

- Improve access to general healthcare through community-based case management and education

- Provide palliative care for chronically ill patients

Georgia has an ambitious to declare the elimination of vertical transmission cases, there have not been detected any case during 2016 and 2017. MoLHSA has developed and the Maternal and Child Care Strategy, that covers EMTCT activities, Tus those are not covered in NSP.

### Governance and Leadership: Achievements and Remaining Challenges

Public Health is one of the priorities declared by the GoG. This is reflected in the governmental documents and supported by 2.5-time increased state healthcare budget for the years 2012-2016. The share of the healthcare expenses in the total public expenditures and the total amount of healthcare spending are increasing. Implementation of the Universal Healthcare Program and C Hepatitis Elimination Program and approval of the National HIV/AIDS and TB Strategic Plans are only some of those many activities that demonstrate the GoG commitment towards improving health status of population.

It should be also noted that continuation of a repressive policy for management of drug addiction can considerably hinder implementation of an effective national HIV/AIDS response. There are no legal documents issued by the Ministry of Health about the needle and syringe programs therefore the Georgian Harm Reduction Network (GHRN) implements this program without any legal basis. Despite the process that has started in the country with establishment of malty-sectoral commission chaired by Minister of Justice and active support of drug policy liberalization by Chair of Parliament Committee of Health Social Issues, no considerable change has been introduced so far. Besides the barriers for expansion of preventive programs, this creates additional tensions in society and contributes to further stigmatization of drug use. Therefore, this problem must be addressed through the policy liberalization before the Global Fund financing is halted.

It is also important for the state to be able to sign contracts with NGOs as non-governmental sector is a very important player in effective implementation of preventive measures. Despite the fact that Georgian legislation allows such contracting, many organizations face problems with meeting requirement of the Public Procurement Law to present a bank guarantee worth 1-2% of the total budget specified in a respective tender proposal. Thus, ability of organizations to participate in public tenders is limited.

Stigma and discrimination associated with certain behaviors remains to be a challenge for Georgia. Despite the antidiscrimination law passed in 2004,  which bans all form of discrimination based on religion, ethnicity, or sexual orientation. However, some experts and NGO representatives are not satisfied with some of the wording and mechanisms. The country also has adopted the strategy against violence which focuses mostly on domestic violence, but it contains a section related to discrimination towards people with addictions. Moreover, the powerful Georgian Orthodox Church creates barriers on the application of such documents by direct or indirect opposition via faith community.

- Create conducive legal environment to ensure smooth implementation of HIV national response and achieve greater engagement of civil society

- Increase Coordination among key players, relevant government bodies, Parliamentary committees, civil society, the National Platform on Drug Policy Reform

- Monitor and foster policy interventions to remove the legislative barriers for access to HIV Prevention and harm reduction service in civil and penitentiary sectors

- Support development and enforcement of the Four-pillar Drug Policy, Anti-Drug Strategy and Action Plan

- Create enabling environment for CSO engagement in HIV national response

    - Assess the barriers and opportunities for  CSOs/CBOs to satisfy the state procurement requirements and in case of need – develop and adopt detailed operational manual describing the rule and procedures for contracting CSOs /CBOs for health service delivery

    - Build Capacity for CSOs/CBOs, their networks and coalitions – through training and technical assistance in management, resource mobilization for CSOs/CBOs to satisfy the state procurement requirements

- Ensure full budgetary commitment and allocative efficiency for national HIV response

- Ensure Adequate and sustainable staffing in HIV response, especially for outreach/social workers

- Sustainable development of Health Information System in HIV national response (Bio BSS and PSE funding)

- Maintain the effective and functional procurement and supply chain for the HIV/AIDS health products by the relevant national structures

- Develop adequate physical infrastructure of  the National AIDS Center, including building and equipment

## Funding Requirements for 2019 – 2022 NSP

## Current Funding Landscape

Funding needs for HIV national response in Georgia are set to increase as the rate of infections is rising, and international and national targets call for increased coverage and access to prevention, treatment and care services.

Indeed, for the past period, national expenditures have been raising. From 2016 to 2018, total annual expenditures for HIV response have increased by 16% and are planned to remain approximately 21.6 mln USD per year in the following mid-term period.

However, starting from the initiation for transition process from donor funding to domestic funds, funding level became volatile. National HIV spending has reached its maximum in 2017 amount 19.92 mln USD. However, starting from 2018, panned expenditures are significantly reduced (by -33%) and remain below an average annual spending for past 4-year period. This has been the highest national spending level for the past decades in the country (Figure 13).

Nonetheless, the national HIV spending has been characterized by the significant level of volatility for the past mid-term period, ranging from -6% to +17% growth rate. Those variations in spending rate are explained by the uneven process of commodity procurement, and overall, by the pressing transition process from donor (the Global Fund) funding to domestic funding. Moreover, during the same period, Georgia has also increased public obligations as the part of transition process -- it had successfully completed transition of methadone substitution treatment from donor funding to public funding in 2017, and made the services universally free of charge at the point of use.

The transition process is not expected to have a dramatic impact on the total level of HIV funding in the country, as the Government of Georgia commits to deliver relatively the same package of services. Other policy factors that might impact the total HIV funding allocation include elimination of legislative barriers to the use of HIV prevention services and decriminalization of drug use, although, funding needs for those policy changes are not currently accounted in national medium-term funding framework.

Sources of funding

Primary sources of funding of HIV response in Georgia are domestic (76% in 2018) and international funds (22% in 2018). Private, out-of-pocket expenditures are insignificant source of funding (≈1%) and include only expenses related to substitution treatment for substance use.

As the transition process from the Global Fund funding to domestic sources intensify, national HIV funding undergoes profound transformation in terms of sources of funding.  While from 2016 to 2018, total expenditures for HIV response have increased by 16%, the domestic expenditures have increase by as large as 1/3 (29%). In the following medium term, annual domestic expenditures are planned to increase by an additional 30% compared to 2018. Overall, compared with 2016, the annual rate of domestic expenditures are planned to increase by 45% for 2021 and will cover 86% of total expenditures (Figure 14).

International funding, mostly received from the Global Fund is projected to nearly halve from 2016 to 2021 and will amount 13% of total HIV funding, compared to 28% in 2016. According to the Global Fund new transition funding policy, Georgia is projected to complete transition by 2025.

Funding priorities

During the last few years, funding for the key priorities in HIV response have also changed. While in previous years, larger share of resources were dedicated to treatment, care and support services, from 2016 the balanced is altered towards more funding for prevention services. Overall, for the following period (2019-2021), expenditures for prevention is planned to increase by 7%, compared to the previous period (2016-2018). One of the key drivers for the increase in spending for prevention is substitution treatment for substance use, which the Government of Georgia has taken over from 2016. Furthermore, spending for Hepatitis C Elimination program also provider significant increase in expenditures for prevention (Figure 15).

Financing policies

HIV prevention and treatment and care services have been free of charge at the point of care (excluding, co-payments for substitution treatment abolished from 2016). This has remained unchanged for the planned period as well. Even more, access to several services has been expanded: testing for HIV and Hepatitis B and C for general population (through Hepatitis C Elimination National Program).  Although, provider network for such services have expanded, reimbursement policies have not been changed/revised during previous period.  This might generate financial pressure for treatment provider network in the country.

Evaluation of HIV Financing Environment

HIV service funding in Georgia has been reliable, with little to no significant interruption. However, transition from donor funding to domestic funding creates significant budgetary pressure, which is coupled with potential financing challenges associated with a pressure to increase detection and treatment adherence rates.

Georgia being a low prevalence country faces rather limited challenges in terms of total financial burden of HIV prevention, care and treatment.

Financial protection: HIV prevention and treatment services in Georgia had been predominantly funded from public (and international) sources, exerting limited to no financial hardship to individuals and their households. The current knowledge about the national HIV expenditures registers out-of-pocket spending only for substance abuse treatments, such as substitution therapy or hospital-based treatments.

Although, the topic could have been studied better, the current funding arrangement leave little to no space for out-of-pocket spending: high-risk, as well as general population has access to free HIV testing through special service centers, or coupled with the National Hepatitis C program service centers; diagnostic services are fully free of charge at the point of use and ARV treatment is also fully covered from public sources. Therefore, it could be said that financial protection for HIV services is universally achieved in the country.

## Funding GAP

It is projected that for the period of this NSP (2019-2022), implementation of HIV response in the country will face a funding gap in the amount of 6.6 mln USD.

Projected funding gap for year fiscal year is presented in the table below:

| Year | Allocation ceiling | NSP projected activities | Funding gap |
| --- | --- | --- | --- |
| 2019 | 22,167,977 | 20,270,242.45 | 1,897,735 |
| 2020 | 21,081,977 | 22,108,361.23 | -1,026,384 |
| 2021 | 21,705,977 | 23,711,900.20 | -2,005,924 |
| 2022 | 21,705,977 | 27,216,693.14 | -5,510,716 |

Activities being largely underfunded in the projected years include HIV prevention activities, and activities in the management and leadership domain, which includes activities necessary for successful transition from donor funding to domestics funding mechanisms (see Transition and Sustainability Plan for Georgia).

Furthermore, large share of domestic funding is currently directed at new activities, or significant programmatic expansion of existing activities. For example, Basic Data and Direction’s document, which stipulates public allocation ceilings for 2019 to 2021, shows that allocations have increased for HCV prevention activities, and OST treatment (where transition process to domestic funding has been completed). However, allocations necessary for transition of HIV response components, such as HIV prevention among KAPs, are not included in the national medium-term expenditure framework.

## 2019 – 2022 NSP Implementation Timelines

# Annexes

### Figures and Graphs

- Figure 1 Health Expenditure as % of total government expenditure (Georgia VS Europe & Central Asia Regional Overage)

Figure 2 Number of new HIV case registered annually (2008 - 2017)7

Figure 3 Main Routs of Transmission

Figure 4 HIV prevalence rates in 2007, 2010, 2012, 2015, Tbilisi based on non-weighted data (sample sizes 136, 271, 216 and 300 respectively)

Figure 5 Prevalence of injecting drug use in adult population in EECA region

Figure 6 PWID Population Size Estimations during 2011-2017

Figure 7 Prevalence among PWID (2009-2017)

Figure 8 HIV prevalence among Female Sex Workers in Tbilisi and Batumi (2002-2017)

Figure 9 HIV prevalence among prisoners in 2009, 2012, 2015 (sample sizes 211, 286 and 301, respectively)

Figure 10 Proportion of People with TB/HIV Receiving Treatment for Both Diseases

Figure 11 Progress towards 90-90-90 in Georgia, 2017

48%

Figure 12 Coverage with preventive services (MSM population)

Figure 13: Total HIV Expenditures by source; expenditure growth rate (2011-2021)

Figure 14: HIV Expenditures by source for selected years

Figure 15 Funding Priorities

### 2019 – 2022 NSP Detailed Budget

| # | Strategic Priority/ Activity area | Current NSP (USD) |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | 2019 | 2020 | 2021 | 2022 | Total |
| 1 | [HIV Prevention and Detection] | 10,407,068.77 | 10,857,723.34 | 11,346,987.33 | 11,757,784.41 | 44,369,563.84 |
| 1.1 | Prevent HIV transmission, detect HIV, and ensure timely progression to care and treatment among the key affected populations | 6,689,499.02 | 6,945,368.98 | 7,232,634.37 | 7,553,962.25 | 28,421,464.62 |
| 1.1.1 | Prevention and detection of HIV among PWID | 2,589,112.30 | 2,704,451.21 | 2,831,324.01 | 2,970,884.09 | 11,095,771.59 |
| NEW 1 | MODIFIED: HEP B vaccination (Adding vaccination/treatment of Hep C and B to HIV case management protocol) | 323,781.32 | 323,781.32 | 323,781.32 | 323,781.32 | 1,295,125.29 |
| NEW 2 | Special Programs for adolescents and young people who inject drugs | 18,000.00 | 18,000.00 | 18,000.00 | 18,000.00 | 72,000.00 |
| 1.1.2 | Opioid Substitution Treatment (OST) and other forms of treatment and rehabilitation | 2,509,600.00 | 2,509,600.00 | 2,509,600.00 | 2,509,600.00 | 10,038,400.00 |
| 1.1.3 | Prevention and detection of HIV among MSM | 602,624.38 | 693,018.04 | 796,970.74 | 916,516.35 | 3,009,129.51 |
| NEW 3 | MODIFIED: HEP B vaccination (Adding vaccination/treatment of Hep C and B to HIV case management protocol) | 100,923.42 | 100,923.42 | 100,923.42 | 100,923.42 | 403,693.68 |
| NEW 4 | PrEP | 65,497.10 | 75,321.67 | 86,619.91 | 99,612.90 | 327,051.58 |
| 1.1.4 | HIV Prevention and detection among FSW | 335,334.90 | 368,868.39 | 405,755.23 | 446,330.76 | 1,556,289.28 |
| 1.1.5 | HIV Prevention and Detection among Prisoners | 89,863.95 | 89,863.95 | 89,863.95 | 89,863.95 | 359,455.82 |
| 1.1.6 | Improving quality of services | - | - | - | - | - |
| NEW 4 | Mental health services for all KAPs | 12,000.00 | 12,000.00 | 12,000.00 | 12,000.00 | 48,000.00 |
| NEW 5 | Improve access to RSH services for all KAPs | 28,000.00 | 36,000.00 | 40,000.00 | 44,000.00 | 148,000.00 |
| NEW 6 | Introduction and expansion of HIVST among KAPs and other vulnerable groups | 14,761.64 | 13,540.99 | 17,795.78 | 22,449.46 | 68,547.87 |
| 1.2 | Prevention and detection of HIV in healthcare settings | 3,717,569.76 | 3,912,354.36 | 4,114,352.96 | 4,203,822.16 | 15,948,099.22 |
| 1.2.1 | Enhancing Provider Initiated Testing (PIT) for HIV | 471,581.20 | 552,565.80 | 566,164.40 | 567,313.60 | 2,157,625.00 |
| NEW 6 | Provider initiated testing at primary care setting | 442,080.00 | 553,080.00 | 645,480.00 | 733,800.00 | 2,374,440.00 |
| NEW 7 | Provider initiated HIV testing in hospitalized persons | 1,080,000.00 | 1,080,000.00 | 1,080,000.00 | 1,080,000.00 | 4,320,000.00 |
| 1.2.2 | Ensuring safety of donor blood | 760,000.00 | 760,000.00 | 760,000.00 | 760,000.00 | 3,040,000.00 |
| 1.2.3 | Post-exposure prophylaxis of HIV infection (PEP) | 5,508.56 | 5,508.56 | 5,508.56 | 5,508.56 | 22,034.22 |
| 1.2.4 | Prevention of Mother to Child Transmission of HIV (PMTCT) | 958,400.00 | 961,200.00 | 1,057,200.00 | 1,057,200.00 | 4,034,000.00 |
| 1.2.5 | Prevention programs currently under State HIV/AIDS Program | - | - | - | - | - |
| 2 | [HIV Care and Treatment] | 7,315,768.46 | 8,494,332.67 | 9,716,207.66 | 11,010,205.23 | 36,536,514.02 |
| 2.1 | Ensure uninterrupted delivery of high quality treatment and care | 6,459,875.66 | 7,638,439.88 | 8,860,314.87 | 10,154,312.44 | 33,112,942.84 |
| 2.1.1 | Delivery of essential clinical care services to all people living with HIV (PLHIV) | 6,241,635.66 | 7,420,199.88 | 8,642,074.87 | 9,936,072.44 | 32,239,982.84 |
| 2.1.2 | Provision of ART to all PLHIV in need in accordance with existing guidelines, including in the region of Abkhazia | 66,392.00 | 66,392.00 | 66,392.00 | 66,392.00 | 265,568.00 |
| 2.1.3 | Effective programme administration and quality of service delivery | 151,848.00 | 151,848.00 | 151,848.00 | 151,848.00 | 607,392.00 |
| 2.1.4 | Necessary investments in the infrastructure | - | - | - | - | - |
| 2.2 | Reduce morbidity and mortality due to TB and HCV co-infections and injecting drug use | - | - | - | - | - |
| 2.2.1 | Intensify HIV/TB collaborative activities (funded from the TB program) |  |  |  |  | - |
| 2.2.2 | Provide treatment and care for viral hepatitis to all PLHIV (funded from the HVC program) | 7,706,000.00 | 7,706,000.00 | 7,706,000.00 | 7,706,000.00 | 30,824,000.00 |
| 2.3 | Ensure provision of care and support services for PLHIV | 855,892.79 | 855,892.79 | 855,892.79 | 855,892.79 | 3,423,571.18 |
| 2.3.1 | Ensure operation of peer-support services | 698,000.00 | 698,000.00 | 698,000.00 | 698,000.00 | 2,792,000.00 |
| 2.3.2 | Provide palliative care for chronically ill patients | 151,848.00 | 151,848.00 | 151,848.00 | 151,848.00 | 607,392.00 |
| 2.3.3 | Support effective linkage of PLHIV to HIV and other medical care, as well as supportive services (case-manager) | 6,044.79 | 6,044.79 | 6,044.79 | 6,044.79 | 24,179.18 |
| 3 | [Leadership and Policy Development] +TSP related activities | 2,178,198.27 | 2,387,098.27 | 2,279,498.27 | 4,079,496.55 | 10,924,291.37 |
| 4 | Management of contribution from international funding mechanism | 369,206.95 | 369,206.95 | 369,206.95 | 369,206.95 | 1,476,827.78 |
|  | TOTAL | 20,270,242.45 | 22,108,361.23 | 23,711,900.20 | 27,216,693.14 | 93,307,197.01 |

### 2019 – 2022 NSP M&E Framework

|  |  | Baseline |  |  | Timeframe and targets |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| SP/Ind | Indicator name | Value | Year | Source | 2019 | 2020 | 2021 | 2022 | Source of data |
|  | Impact indicators |  |  |  |  |  |  |  |  |
| I1 | HIV prevalence rate (% and per 100,000 population) | 0.40% (400/100,000) | 2017 | SPECTRUM | <500 | <500 | <500 | <500 | SPECTRUM |
| I2 | AIDS-related mortality per 100,000 population | 1.9/100,000 | 2017 | Routine monitoring data | ≤2.0 | ≤2.0 | ≤2.0 | ≤2.0 | Routine monitoring data/Civil registration/SPECTRUM |
| I3 | Percentage of men having sex with men (MSM) who are living with HIV | 21% (Tbilisi) | 2015 | IBBSS | <25% | <25% | <25% | <25% | IBBSS |
| I4 | Percentage of sex workers (SW) who are living with HIV | <2% | 2017 | IBBSS | <2% | <2% | <2% | <2% | IBBSS |
| I5 | Percentage of people who inject drugs (PWID) who are living with HIV | 2.30% | 2017 | IBBSS | <3% | <3% | <3% | <3% | IBBSS |
| I6 | HIV Incidence rate (per 1,000 population) | 0.22 | 2017 | SPECTRUM | 0.19 | 0.16 | 0.13 | 0.1 | SPECTRUM |
| I7 | Congenital syphilis rate (per 100,000 live births) | 15.2 (N=8) | 2017 | Routine HIS | <50 | <50 | <50 | <50 | Routine HIS |
|  | Outcome indicators |  |  |  |  |  |  |  |  |
| O8 | Percentage of people living with HIV who know their status | 48% | 2017 | SPECTRUM | 60% | 70% | 80% | 90% | SPECTRUM/ monitoring data |
| O9 | Late HIV diagnosis | 51.4% (=<350); | 2017 | Monitoring data | 45% | 40% | 35% | 30% | Monitoring data |
|  |  | 33.7% (=<200) | 2017 | Monitoring data | 30% | 25% | 20% | 20% | Monitoring data |
| O10 | ART coverage: Percentage of people living with HIV currently receiving ART among the estimated number of adults and children living with HIV | 39% | 2017 | SPECTRUM | 54% | 63% | 72% | 81% | SPECTRUM |
| O11 | Percentage of adults and children with HIV known to be on treatment 12 months after initiating treatment among patients initiating antiretroviral therapy | 87% | 2017 | Routine HIS | 89% | 90% | 90% | 90% | Routine HIS |
| O12 | Number of People living with HIV who know their status | 5,090 | 2,017 | Surveillence/National AIDS HIS | 6,800 | 8,200 | 9,600 | 11,000 | Surveillence/National AIDS HIS |
| O13 | Percentage of men reporting the use of a condom the last time they had anal sex with a male partner | 63.2% in Tbilisi | 2015 | IBBSS | 70% |  | 80% |  | IBBSS |
|  |  | 78.8% in Batumi | 2015 | IBBSS | 80% |  | 85% |  | IBBSS |
| O14 | Percentage of SW reporting the use of a condom with their most recent client | 96% in Tbilisi; 90% in Batumi | 2017 | IBBSS |  | >90% |  |  | IBBSS |
| O15 | Number of needles and syringes distributed per PWID per year | 73 syringes per person per year | 2017 | Program data | 100 | 110 | 120 | 150 | Program data |
| O16 | Percentage of PWID reporting the use of sterile injecting equipment the last time they injected | 81% | 2017 | IBBSS |  | >90% |  |  | IBBSS |
|  | Coverage/Output indicators |  |  |  |  |  |  |  |  |
| SP1 | Prevent HIV transmission, detect HIV, and ensure timely progression to care and treatment among the key affected populations |  |  |  |  |  |  |  |  |
| 1.1 | HIV Prevention among PWID |  |  |  |  |  |  |  |  |
| COV17 | Percentage of PWIDs reporting having received a combined set of HIV prevention interventions (last year) | 23% | 2017 | IBBS |  | 60% |  |  | IBBSS |
|  |  | 52% | 2017 | Program data | 60% | 65% | 70% | 75% | Routine monitoring data |
| COV18 | Percentage of PWIDs reporting having received a combined set of HIV prevention interventions (past three months) | NA |  | IBBSS |  | TBD |  |  | IBBSS |
| COV19 | Percentage of PWIDs who tested for HIV in the past 12 months, or who know their current HIV status | 36% | 2017 | IBBSS |  | 50% |  |  | IBBSS |
|  |  | 50% | 2017 | Program data | 55% | 60% | 65% | 70% | Routine monitoring data |
|  | Opioid Substitution Treatment (OST) |  |  |  |  |  |  |  |  |
| COV20 | Number of individuals receiving OST | 8038 | 2017 | Program data | 9500 | 11000 | 11000 | 11000 | Program data |
| COV21 | Percentage of people who inject drugs (PWID)receiving OST | 49% | 2017 | Program data | 58% | 68% | 68% | 68% | Program data |
| COV22 | Percentage of individuals receiving OST who received treatment for at least 6 months | 47% | 2017 | Program data | 65% | 70% | 70% | 70% | Program data |
| COV23 | Number of prisoners who received OST in penitentiary system | 533 | 2017 | Program data | NA | NA | NA | NA | Program data |
|  | HIV Prevention among MSM |  |  |  |  |  |  |  |  |
| COV24 | Percentage of MSM reporting having received a combined set of HIV prevention interventions (last year) | 43.5% in Tbilisi; 40% in Batumi | 2015 | IBBSS | 50% |  | 60% |  | Routine monitoring data |
|  |  | 22% in Tbilisi, Batumi, Kutaisi | 2017 | Program data | 30% | 35% | 40% | 45% | Program data |
| COV25 | Percentage of MSM reporting having received a combined set of HIV prevention interventions (past three months) | NA |  | IBBS | TBD |  | TBD |  | IBBS |
| COV26 | Percentage of MSM who tested for HIV in the past 12 months, or who know their current HIV status | 38.4% in Tbilis; 43% in Batumi | 2015 | IBBS | 45% |  | 60% |  | Routine monitoring data |
|  |  | 13% in Tbilisi, Batumi, Kutaisi | 2017 | Program data | 20% | 25% | 30% | 35% | Program data |
| COV27 | People receiving pre-exposure prophylaxis | 50 | 2017 | Program data | 200 | 300 | 400 | 500 | Program data |
|  | HIV Prevention among FSW |  |  |  |  |  |  |  |  |
| COV28 | Percentage of SWs reporting having received a combined set of HIV prevention interventions (last year) | 63% in Tbilisi; | 2017 | IBBS |  | 70% |  |  | IBBS |
|  |  | 77% in Batumi | 2017 | IBBS |  | 80% |  |  | IBBS |
|  |  | 52% in Tbilisi, Kutaisi, Batumi, Zugdid, Telavi | 2017 | Program data | 55% | 60% | 60% | 60% | Program data |
| COV29 | Percentage of SWs reporting having received a combined set of HIV prevention interventions (past three months) | NA |  | IBBS |  | TBD |  |  | IBBS |
| COV30 | Percentage of SWs who tested for HIV in the past 12 months, or who know their current HIV status | 31% in Tbilisi | 2017 | IBBS |  | 50% |  |  | IBBS |
|  |  | 58% in Batumi | 2017 | IBBS |  | 60% |  |  | IBBS |
|  |  | 33% in Tbilisi, Kutaisi, Batumi, Zugdid, Telavi | 2017 | Program data | 40% | 45% | 50% | 55% | Program data |
|  | HIV Prevention among prisoners |  |  |  |  |  |  |  |  |
| COV31 | Percentage of prisoners that have received an HIV test during the reporting period and know their results | 60% | 2017 | Routine monitoring data | 65% | 70% | 75% | 75% | Routine monitoring data |
|  | Expanding Provider Initiated Testing (PIT) to improve HIV case detection |  |  |  |  |  |  |  |  |
| COV32 | Number of hospitalized patients who received PIT and know their results | NA | 2017 | Routine monitoring data | 300,000 | 300,000 | 300,000 | 300,000 | Routine monitoring data |
| COV33 | Number of patients visiting primary healthcare who received PIT and know their results | NA | 2017 | Routine monitoring data | 120,000 | 150,000 | 175,000 | 200,000 | Routine monitoring data |
| COV34 | Sero-positivity rate among persons tested through PIT | NA |  | Routine monitoring data | NA | NA | NA | NA | Routine monitoring data |
|  | Ensuring safety of donor blood |  |  |  |  |  |  |  |  |
| COV35 | Percentage of blood units screened for HIV in a quality assured manner | 100% | 2017 | Routine monitoring data | 100% | 100% | 100% | 100% | Routine monitoring data |
| COV36 | Percentage of voluntary donors | 28% | 2018 | Routine monitoring data | 30% | 35% | 40% | 45% | Routine monitoring data |
|  | Elimination of Mother to Child Transmission of HIV (EMTCT) |  |  |  |  |  |  |  |  |
| COV37 | Percentage of pregnant women who were tested for HIV and received results | 94% | 2017 | Routine Monitoring data | >=95% | >=95% | >=95% | >=95% | Routine monitoring data |
| COV38 | Percentage of HIV-positive pregnant women who received antiretroviral to reduce the risk of mother-to-child transmission | 85% | 2017 | SPECTRUM | >= 95% | >= 95% | >= 95% | >= 95% | Routine monitoring data |
| COV39 | Percentage of infants born to HIV-positive women receiving a virological test for HIV within 2 months of birth | 100% (actual N=51) | 2017 | Routine Monitoring data | >= 95% | >= 95% | >= 95% | >= 95% | Routine monitoring data |
| COV40 | HIV prevalence among pregnant women (%) | 0.10% | 2017 | Routine Monitoring data (MCH Strategy) | <0.05% | <0.05% | <0.05% | <0.05% | Routine monitoring data |
| COV41 | Coverage of syphilis testing in women attending antenatal care services: Percentage of pregnant women who were tested for syphilis (at least once during pregnancy) | 92% (52,938/57,428) | 2017 | Routine Monitoring data | >= 95% | >= 95% | >= 95% | >= 95% | Routine monitoring data |
| COV42 | Percentage of pregnant women attending antenatal clinics with a positive (reactive) syphilis serology | 0.3% (176/52,938) | 2017 | Routine Monitoring data | 0.10% | <0.1% | <0.1% | <0.1% | Routine monitoring data |
| COV43 | Percentage of antenatal care attendees during a specified period with a positive syphilis serology who were treated adequately | NA | NA | NA | >95% | >95% | >95% | >95% | Routine monitoring data |
| 2 | [HIV Care and Treatment] Improve HIV health outcomes through ensuring universal access to quality treatment, care and support |  |  |  |  |  |  |  |  |
|  | Ensure uninterrupted delivery of high quality treatment and care |  |  |  |  |  |  |  |  |
| COV44 | Number of adults and children currently receiving antiretroviral therapy in accordance with the nationally approved treatment protocol at the end of the reporting period. | 4144 including abkhazia | 2017 | Routine monitoring data/ National AIDS HIS | 6100 | 7400 | 8600 | 9900 | National AIDS Health Information System Routine monitoring data |
| COV45 | Percentage of people on ART who are virologically suppressed (VL) with VL level ≤ 1000 copies/ml | 89% | 2017 | Routine monitoring data/ National AIDS HIS | 90% | 90% | 90% | 90% | Routine monitoring data/ National AIDS HIS |
| COV46 | Percentage of healthcare facilities reporting no stock-outs of ARV medicines | 100% | 2017 | Routine monitoring data | 100% | 100% | 100% | 100% | Routine monitoring data |
|  | Reduce morbidity and mortality due to TB and HCV co-infections and injecting drug use |  |  |  |  |  |  |  |  |
| COV47 | Percentage of estimated HIV-positive incident TB cases that received treatment for both TB and HIV | 92% | 2016 | Routine monitoring data | >90% | >90% | >90% | >90% | Routine monitoring data |
| COV48 | Number of adults and children newly enrolled in HIV care who also start isoniazid preventive therapy treatment during the reporting period | 115 | 2017 | Routine monitoring data |  |  |  |  | Routine monitoring data |
|  | Ensure provision of care and support services for PLHIV |  |  |  |  |  |  |  |  |
| COV49 | Number of People living with or affected by HIV reached with community care and support services in community settings | 1578 | 2017 | Program data | 1700 | 1900 | 2100 | 2300 | Program data |
| 3 | Governance and Policy development: Ensure sustainability of response to the epidemic through enhanced government commitment, enabling legislative and operational environment, and greater involvement of civil society. |  |  |  |  |  |  |  |  |
| 3.1 | Create Conducive legal environment for HIV response |  |  |  |  |  |  |  |  |
| GOV50 | Georgian Criminal Code and Administrative Offences Code, Georgia Framework Law on Drugs, Psychotropic Substances, Precursors and Narcological Aids - revised; amendments adopted to remove barriers to HIV& harm reduction services | NA |  |  | X |  |  |  | Matsne.gov.ge |
| GOV51 | The 4-pillar Drug Policy, Anti-drug strategy and 3-year Action Plan developed and approved by the Government | NA |  |  |  | X |  |  | Drug Policy; Anti-drug Strategy; Action Plan; Government resolution |
|  | Review HIV/AIDS State Law and development and adoption of corresponding bylaws |  |  |  |  |  |  |  |  |
| 3.2 | Ensure adequacy of state budget allocations for HIV prevention and treatment to sustain and scale-up the national response |  |  |  |  |  |  |  |  |
| GOV52 | Share of public spending out of the total spending for HIV national response | 76% | 2018 |  |  |  | 86% |  | HIV/AIDS Spending data |
| GOV53 | Total allocation of public funding for prevention programs targeting KAPs including low threshold services, and community support services |  |  |  |  |  |  |  | Program Budgets; AIDS spending data ; GARP Funding Matrix |
| GOV54 | Total public funding for HIV prevention services targeting FSWs | $ 8,169.00 | 2018 | HIV NSP 2016-2018 |  |  |  |  |  |
| GOV55 | Total public funding for HIV prevention services targeting MSM | $ 5,783.00 | 2018 | HIV NSP 2016-2018 |  |  |  |  |  |
| GOV56 | Total public funding for HIV prevention services targeting PWIDs (excluding OST) | $ 56,585.00 | 2018 | HIV NSP 2016-2018 |  |  |  |  |  |
| GOV57 | Share of public spending out of the total spending on IBBSs & PSE among KAPs (%) |  |  |  |  | 50% |  | 70% |  |
| GOV58 | Analyzing data on AIDS spending by each KAP to assess allocative efficiency | NA | NA |  | X | X | X | X | AIDS spending annual report, which includes the section on allocative efficiency |
|  | Review State Procurement Law and relevant regulations to identify potential barriers for non-state actors, including community-base dorganizations to deliver HIV services under the state funding |  |  |  |  |  |  |  |  |
| GOV59 | Barriers and opportunities for CSOs/CBOs to satisfy the state procurement requirements identified | NA | NA |  | X |  |  |  | Report outlining barriers and capacity of CSOs for participating in state tenders |
| GOV60 | Detailed operational manual to support CSOs participation in state tendering developed | NA | NA |  | X |  |  |  | Operational manual |
|  | Development and implementation of stigma reduction activities by PLHIV organizations and KAP networks |  |  |  |  |  |  |  |  |
| GOV61 | Percentage of women and men aged 15-49 expressing accepting attitudes | TBD |  | MICS | TBD |  |  | TBD | Routine monitoring data |
| 3.3 | Generate evidence for informed decision making |  |  |  |  |  |  |  |  |
|  | Integrated bio-behavioural surveillance studies (IBBSS) among KAPs incorporating population size estimates: PWID, FSW, MSM, prisoners and street Children and youth. |  |  |  |  |  |  |  |  |
| HIS62 | IBBSS and PSE among PWIDs |  |  |  |  | X |  |  | Routine monitoring data |
| HIS63 | IBBSS and PSE for FSWs |  |  |  |  | X |  |  | Routine monitoring data |
| HIS64 | IBBS and PSE among MSM |  |  |  |  |  | X |  | Routine monitoring data |
| HIS65 | IBBS among prisoners |  |  |  |  | X |  |  | Routine monitoring data |
| HIS66 | HIV vulnerability and size estimation study among street children |  |  |  | X |  |  |  |  |
| HIS67 | IBBSS among youth |  |  |  | X |  |  |  | Routine monitoring data |
|  | Improve quality of HIV prevention services |  |  |  |  |  |  |  |  |
| SER68 | HIV prevention service national standards for each KAP (MSM&MSMW; FSWs) approved | NA |  |  | X |  |  |  | Approval notification /formal resolution |
| SER69 | Harm Reduction service national standards approved | NA |  |  | X |  |  |  | Approval notification /formal resolution |
|  | Accountability |  |  |  |  |  |  |  |  |
| ACC70 | HIV programmatic and financial reports published and are accessible on public domains | NA |  |  | X | X | X | X | Programmatic/financial reports; websites. |
|  | Monitoring and Evaluation of HIV NSP 2018-2022 |  |  |  |  |  |  |  |  |
|  | Monitoring the progress towards implementation of NSP by external M&E committee and communitiy reveiwers |  |  |  |  |  |  |  |  |
| MON71 | Operational Manual for NSP Monitoring and Evaluation developed | NA | NA |  | X |  |  |  | Operational Manual |
| MON72 | M&E reports about achievements against the Transition Plan indicators produced annually and are accessible to public | NA | NA |  | X | X | X | X | Annual M&E reports uploaded on the NCDC, MOH, CCM websites |

# References

- 90–90–90 - An ambitious treatment target to help end the AIDS epidemic. http://www.unaids.org/en/resources/documents/2017/90-90-90

- Chkhartishvili N, Sharvadze L, Chokoshvili O et al. Mortality and causes of death among HIV-infected individuals in the country of Georgia: 1989-2012. AIDS Res Hum Retroviruses. 2014;30:560-6.

- Evaluation cost-effectiveness of needle and syringe program in Georgia, UNAIDS, 2011 http://altgeorgia.ge/2012/myfiles/UNAIDS_reporrt_eng.pdf

- Government of Georgia. Ordinance No 36. February 2013 http://ssa.gov.ge/files/01_GEO/KANONMDEBLOBA/Kanon%20Qvemdebare/92.pdf

- Government of Georgia. Ordinance No 724. December 2014. https://matsne.gov.ge/en/document/view/2657250

- HIV risk and prevention behaviours among Prison Inmates in Georgia; Curatio International Foundation Center for Information and Counseling on Reproductive Health – Tanadgoma; http://new.tanadgomaweb.ge/upfiles/dfltcontent/3/157.pdf

- http://www.unaids.org/en/regionscountries/countries/georgia

- https://aidscenter.ge/epidsituation_eng.html

- https://www.theglobalfund.org/media/5641/core_projectedtransitionsby2025_list_en.pdf?u=63657063671000000020

- https://www.un.org/sustainabledevelopment/sustainable-development-goals/

- Integrated Bio-behavioral surveillance and population size estimation survey among Female Sex Workers in Tbilisi and Batumi, Georgia; Curatio International Foundation Center for Information and Counseling on Reproductive Health – Tanadgoma; http://new.tanadgomaweb.ge/upfiles/dfltcontent/3/167.pdf

- National Bank of Georgia; https://www.nbg.gov.ge/index.php?m=340&newsid=3320 Accessed on April 10, 2018

- Population Size Estimation of Female Sex Workers In Tbilisi and Batumi, Georgia 2014; Curatio International Foundation Center for Information and Counseling on Reproductive Health – Tanadgoma; http://new.tanadgomaweb.ge/upfiles/dfltcontent/3/150.pdf

- Population Size Estimation of Men Who Have Sex with Men in Georgia, 2014; Curatio International Foundation Center for Information and Counseling on Reproductive Health – Tanadgoma; http://www.georgia-ccm.ge/wp-content/uploads/MSM-PSE-09.12.2014_Geo.pdf

- Population Size Estimation of People Who Inject Drugs in Seven Cities of Georgia, 2016-2017, Bemoni Public Union(BPU); Curatio International Foundation (CIF)

- The Georgia Law on the State Budget of Georgia, MoF, 2016.

- UNAIDS estimates 2017. http://www.unaids.org/en/regionscountries/countries/georgia/

- World Health Organization. Global Tuberculosis Report 2017. Geneva: WHO; 2017.

- World Health Organization. Tuberculosis country profiles (http://www.who.int/tb/country/data/profiles/en/). 2018 vol; 2018

- World Health Organization. World Tuberculosis Report 2016. Geneva: WHO; 2016.

Government of Georgia. Ordinance No 36. February 2013 http://ssa.gov.ge/files/01_GEO/KANONMDEBLOBA/Kanon%20Qvemdebare/92.pdf

Government of Georgia. Ordinance No 724. December 2014. https://matsne.gov.ge/en/document/view/2657250

The Georgia Law on the State Budget of Georgia, MoF, 2016.

National Bank of Georgia; https://www.nbg.gov.ge/index.php?m=340&newsid=3320 Accessed on April 10, 2018

https://www.theglobalfund.org/media/5641/core_projectedtransitionsby2025_list_en.pdf?u=63657063671000000020

https://www.un.org/sustainabledevelopment/sustainable-development-goals/

### 90–90–90 - An ambitious treatment target to help end the AIDS epidemic. http://www.unaids.org/en/resources/documents/2017/90-90-90

https://aidscenter.ge/epidsituation_eng.html

UNAIDS estimates 2017. http://www.unaids.org/en/regionscountries/countries/georgia/

Population Size Estimation of Men Who Have Sex with Men in Georgia, 2014; Curatio International Foundation Center for Information and Counseling on Reproductive Health – Tanadgoma; http://www.georgia-ccm.ge/wp-content/uploads/MSM-PSE-09.12.2014_Geo.pdf

http://www.unaids.org/en/regionscountries/countries/georgia

Population Size Estimation of People Who Inject Drugs in Seven Cities of Georgia, 2016-2017, Bemoni Public Union(BPU); Curatio International Foundation (CIF)

Population Size Estimation of Female Sex Workers In Tbilisi and Batumi, Georgia 2014; Curatio International Foundation Center for Information and Counseling on Reproductive Health – Tanadgoma; http://new.tanadgomaweb.ge/upfiles/dfltcontent/3/150.pdf

Integrated Bio-behavioral surveillance and population size estimation survey among Female Sex Workers in Tbilisi and Batumi, Georgia; Curatio International Foundation Center for Information and Counseling on Reproductive Health – Tanadgoma; http://new.tanadgomaweb.ge/upfiles/dfltcontent/3/167.pdf

HIV risk and prevention behaviours among Prison Inmates in Georgia; Curatio International Foundation Center for Information and Counseling on Reproductive Health – Tanadgoma; http://new.tanadgomaweb.ge/upfiles/dfltcontent/3/157.pdf

Chkhartishvili N, Sharvadze L, Chokoshvili O et al. Mortality and causes of death among HIV-infected individuals in the country of Georgia: 1989-2012. AIDS Res Hum Retroviruses. 2014;30:560-6.

World Health Organization. World Tuberculosis Report 2016. Geneva: WHO; 2016.

World Health Organization. Global Tuberculosis Report 2017. Geneva: WHO; 2017.

World Health Organization. Tuberculosis country profiles (http://www.who.int/tb/country/data/profiles/en/). 2018 vol; 2018

National AIDS Center (Infectious Diseases, AIDS and Clinical Immunology Research Center) Data

Evaluation cost-effectiveness of needle and syringe program in Georgia, UNAIDS, 2011 http://altgeorgia.ge/2012/myfiles/UNAIDS_reporrt_eng.pdf

Expenditures for 2018 are projected

Expenditures for 2018 are projected

http://databank.worldbank.org/data/reports.aspx?source=world-development-indicators#

HIV risk and prevention behaviors among People Who Inject Drugs in seven cities of Georgia, 2016-2017, Bemoni Public Union(BPU); Curatio International Foundation (CIF)

Estimated number of PLWH was recently validated by UNAIDS in the process of SPECTRUM update.