Recommendations on the Development of

Quality Improvement Organizations for the Republic of Georgia

Dr. Ben Chan, MD MPH MPA

World Bank Consultant

15 April 2014

Table of Contents

Executive Summary	6

Context	11

Key Findings – Quality Management Infrastructure in Georgia	13

1 Quality Measurement	13

2 Public Reporting	14

3  QI capacity	15

4  Improvement Campaigns	16

5 Decision Supports	17

6 Patient and Public Engagement	18

7 Accreditation	19

8 Regulation and Inspection	20

9 Incentives and Accountability	21

10 Quality Planning	22

Configuration of Roles for Quality Management in Other Jurisdictions	23

Recommendations:	24

Potential Benefits	32

Proposed High-level Workplan	33

Appendix 1:  Terms of Reference	35

Appendix II:  Methods	38

Appendix III:  Key Informant Interviews	40

Appendix IV:  Participants in Stakeholder Roundtable	41

Appendix V:  Examples of Public Reporting	42

Appendix VI:  Examples of Decision Tools	44

Appendix VII:  Roles and Governance Structures of Health Quality Organizations Around the World	51

Appendix VIII:  Sample Job Description for Quality Improvement Facilitators	54

References	56

# Executive Summary

The Republic of Georgia has made important strides in strengthening its health system, including investments in primary care infrastructure, practice guideline development, disease surveillance mechanisms, and most recently, establishment of universal health coverage for its citizens.  Despite these advancements, important gaps remain in ensuring the quality of health services.  Patients with chronic conditions, such as hypertension, are not being adequately managed; cancer screening is suboptimal; and there are further opportunities to improve maternal and child health outcomes.

A critical next step is the establishment of a robust infrastructure for managing quality.   This World Bank mission analysed models used in other countries, and examined the opinions of key government and external stakeholders on their preferences for what the quality management infrastructure would do and how it should be organized.

Based on the review of international quality organizations, this report identifies ten core functions necessary in a quality improvement strategy.  Table 1 describes, in each of these functions, what leading jurisdictions in the world are doing, and current activities or strengths within Georgia which can be leveraged as well as gaps that need to be filled.  In general, Georgia has some important activities and experience in gathering health data to build upon, but will require a significant expansion of these functions in order to collect more detailed data on quality.  More importantly, its current infrastructure is geared more towards quality assurance (QA)– the process of inspecting for quality and issuing sanctions – rather than quality improvement (QI), the science of helping health care teams diagnose system-based problems with quality and develop solutions.  Changing this paradigm and culture will require a massive re-orientation of activities from QA to QI, and intensive investment in capacity building and training on QI methods.

The literature review shows that health care jurisdictions around the world generally have multiple quality management entities to support their quality agendas, each with a different combination of the ten roles described above.  These entities may operate branches within Ministries of Health, arms-length government agencies, or as independent not-for-profit organizations on contract with the Ministry.

Table 1:  Implementation of Ten Quality Functions in International Settings Compared to Georgia

| Quality Function | International Context | Situation in Georgia |
| --- | --- | --- |
| 1 Quality Measurement | Broad range of quality measures collected in different sectors (hospital, primary care, prevention) across multiple dimensions of quality (e.g. timeliness, effectiveness, safety, experience). Many places collect patient-level quality data, while others institution-level data. | The National Center for Disease Control (NCDC) has strengths in data collection and analysis of disease surveillance and utilization. Most data is at an institution-level. There major gaps in quality data (e.g. adoption of best practices, chronic disease management, patient experience, adverse events). |
| 2 Public Reporting | Jurisdictions moving to public reporting of quality measures by individual health care institution to increase public accountability. | Public reporting on disease surveillance measures exists but only at a regional level. |
| 3 QI Capacity Building | Quality agencies provide training, coaches to increase QI skills in the health care workforce (eg. root cause analysis, process mapping, implementing tests of change, team-building, conflict resolution). | No such national infrastructure exists. |
| 4 QI Campaigns | Quality agencies launch campaigns around specific topics (e.g. reducing wait times, adverse events, nosocomial infections, improving chronic disease management), and recruit health care organizations to participate voluntarily. | No national campaigns exist. The Health System Strengthening initiative in Imereti, led by University Research Corporation & funded by USAID, is a strong example of such a campaign at a regional level. |
| 5 Decision Supports | Practical tools (e.g.flowsheets, standard orders) remind providers to prescribe the right drugs, tests at the right time. Some jurisdictions select standard tools for use by all providers, while others rely on voluntary adoption. | The Imereti project (above) led to the creation of some standard tools (e.g. flowsheets) but there is no plan yet to spread these across the country. |
| 6 Patient Engagement | Different methods are used to get patients to be involved in care decisions, be vigilant about quality issues, and participate in system redesign. | Public awareness campaigns helped patients access universal health coverage. Major gaps still exist. |
| 7 Accreditation | Independent accrediting bodies conduct periodic assessments of organizations against established standards. | Successful pilot project for hospital accreditation for perinatal care is near completion. |
| 8 Quality Assurance & Regulation | Government entities conduct inspection of facilities. Licensing bodies issue licenses to providers, with increasing emphasis on recertification. | The State Regulatory Agency for Medical Services inspects facilities, issues licenses, investigates complaints. Gaps in use of quality criteria in inspections. Major concerns regarding consistency of clinical skills in workforce. |
| 9 Accountability & Incentives | Many jurisdictions looking to tie quality expectations to funding arrangements. | No funding mechanisms yet which account for quality. |
| 10 Quality Planning | Some jurisdictions have detailed plans which cascade to specific expectations for each health care organization and expectations for providers within each organization. | There have been past attempts at setting national priorities (e.g. the Mililenium Development Goals) but this has not been backed with specific expectations, indicators and targets for individual organizations. |

Recommendations

- The MOLHSA should establish a national quality improvement agency, with a mandate to:

- Provide support to health care organizations to develop QI capacity.

- Make recommends to government on a national quality indicator dataset, priority topics for improvement, and quality indicators to be included in accountability agreements with health care organizations.

- Lead improvement campaigns in areas identified by MOLHSA as a priority for action.

- Recommend clinical decision support tools for national adoption, and make recommendations to the IT division of MOLHSA on decision supports to be incorporated in the design of future electronic health record systems.

- Encourage patients on how to be engaged in their health care in order to improve quality.

- Conduct public reporting at an individual organizational level in the long-term.

1b The agency should be established as a legal entity under public law(LEPL), although in the short-term (first 12 months) it could be created within the Ministry to expedite its creation.

1c  The Agency should have a strong Advisory Board to provide strategic advice to the Head of the Agency and act as ambassadors for quality improvement,  with a maximum size of 12 persons or less.

1d.  A communications and stakeholder relations function should be formally established within the Agency.

1e.  Evaluation of the Agency’s success should be based primarily on the extent to which health care organizations find the Agency’s support useful and the amount of quality improvement capacity achieved, and secondarily on the success rate that organizations are having in making improvements in quality indicators.

1f.  The QI Agency should have a minimum staff complement of 20, based on benchmarks from similar international agencies.

2.  The National Center for Disease Control should be assigned the responsibility of standardized quality measurement, responsible for:

- Working in partnership with the QI agency and MOLHSA to develop a national quality indicator dataset (with the final decision on indicator choice to rest with MOLHSA, as noted below)

- Setting technical definitions for all indicators

- Setting standards for data collection and reporting

- Establishing training and certification program for data coders

- Conducting statistical analyses of data, including:  comparisons on quality indicators by individual organization and administrative region; changes over time, for each organization, each region and at the national level

- Preparing reports.

NCDC should start with requiring mandatory data submissions on quality indicators from health care institutions.  This will require 5 to 10 additional staff for these new responsibilities.

NCDC should give consideration to the development of person-oriented databases to allow for more detailed data on quality.  This will require additional resources should this option be chosen.

- The Ministry should create a separate Accreditation Body, preferably as a legal entity under public law, in order to ensure that ratings of organizations is done independently and free from political interference.   The Accreditation Body can be started within the Ministry first, but LEPL status should be achieved within 12 to 18 months.

3b.  The Accreditation Body should implement hospital perinatal care standards first.  For subsequent clinically-focused accreditation standards, the choice of clinical area should be aligned with national quality campaigns launched by the QI Agency.

3c.  The Accreditation Body should appoint an Advisory Council to advise and approve continuing improvements to the accreditation process and oversee decisions on the granting of accreditation status.

3d.  The Accreditation Body should seek accreditation by the International Society for Quality (ISQuA).

3e.  The Accreditation Body will require an estimated 5 staff to commence operations.

- The State Regulatory Agency for Medical Activities should continue its QA roles (issuing permits & certifications for medical professionals & hospitals, investigating patient complaints, conducting inspections).  To improve its effectiveness, it should:

- Introduce some clinically relevant standards into the inspection process.

- Consider introducing some form of physician re-licensure, with observed, structured clinical examinations (OSCE) which are now the standard for assessing physician skills in many countries.

- Consider taking on responsibilities for verifying that health care organizations are submitting accurate data on quality to NCDC.

- Examine means of shifting resources from QA to QI activities (described in recommendation 1) or to the more value-added QA activities described above.

- The Ministry should establish a quality strategy and planning group within the Ministry itself. The role of this unit will be to:

- Draft a national quality plan, with annual updates

- Set system-wide priorities for quality improvement initiatives

- Ensure alignment of activities across the health system with these priorities

- Approve the national quality indicator set which will monitor progress with the plan

- Suggest specific system-wide targets for improvement with a time period for completion

- The Ministry should phase-in over a multi-year period expectations for quality as a condition of receiving funding from the Universal Health Coverage program.  This could be done in four phases:  pay for completion of training; pay for submission of data; pay for process improvements; pay for improvements in outcomes. Responsibility for financial accountability for quality should remain in the Ministry.

Table 2 summarizes the proposed roles and responsibilities:

| Organization / Agency | Role |
| --- | --- |
| MOLHSA – Quality Strategy & Planning Group | Set clinical priorities for improvement Establish a national quality improvement plan Approve the national quality indicator set (items above to be updated annually, taking into account technical advice from QI Agency) |
| Quality Improvement Agency | Support QI capacity building Lead national improvement campaigns Implement national clinical decision supports |
| National Center for Disease Control | Collect and analyze data based on national quality indicator dataset Develop data collection standards and processes |
| Accreditation Body | Set accreditation standards Accredit individual health care organizations |
| MOLHSA – Social Service Agency | Set accountabilities for quality for each health care organization receiving public funds (based on recommendations from QI Agency) Issue regulations and mandates periodically |
| State Regulatory Agency for Medical Activities | Issue permits and licenses to practice/operate Inspect organizations for clinically relevant standards for infrastructure Manage re-licensure initiatives with skills verification for physicians Inspect compliance with data collection standards Investigate unresolved patient complaints |
| MOLHSA – IT division | Implement decision support and data collection tools into electronic health record, as recommended by QI Agency |

Sustaining this quality infrastructure will require annual commitments by MOLHSA of additional 30-35 staff within the QI Agency, Accreditation Body and NCDC.   The Ministry may consider offsetting these costs through reallocation of resources from the State Regulatory Agency on Medical Activities.  Resources will also be needed for training,travel, meetings, office overhead, and purchase of decision supports or learning materials from other sources.

To accelerate the development of QI infrastructure, the Ministry may wish to consider a one-time investment in the form of donor grants or loans for a large-scale national improvement initiative on multiple topics in hospital, primary care and preventive care sectors, which could potentially train over 150 individuals in health care organizations to become improvement advisors.

# Context

Georgia, a nation of 4.5 million persons in the central Caucasian region of Europe, is in the midst of a major transformation of its health system.  In 2013, the nation’s new political leadership passed legislation extending universal health coverage for core medical services to all citizens.  This important step builds on other initiatives to strengthen the health care sector, such as major investments by donor organizations to establish a primary care system, development of national clinical practice guidelines, and creation of the National Centre for Disease Control.

However, with these milestones accomplished, larger questions remain regarding the ability of the health care system to meet the needs of the population.  Are the services being provided of good quality?  Are patients getting the evidence-based best practices recommended for their condition?  Are there barriers to accessing services, beyond financial ones?  Do patients have confidence in the system?  Will health outcomes improve?

Major concerns exist about the quality of health care in Georgia.    Utilization of primary care has been very low, less than two visits per year, and although lack of insurance was a critical barrier, there may be other barriers at play.  Drug expenditures are unusually high, with frequent self-medication in lieu of seeking primary care and likely inappropriate drug use.  Life expectancy had seen important gains in the past decade, but has been stalled at 74 years over the past 4 years.  There has been important progress in certain millennium development goals (MDGs) such as maternal and child mortality, but these figures are still short of the intended target.  Non-communicable diseases are a major concern.  There are many gaps in knowledge about how well chronic diseases such as diabetes and heart disease are managed.  In areas where there are some survey data, the answers are not encouraging.  The prevalence of hypertension in adults is 34%, and 61% of these individuals are not receiving the right therapy.  For cancers such as breast, colon, and cervix, many patients are diagnosed at a late stage with an accompanying high mortality rate, suggesting lost opportunities to screen for these conditions and treat them at an early stage.

A previous World Bank mission in May-June 2013 documented these quality concerns in greater detail as well as the weaknesses in the primary care infrastructure, and made recommendations regarding the development of a quality improvement strategy for primary care.  These recommendations included:  establishment of an indicator framework; the adoption of standard flowsheets to track the use of high-priority best practices in the management or monitoring of chronic diseases, maternal and child health and preventive screening; a data collection plan; accreditation; and results-based financing on a phased-in basis to support the adoption of these best practices.

Subsequent discussions with the Ministry of Labour, Health and Social Affairs (MOLHSA) revealed that implementing the above tasks requires dedicated resources, core staff and expertise in quality management and planning.  Other governments around the world have established quality management entities to carry out different activities of a broad quality strategy.  Hence, this World Bank mission aims to assist the MOLHSA establish such a quality management entity – to identify its roles and responsibilities, working relationships with other parts of the Ministry, its governance model and organizational structure, core competencies needed, ranges for possible number of staff required, and a workplan for its establishment (see Terms of Reference in Appendix I).

Quality of Health Care:  Conceptual Frameworks

The Agency for Healthcare Research in Quality in the USA defines quality health care as "doing the right thing at the right time in the right way for the right person and having the best results possible."  The Institute of Medicine in the USA recognizes six dimensions of quality: timeliness (access), safety, effectiveness, patient-centredness, efficiency and equity.  Health care systems need to optimize care in all six dimensions in order to achieve a holistic view of quality.

There are two main paradigms for how organizations manage quality:  quality assurance (QA) and quality improvement (QI).  QA refers to a program for the systematic monitoring and evaluation of the various aspects of a project, service, or facility to ensure that standards of quality are being met.  Typically, a designated inspector examines the product or service for defects in quality or in the manner in which the product/service is produced.  The inspector may then issue directives to improve quality, and may issue sanctions or penalties for failure to comply with established procedures or policies.

QI is defined as “the combined and unceasing efforts of everyone—healthcare professionals, patients and their families, researchers, payers, planners and educators—to make the changes that will lead to better patient outcomes (health), better system performance (care) and better professional development.”   Quality problems occur because health care is delivered within a complex system, with many processes occurring which require a high degree of coordination.  The system fails when there are  poor handoffs from one person to the next, miscommunication, inconsistencies in how things are done, or steps which do not add value and waste time and resources. QI focuses on empowering people to identify and fix these system failures, rather than punishing them for mistakes.

In Baker et al’s world-wide analysis of health care systems with the best results on quality, leaders appear to invest heavily in both dedicated staff and organization-wide activities to bring this type of systems thinking into practice, and operate primarily on a QI rather than QA framework.

Methods

Methods used in this report included review of key government documents, a literature review on mandates and organizational structures of health quality management units worldwide, key informant interviews within Georgia, a stakeholder forum and a site visit to one hospital.

The roles of different quality management entities around the world was mapped, based on the following categories of activities:

- Quality measurement

- Public reporting

- Quality improvement capacity building

- Improvement campaigns

- Decision supports

- Accreditation

- Regulation / inspection

- Accountability & incentives for quality

- Public / health user engagement

- Quality planning

The capacity of health systems with well-developed quality infrastructures in each of these areas was documented and local interviews were conducted to determine the extent to which Georgia had existing strengths to draw upon and gaps in capacity that need to be filled.  Further details on methods are provided in Appendix I.

# Key Findings – Quality Management Infrastructure in Georgia

### 1 Quality Measurement

International context

Data collection is critical to any quality management infrastructure.  The classic tenet is that “you can’t manage what you can’t measure.”  Key activities include:

- Setting standards for data collection

- Selecting quality indicators, which should include outcomes, processes and balancing measures (measures of unintended consequences)

- Conducting regular data quality audits to ensure validity and reliability.

Data can be collected either for each encounter with each individual patient, or as an aggregate result for each institution.  The former is more expensive but provides richer information which allows for identifying factors related to poor quality.  Sweden goes further in use of individual patient data by developing national disease registries, which have for example have avoided an estimated 7500 hip and knee replacement revision surgeries by identifying which implants are most likely to fail.

Reporting of data is another critical function, and should follow the following principles:

- Results should be fed back to providers in as close to real-time as possible

- Results should be reported over  time for each organization so they can track improvements

- Comparisons between peer organizations should be reported to encourage improvement.

Table 3:  Examples of Quality Measurement Activities Worldwide

| Example | Hospital Quality | Nursing Home, Home Care | Primary Care | Patient Experience |
| --- | --- | --- | --- | --- |
| Centres for Medicare & Medicaid (USA) | Hospital Inpatient Quality Reporting Program - each hospital submits aggregate results for selected indicators | RAI-MDS* - quality indicator data on each patient is submitted every quarter | HEDIS – primary care sites submit data on cancer screening, chronic disease management, immunizations | CAHPS family of surveys **(standardized for hospital, nursing home, home care) |
| Canadian Institute for Health Information | Discharge Abstract Database**, National Ambulatory Care Reporting System** - hospitals submit data on each admission, emergency dept visit | RAI-MDS** (as above) |  | National survey under development; CAHPS used in some provinces** |
| Specific provinces in Canada | Wait times registries for surgeries**, patient safety indicators |  |  |  |
| Sweden | Registries (e.g. hip & knee, cataract)** |  | Registries (e.g. diabetes)** |  |

** = data sets which contain individual patient-level data

Situation in Georgia

There are two main organizations in Georgia that collect health data:  the National Centre for Disease Control (NCDC) and the Social Services Agency.  NCDC, a legal entity under public law, is responsible for collecting a broad array of disease surveillance and mortality data.  It also administers programs for control of TB and sexually transmitted diseases and collects program-specific data.  The Social Services Agency collects administrative data necessary for managing reimbursement of health care organizations for services provided.  In general, institutions are required to report aggregate, rather than individual patient-level data.  Table 4 lists strengths and weaknesses of current measurement activities in Georgia.

Table 4:  Strengths and Weaknesses of Quality Measurement Activities in Georgia

| Setting | Strengths | Weaknesses |
| --- | --- | --- |
| Hospital | Hospitals required to submit aggregate data on hospital infections, number of admissions for different conditions (e.g. cancer), maternal and neonatal mortality. Readmission rates can in theory be calculated from existing data. | Stakeholders expressed lack of confidence in quality of hospital infection data. No quality data in other areas (e.g. wait times, rates of complications or adverse events, patient satisfaction) |
| Primary Care | Reproductive Health Survey , STEPS survey for chronic disease risk factor surveillance. Immunization rates, TB completion rates, rates of infectious diseases | No data on chronic disease management and rate of adoption of best practices (e.g. whether or not the right drugs, tests and monitoring are being carried out for patients with diabetes, hypertension, heart disease or other conditions). No data on access to primary care. No patient satisfaction data. |

### 2 Public Reporting

International context

Public reporting of quality measures is now common in many countries (see Appendix IV for examples).  Reporting can be done at multiple levels -- national, by region or province, or by individual institution.  One of the main rationales for public reporting is that when information on quality is released publicly, leaders are motivated to improve because they do not wish to be perceived as lagging behind their peers.  This is the case, even if the public itself does not routinely check on these results.

Achieving transparency to the level of individual institution typically occurs incrementally over several years.  Providers resist micro-level reporting if they feel that the quality of data is poor or that indicators are not valid.  It requires considerable time to develop robust data collection processes and data quality audits, and organizations generally prefer a lead-in period to allow them to validate their data and consider to use the data to improve.  Only when these activities have taken place will public reporting be beneficial.  Without such groundwork taking place, public reporting may encourage under-reporting or miscoding of data and more time will be spent arguing over data quality than on improvement.

Situation in Georgia

At present, there were no examples of public reporting of data by individual organizations.  Reporting does take place at a national and regional level, through the NCDC’s Georgia Yearbook series.

### 3  QI capacity

International context

The ability for organizations to change depends on the existence of strong skills for quality improvement in the workforce.  Such skills include the ability to measure quality; map processes and optimize them; lead teams; and manage conflict and resistance to change, which may arise whenever new processes or ideas or tried.  The concept of organizations investing in developing this type of capacity is recognized in industrial settings.  One branch of QI science derived from the manufacturing industry, six sigma, recommends that organizations aim to ensure that 1-2% of their health care workforce have expert-level (“black belt”) skills, and 10% have moderate level skills (“green belt”).  [REF]

A number of quality management units in the world have made the creation of QI capacity a high priority.  Such organizations have set explicit goals for the number of individuals trained.  For example, Health Quality Ontario trained over 600 clinician-managers, or approximately one individual per nursing home, in core QI skills over a five-year period as part of its Residents First campaign to improve outcomes in this sector.  The Health Quality Council of Saskatchewan is now embarking on an ambitious, $30 million multi-year campaign to provide advanced training in LEAN process management techniques to virtually all senior health care executives in the province, and provide basic training to 25% of all health care workers.

The Qulturum in Jonkoping county, Sweden is an institute with 40 staff dedicated to QI skills development.  Jonkoping’s health system is widely regarded as an international leader in quality, with superior outcomes and lower costs compared to its peers in Sweden.  Individuals with an improvement idea can spend a week at the Institute and receive training and mentorship.  Over 40% of the entire workforce at Jonkoping have receive some degree of training at Qulturum.

Situation in Georgia

All respondents acknowledged that that to date, the primary means of managing quality in Georgia has been quality assurance, rather than quality improvement.  All respondents agreed that a shift towards more modern approaches weighted towards QI is needed, and as such, training in these skills is necessary.  Respondents also noted that as a post-Soviet country, Georgia still had progress to make to reform the culture in many organizations where adherence to bureaucratic procedures under threat of punishment had blunted the skills and desire of individuals to make innovative changes to their work environment.

In October 2012, the MOLHSA issued order N01-63/b, requiring hospitals to develop and implement internal quality improvement systems to continually improve quality and patient-centred care.  While interviewees welcomed this initiative, there was universal concern that there were no clear standards or expectations about the skill levels of the individuals implementing this order, or the types of activities they would be responsible for.  Again, training in QI skills could strengthen the impact of this order.

### 4  Improvement Campaigns

International context

QI organizations periodically launch campaigns around specific, high priority topics.  Health care providers join these campaigns on a voluntary basis and receive support which may include training, data collection tools, decision supports (see below), the assistance of QI coaches, and “learning collaborative” sessions, where participating teams meet regularly in person or through web-based forums to discuss progress and share ideas for improvement.  Some campaigns declare only the topic of improvement, while others (such as the “100,000 lives campaign” of the Institute for Healthcare Improvement in the US) set a specific target for improvement aggregated across all participants, with a specific timeframe for completion.  Table 5 lists examples of past and current campaigns worldwide:

Table 5:  Examples of Quality Improvement Campaigns Worldwide

| Campaign | Organization | Jurisdiction | Aims |
| --- | --- | --- | --- |
| 100,000 Lives Campaign | Institute for Healthcare Improvement | USA | Prevent central line infections, ventilator-associated pneumonia, surgical site infections, adverse drug events, AMI deaths, cardiac arrest |
| Nursing Home Quality Collaborative | Centers for Medicare & Medicaid, State QI Organizations | USA | Reduce restraint use, falls, ulcers in nursing homes |
| Improved Access and Efficiency | Health Quality Ontario | Ontario, Canada | Reduce wait times for a family physician appointment |
| Releasing Time to Care | National Institute for Innovation & Improvement | UK | Reduce wasted staff time due to excess documentation, unnecessary steps, poor space organization |
| Safer Healthcare Now | Canadian Patient Safety Institute | Canada-wide | Reduce hospital infections, pressure ulcers, falls, venous thromboembolism |
| Chronic Disease Management Collaborative | Health Quality Council | Saskatchewan, Canada | Improve process and outcome measures for diabetes & coronary artery disease |

Situation in Georgia

Georgia has adopted the millennium development goals for maternal and child health, but has not implemented national improvement campaigns of the nature described above.  At a regional level, however, the Health Care Improvement Project in Georgia meets all criteria for a campaign.  This initiative, led by the University Research Corporation (URC) and funded by USAID,  is  taking place in 17 ambulatory clinics and village solo practices, two local hospitals and one tertiary care hospital in the Imereti region, with a population of 700,000.  Topics include cardiovascular disease, chronic obstructive pulmonary disease, asthma, and other chronic conditions.  The initiative uses classic QI techniques, learning collaboratives to spread change, and periodic coaching from the URC staff to individual teams. Preliminary results reveal progress in a number of quality measures.  This initiative has funding until 2014.  How this work will be sustained and spread, however, remains unresolved.

### 5 Decision Supports

International context

Medical knowledge is increasing exponentially and practice guidelines are increasingly complex.  It is nearly impossible for individual practitioners to stay current and remember to execute all best practices all the time.  Decision supports are practical tools that help clinicians make diagnosis or treatment decisions.  Examples include checklists, flow sheets, decision trees, clinical pathways, or standard orders.  These tools may exist in paper charts, or can be embedded in electronic medical records (EMRs).

Within primary care, the flowsheet is the most common tool.  Flowsheets allow for systematic recording of patient information at each visit and list medications, treatments, tests or monitoring of symptoms that should occur at specific time periods.  They remind the care provider to implement these best practices, and can also serve as a data collection tool for tracking process and outcome measures.

Many hospitals now use standard order sets, which incorporate all evidence-based practices for a clinical condition.  For example, pre-printed orders for unstable angina include orders for aspirin, heparin, beta-blockers, ACE inhibitors, serial ECGs and troponin levels, so that the doctor will not forget to order them.  The doctor retains the right to cancel any particular order in exceptional circumstances (e.g. drug allergy).  Order sets exist mainly for admission to hospital but can also be used at the time of discharge to ensure certain follow-up activities take place.  There are private vendors of order sets  and the non-profit Institute for Clinical Systems Improvement in Minnesota makes them publicly available (www.icsi.org).

In the international jurisdictions examined, there were few examples of a unified national strategy for deployment of decision tools.  Of note is that the AHRQ in the USA is examining common approaches to reminder systems in EMRs.  Some governments have approved jurisdiction-wide versions of selected tools; in British Columbia and Sakatchewan, Canada,  flowsheets for diabetes, coronary artery disease have been standardized and are used to record data in central databases (see Appendix V).  Prenatal flow sheets are also standardized in each province.  In other instances, QI organizations develop decision tools for a specific improvement campaign, and their adoption is voluntary.

Situation in Georgia

Interviewees were not aware of any national strategy on decision supports.   While there has been good work on developing practice guidelines, the question of adoption has not been addressed.  Interviewees noted that Georgia has made some initial investments in EMRs, but the prototype currently developed has not expanded beyond the ten physician practices representing the pilot testing phase, and tools such as EMR-based reminders have not yet been developed.

The Health System Strengthening initiative of USAID-URC, described above, led to the creation of a number of clinical decision support tools, including flowsheets for chronic conditions, such as diabetes, hypertension, heart disease and COPD.  At a site visit last June to the primary care research and teaching center, some examples of simple tools to assist practitioners in monitoring cardiovascular disease risk were in place.   Interviewees familiar with both these initiatives expressed concern that there are no nation-wide activities to standardize and spread the adoption of these tools.

### 6 Patient and Public Engagement

International context

Patient engagement is important to best practice adoption.  Ensuring that patients understand their condition well is essential to their remembering to take medications and showing up for tests.  Patients who are engaged can help spot medical errors before they occur, and can advocate for better service.

Quality organizations have implemented a variety of patient engagement activities, usually as part of an improvement campaign.   The Manitoba Institute for Patient Safety, for example, runs the “It’s Safe to Ask” campaign, which encourages patients to ask:  “What is my health problem?”, “What do I need to do?”, and “Why do I need to do this?”.  The campaign also features a “It’s Safe to Ask Medication Card” which helps patients record the purpose of each drug and how to take it, to avoid medication errors.

Patients and families can also advocate for better quality.  For example, the Ontario Health Quality Council introduced began publicly reporting falls and pressure ulcers in nursing homes in 2009.  It coupled this milestone with a campaign to encourage family councils in each nursing home to review their local data and ask their administrators what they were doing to reduce these events.

Another example is found in some handwashing campaigns, where patients are encouraged to insist on adoption of best practices, and staff wear buttons saying “Ask me if I’ve washed my hands”.

Many experts advise that patients should participate in QI teams as the patient has unique perspectives that providers do not have.  The Change management guide of NHS Improvement (the UK’s new QI agency) devotes an entire chapter on how QI teams can recruit the ideal patient and manage team dynamics when the patient is included with providers.

Situation in Georgia

Participants were not able to identify any major examples of public engagement campaigns aimed specifically at improving adherence to best practices.  Implementation of universal health insurance, however, did require public education activities aimed at helping the public understand how to register for health insurance and educate them about the benefits available to them.

### 7 Accreditation

Accreditation refers to the a self-assessment and external peer assessment process used by health care organisations to accurately assess their level of performance in relation to established standards and to implement ways to continuously improve.  Accreditation is typically carried out by organisations specialized in this function, who over time have developed a broad range of standards on both clinical quality and management with expert input.  Examples of topics for which standards exist include safe medication practices, infection control procedures, hand hygiene and falls prevention.  Surveyors conduct site visits and assess the extent to standards are met, using various tracer methodologies which may include reviewing processes, procedures and documentation.  The accrediting body provides a rating, depending on the extent to which it meets standards.

Many accreditation organizations provide expertise to other countries to help them implement their own programs.  Examples include Accreditation Canada International, Joint Commission International (USA), QHA Trent Accreditation (UK) and the Australian Council for Healthcare Standards (International).

In all jurisdictions studied, organizations which conduct accreditation are stand-alone organizations or agencies whose sole purpose is accreditation.  Jurisdictions vary as to whether accreditation is voluntary or mandatory.

Local situation in Georgia

There is no formal accrediting body yet in Georgia.  However, developing an accreditation process is a high priority for MOLHSA.  As part of a past development policy operation (DPO) with the World Bank, the Republic of Georgia committed to initiating activities that would build towards accreditation as one of the conditions for receiving funding and loan support. Ministry officials have expressed a preference for locally-developed accreditation standards and processes.  This is driven in part by the prohibitive cost of outsourcing tools from international organizations, as well as the desire to have standards that match local needs and capacity.

To that end, the USAID-Sustain project, managed by John Snow International (JSI), has led to the development of accreditation standards and an accreditation survey process for the specific area of in-hospital perinatal care.  This initiative is nearing completion and is now ready for adoption nation-wide.  The intent is apply the methodologies developed in this project to other clinical areas.

### 8 Regulation and Inspection

International context:

While quality improvement is increasingly seen as the paradigm that should dominate in any health system quality strategy, jurisdictions still maintain QA-type inspection mechanisms in parallel with QI activities.  Even with investments in QI, there are still exceptional examples of individuals or organizations that fall far below an acceptable standard of care.  Issues with negligence or disruptive, abusive behaviour exist, and appropriate mechanisms must be in place to handle them. Recently in the UK, the Stafford Hospital was found to have exceptionally high mortality rates and incompetent management, such as use of junior or untrained staff in critical situations and leaving patients without water or assistance to go to the bathroom.  The ensuing inquiry has led to strengthening of QA mechanisms in that country.

International jurisdictions have inspection agencies which are either housed within the Ministry of Health or stand-alone organizations.  In the UK, the Health Care Commission inspects services at hospitals, nursing homes, primary care and home care and publishes results on its website (cqc.org.uk).  About 2% of places inspected have issues requiring an enforcement action.  Hospitals, for example, are evaluated on 21 measures, such as courtesy and respect, staffing levels, cleanliness, safety of equipment, proper medical records and quality of management.

Georgian context:

Georgia currently has a licensure and inspection function, housed in the State Regulatory Agency for Medical Services.  This organization is a legal entity under public law and issues licenses to new health care providers and health care organizations; inspects facilities to ensure compliance with certain standards regarding physical comfort (e.g. minimum number of square feet per hospital bed); and follows up on patient complaints.  There are approximately 156 individuals working for the agency, many with clinical backgrounds.

Interviewees noted a number of current weaknesses in the existing inspection function. Inspections address issues such as physical comfort, but not clinically relevant standards.  The process of licensure takes place only once, and there is no system of re-licensure, where organizations or individuals have to demonstrate on-going compliance with standards.

Clinical skills training was outside of the scope of this project.  Nonetheless, it deserves mention given the frequency with which interviewees raised it as a quality concern.  Interviewees felt that the current medical training system emphasizes book knowledge and memorization of facts, rather than clinical bedside skills, the ability to accurately diagnosis conditions as well as the quality of communication between patient and provider.  Licensure is granted based on written exams.  Interviewees noted weaknesses in on-going supervision and verification of skills, given the lack of re-licensure requirements.

### 9 Incentives and Accountability

International trends

Many jurisdictions are moving to greater accountability for quality, and linking payment to quality.  Traditional funding systems based on fee-for-service or diagnosis-related group payment reward only utilization, and methods like capitation or salary do not acknowledge quality.  Some payment methods may penalize high quality; for example, a fee-for-service doctor who spends more time with patients will see fewer patients and earn less.  Models for accountability used elsewhere include:

- accountability agreements, with expectations of quality but no financial penalties.  In Ontario, Canada, for example, hospitals must meet targets for readmission rates, and missing the target results in hospitals undergoing an arduous process of explaining why and its plan of action [ref].

- meeting quality standards as a contractual obligation.  Clear specifications about quality are laid out and payment is withheld if they are not met. For example, Medicare in the US refuses to pay for “never-events” (e.g. wrong-site surgery) and other preventable adverse events.

- Pay for performance models, which offer more pay for higher quality.  Under the UK’s Quality Outcomes Framework, general practitioners received bonuses based on a wide range of quality measures.  In the USA, Medicare hospital remuneration is based in part on readmission rates and patient satisfaction.  The experience with pay-for-performance has been mixed.  Some studies show only modest improvements in the range of 4%, and risks of this model include “cherry-picking” only the easiest cases, decreased quality of care for those services not tied to pay-for-performance, and creation of an entitlement culture where providers follow best practices only if they are paid to do so [ref].

- Bundled payment mechanisms, where payment is for services for a specific patient group across the continuum of care.  This is to prevent situations where one part of the system is optimized at the expense of another (e.g. short length of stay reduces hospital costs but create quality problems later).  For example, bundled stroke care would include the initial hospitalization, post-hospital rehabilitation and readmissions.  There would be an inherent incentive to minimize readmissions because no additional payment is given for them, and expectations could be set on the amount of recovery achieved.  Prices for the bundle are set to reflect the cost of care of an organization that carried out best practices and avoided costly complications.

The World Bank has promoted Results-Based Payment, where funding is tied to attainment of certain expectations for quality.  Projects have tended to follow either the second or third model above.

In all jurisdictions studied, responsibility for payment policy has resided within the government itself.  In some instances, the government may ask for technical advice from a quality management entity to help set the clinical expectations that should be put into the funding system.

Current status in Georgia:

Georgia has a mixed payer system with some individuals receiving private health insurance coverage (usually through an employer).  Until recently, only certain groups (low-income earners, pensioners, children and teachers) received state-funded health coverage; now, all citizens can take advantage of the new universal health coverage plan.  Within the government’s plan, payment for primary care is based on a capitation system covering primary care, basic specialist services and basic lab tests.  There are fee-for—service payments for selected additional services such as sub-specialist consultations and more complex tests and investigations.  Hospital services are paid for on a fee-for-service basis per hospitalization.  Many respondents concerns about the pricing method and that a diagnosis-related grouping (DRG) method of payment was needed.

Interviewees noted that there was no official method of tying setting accountabilities or incentives for quality, and current remuneration methods are still tied primarily to quantity.  Furthermore, for patients who are receiving care through private insurance, it was not clear how the government could enact funding reforms to encourage better quality.

### 10 Quality Planning

International context

For many jurisdictions, effective quality planning is elusive.  Governments and health care CEOs create plans, but execution remains challenging.  Often, leaders struggle engage health care workers who are critical to success.  Leaders are also concerned that different activities such as accreditation, public reporting or improvement campaigns are not coordinated and they feel pulled in too many different directions.

Effective plans have clearly defined national priorities and a clearly defined hierarchy of activities which have each health care organization has specific goals which, once met, would contribute to progress at a national level.  For example, if the government sets a national goal of reducing hospital-acquired infections (HAIs) by half, then individual hospitals might be asked to set specific goals for HAIs in order to meet the national goal (i.e. all hospitals might aim for 50% reduction, or better-performing hospitals might aim for 30% and the poorest performers 70%).  Individual units within hospitals would in turn set targets for their own performance; for example, the ICU might aim for elimination of VAP and CLI, surgery departments might aim for a 50% reduction in surgical site infections, and the general medical award might aim to reduce C difficile infections by 50%.

This type of planning, with system-wide goals linked to organization-specific goals and micro-level goals for work units within each organization, is consistent with the Hoshin Kanri approach used by practitioners of LEAN, and in the Canadian province of Saskatchewan.  Other key elements of Hoshin Kanri include the use of data to monitor the strategy, and engagement of workers and leaders at all levels of the system in the development of the plan.  The government retains responsibility for setting the quality plan, but works closely with its Health Quality Council in its development.

Situation in Georgia

Opinions varied among interviewees about quality planning in Georgia.  Some felt that there was no clear plan for improving quality, or, if it existed, it had not been clearly communicated.  Others felt that there were in fact many examples of plans developed over the years, such as the 2011-15 health strategy of the previous government.  These interviewees, however, felt that the main problem was with implementation, and lack of a detailed description of responsibilities of individual organizations that characterizes the planning examples described above.

### Configuration of Roles for Quality Management in Other Jurisdictions

In the United States, Canada and UK, no single entity takes on all ten roles above; responsibilities are divided into different organizations.   Appendix VI lists the different configurations of organizations and their governance structures in greater detail.  Some general observations are as follows:

- All of these jurisdictions have dedicated agencies for promoting QI capacity and leading QI campaigns.  In the USA, this function is carried out by Quality Improvement Organizations (QIOs), which operate as non-profit corporations.  There is one QIO per state, and each holds a contract with the Centers for Medicare and Medicaid (CMS) for key deliverables on QI support.  In Canada, this function is generally carried out by provincial quality councils, most of which are government agencies established in legislation but which operate at arms-length, usually with a government-appointed Boards and a CEO appointed by the Board.  In the UK’s National Health Service (NHS), governmental organizations have played this role, with the largest being the former Institute for Innovation and Improvement, now replaced by NHS Improving Quality.

- entities for quality improvement support have taken on different forms, including departments within Ministries of Health; arms-length bodies established in legislation; and non-profit corporations on contract to government.  In general, however, the most common choice of model is the second or third.  One likely reason for this is that such organizations thrive in an environment of innovation and freedom to redesign and optimize processes.   Such environments may have a different culture than government cultures with an emphasis of firm adherence to policies, which are necessary to ensure fairness.  Furthermore, QI capacity-building organizations tend to operate on a voluntary basis recruiting participants, whereas a key government function is to enact legislation and regulations that mandate change.

- QI and QA activities tend to be kept separate, with QA activities either left within government or placed in an arms-length body.  The likely explanation for this is that these represent two significantly different paradigms.

- Most jurisdictions rely on separate entities to lead quality measurement activities.  In the USA,  the Agency for Health Research on Quality (AHRQ) provides guidance on indicator definitions and ensures there is solid evidence behind these indicators, and CMS is responsible for collecting data.  Both are entities operate within Health and Human Services, the Federal government’s Health Ministry.  In Canada, there is also a separate non-profit organization for quality measurement, the Canadian Institute for Healthcare Information.

- In all jurisdictions studied, there is a separate body in charge of accreditation.  These organizations (e.g. Joint Commission in the USA, Accreditation Canada, QHA Trent Accreditation in the UK) focus only on accreditation, and are themselves accredited by the International Society for Quality (IsQuA).  Their independent status is a reflection of both the natural evolution of these organizations as well as a desire to ensure that the granting of accreditation status represents an independent assessment of an organization’s policies and structures, free from political interference or bias.

# Recommendations:

- The MOLHSA should create a national Quality Improvement Agency.

1a.  The roles and responsibilities for the Agency should include the following functions:

  - Make recommends to government on a national quality indicator dataset, priority topics for improvement, and quality indicators to be included in accountability agreements with health care organizations.

  - Provide support to health care organizations to develop QI capacity, including training and mobilization of improvement facilitators to support local QI teams.

  - Lead improvement campaigns in areas identified by MOHLSA as a priority for action.

  - Document barriers and solutions to implementation of best practices, as a resource for health care organizations to improve.

  - Recommend clinical decision support tools for national adoption and for incorporation into future electronic health record systems.

  - Encourage patients to be engaged in their health care in order to improve quality.

  - Conduct public reporting at an individual organizational level in the long-term.

An acceptable alternative is for the last item (public reporting) to be assigned to the NCDC.  Having the QI agency do public reporting promotes integration of this function with improvement activities.  Having NCDC do this function allows for consolidation of measurement expertise in one location.  Regardless of the option chosen, it is essential that the QI Agency and NCDC collaborate closely.

For greater clarity, the QI Agency should be viewed by health care organizations as a supportive resource to help organizations improve.  Placing this function in a LEPL allows for a clear separation between voluntary, bottom-up approaches to quality and mandatory, top-down approach which belongs with the Ministry.  When change needs to be mandated, it should be enacted by the Government, not the QI Agency.

1b.  The governance structure of the unit should be a legal entity under public law (LEPL).  This commonly-used model in Georgia is most similar to the model in other jurisdictions, where there is a desire for the Agency to develop a culture distinct from government.  The MOLHSA has indicated a preference for establishing the QI unit within the Ministry in the short-term, in order to expedite its creation.  This is reasonable and has precedents elsewhere.  The transition to a LEPL should be completed within one year, and the home for the interim QI unit should be within the Ministry itself, rather than other LEPLs such as the State Regulatory Agency for Medical Services, which has a quality assurance mandate.

1c.  The QI Agency should have an Advisory Board with a maximum of 12 members, to provide strategic advice to the Head of the Agency and act as ambassadors for quality improvement.  One important difference in governance is that in Georgia’s LEPLs, the Head of the Agency is appointed by the Government and reports to the Minister.  In other jurisdictions, the Chief Executive Officer is appointed by a Board of Directors, who may be Government appointees.  Hence, LEPLs are one step closer to government than their international counterparts.  Because of this, an Advisory Board is essential to conveying a sense of peer leadership of quality.

As strategic advisors, board members may take on tasks such as setting priorities for clinical topics for improvement, selecting the best mix and design of improvement activities at any given moment, and continually identifying the most important system barriers to implementing QI that need to be addressed.  As QI ambassadors to managers and front-line staff, Board members can articulate the need to move from a QA to a QI paradigm, promote the activities of the Agency and encourage participation in national improvement campaigns.

The recommended composition of the Advisory Board should consider the following guidelines:

  - Balance across regions and rural vs urban centers, gender, health professional groups (doctors, nurses, pharmacy or other allied health), and care settings (hospital, primary care, preventive care)

  - Inclusion of leaders who are strategic thinkers and well-respected by their peers among health care management or health professionals.

  - Inclusion of individuals with strong experience in process improvement and systems design.  Sectors outside of health, such as industrial engineering or manufacturing, may be sources of such candidates.

  - A patient perspective – for example, a well-respected prominent citizen who has frequent interactions with the health care system.

Capping membership as 12 helps ensure strong participation of each member, and increases the importance of each individual position, which makes the position attractive to top talent.

1d.  A communications and stakeholder relations function should be formally established within the Agency.  This reflects the need to engage with health care organizations closely to implement improvements in QI capacity.  The Agency will need to create networks of stakeholders to reach all health sectors, regions and health professions.

1e.  The evaluation criteria the Agency should be based primarily on the extent to which health care organizations find the Agency’s support useful and the amount of quality improvement capacity achieved, and secondarily on the success rate that organizations are having in improving outcomes.  The exact choice of criteria should be determined by the Agency head in conjunction with the Advisory Board and MOLHSA.  Options include:

  - the extent to which organizations are using the tools and resources of the Agency

  - the participation rate in the Agency’s quality campaigns

  - the satisfaction rate of health care organizations with the Agency’s activities

  - the number of staff or management in the health care system who have achieved a certifiable level of skills in quality management

Improvements in patient outcomes is the ultimate goal of the Agency and of government.  However, the emphasis on outcome improvements must be tempered by the fact that the Agency does not directly control the activities of health care organizations, and cannot be held accountable for the actions of front-line managers.  Hence, primary evaluation criteria should be on activities the Agency has control over (e.g. capacity-building) with secondary criteria being outcome improvements.

1i.  Staffing for the QI Agency  should start at a minimum of 20 persons, based on benchmarks from similar international agencies (see Table 5).  A staff size of 25 to 40 would provide greater flexibility to launch multiple campaigns in different sectors and offer more intensive support to QI teams, which will help ensure success.  The staff should include:

  - project management experts, needed to manage large national campaigns

  - QI facilitators or coaches, at a ratio of one coach per 3 to 7 QI teams

  - quality measurement experts

  - communications and stakeholder relations staff

  - administration and finance staff (typically about 15-20%)

Table 5:  Staffing Levels at QI Agencies in Other Jurisdictions

| Quality Improvement Organization | Jurisdiction | # Staff | Popula-tion (million) | # staff per million population | Equivalent Staff for Georgia (4.5 million) |
| --- | --- | --- | --- | --- | --- |
| National Institute for Improvement & Innovation | United Kingdom | 273 | 59 | 5 | 21 |
| Health Services Advisory Group | Arizona , Florida & California | 370 | 73 | 5 | 23 |
| BC Patient Safety & Quality Council | British Columbia, Canada | 30 | 4.6 | 7 | 29 |
| Health Quality Ontario | Ontario, Canada | 130 | 13 | 10 | 45 |
| Health Quality Council | Saskatchewan, Canada | 45 | 1 | 45 | 203 |

Data source:  websites and annual reports for each organization.  The NHS staffing figures should be interpreted with caution as this organization had a £70 mil budget, suggesting that some key functions are outsourced.

QI facilitators should have some formal, certified level of competency in QI science.  Where possible, the Agency should draw on expertise from the current quality improvement initiative in Imereti region.  If individuals are not available with past QI expertise, then having experience in clinical care and in leading teams would be desirable.  A sample of job descriptions for facilitators is found in Appendix VIII.

- NCDC should be expanded and assigned the role of standardized quality measurement.  Responsibilities include:

  - Working with the QI agency and MOLHSA to develop a national quality indicator dataset (with the final decision on indicator choice to rest with MOLHSA, as noted below)

  - Setting technical definitions for all indicators

  - Setting standards for data collection and reporting

  - Establishing registries for patients with selected chronic conditions

  - Establish training and certification program for data coders

  - Conducts statistical analyses of data, including:  comparisons on quality indicators by individual organization and administrative region; changes over time, for each organization, each region and at the national level

  - Preparing reports to individual provider organizations on their performance.

NCDC will require additional staffing for these tasks – approximately 5 to 10 individuals.

- The Ministry should create a separate Accreditation Body, preferably as a legal entity under public law.    The rationale for this status is that it allows elected officials to reassure the public that health care organizations are meeting minimum standards, as verified by an independent source.  The Ministry has indicated a desire to establish the Accreditation Body within the Ministry first.  This is an acceptable option, and would allow time for the Ministry to be satisfied that the new body meets its expectations prior to granting it LEPL status.  In any case, LEPL status should be accomplished within 12 to 18 months.

During the start-up phase, it is recommended that the Accreditation Body be placed within the Ministry itself, rather than within other entities such as the State Regulatory Agency for Medical Services.  Accreditation tends to occupy a middle ground between QA and QI approaches; it relies on inspection, but aims to be supportive by making recommendations on how to improve rather than issuing punitive sanctions.  As such, its culture may not be entirely compatible with an entity that has a purely regulatory function.

2b.  The Accreditation Body should implement hospital perinatal care standards first.  For subsequent clinically-focused accreditation standards, the choice of clinical area  should be aligned with national quality campaigns launched by the QI Agency.

2c.  The Accreditation Body should appoint an Advisory Council to advise and approve continuing improvements to the accreditation process and oversee decisions on the granting of accreditation status.  This Council should have a maximum of 12 individuals with representation from different clinical disciplines (e.g. medicine, nursing, pharmacy, etc.) and sectors (e.g. hospital and primary care).

2d.  The Accreditation Body should seek accreditation by the International Society for Quality (ISQuA).  This will ensure that it meets international standards and will help reassure the public that its assessments are fair and objective.

2e.  The Accreditation Body will require an estimated 5 staff to commence operations.

- The State Regulatory Agency for Medical Activities should continue its QA roles (issuing permits & certifications for medical professionals & hospitals, investigating patient complaints, conducting inspections).  To improve its effectiveness, it should:

- Introduce some clinically relevant standards into the inspection process.  The clinical area should align with the national quality plan and current improvement campaigns.  For example, if there is a campaign on hospital-acquired infections, a standard could be introduced regarding general cleanliness, adequacy of ventilation of isolation rooms, hand hygiene stations functioning and conveniently located, and use of an appropriate room disinfection protocol.

- Consider introducing some form of physician re-licensure, with observed, structured clinical examinations (OSCE) which are now the standard for assessing physician skills in many countries.  This addresses the extensive concerns listed by interviewees about skill levels.  The choice of clinical topics for the exam should be aligned with the national quality plan and current improvement campaigns.

- Consider taking on responsibilities for verifying that health care organizations are submitting accurate data on quality to NCDC.

- Examine means of shifting resources from QA to QI activities (described in recommendation 1) or to the more value-added QA activities described above.  This is essential in order to ensure Georgia’s transition from a QA to a QI culture.  One idea to consider is to reform the patient complaints management process where initial responsibility of following complaints falls to the responsible health care organization.  Organizations would have to follow certain standard procedures and only those complaints not satisfactorily resolved would be referred to the State Regulatory Agency.

- Quality Strategy and Planning

The Ministry should establish and quality strategy and planning group within the Ministry itself. This could be either a special unit within the Ministry or a working group of Ministry staff who already have similar functions.  The role of this unit will be to:

- Draft a national quality plan, with annual updates

- Set system-wide priorities for quality improvement initiatives

- Ensure alignment of activities across the health system with these priorities

- Approve the national quality indicator set which will monitor progress with the plan

- Suggest specific system-wide targets for improvement with a time period for completion

On all of these functions, the strategy and planning unit will take technical advice from the QI Agency.  However, the Minister, with the support of this planning group, retains final decision-making authority.  Ultimately, decisions on what to focus on are political decisions, where elected officials must decide between competing worthy causes which impact different segments of society.

- Financial accountability for quality

The Ministry should phase-in over a multi-year period expectations for quality as a condition of receiving funding from the Universal Health Coverage program.  This incremental approach is highly recommended, because organizations should be held accountable for meeting process or outcome measures only after they have had adequate training on how to implement improvements, and are submitting reliable and valid data.  Without these pre-requisites, there will be a high risk of under-reporting of poor quality and other unintended consequences as noted above.  One possibility of a phased approach that the Ministry might consider could consist of the following:

- Pay for training (i.e. eligibility for payment continues upon successful completion of QI training with demonstration of skills learnt)

- Pay for data (i.e. eligibility for payment continues upon successfully submitting data periodically)

- Pay for processes (i.e. meeting certain minimum standards)

- Pay for outcomes (i.e. meeting certain minimum standards)

Responsibility for financial accountability for quality should remain in the Ministry.  The Social Services Agency is already responsible for verifying eligibility for payment and may be well-suited for this task.

Table 6 summaries the proposed roles and responsibilities of each entity:

Table 6:  Proposed Division of Roles for Quality Management in Georgia

| Organization / Agency | Role |
| --- | --- |
| MOHLSA – Quality Strategy & Planning Group | Set clinical priorities for improvement Establish a national quality improvement plan Approve the national quality indicator set (items above to be updated annually, taking into account technical advice from QI Agency) |
| Quality Improvement Agency | Support QI capacity building Lead national improvement campaigns Implement national clinical decision supports |
| National Center for Disease Control | Collect and analyze data based on national quality indicator dataset Develop data collection standards and processes |
| Accreditation Body | Set accreditation standards Accredit individual health care organizations |
| MOHLSA – Social Service Agency | Set accountabilities for quality for each health care organization receiving public funds (based on recommendations from QI Agency) Issue regulations and mandates periodically |
| State Regulatory Agency for Medical Activities | Issue permits and licenses to practice/operate Inspect organizations for clinically relevant standards for infrastructure Manage re-licensure initiatives with skills verification for physicians Inspect compliance with data collection standards Investigate unresolved patient complaints |
| MOHLSA – IT division | Implement decision support and data collection tools into electronic health record, as recommended by QI Agency |

7  Budget Implications

A successful quality agenda will require annual commitments of Ministry resources in the new functions described above, which are sustainable and not dependent on donor funding.  Minimum staff needs are as follows:

| Organization | Staff Requirements | Range of Staff Expenditures per Year |
| --- | --- | --- |
| Quality Improvement Agency | 20 | 130-150k GEL |
| NCDC | 5-10 | 35-75k GEL |
| Accreditation Body | 5 | 30-35k GEL |

Typical average staff costs are estimated at between 550 and 600 GEL per month, the latter figure based on a typical salary for a hospital physician as a benchmark.   Additional costs may include:

- Overhead (office space, computer, telephone, etc.) for each new employee

- Travel costs for improvement facilitators in the QI agency, to visit QI teams across the country

- One-time training costs for improvement facilitators in advanced QI techniques,  at US$3-4,000 / 5-7000 GEL per person

- Meeting costs to bring QI teams together periodically to share experiences

- Statistical software, training, and web-based tools for providing quality reports back to individual health care organizations

- User licenses for decision tools (e.g. order sets), learning materials, OSCE clinical exam materials

As noted above, the Ministry may choose to offset the cost of these new staff by reallocating resources from the existing State Regulatory Agency, as part of the shift from a QA to a QI paradigm.

The above staff allocation will allow for approximately 13 improvement facilitators who could support about 80 to 90 QI teams per year.  Georgia has a total of 221 hospitals, 224 polyclinics and 14 ambulatory care centers (459 in total), and the Agency could serve all provider groups over a six-year period.  Additional improvement facilitators would allow broader coverage of these centers and accelerate the speed of QI campaigns.

Likewise, additions to NCDC of the scale described will result in increased submission of data aggregated for people within the organization.  If the government wishes to consider person-oriented data, it will require even more staff.

8 Option for One-Time Investment in QI Infrastructure

The QI agenda can be dramatically accelerated through a one-time investment in start-up activities over a four-year time period.  Such investments could take the form of donor contributions or loans, and complement the activities already funded by the Ministry noted above.  There are many ways to configure such a campaign, and the following is presented as an illustrative example:

A national improvement campaign over three years is established, with the launch date one year from now to allow time for the establishment of infrastructure for the QI Agency.  The campaign is focused on three broad areas:  primary care, hospital and preventive care.

The initiative would aim to provide intensive QI coaching by facilitators to all 221 hospitals, 224 polyclinics and 14 ambulatory care centers (459 teams in total).  Village doctors would participate by joining with their nearest primary care center. There would be four waves of teams working on their selected topic over the course of 15 months, with each wave spaced 6 months apart.

The initiative would second 153 individuals from these 459 organizations over an 18-month period to work as QI facilitators.  These individuals would still be based at their home institutions but would work exclusively on the QI campaign.  The first three months would involve intensive QI training, leading to formal certification of QI skills.  Each facilitator would mentor approximately three teams, two of which would be situated outside of the individual’s usual workplace.   Core QI staff in the QI Agency would in turn mentor these facilitators.   At the end of the 18-month period, these individuals would return to their home institution and bring to their organization a high level of QI expertise.

The initiative would also include one-time investments in quality measurement, such as training of data abstractors in individual hospitals and primary care sites; the development of standard tools for data submission, analysis and reporting back to organizations; and decision supports (which could be either purchased or developed locally).

Costs for the initiative could include the following:

| Costs | Estimate (USD) |
| --- | --- |
| 153 QI facilitators on secondment, 600GEL/month x 18 months each | $975k |
| Additional training costs for facilitators ($2000 each) | $300k |
| Travel costs for each facilitator ($40/wk x 18 mo) | $450k |
| Certification costs (~$500 per facilitator) | $75k |
| Meeting costs for learning collaboratives (4 waves x 5 sessions each, $5000 per meeting) | $100k |
| Purchase of decision tool licenses | $150k |
| Development of web tool for data submission and generation of reports back to individual provider organizations | $850k |
| One-time training and certification of data abstractors in hospitals and primary care | $500k |
| TOTAL | $3.4 million |

# Potential Benefits

The estimation of the exact benefits of the above investments in quality management infrastructure will depend on the specific topics for improvement that are chosen over the next five years.  Nonetheless, this report examines one example - hypertension - where a targeted approach to improving quality of care could lead to reductions in mortality and morbidity.  This in turn makes the case that short-term loan funding for a quality management infrastructure represents an investment with long-term economic benefits for the country, in much the same way that a loan for a bridge or road improves long-term productivity.

The benefit from a quality management entity lies on the premise that such an investment will increase adoption rates of some key best practices.  This in turn leads to less premature mortality and disability, and more economic output healthy individuals and tax revenue.   More specifically, the approach is as follows.  For each key best clinical practice:

- Estimate the current rate of adoption

- Estimate what would be a reasonably attainable target rate of adoption within a reasonable time frame (e.g. 5 years)

- Estimate the number of people for whom the best practice applies to

- Estimate the number of NEW individuals who will benefit from the best practice

- Identify, from the scientific literature and the original randomized controlled trials about the best practice, what the number needed to prevent a particular complication

- Calculate the number of complications or deaths that will be avoided each year

| Calculations for Benefits of Improved Best Practice Adherence | Figures |
| --- | --- |
| A % of adult population with HBP | 34% |
| B % of those with HBP with some treatment | 39% |
| C Potential future target for % of HBP patients with good BP control | 60% |
| D Number needed to treat (NNT) to prevent one stroke per year | 240 |
| E Size of adult population | 3.5 million |
| F Number of new adults getting BP treatment | 735,000 |
| G Number of strokes prevented per year | 3,000 |
| H Number of stroke-related deaths per year prevented | 500 |
| I Number of stroke-related cases of moderate to severe disability per year prevented | 1,500 |

This example shows that 3000 strokes, 500 deaths and 1,500 cases of significant disability could be prevented with a proper quality management system.  Similar results could be estimated for other chronic diseases, cancer screening and maternal and child health.

# Proposed High-level Workplan

The following table outlines key tasks in the development of the different quality entities and suggests a timeline for completion.  The actual time frames and tasks will need to be adjusted after further consideration by MOLHSA.

| Time Period (month) | Quality Improvement Agency | Accreditation | Other Activities |
| --- | --- | --- | --- |
| 0-6 | - Approve role statement for Agency - Recruit advisory board members - Recruit head of agency - Hire the first five core staff (project manager, senior QI facilitators) - Recommend to Quality Strategy and Planning group list of priorities for improvement | - Approve role statement for unit - Recruit manager for unit, members of Accreditation council, 5 staff, surveyors | - Establish quality strategy & planning (QSP) group - Conduct stakeholder forum to gather consensus on QI plan - NCDC to hire 5-10 new staff |
| 7-12 | - Receive list of priorities for improvement from Ministry - Draft, with NCDC, first version of national quality indicator dataset - Work with NCDC to design decision supports that function as data collection tools (most likely, select standard flowsheets for chronic disease management, preventive screening or maternal/child health, and standard order sets for selected conditions in hospital) - Field test data collection tools, protocols and data submission - Draft & ratify regulations or legislation for creation of the QIA as a LEPL - hire remaining 15 core staff; arrange intensive QI training and certification | - Train surveyors - Launch accreditation for perinatal services - Start development on accreditation standards for new topics in QI plan | QSP – release national quality plan -NCDC to begin designing indicator specifications, data collection protocols - State Regulatory Agency to explore clinical standards for inspection which align to national plan, and OSCE tool for recertification |
| 13-18 | - Launch the new QI Agency - Launch the first national improvement campaign - Prepare “change package” – resource materials for participants - purchase decision supports - Recruit sites - begin recruiting improvement facilitators in the field | - If LEPL option is chosen, draft LEPL legislation and ratify - introduce new topics for accreditation, aligned with national campaign | - MOLHSA to mandate data collection & use of tools (flowsheet, standard orders) - NCDC to begin training data abstractors in hospitals & primary care |
| 19-24 | Launch wave I of national campaign; conduct first two of four learning collaborative sessions |  | - NCDC to begin receiving data & conducting analyses -MOLHSA introduces data submission as a requirement for funding |
| 25-30 | Launch wave II | - introduce new topics for accreditation, aligned with national campaign | - NCDC to begin sending data back to sites - MOLHSA begins phasing in participation in certain training activities as a funding requirement |
| 31-36 | Launch wave III |  | State Regulatory Agency to introduce OSCE exams and re-licensure of healthcare providers |
| 37-42 | Launch wave IV | - introduce new topics for accreditation, aligned with national campaign |  |
| 43-48 | Public reporting of selected indicators by hospital is introduced |  | - MOLHSA introduces minimum expectations on quality as a condition of funding |

# Appendix 1:  Terms of Reference

Programmatic AAA – Georgia Health Systems Strengthening (P133199)

Development of Recommendations for Health Quality Management Entity Republic of Georgia

Background and Context:

- Georgia has undertaken one of the most interesting and ambitious health sector reforms over the past decade. Starting in 2003, significant steps to improve access to health services and financial protection were made with the introduction of the Medical Insurance Program (MIP) for the poor. Hospital modernization and an ambitious renewal of the entire information system were started as well as discussions to increase primary care utilization and the introduction of the family doctor approach.

- The World Bank provided support to the design and implementation of these reforms through the Health Sector Development Project (HSDP) from 2002 to 2012. The Bank’s support focused on the MIP, the development of the information technology (IT) systems, the introduction of family doctors and overall primary health care system strengthening. Support was also given to a large agenda focused on improving quality with reforms in medical education and the development of a certification and accreditation system. In the area of policy advice, the Bank has been engaged in developing the 2011-2015 Health Strategy “Access to Quality Health Care” and has collaborated in more specific areas such as the Health Utilization and Expenditure Surveys (HUES), the Health Performance Assessment reports, impact evaluations, pharmaceutical pricing surveys and quality assessments.

- A significant unfinished agenda remains. A weak quality of health service provision and lack of institutionalized mechanisms for quality monitoring are among major challenges the health  care system is currently facing.

- A new Government was elected in Georgia on 1 October 2012. An important part of its election platform was to achieve universal population coverage for a package of health services, including the reform of existing health financing arrangements and to improve the quality of health services. The Government of Georgia requested the World Bank’s, WHO and USAID to join working groups on the various goals.

- The poor quality of Georgia’s health system has been raised as a serious concern by the MOLHSA. However, apart from a vignette analysis, Georgia has a dearth of data on quality and intermediate performance indicators of the health system, such as waiting times, re-admissions, nosocomial or hospital acquired infection rates. The MoLHSA expressed strong demand to the Bank to assist with developing a system and instrument that would allow better monitoring of quality and performance of facilities and providers. At the same time, Georgia has started to develop a fairly comprehensive monitoring system for health outcomes, and the health financing system upon which could be build.

- The World Bank approved a programmatic Analytical and Advisory Activities (AAA) work-program which includes a quality of service provision component to support the ongoing reforms. The international consultancy was mobilized in 2013 with the main objective to support the Georgian Ministry of Labor, Health and Social Affairs (MOLHSA) to develop a road map for a Quality Improvement Strategy and develop a Measurement Framework. The consultancy built on the vision for quality improvements for health service provision as laid out in the updated 2013 Health Strategy. As a result, the Ministry of Health has requested a follow up consultancy to explore options for the establishment of Health Quality Monitoring Unit aimed at institutionalization of health services quality monitoring.

Objectives:

To develop a short, medium and long-term plan for the establishment of a quality management unit or entity in the Republic of Georgia.

Specific tasks:

- Present an overview of different models of quality management entities used in other jurisdictions, including:

  - Health Quality Councils in Canada

  - Quality Improvement Organizations in the USA

  - Various quality agencies established in the National Health Service in the UK

- Present options to the Minister on how a quality management entity could be structured, with:

  - an analysis of the pros and cons of each option

  - A recommended set of criteria that the Ministry can use to select its preferred option

The following characteristics of the quality management entity will be addressed   to facilitate MOH’s consideration on the possible options:

  - roles of the organization, with potential roles to be considered in- or out-of-scope to include:

    - quality measurement & quality indicator selection

    - public reporting of quality

    - setting national goals

    - defining  the national quality strategy

    - setting accountabilities for health care organizations on delivering quality

    - establishing practice guidelines and standards

    - developing leadership and management skills for quality

    - developing quality improvement capacity and skills in the workforce

    - managing quality assurance mechanisms, including accreditation, professional regulation

  - governance and reporting relationships, with potential options to include:

    - an entity existing within the Ministry

    - an arms-length organization funded by and accountable to the Ministry

  - general categories of staff skills required to support a quality management entity

  - core activities

  - mechanisms for engagement with the field (clinicians, administrators, patient groups, insurers, international agencies)

- For each option, identify areas of firm preference on the part of the Ministry and areas requiring consultation from external parties

- Conduct a consultation workshop with external parties to identify areas of preference among the group.  (The Ministry retains the final decision-making authority in selection of preferences.)

- Facilitate debate on pros and cons of each option

- obtaining input from stakeholders (e.g. multivoting exercises)

- Debrief with Ministry on results of the consultation session and verify preferred direction of the government, based on these results

- Prepare a report outlining the recommended mandate and structure of the quality management entity, with:

  - Preferred choice for each option

    - Rationale for choice

    - Proposed strategy for managing risks associated with the choice

  - Proposed high-level workplan / suggested next steps for establishment of the quality management entity (workplan ~2-3 pages)

    - Option:  prepare a detailed operational plan for establishment of the quality management entity

    - Detailed costing of the quality management entity is out of scope for this mission but major categories of investments necessary will be identified

# Appendix II:  Methods

The following methods were used to prepare this report:

I Review of key documents

The focus here is on reports that describe both direct and indirect activities within Georgia that impact quality, including:

- Georgia Health Care Statistical Year Book, all editions from 2009-2012

- Health Care Georgia:  Short Statistical Highlights 2013

- Review of current clinical practice guidelines of the MOLHSA

- Latest documentation on universal health coverage

- Documentation on current accreditation activities in Georgia

II Analysis of Quality Management Units in other countries

Information was gathered on quality management units established in countries around the world, including:

- Quality Improvement Organizations (QIOs) in the United States

- Key agencies in the USA, including the Agency for Healthcare Research in Quality (AHQR) and Centers for Medicare & Medicaid Services (CMS)

- Health Quality Councils in Canada  at the national and provincial levels (covering the provinces of British Columbia, Alberta, Saskatchewan, Ontario and New Brunswick)

- National organizations in Canada with specialized functions (Canadian Institute for Health Information and Canadian Patient Safety Institute)

- Key organizations in the United Kingdom (e.g. National Institute or Improvement & Innovation, The Care Quality Commission)

- Other key organizations (Qulturum in Jonkoping, Sweden)

The governance structure of these organizations was identified, to see if there were certain models that serve as a prototype for equivalent organizations in Georgia.  Organizations were classified as being either units within a Ministry of Health; an arms-length agency created by government; or an independent, non-profit organization on contract with the government.

The roles of different quality management entities around the world was mapped, based on the following categories of activities:

- Quality measurement

- Public reporting

- Quality improvement capacity building

- Improvement campaigns

- Decision supports

- Public / health user engagement

- Accreditation

- Regulation / inspection

- Accountability & incentives for quality

- Quality planning

III Interviews with key informants within Georgia

Key informant interviews took place with officials from within the MOLHSA at the level of Minister, Deputy Minister and Directors as well as related agencies including the National Center for Disease Control and The State Regulatory Agency for Medical Activities (see Appendix III).

For each of the quality management activities listed above, interviewees were asked about the extent to which such activities were already taking place in Georgia, gaps in the delivery of these activities, and preferences for the type of organization that should be assigned responsibility for the activity.

IV Stakeholder

A stakeholder forum was conducted on Thursday, March 5th with 18 organizations representing hospitals, insurers, primary care organizations, teaching centres, and different professional associations.

Participants were also presented the framework of quality functions, findings from the analysis of international quality organizations, and asked about their preferences for the optimal configuration of these resources (see Appendix IV).

V Site visits

Site visits took place in the preceding June 2013 mission to primary care sites in Mtskheta and Tbilisi and examine the quality infrastructure in primary care settings.   This mission included an additional site visit to a hospital in Tbilisi, MediClub Georgia, to view activities on collecting data for quality and management of quality.

# Appendix III:  Key Informant Interviews

| 3-7 March 2014 |  |  |
| --- | --- | --- |
| Name | Organization | Title |
| David Sergeenko | Ministry of Labor, Health and Social Affairs | Minister |
| Dimitri Makhatadze | Ministry of Labor, Health and Social Affairs | First Deputy Minister |
| Mariam Jashi | Ministry of Labor, Health and Social Affairs | Deputy Minister |
| Rusudan Gogolashvili | Ministry of Labor, Health and Social Affairs | Head, Department in charge of the UHC program implementation |
| Ketevan Goginashvili | Ministry of Labor, Health and Social Affairs | Senior specialist, healthcare department |
| Marina Darakhvelidze | Ministry of Labor, Health and Social Affairs | Head, healthcare department |
| Mikheil Janiashvili | Ministry of Labor, Health and Social Affairs | Head, IT Department |
| Ivan Goliadze | Ministry of Labor, Health and Social Affairs | Senior Specialist, IT Department |
|  | Ministry of Labor, Health and Social Affairs |  |
|  | Ministry of Labor, Health and Social Affairs |  |
| Gia Tvalavadze | State Regulatory Agency of Medical Activities | Head of Agency |
| Temur Pirvelashvili | State Regulatory Agency of Medical Activities | Deputy Head – licensing, permits, accreditation, professional regulations |
| Goderdzi Imnaishvili | State Regulatory Agency of Medical Activities | Deputy head – quality control, legal services, social expertise |
| Merab Urushadze | State Regulatory Agency of Medical Activities | Deputy head - pharmaceutical sector |
| Irma Burduladze | State Regulatory Agency of Medical Activities | Head of department on licenses and permits |
| Zaza Chapidze | State Regulatory Agency of Medical Activities | Representative, pharmaceutical services |
| Amiran Gamkrelidze | National Center for Disease Control and Public Health of Georgia | Director |
| Irma Khonelidze | National Center for Disease Control and Public Health of Georgia | Deputy Director |
| Tamar Chitashvili | University Research Co. | Country Director |
| Nino Berdzuli | John Snow Incorporated | Chief of Party |

Appendix IV:  Participants in Stakeholder Roundtable

| Name | Title | Organization |
| --- | --- | --- |
| Ioseb Bregvadze | Director General | Gudushauri Medical Center |
| Zaza Bokhua | Director | Tbilisi State Medical University, Postgraduate Studies |
| Kakha Chelidze | Vice Rector | Tbilisi State Medical University |
| Dimitri Toklikishvili | Medical Director | LTD “Medison” |
| Nino Buzariashvili | Quality Manager “Aversi Clinic” | LTD “Aversi” |
| Levan Peradze | Head of Control Department | M. Iashvili Children’s Central Hospital |
| Nika Absandze | Consultant | Clinic “Medsi” |
| Revaz Morgoshia | Director | LTD “VERE-XXI”, Clinic “Medsi” |
| Zaza Metreveli | Manager | LTD multiprofile-clinic of Mtsckheta |
| Ketevan Versedjanashvili | President | Association of Nurses |
| Maia Gogashvili | Public Health School | University “Saqartvelo” |
| Maia Kherkheulidze | Head of Department, QRA | M. Iashvili Children’s Central Hospital |
| Eka Kandelaki | Head of Department | M. Iashvili Children’s Central Hospital |
| Ramaz Kurashvili | Chairperson of DEA, Ph.D, Professor | National Center for Diabetes Research |
| Elena Shelestova | Secretary of DEA, Trainer of Trainers | National Center for Diabetes Research |
| Dimitri Kordzaia | Professor | Tbilisi State University |
| Tamar Mandjavidze | Executive office of the Ministry | Ministry of Labour, Health and Social Affairs |
| Giorgi Tsilosani | Vice President | Georgian Medical Association |
| Irina Norakidze | Advisor | Medical Medication Service |
| Giuli Margishvili | Head of Service | Medical Medication Service |
| Nato Berishvili | Policlinic Director | #30, National family Training Center |
| Zurab Vardiashvili | Deputy General Director | Central University Clinic |
| Tamar Gabunia | Chief of Party | USAID, TB Prevention Program, URC |
| Irina Karosanidze | Director | National FM training Center |
| Rema Ghvamichava | Director | Georgian National Screening Center |
| Ketevan Loria | Director | Mtskheta PHC Center |
| Ketevan Sharangia | Manager | Evex Medical Corps |
| Nino Gakhokidze | Clinical Analyst | Evex Medical Corps |

# Appendix V:  Examples of Public Reporting

# Appendix VI:  Examples of Decision Tools

Sample of Flow Sheet for Congestive Heart Failure, British Columbia, Canada

Sample of Flow Sheet for Coronary Artery Disease, Saskatchewan Canada

Example of Admission Order Set from the Institute for Clinical Systems Improvement

(See icsi.org for full version)

Order Set: Admission to CCU for Acute Coronary Syndrome

This order set pertains to those orders from 		Patient Information (Two are required.)

ED or direct admit to the CCU and does not

include orders that pertain to telemetry

admission, step-down or discharge.

Legend: Open boxes are orders that a clinician will need to order by checking the box. Pre-checked boxes are those orders with strong supporting evidence and/or regulatory requirements that require documentation if not done. (See Annotation #1)

Last Name:

First Name:

Date of Birth:___/___/_____

Patient’s age:

ID #:

Admitting data

Date:

Admit unit:

Attending physician:

How to contact:

Diagnosis

Admitting diagnosis:

Secondary diagnosis:

Condition

Stable	 Unstable	 Other

Code status

Full code	 DNR/DNI	 Comfort care	 Not discussed

Vitals

Vital signs and assessments:      Routine per unit protocol      Every       hours

Notify MD if temperature exceeds 38.3oC (101oF), Systolic BP < 90, HR < 45, significant arrythmia

Continuous monitoring telemetry

Notify MD for new ST elevation or depression

Daily weights

Patient weight:      kg

Patient height:       cm

Activity Early ambulation is important for reducing the risk of VTE

Advance activity as tolerated

Other _______________

Allergies/adverse drug reactions

None

Yes, name:      					Type of reaction:

Type of reaction:

Type of reaction:

Nursing orders

Oxygen as needed to maintain O2 saturation greater than or equal 90% by pulse oximetry via:

Nursing discretion – use nasal cannula or mask 	 Nasal cannula	 Mask

Notify MD if mask O2 required

O2 saturation pulse:    Continuous   Monitor with vital signs	 Nursing discretion

Discontinue after:  O2 saturation greater then 90% on room air

Other______________

Notify MD if saturations less than 90%

Glucose by finger stick screening  4 times daily (before meals and at bedtime) for 24 hours

Discontinue after 24 hours for stable blood glucoses less than 140 mg/dL

Subcutaneous Insulin Management Protocol (consider IV insulin protocol for

persistently elevated blood sugars)

Intake and output every shift

Notify MD if urine output is less than 25 mL/hour

Foley catheter at nursing discretion; insertion and removal	 Indwelling

Depression Screen on Day 2

VTE Mechanical Prophylaxis

(If long-term risk for VTE is moderate to high, consider anticoagulation with warfarin.)

Graded compression stockings (remove twice a day for 30 minutes)

Knee high 	 Thigh high

Pneumatic compression

Foot boots	 Knee high	 Thigh high

Instruct patient in foot pumps

Diet

NPO	 Other __________________________

Low sodium, low cholesterol, low saturated fat	 Consistent carbohydrate (CHO) diet

No added salt   Fluid restriction to       mL/24 hours

No caffeine if adenosine stress test planned

IVs

Establish IV saline lock (flush per protocol)

Indicate IV fluid:

at       mL/hour

Sedative/symptom medication

Sleep aid ___________         mg by mouth as needed for insomnia.

Antiemetic ___________         mg by IV every       hours as needed for nausea.

Acetaminophen 650 mg by mouth every 4 hours as needed for discomfort and/or fever.

Antianxiety ___________       mg   IV every       hours as needed for anxiety.

GI stimulant ________________ ______mg by mouth once daily as needed for constipation.

Medications, specific:

Antithrombotic medication

Choose one:  (Aspirin or platelet inhibitors are not recommended as monotherapy.)

Low-molecular-weight heparin (Recommend each institution choose 1 agent, then establish patient selection and dosing criteria guidelines.)

Platelet count every other day beginning day 2 and discontinued on day 14

Discontinue LMWH if platelet count drops 50% or more from baseline value

Notify MD

Hemoglobin every other day beginning day 2

Initiate patient education

Notify MD if bleeding occurs

Unfractionated heparin

60 units/kg IV (max. bolus of 4,000 units)

Maintenance infusion 12 units/kg/hr (max. initial infusion rate of 1,000 units/hr)

Platelet count every other day beginning day 2 and discontinued on day 14

Discontinue heparin if platelet count drops 50% or more from baseline value

Notify MD

PTT every 6 hours after start of drip, then 6 hours after every drip rate change

Hemoglobin every other day beginning day 2

Initiate patient education

Notify MD if bleeding occurs

Anti-Platelet medication

Aspirin

325 mg initial dose by mouth AND

81 mg   162 mg  325 mg daily by mouth (recommended for recent stent placement)

Not indicated due to:

Aspirin allergy

Clopidogrel

600 mg once  300 mg once  No loading dose

75 mg once daily maintenance

Beta-blocker:  Start on day 1

Metoprolol succinate  6.25 mg  12.5 mg  25 mg   50 mg  100 mg by mouth once daily

(Target dose is 100 mg once daily. Maximum dose is 400 mg once daily.)

Give 1/2 dose beta-blocker if heart rate less than 60 or blood pressure less than 100 mmHg

HOLD beta-blocker and notify MD if heart rate less than 55 or blood pressure less than 90 mmHg

ACE Inhibitor (Refer to your institution’s formulary.)

Lisinopril       mg (5-80 mg) by mouth every day (target dose 20 mg daily)

Give 1/2 dose ACE inhibitor if blood pressure less than 95 mmHg

HOLD ACE inhibitor and notify MD if blood pressure less than 90 mmHg

If intolerant to ACE Inhibitor:

Angiotensin Receptor Blocker (ARB) (Refer to your institution’s formulary.)

Valsartan 80 mg by mouth twice daily

Candasartan 8 mg by mouth once daily

Losartan 25 mg by mouth once daily

For special populations consider

Hydralazine 25 mg every six hours

Isosorbide dinitrate 10 mg three times daily

Statin:

Atorvastatin  80 mg by mouth once daily at bedtime

Atorvastatin  40 mg  20 mg  10 mg by mouth once daily at bedtime

Simvastatin   40 mg  20 mg  10 mg by mouth once daily at bedtime

Simvastatin   80 mg by mouth once daily at bedtime

(for patients currently on simvastatin for > 12 months and no signs/symptoms of myopathy)

mg by mouth daily

Not indicated due to:

History of intolerance or adverse reaction

Potassium replacement protocol per institution to maintain K > 4.0 mEq/L

Magnesium replacement protocol per institution to maintain Mg > 2.0 mg/dL

Nitroglycerin 0.4 mg tablet sublingual every 5 minutes as needed for chest pain (max. 3 doses)

Nitroglycerin       mcg/min IV continuous infusion (Start at 10-20 mcg/min.)

Titrate to keep pain-free and BP 90-140 mmHg.

Labs/diagnostic tests:

(First day – those not performed in ED)

Indication:

Done in ER

CBC/Plts

AST

Sodium/potassium

BUN

Creatinine

Glucose

Calcium

Magnesium (if on diuretic or ventricular arrhythmia)

Hgb A1C  (if diabetic or glucose high and unknown if diabetic)

Urinalysis

CPK

Troponin repeat at 90 min. and at 3 hours

TSH

Lipid panel (on admission; if necessary, non-fasting)

PT/INR

PTT		 PTT every AM while on heparin

Electrocardiogram	 With recurrent chest pain

Notify MD of ECG results

Repeat every A.M. on day 2 and day 3

Chest x-ray:	 PA & lateral	 Portable		Indication:

Echocardiogram   Now	 On day

Indication:

Other orders:

___________________________________________________________________

___________________________________________________________________

___________________________________________________________________

Consults

Cardiologist consult:  reason

Phase 1 Cardiac Rehabilitation consult

Tobacco Cessation Education consult (for current users or use within last year)

Nutrition Consult

Discharge planning

Social service consult for assistance in discharge planning

Case management

Financial counselor consult

Cardiac rehabilitation program with transition to Phase III if appropriate

Pneumococcal vaccine 0.5 mg IM per protocol on discharge if:

• Never received vaccine or vaccination status unknown

• First vaccination more than 5 years ago and patient was less than 65 at time of first vaccination

Vaccination record sent to primary care

Authorized Prescriber Signature_________________________________

Printed Name_________________________________________________

Date & Time of Orders:      /     /        	     :

# Appendix VII:  Roles and Governance Structures of Health Quality Organizations Around the World

Table 1a:  Functions of different health care organizations involved in quality in Canada

| Org | Q measure-ment | Pub Reporting | QI support | Decision supports | Accredi-tation/ regulation | Accoun-tability / Incentives | Pt Engage-ment | Quality Strategy |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| BCPSQC |  |  | X |  |  |  |  |  |
| HQCA | (x) | (x) |  |  | X |  |  |  |
| HQC(sk) | (x) | X | X |  |  |  |  | (x) |
| HQO |  | X | X |  |  | (x) | (x) | (x) |
| NBHC | (x) | X |  |  |  |  | X |  |
| Accred Can |  |  |  |  | X |  |  |  |
| CPSI |  |  | X |  |  |  |  |  |
| CIHI | X | X |  |  |  |  |  |  |
| Govern-ments | (x) | (x) |  | (x) |  | X |  | X |

Table:  Division of Responsibilities for Quality Functions Between Different Organizations in USA

| Org | Q measure-ment | Pub Reporting | QI support | Decision supports | Accredi-tation/ regulation | Accoun-tability / Incentives | Pt Engage-ment | Quality Strategy |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| CMS | X | X |  |  |  | X |  | X |
| QIOs |  | x | X |  |  |  | (x) |  |
| TJC |  |  |  |  | X |  |  |  |
| AHRQ | X |  | (x) | (x) |  |  |  |  |

Table:  Variation in Governance Model for Quality Improvement Organizations in Canada

| Organization | Government- Funded Non-Profit | Government Agency, Independent Board | Within Ministry |
| --- | --- | --- | --- |
| BC Centre for Patient Safety & Quality |  | X |  |
| HQC Alberta |  | X |  |
| HQC Saskatchewan |  | X |  |
| Manitoba Institute for Patient Safety | X |  |  |
| Health Quality Ontario |  | X |  |
| New Brunswick Health Council |  | X |  |
| Nova Scotia Quality Unit |  |  | X |

# Appendix VIII:  Sample Job Description for Quality Improvement Facilitators

Source:  Health Quality Council, Saskatchewan, 2014

QUALITY IMPROVEMENT CONSULTANT

Position Summary

The Quality Improvement Consultant participates in project teams and advances quality improvement work under the general direction of a Program Director, and with the advice and direction of senior staff, to achieve the objectives of a specific project. This position is located in Saskatoon and is full-time.

Reporting Relationships

- Given the presence of an organizational matrix structure within the HQC, the Quality Improvement Consultant reports to the Director of Quality Improvement and to one or more Program Directors;

- Is evaluated in annual performance review led by the Director of Quality Improvement with input from Program Directors;

- Although there are no direct reports to this position, the QI Consultant may assume a leadership role within a team and oversee tasks for specific components of project work.

Key Responsibilities

- Leads, coaches, and facilitates initiatives in quality improvement and knowledge exchange;

- Builds capacity for quality improvement through education and mentorship;

- Works with project teams to facilitate and accelerate quality improvement;

- Builds, maintains, and monitors networks of relationships with various components of the health system.

Qualifications

- A Master’s degree in a health care related discipline, education, social sciences, or business administration. or;

- A Bachelor's degree in a health care related discipline, education, social sciences or business administration and one years’ work experience, preferably in a health care environment or;

- Other education or experience related to quality and process improvement, knowledge exchange and transfer and ten years work experience, preferably in a health care environment;

- Must be able to travel independently in the course of duties of the position.

General Responsibilities

- Interacts with health system care and service provision staff and clinical and program managers as required to carry out duties;

- Represents the organization in appropriate health care forums or other stakeholder forums relevant to a particular project, when delegated by a Functional or Program Director;

- Plans and delivers programs and events for learning and knowledge exchange;

- Carries out additional work-related duties assigned by the employer that are related to the job description or are shared or rotated amongst the staff.

Knowledge and Skills

- Demonstrated effective application of quality improvement approaches and tools;

- Demonstrated effective ability to interpret and utilize data to drive improvement;

- Demonstrated effective application of adult learning approaches and facilitation skills;

- Demonstrated ability to work cooperatively in teams;

- Demonstrated effective communication skills, both verbally and in writing with colleagues and stakeholders;

- Proficient in the use of common software applications including Word, Excel, and PowerPoint;

- Demonstrated good judgment within the scope of duties;

- Excellent time management skills.

# References

Georgia Health Care Statistical Year Book 2010, National Centre for Disease Control and Public Health, Ministry of Labour, Health and Social Affairs of Georgia, Tbilisi, 2011.

Georgia Health Care Statistical Year Book 2011, National Centre for Disease Control and Public Health, Ministry of Labour, Health and Social Affairs of Georgia, Tbilisi, 2012.

Agency for Healthcare Research and Quality (AHRQ, 2003c). Your guide to choosing quality health care. Available at: http://www.ahrq.gov/consumer/qnt/.

Crossing the Quality Chasm: A New Health System for the 21st Century Committee on Quality of Health Care in America, Institute of Medicine,Washington, DC, USA: National Academies Press; 2001.

Paul Batalden. What is “quality improvement” and how can it transform healthcare?  Qual Saf Health Care 2007;16:2-3.

Baker GR et al.  High performing health systems:  delivering quality by design.  Longwoods Publishing, Toronto, 2008.

National disease registries for advancing care.  Lancet 2011; 378:9089; 2050. www.thelancet.com/journals/lancet/article/PIIS0140-6736(11)61887-4/fulltext

https://www.cms.gov/Medicare/Quality-Initiatives-Patient-Assessment-Instruments/HospitalQualityInits/HospitalRHQDAPU.html

Wallace, J, G.F. Teare, T. Verrall and   B.T.B. Chan. 2007. Public Reporting on the Quality of Healthcare: Emerging Evidence on Promising Practices for Effective Reporting. Ottawa: Canadian Health Services Research Foundation. < http://www.chsrf.ca/research_themes/safety_e.php >.

Baker GR et al.  High performing health systems:  delivering quality by design.  Longwoods Publishing, Toronto, 2008.

www.ihi.org/Engage/Initiatives/Completed/5MillionLivesCampaign/Documents/Overview%20of%20the%20100K%20Campaign.pdf

www.nhqualitycampaign.org/files/NH_ChangePackage_V1.2_2013_03_05_Final.pdf

www.institute.nhs.uk/quality_and_value/productivity_series/productive_ward.html

For example, PatientOrderSets.com (Canada), ZynxHealth.com (USA) and Provationmedical.com (Netherlands).

http://healthit.ahrq.gov/ahrq-funded-projects/clinical-decision-support-initiative

www.safetoask.ca/?page_id=145

www.qsource.org/tools-resources/improving-healthcare/reducing-healthcare-infections-hospitals/creating-culture-hand-hygiene/

First Steps Towards Quality Improvement:  A Simple Guide to Improving Services.  NHS Improvement, National Health Service, London, 2013.

www.internationalaccreditation.ca/accreditation/patientsafety.aspx.

en.wikipedia.org/wiki/Stafford_Hospital_scandal

www.cms.gov/apps/media/press/factsheet.asp?Counter=3042&intNumPerPage=10&checkDate=&checkKey=&srchType=1&numDays=3500&srchOpt=0&srchData=&srchOpt=0&srchData=&keywordType=All&chkNewsType=6&intPage=&showAll=&pYear=&year=&desc=&cboOrder=date

PK Lindenauer, D Remus, S Roman, MB Rothberg et al.  Public reporting and pay for performance in hospital quality improvement.  N Engl J Med 2007 (356): 486-496.

healthcarefunding.ca/bundled-payments/

www.rbfhealth.org/system/files/RBF_Tech_takingstocksummary_R1.pdf

http://hqc.sk.ca/improve-health-care-quality/hoshin-kanri/

A Chen et al.  Independent Evaluation of the 9th Scope of Work, QIO Program:  Final Report.  Mathematica Policy Research 2011.  Available at:  www.cms.gov/Medicare/Quality-Initiatives-Patient-Assessment-Instruments/QualityImprovementOrgs/Downloads/MPRReport.pdf

For example, the Ministry of Health & Long-term Care of Ontario, Canada established the “Quality Management Collaborative” within the Ministry in 2007 and devolved it into a non-profit organization, the “Quality Improvement and Innovation Partnership” in 2008.  This entity later merged into a provincial arms-length agency, “Health Quality Ontario.”