## Sheet1
Developing Strategic Purchasing Strategy, SSA
MONTH | Feb |  | March |  |  |  | April |  |  |  | May |  |  |  |  | June
CALENDAR WEEK | 19.2 | 26.2 | 5.3 | 12.3 | 19.3 | 26.3 | 2.4 | 9.4 | 16.4 | 23.4 | 30.4 | 7.5 | 14.5 | 21.5 | 28.5 | 4.6 | 11.6 | 18.6 | 25.6
ACTIVITIES
1.TRAINING WORKSHOP ON STRATEGIC PURCHASING
2.DESIGNING STRATEGY FOR STRATEGIC PURCHASING
Strategic analyses (PEST, Health Care sector analyses, McKinsey 7S, SWOT)
Designing the strategy map of strategic purchasing
Defining indicators to strategy goals
Defining base values of indicators (where available)
Planning strategic initiatives to implement the strategy
3. PLANNING SSA CAPACITY BUILDING INITIATIVES
4. APPROVAL OF THE STRATEGY VERSION 1
MISSION