## Georgia
Country | Programmatic Area (2017) | Activity | Partner | Milestones |  | Expected Outcome | Budget assumptions
|  |  |  | Pre-Joint Appraisal | 2017-11-30
Georgia | Country planning, management & monitoring | Support to programme management capacity | WHO | Mid-year technical and financial implementation report | End-year technical and financial implementation report | Efficient and timely implementation of programme activities | 50% of country office staff salary
Georgia | Countries on track for successful transition | Support to resource mobilization activities | WHO | Resource mobilization advocacy material development initiated | Resource mobilization materials developed | Efficient efforts to mobilize domestic resources required to achieve programme objectives | Consultancy 2w; In-country advocacy activity
Georgia | Vaccine implementation | Support in preparedness for HPV vaccine introduction | WHO | HPV vaccination communication strategy and plan developed | HPV vaccination communication plan implemented; training materials for health care workers developed; national training on HPV vaccination is conducted; the system to monitor the coverage with HPV vaccine is established | First round of HPV vaccination implemented | Consultancy 2w; In-country training
Georgia |  | Support to reduction of missed opportunities by avoiding false contraindications | WHO | Trainers are identified and equiped with training package | Trainings for front line medical workers conducted | Knowledge of medical workers on true and false contraindications improved | Consultancy 2w; In-country training
Georgia | Data | Provide continued TA and supply support for rotavirus sentinel surveillance | WHO | Surveillance data collected and submitted (from Jan to June) | Surveillance data collected and submitted (from Jan to Dec) | Policy and decision-makers have data on burden of rotavirus disease post vaccine implementation | Consultancy 1w; Training; Data collection
Georgia |  | Provide continued TA and supply support for IB-VPD sentinel surveillance | WHO | Surveillance data collected and submitted (from Jan to June) | Surveillance data collected and submitted (from Jan to Dec) | Policy and decision-makers have data on burden of invasive bacterial disease post-vaccine implementation | Consultancy 1w; Training; Data collection
Georgia | Supply chain | Support to conduct EVM assessment | WHO | NA | EVM assessment conducted | EVM assesment report & improvement plan developed to provide guidance to address identified weaknesses | Consultancy 6w; In-country training; Data collection
Georgia |  | Support to adopt vaccine management SOPs | WHO | Nationa VM SOPs drafted | National VM SOPs formally adopted & district managers trained | Suppy chain policy & guidance strengthened | Consultancy 2w; In-country training
Georgia | Data | Strengthening real-time data collection and analysis for national immunization programme: - Develop e-module for vaccine and safety injection supply stock management and link with the existing immunization and other relevant e-health modules. - Train medical personnel (EPI managers and PHC providers) on using both the established immunization and the new stock management e-modules | UNICEF | Supply stock management e-module is established and linked with immunization and other e-health modules | EPI managers and PHC providers are trained on immunization and new stock management e-modules | Immunization abd supply stock management e-module are fully functional, with relevant human capacities build for real-time data collection and analysis. | Technical Assistance (consultancy) for the development of stock management module; Training materials on how to use the new electronic modules; Fees for training facilitator & logistical travel arrangements and other relvent training costs
Georgia | Vaccine implementation | Capacity development of health care workers on real and false contraindications, vaccine hesitancy and resistance | UNICEF | Training curricula is developed. | Training is successfully delivered with participation of key counter-parts. | Healthcare workers have better understanding of true and fase contraindications, vaccine hesitancy and resistance. | Fees for consultant and in country training expences
Georgia | Demand generation | Development and printing of communication materials on immunization | UNICEF | Communication material developed. | Communications materials are printed and distributed. | Improved immunization knowledge and compliance among general public and target groups | Technical support for the development of communication materials - consultancy x 2 moths. Fees for the production and distribution of IEC materials.
Georgia | Vaccine implementation | Support the outreach sessions in the rural and remote settlements all around Abkhazia | UNICEF | Target settlements with low immunization coverage identified and outreach plan developed | Outreach session conducted | Iimmunization coverage in targeted settements is improved. | Coverage of travel, consultancy, DSAs, in coutry workshops
Georgia |  | Strengthen electronic database, community events, capacity-building of staff, rural outreach, overall coordination of implementation and monitoring of immunization program | UNICEF |  |  |  |  | For details refer to sheet "Additional support Abkazia"

## Additional support Abkazia
Country | Programmatic Area (2017) | Activity | Partner | Milestones |  | Expected Outcome | Budget assumptions
|  |  |  | Mid-year | End-year
Georgia /Abkhazia | Data | Strengthening electronic immunization data base; Capacity building of relevant local medical staff on immunization data entry and analysis | UNICEF | Data gap analysis report; One workshop for the staff on immunization data entry and analysis | Two workshops for the staff on immunization data entry and analysis | Timely and quality immunization data available to identify equity issues and for decision making | Consultancy (3 months); In country training
Georgia /Abkhazia | Coverage & Equity | Immunization support community events | UNICEF | 10 community events to support immunization conducted | 20 community events to support immunization conducted | Better knowledge and awareness on immunization among general public and target groups; Increase compliance and immunization coverage, especially in remote areas | Partnership Agreement with the local NGO
Georgia /Abkhazia | Vaccine implementation | Capacity bulding on Immunization in Practice | UNICEF | 2 trainings on Immunization in Practice completed | 2 trainings on Immunization in Practice completed | Improved knowledge and skills of the local staff, improved provision of immunization services | Training related expenses
Georgia /Abkhazia | Coverage & Equity | Support to outreach sessions to the rural and remote settlements | UNICEF | Target settlements with low immunization coverage identified, outreach plan developed | Outreach sessions conducted | Immunization coverage in targeted settements is improved. | Consultancy, travel costs, DSA and other relevant expenses
Georgia /Abkhazia | Vaccine implementation | Support to adaptation of immunization programme supportive supervision tool to the local context; Capacity building for the team of local supervisors; Support to supervisory visits | UNICEF | Supportive supervision tools adapted Trainings for the team of supervisors conducted | Supportive supervision visits to the healthcare facilities to evaluate immunization programme performance conducted | Establishment of regular supportive supervison activities in Abkahazia to support immunization programme | Consultancy, training, supervision vistits related expences (travel, estc)
Georgia /Abkhazia | Country Planning, management and monitoring | Technical advise, overall coordination of implementation and monitoring of immunization program in Abkhazia region | UNICEF | Mud year technical and financial report related to TCA, HPV demo and additional GAVI support implementation | Mud year technical and financial report related to TCA, HPV demo and additional GAVI support implementation | Improvement and proper functioning of immunization programme in Abkhazia is ensured, including HPV demo | Salary costs for four months of P3 position International Health & Nutrition Officer