## Sheet1
Core areas | Actions | Responsible institution | Responsible person | Start date | End date | Transition phase | Comments | Status in February 26, 2018
1.Adoption of DRG system | 1.1 Decide which DRG grouper will be implemented | MOLHSA | N.Berdzuli; Z.Sopromadze | Dec 2017 | Dec 2017 | Phase 1 | Decision made to use Nordic DRG grouper | Done
1.Adoption of DRG system | 1.2 Contact the organization delivering the DRG system and start the negotiations | MOLHSA | Z.Sopromadze/S.Belkania | Dec 2017 | July 2018 | Phase 1 | Letter sent to Nordic Casemix Centre in mid-December 2017 | Due date depends on the negotiations with NCC (to be decided by end of mission). Unformal agreement is given by NCC. Nino will be taken and not replaced.
1.Adoption of DRG system | 1.3 Contact the organization delivering the grouper software | MOLHSA | Z.Sopromadze/S.Belkania/K.Goginashvili | March 2018 | July 2018 | Phase 1 |  | Needs input by NCC (definition tables); email will be sent after call with Martti (Feb27). Add Keti here
2. Development of DRG implementation and transition strategy | 2.1 Define the phases of transition with concrete activities and time frames | MOLHSA/SSA | Z.Sopromadze/S.Belkania | Jan 2018 | July 2018 | Phase 1 |  | Ok, after mission final version will be produced
2. Development of DRG implementation and transition strategy | 2.2 Create the DRG core team with clear TORs within SSA and MOLHSA | MOLHSA/SSA | Z.Sopromadze/S.Belkania | Jan 2018 | July 2018 | Phase 1 |  | Ok, after mission final version will be produced
3.Preparedness of IT systems | 3.1 Analyse (pros and cons of alternative business processes) adoption of the DRG grouper to the SSA’s IT system | SSA | I.Tabatadze | May 2018 | Sept. 2018 | Phase 1 |  | Looks realistics timeline (depends mostly in 1.2). This might need additional analyis after the testing and pilote phase
3.Preparedness of IT systems | 3.2.Adapt the SSA IT system to accommodate the grouper software | SSA | I.Tabatadze | May 2018 | Sept. 2018 | Phase 1
3.Preparedness of IT systems | 3.3 To revise/change/modify business process according to DRG requirements | SSA | I.Tabatadze/M.khomeriki | May 2018 | Sept. 2018 | Phase 1 |  | This might need additional analyis after the testing and pilote phase
4.Improvement of data quality | 4.1.1 Prepare ICD-10 and NCSP to produce DRG definition tables by NCC | SSA/NCDC | M.Khomeriki/N. Tsetskhladze | February 2018 | March 2018 | Phase 1
4.Improvement of data quality | 4.1.2 Translate and adjust DRG terminology into Georgian | NCDC/SSA | N. Tsetskhladze /M.Khomeriki | May 2018 | Aug. 2018 | Phase 1
4.Improvement of data quality | 4.1.3 Develop standard procedure to revise and update ICD-10 and NCSP | SSA/NCDC | M.Khomeriki/M.Kereselidze | July 2018 | Dec 2019 | Phase 4 |  | Add one person from NCDC, add M.Kereselidze. 1st version ICD and NCSP have to be ready for producing 1st version of definition tables.
4.Improvement of data quality | 4.2.1. Prepare basic userfriendly guideline for ICD-10 and NCSP coding standards with basic overview about DRG grouping principles | NCDC/SSA | M. Darakhvelidze/ N. Tsetskhladze /M.Khomeriki | May 2018 | Sept. 2018 | Phase 1 |  | will be discussed in feb27. DRG names translation into Georgian + some user guide forf providers about DRG logic
4.Improvement of data quality | 4.2.2 Revise and improve the coding guidelines for ICD-10 and NCSP | SSA/NCDC | M.Khomeriki/ M.Kereselidze | July 2018 | Dec 2019 | Phase 4
4.Improvement of data quality | 4.3 Develop the external clinical coding audits | SSA/NCDC | M.Khomeriki/M.Kereselidze | Sept 2018 | Dec 2019 | Phase 4 |  | might need postponing, changed to dec 2019
4.Improvement of data quality | 4.4 Revise and improve the SSA claims management process | SSA | M.Khomeriki/ I.Tabatadze | Jan 2019 | April 2019 | Phase 4 | After the clinical coding audit system has been tested | due dates will be decided afterwards when better understanding about coding guidelines etc
5.Adaption of regulation needed for implementation of DRG system | 5.1 Analyze the legal framework to identify needed changes in legislation to implement the DRG system | MOLHSA/SSA | Z.Sopromadze/M.Darakhvelidze | September 2018 | Dec 2018 | Phase 3 | In parallel with implementation of DRG system. However, approval is needed for DRG piloting to involve providers in the first and second phase of the transition period | will be done in paralel, ok
5.Adaption of regulation needed for implementation of DRG system | 5.2 Prepare the legal documents needed for implementing the DRG system | MOLHSA/SSA | Z.Sopromadze/ M.Darakhvelidze | September 2018 | Dec 2018 | Phase 3
6. DRG tariff setting methodology | 6.1.1 Develop cost weights and base rate estimation methodology for 2019 "shadow funding" | MOLHSA/SSA | l.Nikoladze/K.goginashvili | Sept 2018 | Nov 2018 | Phase 3 | I stage: the cost weights for 2018, (when DRGs are not yet used for actual reimbursement) can be borrowed or developed based on GEO data. | will be discussed next mission
| 6.1.2 Develop cost weights and base rate estimation methodology for 2020 actual reimbursement "shadow funding" | MOLHSA/SSA | l.Nikoladze/K.goginashvili | Sept 2019 | Nov 2019 | Phase 4 | II stage - cost weights for actual reimbursement.
6. DRG tariff setting methodology | 6.2 Analyze the vertical programs in the light of DRG implementation | MOLHSA/SSA | l.Nikoladze/K.goginashvili | March 2018 | Sept 2018 | Phase 3 |  | will be discussed next mission
6. DRG tariff setting methodology | 6.3 Conduct simulations for alternative DRG cost weights and base rate scenarios | MOLHSA/SSA | l.Nikoladze/K.goginashvili | Sept 2018 | Nov 2018 | Phase 3 |  | will be discussed next mission
6. DRG tariff setting methodology | 6.4 Calculate the cost weights, base rate and DRG tariffs | MOLHSA/SSA | l.Nikoladze/K.goginashvili | Sept 2018 | Nov 2018 | Phase 3 |  | will be discussed next mission
7.Reimbursement policy | 7.1 Develop the DRG reimbursement policy: a. Define exemptions (e.g. psychiatric care, rehab care, referred patients etc) and the payment method for financing them b. Define reimbursement rules for expensive drugs and devices, ICU, etc, and the payment method for financing them c. Define high-low cost/LOS outliers | MOLHSA/SSA | Z.Sopromadze/M.Darakhvelidze/ | Sept 2018 | Nov 2018 | Phase 3 |  | vertical programs intial mapping could be done before next mission
7.Reimbursement policy | 7.2 Conduct simulations for DRG reimbursement policy scenarios | MOLHSA/SSA | Z.Sopromadze/M.Darakhvelidze/M.Khomeriki | Jan 2019 | May 2019 | Phase 4
8.Monitoring and reporting system | 8.1.1 Group the data, analyze and provide feedback about grouping results to providers (testing period) | SSA | M.Khomeriki/ I.Tabatadze | May 2018 | December 2018 | Phase 1 |  | key priority indictaors during the first phase, will be revised for the next phases
8.Monitoring and reporting system | 8.1.2 Group the data, analyze and provide feedback about grouping results to providers (pilot period) | SSA | M.Khomeriki/ I.Tabatadze | Jan 2019 | Dec 2019 | Phase 4
8.Monitoring and reporting system | 8.2 Develop performance indicators and principles for regular monitoring of providers and reporting by using DRGs | MOLHSA/NCDC/SSA | M.Darakhvelidze/M.Kereselidze/M.Khomeriki/ | March 2019 | May 2019 | Phase 4
9.Capacity building for all stakeholders | 9.1 Asses gaps in capacity and develop a training plan for capacity building among different stakeholders | SSA/NCDC | M.Khomeriki/ I.Tabatadze/M.Kereselidze | May 2018 | September 2018 | Phase 1 | Assessing gaps and improving capacity will be carried out according to the core areas and actions of the implementation plan
9.Capacity building for all stakeholders | 9.2 Improve competence in DRG systems for all stakeholder organizations by offering training and educational opportunities according to need | SSA/NCDC | M.Khomeriki/ I.Tabatadze/M.Kereselidze | May 2019 | April 2021 | Phase 1 - Phase 4 |  | Activities according to the training plan
10.Communication | 10.1 Develop a DRG implementation communication plan | SSA | Z.Sopromadze | April 2018 | September 2018 | Phase 1 |  | Add additional names Revise and correct if needed the Start and End date according to the due dates in to the Communication plan
10.Communication | 10.2 Implement the communication plan | SSA | Z.Sopromadze | September 2018 | Dec 2019 | Phase 1 - Phase 4 |  | Implementation start date depends on the developments with DRG grouper, probably should begin earlier