## Initiatives
Goal | Initiatives | Q3 18 | Q4 18 | Q1 19 | Q2 19 | Q3 19 | Q4 19 | Q1 20 | Q2 20 | Q3 20 | Q4 20 | Date | Owner
Improve payment and contracting mechanisms | Developing and introducing DRG system | DRG grouper integrated to the SSA system; DRG terminology in Georgian; feedback to providers | DRG cost weights and reimbursement principles for the "virtual implementation" | Simualtions and analytics to develop DRG cost weights and reimbursement rules |  | DRG cost weigts and reimbursement policy for 2020; overall preparedness for DRG implementation | [5 empty] | 12.2019 | Director of SSA
| Critical assessment of basic financing PHC (considering the need for integration of rural and UHC, state vertical programs) including RBF principles | Assessment of current financing mechanisms of PHC considering possibility of integration of rural and UHC | Revision/redign of financing issues of PHC | Piloting RBF using redesigned financing of PHC, without financial obligations | Final revision/preparation for redesigned PHC financing | [6 empty] | 6.2019 | Head of Health Care Department, MoLHSA
| Developing principles of contracting for purchasing services, including selective contracting and monitoring and evaluation system of contracts performance | Assessment of current contracting arrangements, incl selective contracting practice of MCH care |  | Design of new contracting system, the concept | Design of MDC and case based planning system | Analyses of provider performance, forecast of MDC and case based planning, drafting SOP, SSA internal capacity building |  | Piloting volume based contracting, without financial obligations | Develop monitoring procedures and SOP | Develop legal regulation. Linking with payment mechanisms. | Final preparation for going live. | 12.2020 | Head of UHC, SSA
| Health needs assessment (for health services) for hospital care | Assessment of what kind of hospital services are priorities for needs assesement (ex. onco surgery, critical care, NICU..) | Analyze epidemiological data | Analyze service utilization, existing resources, international experience |  | elaborate the requirements for each directions based on statistical data taking into consideration the geografical accsessibility and utilization) | [5 empty] | 12.2019 | Head of UHC, SSA
HBP in line with population health needs | Designing the system and process of HBP revision and renewal | elaborate of the methodology for assesment of health needs and HBP design | analyze the health service utilization of existing HBP and detect weak an strong sides |  | assesment of health (among them essential) needs, servuce alocation and finansial resoirses |  | Redesighn HBP |  |  |  |  | 3.2020 | Head of Health Care Department, MoLHSA
Consolidate highly specialised and hospital care | Analysing the need for hospital care services including highly specialised services and current distribution of service providers. | Analyse the current distribution of Highly specialised hospital services | Analyze the epidemiological data, existing services allocation comparing to international experience | Elaborate highly specialised hospital services allocation according to analysis data | [7 empty] | 3.2019 | Head of UHC, SSA
| Developing a plan for sustainable purchasing of hospital and highly specialised medical services. |  |  | Elaborate strict criteria for purchasing of highly specialised hospital services | Final revision of criteria for purchasing of highly specialised hospital services according to service alocation | [6 empty] | 6.2019 | Head of UHC, SSA
Ensure equitable access to essential specialist care and strengthen PHC | Analysing and mapping geographical distribution of service providers and population service needs. | Analyse the current distribution of service comparing to epidemiological data |  | Mapping geographical distribution of services according to analysis data | [7 empty] | 3.2019 | Head of Health Care Department, MoLHSA
| Developing a concept for geographically equitable provision of essential medical and primary care services, considering better integration and strengthening of service provider capacity (Integrating the concepts of rural medicine and UHC primary care programs to secure equal rights for patients and quality of service). |  |  | Identify geographical areas with lack of essential medical and primary care service distribution | Elaborate requirements (technical , specialisation …) for service providers taking into consideration mapping results |  | Final revision of concept |  |  |  |  | 12.2019 | Head of Health Care Department, MoLHSA
| Revision of referral system and developing gate-keeping functions. | elaborate the data-collecting system to receive the data from PHC centers about pacients with ambulatory care-sensitive conditions, their outpatient visits and referrals |  | Analyze received data, hospitalization rate with ambulatory care sensitive conditions according to PHC centers | revise/redign the referral system | [6 empty] | 6.2019 | Head of UHC, SSA
| Upgrading the training and re-qualification system of GP. |  | Elaborate the training and qualifications system of GP taking into consideration the data received by analysis of work of PHC centers with patients ambulatory care-sensitive conditions |  | Consider draft of training sistem with primary health care professionals and international partners and analyze their remarks and comments. |  | revise/finalise the wonk on training and re-qualification system of GP. |  |  |  |  | 12.2019 | Head of Health Care Department, MoLHSA
Improvement efficiency and quality of health services | Defining set of indicators to assess the quality of medical services, mechanism to monitor and control quality, and coordinate the quality functions with Regulatory Authority | Involve stakeholders, determine the audit topic, plann the delivery of audit fieldwork | Define the set of quality indicators | Elaborate the mechanism to monitor and control quality | [7 empty] | 3.2019 | Head of UHC, SSA
| Develop concept of medical audits (in cooperation with Regulatory Authority). |  | Identify the standards and audit criteria | selecting and developing appropriate performance levels; identify inclusion/exclusion criteria abd exceptions | Elaborate measuring performance methodology: data collection, data analysis, drawing conclusions, presentation of results; Identify principal steps of quality improvement plans and sustaining improvements according the elaborated mechanism to monitor and control quality |  | Final revision of concept of medical audits, analysing feedback from professionals and international partners |  |  |  |  | 12.2019 | Head of Health Care, SSA
| Critical revision of current system and develop a concept to upgrade the system of licencing and accreditation of service providers. | Analyse the current system of licensing and accreditation of service providers in the context of international experience |  | Make remarks/corrections in the system of licencing and accreditation of service providers taking into account results of analysis and internal experience | Final work on the system of licencing and accreditation of service providers, analisyng feedback from professionals | [6 empty] | 6.2019 | Head of Health Care Department, MoLHSA
| Develop principles and functions of health economics within SSA, the structural alignment of functions. | Analysis of current structural alignment of functions of SSA | Revision/redign of structural alignment of functions according to principles and functions of health economics within SSA | [8 empty] | 12.2018 | Director of SSA
Enhance electronic data exchange and improve quality of data | Mapping of key processes related with health service provision and SP and defining the needs for developing solutions for electronis echange of data with stakeholders. | Defining SP key areas in need of IT development, new tech applications and solutions. Planning initiatives for 2019. |  | System analyses and TOR for ... | [7 empty] | 6.2019 | Deputy Director (IT) of SSA
| Introduce the use of electronic signature. | Implement the relevant software with legislative changes on electronic signature |  | estimate the software characteristics | Final preparation for going live. | [6 empty] | 6.2019 | Deputy Director (IT) of SSA
| Mapping of claims management process and design of electronic claims management solution. | Mapping of claims manage ment process AS-IS | Designing SHOULD BE SOP (incl TOR for tech application?) | SSA wide training to introduce new practice | New claims management process introduced | [6 empty] | 6.2019 | Deputy Director (IT) of SSA
Improve population awareness | Development of Citizen Portal and applications to increase transparency for patients. | Ensure to provide precise information for beneficiaries about covered services by State and other (municipal and etc.) programs |  | Elaborate the questionary for visitors of web site |  | Analyze the feedback for improvement of site data/information/characteristics/appearance | Final work on Citizen Portal and applications to present a transparent clear information/data for beneficiaries |  |  |  |  | 12.2019 | Deputy Director (IT) of SSA
| Develop concept of citizen communication and communication plan for 2019. | [10 empty] | 12.2018 | Head of PR Department, MoLHSA
Increase transparency and accountability | Development of reporting and benchmarking system of health service provision, based on indicators. | [10 empty] | 6.2019 | Head of Health Care Department, MoLHSA
| Development and introducing of quarterly reporting on SP performance | Designing Q(A reporting system, defining data needs | Piloting reporting based on Q 3 & 4 | [8 empty] | 3.2019 | Head of SP/Health Economics? SSA
Initiative under develepoment with milestone definition
Initiiative due date with final approval

## Iniciatives last version
Goal | Initiatives | Q3 18 | Q4 18 | Q1 19 | Q2 19 | Q3 19 | Q4 19 | Q1 20 | Q2 20 | Q3 20 | Q4 20 | Date | Owner
Improve payment and contracting mechanisms | Developing and introducing DRG system | Contact the organization delivering the grouper software and license | DRG grouper integrated to the SSA system; DRG terminology in Georgian; feedback to providers; Adaption of regulation needed for implementation of DRG system; Preparation for DRG cost weights and reimbursement principles |  | DRG cost weights and reimbursement principles for the "virtual implementation" | Simualtions and analytics to develop DRG cost weights and reimbursement rules | DRG cost weigts and reimbursement policy for 2020; overall preparedness for DRG implementation |  |  |  |  | 3.2020 | SSA
| Critical assessment of basic financing PHC (considering the need for integration of rural and UHC, state vertical programs) including RBF principles | Assessment of current financing mechanisms of PHC considering possibility of integration of rural and UHC | Revision/redisign of financial mechanisms of PHC including RBF indicators; Piloting RBF using redesigned financing of PHC, without financial obligations |  | Final revision/preparation for redesigned PHC financing | [6 empty] | 6.2019 | MoLHSA
| Developing principles of contracting for purchasing services, including selective contracting and monitoring and evaluation system of contracts performance | Assessment of current contracting arrangements, incl selective contracting practice of MCH care |  | Design of the concept for new contracting system | Design of MDC and case based planning system | Analyses of provider performance, forecast of MDC and case based planning, drafting SOP, SSA internal capacity building |  | Piloting volume based contracting, without financial obligations | Develop monitoring procedures and SOP | Develop legal regulation. Linking with payment mechanisms. | Final preparation for going live. | 12.2020 | SSA
| Health needs assessment (for health services) for hospital care | Assessment of what kind of hospital services are priorities for needs assesement (ex. onco surgery, critical care, NICU..) |  | Analyze epidemiological data, service utilization, existing resources, international experience |  | elaborate the requirements for each directions based on statistical data taking into consideration the geografical accsessibility and utilization) | [5 empty] | 12.2019 | SSA
HBP in line with population health needs | Designing the system and process of HBP revision and renewal | elaborate of the methodology for assesment of health needs and HBP design | analyze the health service utilization of existing HBP and detect weak an strong sides |  | assesment of health (among them essential) needs, service alocation and finansial resoirses |  | Redesighn HBP |  |  |  |  | 3.2020 | MoLHSA
Consolidate highly specialised and hospital care | Analysing the need for hospital care services including highly specialised services and current distribution of service providers. | Analyse the current distribution of Highly specialised hospital services | Analyze the epidemiological data, existing services allocation comparing to international experience |  | Elaborate highly specialised hospital services allocation according to analysis data | [6 empty] | 6.2019 | SSA
| Developing a plan for sustainable purchasing of hospital and highly specialised medical services. |  |  | Elaborate transparent criteria for purchasing of highly specialised hospital services |  | Final revision of criteria for purchasing of highly specialised hospital services according to service alocation | [5 empty] | 9.2019 | SSA
Ensure equitable access to essential specialist care and strengthen PHC | Analysing and mapping geographical distribution of service providers and population service needs. | Analyse the current distribution of service comparing to epidemiological data |  | Mapping geographical distribution of services according to analysis data | [7 empty] | 6.2019 | MoLHSA
| Developing a concept for geographically equitable provision of essential medical and primary care services, considering better integration and strengthening of service provider capacity (Integrating the concepts of rural medicine and UHC primary care programs to secure equal rights for patients and quality of service). | Elaboration of PHC strategy |  | Identify geographical areas with lack of essential medical and primary care service distribution | Elaborate requirements (technical , specialisation …) for service providers taking into consideration mapping results |  | Final revision of concept |  |  |  |  | 12.2019 | MoLHSA
| Revision of referral system and developing gate-keeping functions. | elaborate the data-collecting system to receive the data from PHC centers about pacients with ambulatory care-sensitive conditions, their outpatient visits and referrals |  | Analyze received data, hospitalization rate with ambulatory care sensitive conditions according to PHC centers | revise/redign the referral system | [6 empty] | 6.2019 | SSA
| Upgrading the training and re-qualification system of GP. |  | Elaborate the training and qualifications system of GP taking into consideration the data received by analysis of work of PHC centers with patients ambulatory care-sensitive conditions |  | Consider draft of training sistem with primary health care professionals and international partners and analyze their remarks and comments; Elaboration of GP qualification monitoring syste |  | revise/finalise the wonk on training and re-qualification system of GP. |  |  |  |  | 12.2019 | MoLHSA
Improvement efficiency and quality of health services | Defining set of indicators to assess the quality of medical services, mechanism to monitor and control quality, and coordinate the quality functions with Regulatory Authority | Involve stakeholders, determine the audit topic, plann the delivery of audit fieldwork |  | Define the set of quality indicators | Elaborate the mechanism to monitor and control quality | [6 empty] | 6.2019 | SSA
| Develop concept of medical audits (in cooperation with Regulatory Authority). | Identify the standards and audit criteria |  | selecting and developing appropriate performance levels; identify inclusion/exclusion criteria abd exceptions | Elaborate measuring performance methodology: data collection, data analysis, drawing conclusions, presentation of results; Identify principal steps of quality improvement plans and sustaining improvements according the elaborated mechanism to monitor and control quality |  | Final revision of concept of medical audits, analysing feedback from professionals and international partners |  |  |  |  | 12.2019 | SSA
| Critical revision of current system and develop a concept to upgrade the system of licencing and accreditation of service providers. | Analyse the current system of licensing and accreditation of service providers in the context of international experience |  | Make remarks/corrections in the system of licencing and accreditation of service providers taking into account results of analysis and internal experience |  |  | Final work on the system of licencing and accreditation of service providers, analisyng feedback from professionals |  |  |  |  | 12.2019 | MoLHSA
| Develop principles and functions of health economics within SSA, the structural alignment of functions. | Analysis of current structural alignment of functions of SSA |  | Revision/redign of structural alignment of functions according to principles and functions of health economics within SSA | [7 empty] | 6.2019 | SSA
Enhance electronic data exchange and improve quality of data | Mapping of key processes related with health service provision and SP and defining the needs for developing solutions for electronis echange of data with stakeholders. | Defining SP key areas in need of IT development, new tech applications and solutions. |  | System analyses and TOR for SP and IT development |  | Final preparation for going live. | [5 empty] | 12.2019 | SSA
| Introduce the use of electronic signature. | Implement the relevant software with legislative changes on electronic signature |  | estimate the software characteristics | Final preparation for going live. | [6 empty] | 6.2019 | SSA
| Mapping of claims management process and design of electronic claims management solution. | Mapping of claims manage ment process AS-IS | Designing SHOULD BE SOP (incl TOR for tech application?) |  | SSA wide training to introduce new practice |  | New claims management process introduced |  |  |  |  | 12.2019 | SSA
Improve population awareness | Development of Citizen Portal and applications to increase transparency for patients. | Ensure to provide precise information for beneficiaries about covered services by State and other (municipal and etc.) programs |  | Elaborate the questionary for visitors of web site |  | Analyze the feedback for improvement of site data/information/characteristics/appearance | Final work on Citizen Portal and applications to present a transparent clear information/data for beneficiaries |  |  |  |  | 12.2019 | SSA
| Develop concept of citizen communication and communication plan for 2019. | elaboration of communication plan; elaboration of key messages | Finaising communication plan | [8 empty] | 12.2018 | MoLHSA
| Development and introducing of quarterly reporting on SP performance | Designing Q(A reporting system, defining data needs |  | Piloting reporting based on Q 3 & 4 | [7 empty] | 3.2019 | SSA
Initiative under develepoment with milestone definition
Initiiative due date with final approval