Communication plan to support DRG implementation

Objective(s)

- Build an environment for providers to participate and collaborate

- Raise awareness of the public and providers about ongoing changes

Feedback and comments:

Consider adding DRG name in the objective explicitly

Assure that communication activities are aligned with implementation plan, capacity building and provider feedback reporting

Additional target audiences discussed: medical associations, business associations

Revise key messages by target groups (we discussed transparency and efficiency)

Prepare few pages background document (what DRG is, international experiences supporting Georgian plans, why Geo moving to DRG and what is the implementation plan) that could be used for multiple purposes – first draft with further guidance will be provided by WHO by March 19

Prepare FAQ, initial list of Q with guidance will be provided by WHO by March 19

Focus in more detail on the first steps of communication (year 2018), adjust afterwards

Target audience

- Hospitals

- doctors

- Managers

- IT persons

- Medical associations

- Private insurers

- Business association

- Beneficiaries

- Politicians

- Media

- SSA and MOLHSA staff

Key messages

Communication area:

- To inform target audience about DRG reform objectives

- To inform target audience about DRG reform implementation plan

- To inform target audience about progress during the DRG implementation process

- To inform target audience about some technical aspects of DRGs

| Target audience | Key messages |
| --- | --- |
| Hospitals | Simplicity of reporting, more realistic prices, comparable statistics; well-organized information system; |
| Beneficiaries | Transparent service prices, |
| Politicians | DRG - Cost containment, transparency and cost efficiency of expenses; |
| SSA and MOLHSA staff | Simplicity of planning, reporting, and monitoring |
| Media | DRG - Other health needs of vulnerable groups will be satisfied and Perhaps efficient use of resources |

Channels

Potential channels: website, social media, media release, briefing, seminar, email, radio, TV, Training, hotline

Action plan

DRG implementation communication plan

| Communication area | Activity | Target audience | Responsible institution/person | Channel(s) of communication | Frequency | Due date | Budget | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| To inform target audience about DRG reform objectives | Organize meeting | Hospitals; private insurers beneficiaries, politicians, SSA and MOLHSA staff, Media | MoLHSA/SSA PR department | Meeting | Before the start of implementation | April 2018 |  |  |
|  | Preparation and printing of press release | Hospitals; private insurers beneficiaries, politicians, SSA and MOLHSA staff, Media | MoLHSA/SSA PR department/ Health care department | Meeting | Before the start of implementation | April 2018 |  |  |
|  | Prepare information for MoLHSA and SSA websites | Hospitals; private insurers beneficiaries, politicians, SSA and MOLHSA staff, Media | MoLHSA/SSA PR department/ Health care department | website | Before the start of implementation | April 2018 |  |  |
|  | Participation in medical programs in TV, Radio | Hospitals; private insurers beneficiaries, politicians, SSA and MOLHSA staff, Media | MoLHSA/SSA PR department/ Health care department | TV, radio | Before the start of implementation | April 2018 |  |  |
|  | Preparation and printing of Brochures | Hospitals; private insurers beneficiaries, politicians, SSA and MOLHSA staff, Media | MoLHSA/SSA PR department/ Health care department | Meeting/SSA branches | Before the start of implementation | April 2018 |  |  |
|  | Preparation of information for Facebook | Hospitals; private insurers beneficiaries, politicians, SSA and MOLHSA staff, Media | MoLHSA/SSA PR department/ Health care department | Social Media | Before the start of implementation | April 2018 |  |  |
|  | Prepare Infographics and Banners | Hospitals; private insurers beneficiaries, politicians, SSA and MOLHSA staff, Media | MoLHSA/SSA PR department/ Health care department/ SSA UHC department | Social Media; TV; | Before the start of implementation | April 2018 |  |  |
| To inform target audience about DRG reform implementation plan | Organize meeting | Hospitals; private insurers SSA and MOLHSA staff, politicians, Media | MoLHSA/SSA PR department/ Health care department | Meeting | Before the start of implementation | September, 2018 |  |  |
|  | Preparation and printing of press release | Hospitals; private insurers SSA and MOLHSA staff, politicians, Media | MoLHSA/SSA PR department/ Health care department | Meeting | Before the start of implementation | September, 2018 |  |  |
|  | Prepare information for MoLHSA and SSA websites | Hospitals; private insurers SSA and MOLHSA staff, politicians, Media | MoLHSA/SSA PR department/ Health care department | website | Before the start of implementation | September, 2018 |  |  |
|  | Participation in medical programs in TV, Radio | Hospitals; private insurers SSA and MOLHSA staff, politicians, Media | MoLHSA/SSA PR department/ Health care department | TV, radio | Before the start of implementation | September, 2018 |  |  |
| To inform target audience about some technical aspects of DRGs | Organize meeting | Hospitals; SSA and MOLHSA staff | MoLHSA/SSA PR department/ SSA UHC department | Meeting | If necessary | April, 2018 -November, 2019 |  |  |
|  | Prepare information for MoLHSA and SSA websites | Hospitals; SSA and MOLHSA staff | MoLHSA/SSA PR department/ SSA UHC department | website | If necessary |  |  |  |
|  | Organize Workshop | Hospitals; SSA and MOLHSA staff, media | MoLHSA/SSA PR department/ Health care department/ SSA UHC department | Workshop | Before the start of implementation | April, 2018 -November, 2019 |  |  |
|  | Prepare technical manuals | Hospitals; SSA and MOLHSA staff | MOLHSA;/SSA;PR department | Website; video-manual; Print version. | Before the start of implementation | April, 2018 -November, 2019 |  |  |
|  | Training for MOLHSA Hot Line | Hot line of MOLHSA | MOLHSA/SSA; PR department; SSA UHC department | Training; | Before the start of implementation | April, 2018 -November, 2019 |  |  |
| To inform target audience about progress during the DRG implementation process | Organize conference | Hospitals; private insurers beneficiaries, politicians, SSA and MOLHSA staff, Media | MoLHSA/SSA PR department/ Health care department/ SSA UHC department | Conference | End of Implementation | January, 2019 |  |  |
|  | Preparation and printing of press release | Hospitals; private insurers beneficiaries, politicians, SSA and MOLHSA staff, Media | MoLHSA/SSA PR department/ Health care department/ SSA UHC department | Meeting | End of Implementation | January, 2019 |  |  |
|  | Prepare progress information for MoLHSA and SSA websites | Hospitals; private insurers beneficiaries, politicians, SSA and MOLHSA staff, Media | MoLHSA/SSA PR department/ Health care department/ SSA UHC department | website | End of Implementation | January, 2019 |  |  |
|  | Preparation and printing of Scientific reports | Hospitals; private insurers politicians, SSA and MOLHSA staff | MoLHSA/SSA PR department/ Health care department/ SSA UHC department | Scientific journals | End of Implementation | January, 2019 |  |  |