## Sheet1
Assignment | N of days
At least one meeting with staff organized and presentation with the overview of a selected model of performance appraisal ( two groups + 1 day for preparation) | 1
Groups meetings with managers (at least two meetings) | 2
Individuals consultations with line managers held | 15
Elaborated/revised necessary documentation (e.g. job description; basic evaluation forms) | 5
Training of HR staff conducted; necessary tools for monitoring of performance appraisal processes selected | 2
At least one training for line managers delivered (one day - training; 2 groups; 2 day preparation) | 4 | we'll need 3 groups
Ad hoc consultations | 2
Capacity building activities for line managers through role plays organized (two groups + 2 days for preparation) | 6 | at least 2-day training is necessary for Communications per each group. group shouldn't be more than 15(preferebly 12). This leads to 4*2=8 days +2 days preparation | we'll need video recording, giving feedback and debriefing. It'll only be possible with small group (max 14 ppl)
Training of staff on self-evaluation techniques delivered | 2
Consultation meetings with line managers held, upon request | 5
An analysis of midterm results of staff performance appraisal and lessons learned | 4
Capacity building activities for line managers through role plays organized; | 6
Training of staff on self-evaluation techniques delivered | 2
Consultation meetings with line managers held, upon request | 5
Support HR in finalization of results | 2
An analysis of results of staff performance appraisal, lessons learned | 5
Final mission report detailing work conducted during the consultancy including major findings and recommendations. | 2
Total: | 70