Elimination program Report May	 2016

We will briefly review ongoing processes in current month.

A new data management system has been already developed to collect demographic, diagnostic, clinical, and pharmacy data on patients registered for treatment in order to accommodate the increased demand for treatment. Currently the training of stakeholders on new software is ongoing. New software/database includes different modules we are launching with screening module which will incorporate all exiting information about screened people throughout Georgia. And further probably next week we will launch other modules.

As you may recall more than 11,000 patients with severe liver disease are on the treatment though considering that we still have inclusion criteria F3/F4 fibrosis, severe extrahepatic manifestations HIV/HCV co-infection, liver transplantation the flow of patients has reduced so we’ve planned to end restrictions and open criteria.

In the middle of June we plan to open service agency in Tbilisi and, which will be dedicated for screening, management of patient flow and other related activities, to directly register patients in new electronic program as you may see from the below numbers some proportion of beneficiaries have been already diagnosed and in order to prevent any delays in the treatment initiation, Agency will manage the flow of patients patient accordingly in parallel each clinic will receive the number (the list) of patients in advance every week, which they are considered to manage, and the program will automatically sort out the patients who have completed their diagnostics and are ready to start treatment. After filling out all required fields in database, including lab results, risk factors, co-morbidity and etc. an e-health record will be closed

There is big interest from different stakeholders; it is reflected with high level conferences and meetings one of above mentioned meetings is planned on June 18th Liver institute and foundation for education and research in collaboration with Ministry has planned HCV Elimination Program for Georgia: National Guidance and Education Symposium which will take place at the Radisson Blu Iveria Hotel, Rose Revolution Square 1, 0108 Tbilisi, Georgia. This symposium is designed for general practitioners, gastroenterologists, infectious disease specialists, nurse practitioners, physician assistants, and other healthcare providers involved in the care and management of patients with hepatitis C infection. This interactive program will focus on the latest advances in managing chronic infection with HCV. Participants will receive specific and practical guidance on how to integrate new therapies into clinical care. The application and benefits of Project ECHO, an initiative that expands specialty care knowledge to primary care providers, will be described in detail. The overall progress of the HCV Elimination Program for Georgia will also be outlined and discussed.

As for results:

Hepatitis C Care and treatment Cascade, Georgia, April2015 – May 2016

Total number of registered patients: 28, 500 are Anti HCV positive, those total 22,275 are HCV RNA 11,000 approximately meet criteria for inclusion completed HCV diagnostic work up, obtained necessary documentation, and await case review.

More than 10 000 patients are granted access to the program among these patients, more than 5,600 completed treatment. Of those approximately 4,000 are SVR eligible and SVR is achieved in 86-87% of these patients.

- Total number of disbursed Sovaldi bottles: 34596

  - To service Providers: 31504 boxes

  - Remaining in central stock: 3092

- Total number of disbursed Harvoni bottles: 17000

  - To service Providers: 5185 boxes

  - Remaining in central stock: 11815

Data source: Georgia MOLHSA