## All documents
Doc # | Date | File | Type | Document description | Milestone / Outcome | Done | Notes | Author | Pages | File Path
NA | 2013 | მიღება-ჩაბარების აქტი.pdf | PDF | Confirmation |  | Yes |  | NA | 4 | \migeba-chabareba acts
[5 empty] | Docset1: LBMWP1DOCset1-1-3 - security design | Yes | LBMWP1DOCset1-1-3 - security design.pdf
[5 empty] | Docset1: LBMWP1DOCset1-2-3 - integration design day 1 | Yes | LBMWP1DOCset1-2-3 - integration design day 1.pdf
[5 empty] | Docset1: LBMWP1DOCset1-3-3 - integration expected output | Yes | LBMWP1DOCset1-3-3 - integration expected output.pdf
[5 empty] | Docset1: LBMWP4-1-1 | Yes | LBMWP4-1-1 Resource Translation guide.pdf
[5 empty] | Docset1: LBM4 - Smart-Card UAT | Yes | LBM4- Smart-Card UAT.docx
[5 empty] | DocSet1: ENG-GEO - Dropdown and tree table value | Yes | ENG-GEO - Dropdown and tree table value.xls
[5 empty] | Docset1: ENG-GEO - Fields name | Yes | ENG-GEO - Fileds name.xls
[5 empty] | Mokipay mobile server development environment | ?? | 172.17.20.21 (SQL), 172.17.217.52 (App)
[5 empty] | Mokipay mobile server testing environment | ?? | 172.17.21.21 (SQL), 172.17.217.55 (App)
[5 empty] | Mokipay mobile server production environment | ?? | 172.17.22.23/24 (SQL), 172.17.217.60/61 (App)
[5 empty] | Mokipay 1: MKPWP1-1-1 Mobile Server Software Installation document | Yes | MKPWP1-1-1 Mobile Server Software Installation document.pdf
[5 empty] | Mokipay 2: MKPWP2-1-1 Mobile App Design Doc | Yes | MKPWP2-1-1 Mobile App Design Doc.pdf
[5 empty] | Mokipay_Android_moHealth_app_v0.5.6[Beta].zip | Yes | Mokipay_Android_moHealth_app_v0.5.6[Beta].zip
[5 empty] | Mokipay_iOS_moHealth_app_v0.4.8_b23[Beta]_LIVE.zip | Yes | Mokipay_iOS_moHealth_app_v0.4.8_b23[Beta]_LIVE.zip
[5 empty] | EMC_- Mokipay_ data exchange UAT.docx | Yes | EMC_- Mokipay_ data exchange UAT.docx
[5 empty] | MKPWP3-1-1 XDX HIP Integration.pdf | Yes | MKPWP3-1-1 XDX HIP Integration.pdf
[5 empty] | iPhone app on Apple App Store | Yes | EMC_GeorgiaCentralEMR_MokipayApplicationSubmitionToStores.docx
[5 empty] | Android app on Google Play store | ??
[5 empty] | Final versions of the applications | ??
[5 empty] | Mokipay user guide | Yes | MKPWP4-1-5 Training - Admin.pdf
[5 empty] | Mokipay administrator guide | Yes | MKPWP4-2-5 Training - User.pdf
[5 empty] | Mokipay test scenarios | Yes | MKPWP4-3-5 Test Cases.pdf
LBMWP1DOCset1-1-3 | 2013-11-29 | LBMWP1DOCset1-1-3 - security design.pdf | PDF | Security - Design Workshop Results | Docset1: LBMWP1DOCset1-1-3 - security design | Yes | Presentation unreadable | Chris Hyams | 16 | \Completed WPs\9 WP completed\LBM1\docset 1
LBMWP1DOCset1-2-3 | 2013-11-29 | LBMWP1DOCset1-2-3 - integration design day 1.pdf | PDF | Integraion - Design Workshop Day 1 Results | Docset1: LBMWP1DOCset1-2-3 - integration design day 1 | Yes | Workshop canceled | Chris Hyams | 5 | \Completed WPs\9 WP completed\LBM1\docset 1
LBMWP1DOCset1-3-3 | 2013-11-29 | LBMWP1DOCset1-3-3 - integration expected output.pdf | PDF | Integraion workshops - expected output - DocSet1 | Docset1: LBMWP1DOCset1-3-3 - integration expected output | Yes | Page 5: "A complete list of resources can be found in the Error! Reference source not found" | Vania Manzelli | 20 | \Completed WPs\9 WP completed\LBM1\docset 1
[5 empty] | Civil registry integration | Yes
[5 empty] | Digital signature (Eid Applet by CRA) | Yes
[5 empty] | Registries and classifiers | Part.
LBMWP4-1-1 | 2013-11-29 | LBMWP4-1-1 Resource Translation guide.pdf | PDF | Clinical forms data & Resource files translation procedures | Clinical forms data & Resource files translation procedures | Yes |  | Bhavesh Singh | 29 | \Completed WPs\9 WP completed\LBM4
[5 empty] | Browser language settings | Yes
[5 empty] | How to change data in clinical forms (dropdown, support tables) | Yes
NA | 2013-10-28 | ENG-GEO - Dropdown and tree table value.xls | XLS | Values English-Georgian translation file | Values English-Georgian translation file | Yes |  | Bhavesh Singh | NA | \Completed WPs\9 WP completed\LBM4
NA | 2013-10-28 | ENG-GEO - Fileds name.xls | XLS | Field names English-Georgian translation file | Field names English-Georgian translation file | Yes |  | Bhavesh Singh | NA | \Completed WPs\9 WP completed\LBM4
NA | 2013-10-31 | LBM4- Smart-Card UAT.docx | DOCX | User acceptance Test - Smart Card | User Test Acceptance Apps Demonstration Versions on Hosted within the MoH Development and Test Environments | Yes |  | Lorenzo Rossi | 6 | \Completed WPs\9 WP completed\LBM4
NA | 2013-10-28 | Resource files for translation.xlsx | XLSX | Resource file for translation | translated | Yes |  | Bhavesh Singh | NA | \Completed WPs\9 WP completed\LBM4
MKPWP1-1-1 | 2013-11-29 | MKPWP1-1-1 Mobile Server Software Installation document.pdf | PDF | Mokipay Server Software - Installation Document | 3 environments installation details | Yes |  | Edvardas Cirtautas | 16 | \Completed WPs\9 WP completed\mokipay 1
MKPWP2-1-1 | 2013-11-29 | MKPWP2-1-1 Mobile App Design Doc.pdf | PDF | Mokipay mobile applications -Design Document | Mokipay mobile applications - Design Document | Yes |  | Edvardas Cirtautas | 9 | \Completed WPs\9 WP completed\mokipay 2
NA | 2013-10-31 | Mokipay_Android_moHealth_app_v0.5.6[Beta].zip | ZIP | moHealth Android app | moHealth Android app | Yes |  | NA | NA | \Completed WPs\9 WP completed\mokipay 2
NA | 2013-10-31 | Mokipay_iOS_moHealth_app_v0.4.8_b23[Beta]_LIVE.zip | ZIP | moHealth iOS app | moHealth iOS app | Yes |  | NA | NA | \Completed WPs\9 WP completed\mokipay 2
[5 empty] | Settings ("to be developed") | ??
[5 empty] | Profile ("to be developed") | ??
NA | 2013-10-31 | EMC_- Mokipay_ data exchange UAT.docx | DOCX | User acceptance Test - Android and iOS | User acceptance Test - Android and iOS | Yes |  | Edvardas Cirtautas | 10 | \Completed WPs\9 WP completed\mokipay 3
MKPWP3-1-1 | 2013-11-29 | MKPWP3-1-1 XDX HIP Integration.pdf | PDF | XDS wHospital-Hip Documentum - Integration test results | XDS wHospital-Hip Documentum - Integration test results | Yes |  | Vania Manzelli | 34 | \Completed WPs\9 WP completed\mokipay 3
NA | 2013-10-31 | EMC_GeorgiaCentralEMR_MokipayApplicationSubmitionToStores.docx | DOCX | Mokipay Applications Submittion to Apple APP Store and Google Play Store | Applestore submission proof document | Part. | status “Draft in Prod” | Edvardas Cirtautas | 10 | \Completed WPs\9 WP completed\mokipay 4
MKPWP4-1-5 | 2013-11-29 | MKPWP4-1-5 Training - Admin.pdf | PDF | Mokipay administrator guide | Mokipay administrator guide | Yes |  | Edvardas Cirtautas | 8 | \Completed WPs\9 WP completed\mokipay 4
MKPWP4-2-5 | 2013-11-29 | MKPWP4-2-5 Training - User.pdf | PDF | Mobile Application User Guide | Mobile Application User Guide | Yes |  | Edvardas Cirtautas | 11 | \Completed WPs\9 WP completed\mokipay 4
MKPWP4-5-5 | 2013-11-29 | MKPWP4 5-5 Test Summary Report.pdf | PDF | Mokipay testing request and summary scenarios | Strategies for Mokipay test cases | Yes |  | Edvardas Cirtautas | 12 | \Completed WPs\9 WP completed\mokipay 4
MKPWP4-3-5 | 2013-11-29 | MKPWP4-3-5 Test Cases.pdf | PDF | Mokipay test cases | Mokipay test cases | Yes |  | Edvardas Cirtautas | 41 | \Completed WPs\9 WP completed\mokipay 4
[5 empty] | Citizen portal - create user password | Yes
[5 empty] | Citizen portal - change user password | Yes
[5 empty] | iPhone - download & install app | Yes
[5 empty] | iPhone - Login | Yes
[5 empty] | iPhone - incorrect login/password | Yes
[5 empty] | iPhone - repeated login | Yes
[5 empty] | iPhone - log out | Yes
[5 empty] | iPhone - document list | Yes
[5 empty] | iPhone - read/unread documents | Yes
[5 empty] | iPhone - replaced documents | Yes
[5 empty] | iPhone - deleted documents | Yes
[5 empty] | iPhone - document list manual refresh | Yes
[5 empty] | iPhone - document list refresh with launching application | Yes
[5 empty] | iPhone - search | Yes
[5 empty] | iPhone - displaying document details | Yes
[5 empty] | iPhone - map | Yes
[5 empty] | iPhone - changing language | Yes
[5 empty] | iPhone - deleting application | Yes
[5 empty] | Android - download & install app | Yes
[5 empty] | Android - Login | Yes
[5 empty] | Android - incorrect login/password | Yes
[5 empty] | Android - repeated login | Yes
[5 empty] | Android - log out | Yes
[5 empty] | Android - document list | Yes
[5 empty] | Android - read/unread documents | Yes
[5 empty] | Android - replaced documents | Yes
[5 empty] | Android - deleted documents | Yes
[5 empty] | Android - document list manual refresh | Yes
[5 empty] | Android - document list refresh with launching application | Yes
[5 empty] | Android - search | Yes
[5 empty] | Android - displaying document details | Yes
[5 empty] | Android - map | Yes
[5 empty] | Android - changing language | Yes
[5 empty] | Android - deleting application | Yes
NA | 2013 | MoLHSA stuff trained in EMR Project.docx | DOCX | Georgian Healthcare EMR Project, MoLHSA staff trained | Staff training | Yes |  | Ian Clarke | 2 | \
"All Participants agreed that they felt competent using the system"
Current status and roles of the trainees
Why "Aversi"?
NA | 2013 | confirmation for 9 milestones.pdf | PDF | Confirmation | Confirmation | Yes | მიღება-ჩაბარების აქტი.pdf | NA | 4 | \
6PMWP4 1-1 | 2013-11-29 | 6PMWP4 1-1-GeorgiaCentralEMR_TrainingPlanv1.2.pdf | PDF | Training Plan - Implementation and Good Practice Guidance Document |  | Yes | Who is MoHLSA training coordinator? | Ian Clarke | 20 | \Completed WPs\9 WP completed\6PM4
[5 empty] | Technical/Administrative training plan | Yes | Training contacts from EMC, 6pm, Laserbiomed, Mokipay
[5 empty] | Train-the-Trainer plan | Yes
EMCWP3-1-1 | 2013-11-29 | EMCWP3-1-1 EMC HIP Installation document .pdf | PDF | EMC server software installation document | Installation of Mokpay server side: Production, Development and Testing environments | Yes |  | Daniel Egorov | 16 | \Completed WPs\9 WP completed\EMC3
[5 empty] | MS SQL Server Database (EMC) module | Yes | MS SQL Server 2008 R2 SP1 (Windows 2008 R2 SP1 (64-bit) for all the servers)
[5 empty] | XDS Repository Documentum Server module | Yes | EMC Documentum Content Server 6.7 SP1 (with RPS, TCS, DA and CSS components)
[5 empty] | XDS Services module | Yes | XDS Web Services or XDS Repository hosted on Apache Tomcat Server
[5 empty] | Documentum xDB module | Yes | EMC Documentum XDB server
LBMWP1DOCset2-1-9 | 2013-11-29 | LBMWP1DOCset2-1-9 - design workshop.pdf | PDF | WP1 - Design Workshops - DocSet2 - Deliverable Document | The document analyzes structure of the documents stored in cEMR | Yes |  | Lorenzo Rossi | 16 | \Completed WPs\9 WP completed\LBM1\docset 2
XSD file validates CDA2 document format and structure (CDA2.xsd)
HL7 gateway is a web services set to connect external HCP system to cEMR
4 CDA2 template models: 1. Continuity of Care Document. 2. Clinical Care Record Discharge Summary. 3. Consult note. 4. Lab Result
templates are located in \CDA2templates
external CDA2 must have digital signature and doc. Authorization and obscuration (DAO) metadata encapsulated in p7m or m7m format (DocSet3 and DocSet4)
Sigle header for all CDA2 (Header.xml)
<languageCode> must be changed to "kaz" if clinical the data are in Georgian
11-digit id is used to identify the <patientRole><id>. This is also username
The only source for demographic information (incl. address) is CRA
Versioning by <relatedDocument> and <parentDocument>
Continuity of Care (CCD) template - by HL7 CCD v1.0 standard (page 11)
CCDsample.xml - example of document ready to send to HL7 gateway
cForm sections rules and the data - CCDsections.xls
Clinical Care Record Discharge Summary template - listed sections (page 12)
Consult note template - sections list (page 13)
Laboratiry studies template (LaboratoryResult_body.xml) (page 14) - produced by Laboratory Information System (LIS)
Code systems (terminology systems?): ICD-10, NCSP, ICPC, Georgia Laboratory Result code system, SNOMED, LOINC
LBMWP1DOCset2-3-9 | 2013-11-29 | LBMWP1DOCset2-3-9 - design workshop portals.pdf | PDF | Design Workshop - Portals - workshop results | Define and agree content, layout and success criteria of 4 portals | ?? | Presentation unreadable | Chris Hyams | 14 | \Completed WPs\9 WP completed\LBM1\docset 2
LBMWP1DOCset2-2-9 | 2013-11-29 | LBMWP1DOCset2-2-9 - design workshop portals 2.pdf | PDF | Design Workshop - Portals 2 - workshop results | Define and agree content, layout and success criteria of 4 portals | Yes | Presentation unreadable | Chris Hyams | 10 | \Completed WPs\9 WP completed\LBM1\docset 2
LBMWP1DOCset2-4-9 | 2013-11-29 | LBMWP1DOCset2-4-9 - design workshop payers.pdf | PDF | Clinical Forms - Design Workshop - Payers - workshop results | Design Payers cForm (values: insurance, gevernment, self-pay, other) | Yes |  | Chris Hyams | 8 | \Completed WPs\9 WP completed\LBM1\docset 2
LBMWP1DOCset2-5-9 | 2013-11-29 | LBMWP1DOCset2-5-9 - design workshop gp.pdf | PDF | Clinical Forms - Design Workshop - GP - workshop results | Design GP cForm | Yes | Presentation mostly unreadable | Chris Hyams | 27 | \Completed WPs\9 WP completed\LBM1\docset 2
~2000 patients per GP
Visit form review
LBMWP1DOCset2-6-9 | 2013-11-29 | LBMWP1DOCset2-6-9 design workshop clinical forms d1.pdf | PDF | Clinical Forms - Design Workshop - Day 1 - workshop results | Details of 3 cForms - including the list of values | Yes |  | Chris Hyams | 27 | \Completed WPs\9 WP completed\LBM1\docset 2
[5 empty] | Family History cForm | Yes | patient's generic relatives in terms of risk factors
[5 empty] | Social History cForm | Yes | occupational, lifestyle, social, environmental details + marital status, race, religicion, etc.
[5 empty] | Functional Status cForm | Yes | ambulatory ability, mental status, Activities of Daily Living (ADLs), home situation, ability of self-care, friends, housework, speech, writing, cognition, sight, hearing, taste, etc.
LBMWP1DOCset2-7-9 | 2013-11-29 | LBMWP1DOCset2-7-9 - design workshop clinical forms d2.pdf | PDF | Clinical Forms - Design Workshop - Day 2 - workshop results | Details of 4 cForms - fields and list of values | Yes |  | Chris Hyams | 17 | \Completed WPs\9 WP completed\LBM1\docset 2
[5 empty] | Immunisations | Yes | Immunization status and history
[5 empty] | Allergies | Yes | alergies, adverse reactions and alerts
[5 empty] | Medication | Yes | current medication status and history. Active medication status is a must
[5 empty] | Vital Signs | Yes | blood pressure, heart rate, respiratory rate, wight , BMI, pulse oximetry
LBMWP1DOCset2-8-9 | 2013-11-29 | LBMWP1DOCset2-8-9 - design workshop clinical forms d3.pdf | PDF | Clinical Forms - Design Workshop - Day 3 - workshop results | Details of 4 cForms | No | Manual clinical forms should be translated from Georgian to English | Chris Hyams | 6 | \Completed WPs\9 WP completed\LBM1\docset 2
[5 empty] | Encounters | No | Healthcare encounters
[5 empty] | Procedures | No | Interventional, surgical, diagnostic and therapeutic procedures
[5 empty] | Problems | No | Current and historical clinical problems. "Observations" in CDA R2
[5 empty] | Payers | No | "Third party" insurance, self-pay, other payer or guarantor r combinations of payers
LBMWP1DOCset2-8-9 | 2013-11-29 | LBMWP1DOCset2-9-9 - design workshop clinical forms d4.pdf | PDF | Clinical Forms - Design Workshop - Day 4 - workshop results | Details several cForms - fields and list of values | Part. |  | Chris Hyams | 18 | \Completed WPs\9 WP completed\LBM1\docset 2
[5 empty] | Visits | No | Should be discussed with GP
[5 empty] | CCD Summary | Part. | CCD is core dataset for administrative, demographic and clinical information. Data for this form will be gathered through the use of other forms
[5 empty] | Form 100 | Yes | Form 100 will be automatically generated from the data already inputed in other cForms
[5 empty] | Encounters | Yes | Healthcare encounters
[5 empty] | Procedures | Yes | Interventional, surgical, diagnostic and therapeutic procedures
[5 empty] | Problems | Yes | Current and historical clinical problems. "Observations" in CDA R2. Episode observations are used to distinguish among multiple problem occurences
[5 empty] | Payers | No | Participants pointed out they don't have enough background for discussion
[5 empty] | Advance directives | No | Patient's advance directives (eg. Resuscitation directive) - decided not to include in this project
[5 empty] | Medical Ecquipment | No | Decided not to include in this project
[5 empty] | Plan of Care | Yes | Pending orders, interventions, encounters, services and procedures + goals and clinical reminders
LBMWP1DocSet3-1-2 | 2013-11-29 | LBMWP1DocSet3-1-2 - HL7 messaging fabric spec.pdf | PDF | Integration Workshop - HL7 Message to connect HIS - workshop results | Define process and services for HIS connect to wHospital HL7 gateway | Yes | Through connecting HIS to HL7 gateway CCD structure of cEMR will be populated | Vania Manzelli | 18 | \Completed WPs\9 WP completed\LBM1\docset 3
For phase 1 the connection will be one-way: hospitals will not download patient data from cEMR. But they will be able to see the document repository (with appropieate privacy and security issues) via Hospital portal
Contains UML diagrams for document submission process
wHL7Gateway will be exposed on HTTPS with SSLv3
wHospital HIS-HL7 Available Transactions:
ADT (Admission Discharge Transfer) - ADT_A01, ADT_A11, ADT_A02, ADT_A12,ADT_A03, ADT_A13, ADT_A04, ADT_A05, ADT_A38, ADT_A45
Patient Administration - ADT_A28, ADT_A31, ADT_A40
Patient Lookup - QBP_Q22
Vitals from electro medical decice monitors - ORU_R01
Laboratory observation results - OUL_R22
Order management (LIS and ambulatory orders) - OMG_019, OML_O21, ORL_O11, QPB_Q11 - RSP^SLP^RSP_K11 (labeling transaction)
MDM_T02, MDM_T01, MDM_T03, MDM_T04
XDS ITI-18,41,42,43
LBMWP1DocSet3-2-2 | 2013-11-29 | LBMWP1DocSet3-2-2- hl7 design.pdf | PDF | WP1 - Design Workshops - DocSet3 - Deliverable document | What HL7 and IHE defined for Healthcare scenarios + define imlementation guidelines to promote interoperability between HCP and MoHLSA through wHL7Gateway + HL7 messaging details | Yes | IHR HL7 profiles: PAM, LAB and RAD - inside hospital or hospital network; XDS or XUA - national HIS | Vania Manzelli | 54 | \Completed WPs\9 WP completed\LBM1\docset 3
[5 empty] | IHR HL7 profile - Patient Administration Management (PAM): | Yes | establishes continuity and integrity of patient data across acute care units + ambulatory caregivers
[5 empty] | Patient Identity Feed | Yes | Maintains consistency of patient demographics (ITI-08 in HL7 v2.5). Patient Identity Management Use Case -Creation of new patient demographic record, temporary identification and unknown patient record,update record, merge record, link 2 patients' records
[5 empty] | Patient Encounter Management | Yes | Coordinates the exchange of patient account, encounter and location information. Transaction Patient Encounter Management - Create, update and close inpatient/outpatient encounters; pre-admition, transfer, cancel patient; pending admit, transfer and discharge; levels of absense; Track patient moves through HCP - radiology, scanner, ECG, etc.
[5 empty] | HL7 messages structure | Yes | ADT^01 - patient admit
[5 empty] | DataType structure | Yes | IS, ST(string), TS, AD (Address), TQ (Timing Qantity), CE (Coded Element), PL (Person Location), XON (eXtended Composite Name), XCN (eXtended Composite ID Number), XAD (eXtended Address), eXtended Person Name), XTN (eXtended Telecommunication number),
[5 empty] | Cross Data Sharing profile (XDS.b) | Yes | Document Repository, Registry, Source, Consumer
[5 empty] | Use Cases and Transactions | Yes | Transation for document source actors (ITI-41, ITI-42), document consumer actors (ITI-18)
[5 empty] | wHL7Gateway | Yes | Web application layer to submit HL7 and XDS messages to cEMR. Roles: receive CDA2, check security and privacy, parse CDA2 document, publish document to HIP by XDS-ITI41 messages
[5 empty] | XDS_Repo | Yes | Share documents with Repository. HTTPS + SSLv3 + Mapping Clien Certificate. wHL7Gateway XDS Stub Sequence diagram presented. XDS_repo.wsdl for creating automatical references and stup clases. SOAP 1.1 and SOAP 1.2
[5 empty] | HL7_In | Yes | Share IHE transactions with wHospital. Connection schema presented. HL7_In.wsdl for creating automatical references and stup clases. SOAP 1.1 and SOAP 1.2
[5 empty] | Web-service Standard | Yes | Web Service Description Language (WSDL). Universal Discovery Description and Integration protocol (UDDI).
[5 empty] | Design principles | Yes | Modularity, General purpose, Based on interoperable standards
[5 empty] | Introduction to the standards | Yes | SOAP 1.1/1.2 (XML based); WSDL 1.1 (defines XML based grammar for describing web services and a set of endpoints that accept messages); UDDI (defines SOAP-based Web service for locating WSDL-formatted protocol descriptions)
[5 empty] | HL7 web sevices profile guideline | Yes | Vision, Requirements, use case scenario, Detailed Workflow - WSDL processing, SOAP message construction, Sending, receiving and replying SOAP message… HL7 Web Services Profile (WSP)
[5 empty] | Design - application layers | Yes | Up-to-Down: HL7 - WS-* - SOAP - transport bindings (HTTP, SMTP, MLLP) - Network (TCP/IP, UDP)
[5 empty] | Sample WSDL Documents | Yes | "Strongly typed" and "Not typed"
LBMWP1DocSet4 | 2013-11-29 | LBMWP1DocSet4 -1-1- HL7 message design workshop.pdf | PDF | WP1 - Design Workshops - DocSet4 - Deliverable document | LBMWP1DocSet3-2-2- hl7 design.pdf | ?? | Parts about wHL7Gateway and XDS_Repo from LBMWP1DocSet3-2-2- hl7 design.pdf | Vania Manzelli | 20 | \Completed WPs\9 WP completed\LBM1\docset 4
LBMWP3-1-1 | 2013-11-29 | LBMWP3-1-1 XDS Integration Test end results.pdf | PDF | XDS wHospital-Hip Documentum - Integration test results | MKPWP3-1-1 XDX HIP Integration.pdf | ?? | Duplicate document | Vania Manzelli | 34 | \Completed WPs\9 WP completed\LBM3
NA | 2013-06-05 | EMC_GeorgiaCentralEMR_BusinessSolutionDefinition_v1 0.pdf | PDF | Business Solution Definition | Conceptual model for phase 1 of cEMR project | Yes |  | Chris Hyams | 14 | \Completed WPs\3 WP completed\6PMWP1
[5 empty] | Project Approach |  | EPDM and AGILE methodologies
[5 empty] | Project Deliverables |  | EMR, citizen portal ("light version"), doctors portal ("light version"), mobile EMR, Train the trainer
Project Objectives
[5 empty] | Project Exclusion |  | EMC VCE vBlock Infrastructure, EMC HealthCare Connector, Medical Imaging (DICOM), Cloud based HIS, Financial information systems (ePrescriptions/pharmaceuticals portal, public awareness portal)
[5 empty] | High Level Business Requirements |  | Detailed requirements for cEMR, GP, citizen, mobile EMR portals, templated and applications
NA | 2013-06-04 | EMC_GeorgiaCentralEMR_CommunicationPlan_v1 0.pdf | PDF | Communication Plan | Communication Plan | Yes | Communication audience, communicators, communication messages, communication mediums, communication deliverables | Chris Hyams | 8 | \Completed WPs\3 WP completed\6PMWP1
NA | 2013-06-14 | EMC_GeorgiaCentralEMR_PrioritisedRequirementsCatalogue_v1.0.pdf | PDF | High Level Prioritised Requirements Catalogue | Requirements per components (cEMR, GP Portal, citizen portal, etc.) | Yes |  | Karen Cuschieri | 4 | \Completed WPs\3 WP completed\6PMWP1
NA | 2013-06-03 | EMC_GeorgiaCentralEMR_ProjectManagementPlan_v1 0.pdf | PDF | Project Management Plan | Project Management Plan | Yes | Some parts covered in Business Solution Definition | Karen Cuschieri | 30 | \Completed WPs\3 WP completed\6PMWP1
[5 empty] | Project Summary (approach, deliverables, objectives, delivery methodology, etc) | Yes
[5 empty] | Project team structure and responsibilities | Yes
[5 empty] | User involvment strategy | Yes
[5 empty] | Escalation procedures | Yes
[5 empty] | Risk process | Yes
[5 empty] | Change Control | Yes
[5 empty] | Quality Management | Yes
[5 empty] | Acceptance criteria | Yes
[5 empty] | Testing process | Yes
[5 empty] | Project reporting mechanisms and repositories | Yes
NA | 2013-06-10 | EMC_GeorgiaCentralEMR_ProjectPlan_20130610.mpp | MPP | cEMR project plan | cEMR project plan | Part. |  | NA | NA | \Completed WPs\3 WP completed\6PMWP1
NA | 2013-06-14 | EMC_GeorgiaCentralEMR_ProjectCharter_v1 0 28062013.pdf | PDF | cEMR project charter | Beta-version of "Project Management Plan" | Part. | EMC_GeorgiaCentralEMR_ProjectManagementPlan_v1 0.pdf | Tom Graham | 13 | \Completed WPs\3 WP completed\EMC_WP1
NA | 2012-10-18 | EMC_GeorgiaCentralEMR_TechnicalArchitectureDefinition_v1.4.pdf | PDF | Technical Architecture for Centralised Electronic Medical Records System | Designed according to Statement of Work number 1635063 | Yes | SoW.docx | Daniel Egorov | 54 | \Completed WPs\3 WP completed\EMC_WP2
[5 empty] | 3 blocks: | Yes | EMC, wHospital amd Mobile blocks
[5 empty] | EMC block | Yes | SQL database (EMC); XDS Repository Documentum Server (6.7 SP1, RPS, TCS, DA and CSScomponents), XDS services module (Apache Tomcat, XDS web-services app.), Documentum xDB module
[5 empty] | wHospital block | Yes | SQL database (wHospital), Application Server wHospital engine (wHospital Framework 3.16), Application Server wHospital services
[5 empty] | Mobile block | Yes | SQL database (mobile), Mobile Application server (Mokipay engne), ISS, .NET 4.0
[5 empty] | Sizing considerations | Yes | 500 concurent GP portal users, 800 concurent citizen portal sessions, 1000 concurent mobile portal sessions
[5 empty] | Software and hardware specifications for the blocks | Yes | Detailed specifications in Appendix A
[5 empty] | Technical architecture | Yes | 9 Vmware ESX servers (BL460c G8 blades). 4 blades for DR site. Storage 2 EMC VNX5300.
[5 empty] | High level infrastructure | Yes | Redundant DR, supporting nfrastructure (SQL cluster, VLANs…), Vmware ESX, Storage and backup, network, load balaner,
[5 empty] | High Availability (HA) and Disaster Recovery (DR) design | Yes | DR: Recovery Point Objective (RPO) - 24 hours, Recovery Time Objective (RTO) - 2 hours
[5 empty] | Backup and Restore | Yes | RPO - 24 hours, RTO - 2 hours
[5 empty] | System Monitoring | Yes
NA | NA | \Completed WPs\8 WP completed\6PM-WP2\Weekly Status Report | FOLDER | Weekly status reports | Weekly status reports | Yes | 6pm 19 reports, EMC - 19 reports, LSB - 19 reports, Mokipay - 16 reports. Total - 73 reports | NA | NA | \Completed WPs\8 WP completed\6PM-WP2\Weekly Status Report
NA | 2013-09-26 | Georgia Master Project Plan 20130926.mpp | MPP | Project Management Plan | Project Management Plan | Part. | 63% Completed | NA | NA | \Completed WPs\8 WP completed\6PM-WP2
NA | 2013-09-27 | EMC_GeorgiaCentralEMR_QualityManagementPlan_v1.pdf | PDF | Quality Management Plan | Quality Management Plan | Yes | Quality assurange, quality control, quality management for project documentation, workshops solution development, UAT defect tracking, training | Chris Hyams | 21 | \Completed WPs\8 WP completed\6PM-WP3\Quality Management Plan
NA | 2013-08-08 | UAT Approach V0.0.pdf | PDF | User Acceptance Testing | User Acceptance Testing | Part. | Draft for internal review | Chris Hyams | 13 | \Completed WPs\8 WP completed\6PM-WP3\Quality Management Plan
NA | 2013-10-01 | 05 - LaserBiomed - Testing Request and Summary Report (TRSR).docx | DOC | Testing Request and Summary Report (TRSR) | Testing Request and Summary Report (TRSR) | Yes |  | Lorenzo Rossi | 10 | \Completed WPs\8 WP completed\6PM-WP3\Testing Reports\Laser Biomed
NA | 2013-09-19 | Test plan summary Framework Manager.pdf | PDF | Test Plan Details - Framework Manager | Test Plan Details - Framework Manager | Yes |  | Ryan Vogrinec | 5 | \Completed WPs\8 WP completed\6PM-WP3\Testing Reports\Laser Biomed
NA | 2013-10-05 | Test plan summary Order Entry.pdf | PDF | Test Plan Details - Order Entry | Test Plan Details - Order Entry | Yes |  | Ryan Vogrinec | 4 | \Completed WPs\8 WP completed\6PM-WP3\Testing Reports\Laser Biomed
NA | 2013-10-02 | Test plan summary Patient Privacy List cEMR .pdf | PDF | Test Plan Details - Patient Privacy List cEMR | Test Plan Details - Patient Privacy List cEMR | Yes |  | Ryan Vogrinec | 4 | \Completed WPs\8 WP completed\6PM-WP3\Testing Reports\Laser Biomed
NA | 2013-10-04 | Test plan summary wHospital User.pdf | PDF | Test Plan Details - wHospital | Test Plan Details - wHospital | Yes |  | Ryan Vogrinec | 4 | \Completed WPs\8 WP completed\6PM-WP3\Testing Reports\Laser Biomed
NA | 2013-09-30 | EMC_GeorgiaCentralEMR_Mokipay_TestCases_v1002.docx | DOCX | Mokipay - test cases | Mokipay - test cases | Yes |  | Edvardas Cirtautas | 16 | \Completed WPs\8 WP completed\6PM-WP3\Testing Reports\MokiPay
NA | 2013-09-25 | Mokipay Testing Request and Summary Report (TRSR) v0925.docx | DOCX | Mokipay - Testing Request & Summary Report (TRSR) | Mokipay - Testing Request & Summary Report (TRSR) | Yes |  | Edvardas Cirtautas | 11 | \Completed WPs\8 WP completed\6PM-WP3\Testing Reports\MokiPay
NA | 2013-11-05 | Deliverable Status.xlsx | XLSX | Deliverables Status | Various milestones | Yes |  | Elton Barry | NA | \Completed WPs\8 WP completed\6PM-WP3
NA | 2013-11-06 | EMC_GeorgiaCentralEMR_QualityActivities_0_1.xlsx | XLSX | Georgia Central EMR Project - Quality Control Activities | Various activities status | Yes |  | Karen Cuschieri | NA | \Completed WPs\8 WP completed\6PM-WP3
NA | 2013-10-23 | HL7 Gateway Training TTT.pptx | PPTX | HL7 Gateway training | Hl7 Gateway training presentation | Yes | Powerpoint presentation | Vania Manzelli | 26 | \Completed WPs\8 WP completed\8 WP completed\LSB-WP7\Training & Testing
NA | 2013-11-05 | MoLHSA_Architecture_Config.pptx | PPTX | MoLHSA HP Architecture and Configuration | MoLHSA HP Architecture and Configuration | Yes | Powerpoint presentation | Tatyana Podoynitsina | 34 | \Completed WPs\8 WP completed\8 WP completed\EMC-WP4
NA | 2013-10-23 | MoLHSA_Documentum_Full _HIP_training.ppt | PPT | EMC HIP Patients Records Training Program | EMC HIP Patients Records Training Program | Yes | Powerpoint presentation | Tatyana Podoynitsina | 18 | \Completed WPs\8 WP completed\8 WP completed\EMC-WP4
NA | 2013-10-22 | Paul Ryan_HIPArchitecture_HIP-101-03-XDSx_HIP_Portal_x_VNA.pptx | PPTX | The Healthcare Integration Portfolio | The Healthcare Integration Portfolio presentation | Yes | Powerpoint presentation | NA | 26 | \Completed WPs\8 WP completed\8 WP completed\EMC-WP4\Paul HIP
NA | 2013-10-22 | Paul Ryan-HIP IHE Profiles_Short.pptx | PPTX | Healthcare Integration Portfolio - IHE Profiles | IHE Profiles presentation | Yes | Powerpoint presentation | NA | 28 | \Completed WPs\8 WP completed\8 WP completed\EMC-WP4\Paul HIP
NA | 2013-10-22 | Paul Ryan-HIP XDS Architecture_Short.pptx | PPTX | Healthcare Integration Portfolio - HIP XDS Architecture | HIP XDS Architecture presentation | Yes | Powerpoint presentation | NA | 40 | \Completed WPs\8 WP completed\8 WP completed\EMC-WP4\Paul HIP
NA | 2013-10-18 | Paul Ryan-Registry-Installation_Final.pptx | PPTX | Healthcare Integration Portfolio - HIP 1.4 XDS Registry Windows Installation | HIP 1.4 XDS Registry Windows Installation presentation | Yes | Powerpoint presentation | NA | 19 | \Completed WPs\8 WP completed\8 WP completed\EMC-WP4\Paul HIP
NA | 2013-10-18 | Paul Ryan-Repository-Installation.pptx | PPTX | Healthcare Integration Portfolio - HIP 1.4 XDS Repository Installation and Configuration | HIP 1.4 XDS Repository Installation and Configuration presentation | Yes | Powerpoint presentation | NA | 7 | \Completed WPs\8 WP completed\8 WP completed\EMC-WP4\Paul HIP
NA | 2013-10-18 | Paul Ryan-Sanity Test.pptx | PPTX | Healthcare Integration Portfolio - HIP 1.4 Sanity Check | HIP 1.4 Sanity Check presentation | Yes | Powerpoint presentation | NA | 20 | \Completed WPs\8 WP completed\8 WP completed\EMC-WP4\Paul HIP
NA | NA | \Completed WPs\8 WP completed\8 WP completed\EMC-WP5 | FOLDER | weekly status reports and steering committee meeting minutes | weekly status reports and steering committee meeting minutes | Yes | 11 Weekly reports, 33 pages | NA | 33 | \Completed WPs\8 WP completed\8 WP completed\EMC-WP5
NA | NA | \Completed WPs\8 WP completed\8 WP completed\LSB-WP2 | FOLDER | Training working materials | Training working materials | Part. | Various files - 8 PDF files, 2 videos | NA | NA | \Completed WPs\8 WP completed\8 WP completed\LSB-WP2
NA | NA | \Completed WPs\8 WP completed\8 WP completed\LSB-WP5 | FOLDER | Training working materials | Training working materials | Part. | Various files - 2 PDF files, 6 PowerPoint Presentations | NA | NA | \Completed WPs\8 WP completed\8 WP completed\LSB-WP5
NA | NA | \Completed WPs\8 WP completed\8 WP completed\LSB-WP6 | FOLDER | Training working materials | Training working materials | Part. | Various files - 2 PowerPoint Presentations | NA | NA | \Completed WPs\8 WP completed\8 WP completed\LSB-WP6
NA | 2013-10-23 | EMC_GeorgiaCentralEMR_LaserbiomedServerSoftware_InstallationDocument_v2.pdf | PDF | wHospital Server Software - Installation Document | wHospital Server Software Installation | Yes |  | Vania Manzelli | 28 | \Completed WPs\8 WP completed\LSB-WP7\External Service Bus Handlers for HCP HL7 Integration
3/3504/109 | 2012-09-27 | EMC #109.pdf | PDF | SOFTWARE BPO/SaaS AGREEMENT | Laserbiomed - MoLHSA contract | Yes | English and Georgian languages | NA | 92 | \EMC Contract
[5 empty] | Maintenance for the initial 5 years | Yes
[5 empty] | Annual fes after 5 years | Yes
[5 empty] | 24/7 support | Yes
[5 empty] | Laserbiomed Level 1 Technical support | Yes
??? | ??? | EMC #110.pdf | PDF | ??? | ??? | No | File defect | NA | NA | \EMC Contract
1635063 | 2012 | SoW.docx | DOCX | Statement of Work: EMC & EMC PS - Georgia MoLHSA - Georgia Central EMR | Statement of Work | Yes |  | NA | 50 | \EMC Contract
NA | 2012 | BPO_SaaS EMC-2.docx | DOCX | SOFTWARE BPO/SaaS AGREEMENT | EMC - MoLHSA contract | ?? | Word file, not signed, no date | NA | 35 | \EMC Contract
[5 empty] | Total contract fee | ?? | 3764500
[5 empty] | Non-Production Support Annual Program Fee | Yes | $11,000 per annum
[5 empty] | Initial Infrastructure License fee | Yes | 450000
[5 empty] | First year Enhanced Suport fee | Yes | $103,500 (23% of infrastructure license fee)
[5 empty] | Patient folders fee | Yes | $450,000 for 562,500 patient folders ($0.80 per patient)
[5 empty] | On or before 15th November 2012 Partner shall place an additional irrevocable order on EMC for an additional 2,187,500 Patient Folders | ??
[5 empty] | Partner shall on or before 15th May 2013 place a further irrevocable order on EMC for an additional 1,250,000 Patient Folders | ??
NA | 2012 | BPO_SaaS Laserbiomed.docx | DOCX | SOFTWARE BPO/SaaS AGREEMENT | Laserbiomed - MoLHSA contract | ?? | Word file, not signed, no date | NA | 32 | \EMC Contract
NA | 2012 | BPO_SaaS Mokipay.docx | DOCX | SOFTWARE BPO/SaaS AGREEMENT | Mokipay - MoLHSA contract | ?? | Word file, not signed, no date | NA | 31 | \EMC Contract
NA | 2013-06-18 | EMC_GeorgiaCentralEMR_ClinicalFormsSpecification_V0.1.docx | DOCX | Clinical Forms Specification | Document contains content, layout and configuration of the clinical forms: | Yes |  | Karen Cuschieri | 42 | \
[5 empty] | Family History | Yes
[5 empty] | Social History | Yes
[5 empty] | New Functional Status | Yes
[5 empty] | Vital Signs | Yes
[5 empty] | Medication | Yes
[5 empty] | Allergies and Adverse Reactions | Yes
[5 empty] | Immunisation | Yes
[5 empty] | Payers | Yes
[5 empty] | Problems | Yes
[5 empty] | Procedures | Yes
[5 empty] | Plan of Care | Yes
[5 empty] | History of Encounters | Yes
[5 empty] | Form 100 | Yes
NA | 2014-01-15 | Georgia Health Care Project Closure - Final.doc | DOC | cEMR - Project Phase 1 - Closure Report | Project Phase 1 Closure Report | Yes |  | David Ings | 12 | \
[5 empty] | Completed deliverables | Yes
[5 empty] | Financial summary | Yes
[5 empty] | Action items | Yes
[5 empty] | Risks / Issues | Yes | 1. Limited understanding of Clinical Business processes and procedures may hamper proposed roll out plans, 2. MoLHSA may need support from the EMC Consortium in order to complete their remaining activities
NA | 2013-12-18 | signed_confirm_akt_last8.pdf | PDF | Confirmation | Signed confirmation | Yes |  | NA | 16 | \
NA | 2013-11-12 | ინსპექტირების აქტი.pdf | PDF | ინსპექტირების აქტი | Inspection Act | Yes |  | NA | 6 | \
NA | 2013-08-22 | aleko nodiasTvis pasuxi.docx | DOCX | Answers to Aleko Nodia questions | Questions from USAID HSSP | Yes |  | Nika Tsuleiskii | 3 | \EMR EMC
[5 empty] | Immunisation Clinical form | Yes
[5 empty] | Medication Clinical Form | Yes
[5 empty] | Integration with USAID HSSP modules | Yes
NA | 2013-08-22 | E-health WorkGroup Geo.docx | DOCX | საქართველოს მხრიდან სამუშაო ჯგუფი | List of Georgian project team | Yes |  | Nika Tsuleiskii | 3 | \EMR EMC
NA | 2013-09-25 | recommendations for HIP & xDB training participants.docx | DOCX | Recommendations for HIP & xDB training | Recommendations for HIP & xDB training | Yes |  | Nika Tsuleiskii | 1 | \EMR EMC
NA | 2013-09-05 | NCDC Codes.xls | XLS | NCDC Codes | English and Georgian | Yes | Education, Marital Status, Current Ocupation | Nika Tsuleiskii | 4 | \EMR EMC
NA | 2013-09-24 | MoLHSA_Milestone Payment_Certificate-MokiPay_WP2.docx | DOCX | EMC Project Milestone Payment Certificate | Moki-Pay Work Package 2 - Mobile EMR Localisation & Development | Yes | 90000 | EMC | 1 | \EMR EMC
NA | 2013-09-24 | MoLHSA_Milestone Payment_Certificate-MokiPay_WP1.docx | DOCX | EMC Project Milestone Payment Certificate | Moki-Pay Work Package 1 – Mobile Server Software Installation | Yes | 90000 | EMC | 1 | \EMR EMC
NA | 2013-09-10 | HIS survery for geo hospitals.docx | DOCX | Health care provieder – Information System – Survey | Health care provieder – Information System – Survey | No | Hardware and Software technologies | Lorenzo Rossi | 8 | \EMR EMC
NA | 2013-10-25 | Georgia Master Project Plan v13a 020913 (1).mpp | MPP | Georgia Health Care Project Increment Plan | Georgia Health Care Project Increment Plan | Part. | 29% completed | NA | NA | \EMR EMC
NA | 2013-09-13 | Georgia Master Project Plan V12.mpp | MPP | Georgia Health Care Project Increment Plan | Georgia Health Care Project Increment Plan | Part. | 11% completed | NA | NA | \EMR EMC
NA | 2013-06-03 | cEMR conceptual model.pptx | PPTX | Central EMR conceptual model | Central EMR conceptual model presentation | Yes | 6 slides by Lorenzo Rossi | Lorenzo Rossi | 6 | \EMR EMC\inspection 9 milestones\mixed docs\EMR
NA | 2013-07-03 | XDS_Integration_Tests LSB WP3.pdf | PDF | XDS wHospital-Hip Documentum - Integration test results | XDS wHospital-Hip Documentum - Integration test results | Yes | 34 pages |  | 34 | \EMR EMC\inspection 9 milestones\mixed docs\report emc
NA | 2013-08-02 | wH Framework Academy - Part 10 ian checked.pptx | PPTX | GP portal Part 10: Clinical View, Clinical Concept, Workflow Management | Clinical View, Clinical Concept, Workflow Management training presentation | Yes | 25 slides by Giorgio Lissoni | Giorgio Lissoni | 25 | \EMR EMC\inspection 9 milestones\mixed docs\Training session_Giorgio Lissoni\Friday 2nd August - Part 9 and 10
NA | 2013-11-01 | migeba-chabareba 9 milestones Nov 1.docx | DOCX | CONFIRMATION OF DELIVERY AND RECEIPT OF GOODS PURCHASED WITH ALLOTMENTS FROM THE STATE BUDGET ASSIGNED FOR THE STATE COSTS OF REHABILITATION AND EQUIPMENT OF MEDICAL ESTABLISHMENTS | Confirmation | Yes |  | NA | 9 | \migeba-chabareba acts
NA | 2013-08-29 | MoLHSA_SC_Minutes_of_Meeting_29082013-Final.docx | DOCX | MoLHSA STEERING COMMITTEE MEETING - Minutes of Meeting |  | Part. |  | NA | 4 | \Completed WPs\8 WP completed\8 WP completed\EMC-WP5\Steering Committee
[5 empty] | Project Status update |  | Project is RED due to concerns about MoLHSA resources
[5 empty] | Georgia HealthCare: Project review / Future direction |  | MG stressed the importance of addressing the ‘Next Phase’ activities to avoid losing momentum
NA | 2013-08-12 | Clinical forms value and Resource files translation procedures.pdf | PDF | Clinical forms data & Resource files translation Procedures | reference file of clinical form document, in relation to translation of clinical forms data and resource files | Yes |  | Bhavesh Singh | 29 | \Completed WPs\8 WP completed\8 WP completed\LSB-WP5\From Chris\Administration Manual
NA | 2013-09-02 | Code itemAgenda and Vocabulary configuration manual .pdf | PDF | Sub Operational Units, Coded Items, Coded Systems, Items, Agenda, Trees | Details of what is presented in the training session wH Framework Academy - Part 8 | Yes |  | Giorgio Lissoni | 18 | \Completed WPs\8 WP completed\8 WP completed\LSB-WP5\From Chris\Administration Manual
NA | 2013-10-21 | GP Portal - Patient list.pptx | PPTX | GP Portal:Patients list | Patients list functionality | Yes |  | Bhavesh Singh | 23 | \Completed WPs\8 WP completed\8 WP completed\LSB-WP5\From Chris\Quick Reference
NA | 2013-10-21 | GP Portal.pptx | PPTX | Georgia Central EMR Project - GP Portal | GP Portal training presentation | Yes |  | Ian Clarke | 25 | \Completed WPs\8 WP completed\8 WP completed\LSB-WP5\From Chris\Quick Reference
NA | 2013-10-22 | Hospital Portal - Inpatient,Consultancy, Message.pptx | PPTX | User Manual: Hospital portal | User Manual: Hospital portal | Yes |  | Bhavesh Singh | 31 | \Completed WPs\8 WP completed\8 WP completed\LSB-WP5\From Chris\Quick Reference
NA | 2013-10-21 | Hospital Portal - Main.pptx | PPTX | Georgia Central EMR Project - Hospital portal | Georgia Central EMR Project - Hospital portal | Yes |  | Ian Clarke | 26 | \Completed WPs\8 WP completed\8 WP completed\LSB-WP5\From Chris\Quick Reference
NA | 2013-10-23 | Citizen portal.pptx | PPTX | Citizen Portal | Citizen Portal training presentation | Yes |  | Bhavesh Singh | 17 | \Completed WPs\8 WP completed\8 WP completed\LSB-WP6\From Chris\Quick Reference Guide
NA | 2013-10-26 | Citizen portal - TtT.pptx | PPTX | Citizen Portal - Train the Trainer | Citizen Portal - Train the Trainer | Yes |  | Ian Clarke | 20 | \Completed WPs\8 WP completed\8 WP completed\LSB-WP6\From Chris\Training