## page 1
Course topic | Time -Hour
Project management
What is a project | 0.5
Main concepts | 0.5
Project basics
Creating a project | 0.5
Changing the calendar | 0.5
Creating tasks
Typing in tasks | 0.5
Creating sub-tasks | 0.5
Changing task durations | 0.5
Task annotations | 0.5
Creating a Gantt chart | 0.5
Tasks - other topics
Recurring tasks | 0.5
Creating dependencies | 0.5
Setting task constraints | 0.5
Understanding task types | 0.5
Resources
Creating a resource pool | 0.5
Setting resource availability | 0.5
Setting resource costs | 0.5
Assigning resources | 0.5
Conflicts and Levelling | 0.5
Views
The different views in Project | 0.5
Customising views | 0.5
Assignments
Resource levelling | 0.5
Delaying or splitting tasks | 0.5
Viewing resource conflicts | 0.5
Project tracking
Creating a baseline | 0.5
Recording actuals | 0.5
Critical path analysis | 0.5
Printing
Changing what prints | 0.5
Choosing a report | 0.5