G-CCM Transition – Action Plan

This Action Plan describes in more detail the objectives and activities, indicators for their monitoring, responsible institutions and resources, as well as timelines for the implementation of activities related to G-CCM transition. The Action plan will be adopted for the period of three years. This Action Plan is an integral part of the G-CCM Transition Plan.

| Objectives | Activities | Responsible | Estimated Completion Date | Resources | Indicators |
| --- | --- | --- | --- | --- | --- |
| 1. To deepen the understanding of CCM members and key stakeholders on a need for G-CCM transition | 1.1 Awareness raising meetings/workshops on G-CCM transition | EHG consultants PAAC consultants | By the end of December 2019 | GIZ Backup Initiative project | PAAC and G-CCM members understand transition and start with preparation for the transition |
|  | 1.2 Sharing experiences from other countries | EHG consultants | By the end of December 2019 | GIZ Backup Initiative project | PAAC and G-CCM learn about other country experiences and start with preparation for transition |
|  | 1.3 Awareness raising meetings/workshops on issues concerning sustainable funding | EHG consultants PAAC consultants | By the end of December 2019 | GIZ Backup Initiative project | G-CCM members understand issues related to sustainable funding and start with fund raising |
| 2. To strengthen the existing G-CCM structure for its own transition | 2.1 Revision of the PAAC Terms of Reference (ToR) to address expansion of their mandate to act as a catalyst to raise the awareness among key stakeholders on the G-CCM transition and mobilize resources | G-CCM with support of CCM Secretariat and EHG consultants | By the end of January 2019 | GIZ Backup Initiative project | Revised PAAC ToR in place (in use) |
|  | 2.2 Revision of the existing ToR of the Oversight Committee (OC) to address expansion of their mandate and include oversight of the G-CCM’s transition | G-CCM with support of CCM Secretariat and EHG consultants | By the end of January 2019 | GIZ Backup Initiative project | Revised OC ToR in place (in use) |
|  | 2.3 Revision of the CCM Secretariat ToR to address expansion of their mandate for enhancing the G-CCM’s capacity for transition and for building its capacity to expand its role. | G-CCM; PAAC | By the end of June 2019 | GIZ Backup Initiative project | Revised CCM Secretariat ToR in place (in use) |
|  | 2.4 Renewal of the G-CCM membership to reflect changes (possible expansion) of the CCM role (e.g. key Hepatitis C, STI, stakeholders). | G-CCM with support of CCM Secretariat and EHG consultants | Based on an annual revision of the CCM Transition Plan | N/A | CCM membership renewed / Percentage of new CCM members |
| 3. To build G-CCM capacity to oversee the programmatic transition and implement the necessary steps for its own transition | 3.1 G-CCM self-assessment workshop to identify the potential capacity gaps and areas which require further capacity building for transition | Led by EHG consultants with support of G-CCM Secretariat; might involve all G-CCM members interested | By the end of June 2019 | CCM Budget and GIZ Backup Initiative project | Capacity gaps identified/Report |
|  | 3.2 Development of the G-CCM capacity building for transition work plan including the budget for its implementation based on the self-assessment results | Led by G-CCM Secretariat; might involve all G-CCM members interested (with remote support of EHG consultants) | By the end of June 2019 | GIZ Backup Initiative project | Capacity building work plan for G-CCM transition in place/implementation |
|  | 3.3 Orientation of the CCM members and members of the committees on their new (extended) roles and responsibilities and updated G-CCM governance documents | CCM Secretariat and EHG consultants | By the end of November 2019 | GIZ Backup Initiative project | Number (percentage) of G-CCM members knowledgeable on their new (extended) roles and responsibilities and G-CCM governance documents |
|  | 3.4 Implementation of the capacity building working plan for transition | PAAC; Oversight Committee | By the end of December 2019 and then refresh annually | External TA, if possible | G-CCM enhanced for transition process/able to lead its own transition |
|  | 3.5 Oversight of the G-CCM capacity building plan for implementation | Oversight Committee | By the end of June 2020 and bi-annually | CCM Budget | Minutes of the OC meetings/Reports |
| 4. To develop and/or update the existing governance and legal documents to address changes and possible expanded G-CCM role | 4.1. Development of the G-CCM Transition Plan | EHG and PAAC consultants in the initial phase G-CCM and PAAC | By the end of December 2018 | GIZ Backup Initiative project initially | G-CCM Transition Plan in place |
|  | 4.2 Assess the implementation and propose any adjustments to the plan, if needed | Oversight committee | By the end of December 2019 (annually) | G-CCM budget | Minutes of the meetings; Reports G-CCM evolved |
|  | 4.3 Modifications and amendments to Resolution #220 for the evolution of the G-CCM* | PAAC and MoLHSA | TBD (based on an annual review) | TBD (G-CCM budget/ External TA, if possible) | Updated/revised Resolution #220 G-CCM perform the new updated roles |
|  | 4.4 Adjustment of other relevant document (e.i. national programs, guidelines, etc.) to address G-CCM expanded role* | MoLHSA G-CCM | TBD (based on an annual review) | TBD (G-CCM budget/ External TA, if possible) | Updated/revised national programs (HIV, TB, Hep C, etc) G-CCM perform the new updated roles |
| 5. To deepen the understanding of key stakeholders and of G-CCM members on a need for resource mobilization for G-CCM functioning after GF leaves | 5.1 Awareness raising workshops and/ or discussions on resource mobilization | EHG consultants PAAC consultants | By the end of December 2019 and then refresh annually | GIZ Backup Initiative project | PAAC and G-CCM members understand a need and start with resource mobilization process |
|  | 5.2 Developing budget proposal for G-CCM (after GF support) | G-CCM Secretariat with support of CCM members | By the end of December 2019 and then refresh annually | G-CCM budget |  |
|  | 5.3 Mobilization of potential donors | PAAC; MoLHSA G-CCM Local municipalities | By the end of March 2020 | TBD | Number of donors |
| 6. To establish a system for monitoring of the G-CCM transition process | 6.1 Define system for oversight and monitoring of the G-CCM transition process | PAAC; G-CCM | By the end of June 2019 and then annually | GIZ Backup Initiative project | M&E system in place |
|  | 6.2 Define transition milestones for monitoring G-CCM transition process | PAAC; G-CCM with EHG consultant support | By the end of June 2019 and then annually | GIZ Backup Initiative project | Milestones defined |

* When/if agreed that G-CCM role will be expanded to Hep C, etc....

The renewal of the G-CCM membership is done according to the specifications of the Governance Manual. The latest renewal process was completed in May 2018