G-CCM Transition – Action Plan

Approved: January 2019

To be updated annually or on an as needed basis

This Action Plan describes in more detail the objectives and activities, indicators for their monitoring, responsible institutions and resources, as well as timelines for the implementation of activities related to G-CCM transition. This Action Plan is an integral part of the G-CCM Transition Plan.

| Objectives | Activities | Responsible | Estimated Completion Date | Resources | Indicators | Status |
| --- | --- | --- | --- | --- | --- | --- |
| 1. To deepen the understanding of CCM members and key stakeholders on a need for G-CCM transition | 1.1 Awareness raising meetings/workshops on G-CCM transition/evolution | EHG consultants (remotely through April 2020) PAAC consultants | On-going | GIZ Backup After April 2020, CCM budget, if needed | PAAC and G-CCM members understand transition and start with preparation for the transition | On-going on as needed basis |
|  | 1.2 Sharing experiences from other countries | EHG consultants (remotely through April 2020) PAAC consultants | On-going | GIZ Backup After April 2020, CCM budget, if needed | PAAC and G-CCM learn about other country experiences and start with preparation for transition | On-going on as needed basis |
|  | 1.3 Awareness raising meetings/workshops on issues concerning sustainable funding | EHG consultants (remotely through April 2020) PAAC consultants | By the end of December 2022 | GIZ Backup After April 2020, CCM budget, if needed | G-CCM members understand issues related to sustainable funding and start with fund raising | On-going on as needed basis |
| 2. To strengthen the existing G-CCM structure for its own transition | 2.1 Revision of the PAAC Terms of Reference (ToR) to address expansion of their mandate to act as a catalyst to raise the awareness among key stakeholders on the G-CCM transition and mobilize resources | G-CCM with support of CCM Secretariat and EHG consultants | By end of January 2019 | GIZ Backup After April 2020, CCM budget, if needed | Revised PAAC ToR in place (in use) | Completed (January 2019); to be reviewed annually or on an as-needed basis |
|  | 2.2 Revision of the existing ToR of the Oversight Committee (OC) to address expansion of their mandate and include oversight of the G-CCM’s transition | G-CCM with support of CCM Secretariat and EHG consultants | By the end of January 2019 | GIZ Backup After April 2020, CCM budget, if needed | Revised OC ToR in place (in use) | Completed January 2019; to be reviewed annually or on an as-needed basis |
|  | 2.3 Revision of the CCM Secretariat ToR to address expansion of their mandate for enhancing the G-CCM’s capacity for transition and for building its capacity to expand its role. | EHG Consultants PAAC consultant | By the end of March 2020 | GIZ Backup After April 2020, CCM budget, if needed | Revised CCM Secretariat ToR in place (in use) | On-going |
|  | 2.4 Renewal of the G-CCM membership to reflect changes (possible expansion) of the CCM role (e.g. key Hepatitis C, STI, stakeholders). | G-CCM with support of CCM Secretariat | Based on an annual revision of the CCM Transition Plan | N/A | CCM membership renewed / Percentage of new CCM members | On-going |
| 3. To build G-CCM capacity to oversee the programmatic transition and implement the necessary steps for its own transition | 3.1 G-CCM self-assessment workshop to identify the potential capacity gaps and areas which require further capacity building for transition | Initial self-assessment led by EHG consultants; after April 2020 by PAAC consultant | By the end of December 2019 | GIZ Backup After April 2020, CCM budget, if needed | Capacity gaps identified / Presentation to G-CCM | Completed (December 2019); to be repeated annually, if needed |
|  | 3.2 Development of the G-CCM capacity building for transition work plan including the budget for its implementation based on the self-assessment results | EHG Consultants; after April 2020 by G-CCM Secretariat | By the end of April 2020 | GIZ Backup After April 2020, CCM budget, if needed | Capacity building work plan for G-CCM transition in place/implementation | Will be done, if needed, based on results of self-assessment |
|  | 3.3 Orientation of the CCM members and members of the committees on roles and responsibilities and updated G-CCM governance documents 3.3.a: Regular roles 3.3.b: New roles 3.3.c: Extended roles | CCM Secretariat and EHG consultants | By the end of April 2020 (regular roles) | GIZ Backup After April 2020, CCM budget, if needed | Number (percentage) of G-CCM members knowledgeable on their roles and responsibilities and G-CCM governance documents | Regular: Completed by April 2020 |
|  |  |  |  |  |  | New: As needed based on annual review |
|  |  |  |  |  |  | Extended: As needed based on annual review |
|  | 3.4 Implementation of the capacity building working plan for transition | G-CCM Secretariat Oversight Committee | By the end of December 2019 and then refresh annually | CCM Budget | G-CCM enhanced for transition process/able to lead its own transition | On-going |
|  | 3.5 Oversight of the G-CCM capacity building plan for implementation | Oversight Committee and G-CCM Secretariat | By the end of June 2020 and bi-annually | CCM Budget | Minutes of the OC meetings/Reports | On-going |
| 4. To develop and/or update the existing governance and legal documents to address changes and possible expanded G-CCM role | 4.1. Development of the G-CCM Transition Plan | EHG and PAAC consultants in the initial phase G-CCM and PAAC | Approved January 2019 | GIZ Backup After April 2020, CCM budget, if needed | G-CCM Transition Plan in place | Completed (January 2019); to be reviewed and updated, if needed, annually |
|  | 4.2 Assess the implementation and propose any adjustments to the plan, if needed | Oversight committee | By the end of December 2019 | G-CCM budget | Minutes of the meetings; Reports G-CCM evolved | On-going on annual basis |
|  | 4.3 Modifications and amendments to Resolution #220 for the evolution of the G-CCM | PAAC and MoIDP&LHSA | TBD (based on an annual review) | TBD (G-CCM budget/ External TA, if possible) | Updated/revised Resolution #220 G-CCM perform the new updated roles | Reviewed on an annual basis and the modified, if needed |
|  | 4.4 Adjustment of other relevant document (e.g. national programs, guidelines, etc.) to address G-CCM expanded role | MoIDP&LHSA G-CCM | TBD (based on an annual review) | TBD (G-CCM budget/ External TA, if possible) | Updated/revised national programs (HIV, TB, Hep C, etc) G-CCM perform the new updated roles | Reviewed on an annual basis and the modified, if needed |
| 5. To deepen the understanding of key stakeholders and of G-CCM members on a need for resource mobilization for G-CCM functioning after GF leaves | 5.1 Awareness raising workshops and/or discussions on resource mobilization | PAAC consultants | By the end of December 2022 and then refresh annually | G-CCM budget | PAAC and G-CCM members understand a need and start with resource mobilization process | On-going |
|  | 5.2 Developing budget proposal for G-CCM (after GF support) | G-CCM Secretariat with support of CCM members | By the end of December 2022 and then refresh annually | G-CCM budget | Budget proposal completed | On-going |
|  | 5.3 Mobilization of potential donors | PAAC; MoIDP&LHSA G-CCM Local municipalities | By the end of December 2022 | TBD | Allocated budget as a percentage of planned/requested funding | On-going |
| 6. To establish a system for monitoring of the G-CCM transition process | 6.1 Define system for oversight and monitoring of the G-CCM transition process | PAAC; G-CCM | By the end of June 2019 and then annually | GIZ Backup | M&E system in place | Completed (January 2019); to be updated annually |
|  | 6.2 Define transition milestones for monitoring G-CCM transition process | PAAC; G-CCM with EHG consultant support | By the end of June 2019 and then annually | GIZ Backup | Milestones defined | Completed (January 2019); to be updated annually |
|  | 6.3 Regular monitoring of the Transition Plan | OC with support from G-CCM Secretariat | On-going | CCM budget | Minutes of the OC meetings/Reports | On-going |
|  | 6.4 Revision of Transition Plan indicators | PAAC consultant and OC with support from G-CCM Secretariat | On-going as needed | N/A | Revised indicators incorporated into Transition Action Plan | On-going on as needed basis |

The renewal of the G-CCM membership is done according to the specifications of the Governance Manual. The latest renewal process was completed in May 2018

To be reviewed annually.

When/if agreed that G-CCM role will be expanded to Hep C, etc....

When/if agreed that G-CCM role will be expanded to Hep C, etc....