## Sheet1
Action Plan for implementation of IDP State Strategy 2019-2020
Results of the Policy | Activity | Indicator of results | Timeline of Implementation | Implementation Report of 2019 | Status
2.1.1. General Preparatory measures: 1) Updating IDP database; 2) Updating data on social-economic conditions of IDPs; 3) Updating Data on Durable Housing Solution programs. | 2.1.1.1. Regular updating of IDP database according to the legislation | IDP database is updated, available for elligible persons, it functions and information is updated through the segregated data system (sex, age, and region); it contains all the necessary information in order to measure the progress. | 2019: monthly 2020: monthly | 27638 persons were granted with IDP status in 2019. IDP status was suspended / deprived of 10005 persons. | Implemented
| 2.1.1.2. Requesting personal details, personal identification documentation, registration address, death, and/or birth of IDPs with the purpose of verification |  | 2019: monthly 2020: monthly | Information was requested from the Ministry of Justice monthly in 2019 | Implemented
| 2.1.1.3. Updating data on beneficiaries enrolled in different social programs, also on various social statuses. | Updated Data | 2019: monthly 2020: monthly | Information data was updated monthly. 30,194 IDPs were registered in database of socially vulnerable people as of December 2019. | Implemented
| 2.1.1.4. Updating information on IPDs' monthly income according to the legislation. |  | 2019: monthly 2020: monthly | Monthly income of IDPs was updated in database once in a month. IDP status has been deprived to 14018 persons because of their income in December 2019. | Implemented
| 2.1.1.5. Regular updating of information about IDP accommodation, and such buildings, which are being or are going to be rehabilitated | Updated Data | 2019: monthly 2020: monthly | 9 building were rehabilitated | Implemented
| 2.1.1.6. Identifying unused, state owned non-agricultural land in order to build houses or apartment buildings in various municipalities. | Identifiied land plots for construction in m2 | 2019: 0.5 ha 2020: 0.5 ha | Large-scale constructions are ongoing in Tskaltubo, Kutaisi and Zugdidi, covering 66166m2. | Implemented
| 2.1.1.7. Technical Evaluation of IDP Long Term Resettlement Facilities for Refurbishment | Number of technically evaluated buildings | 2019: 75 buildings 2020: 75 buildings | technical evaluation of 49 building was carried out | Mostly performed
| 2.1.1.8. Revision of IDP accomodation criteria. Procedures, living standarts and other legal acts related to this issue. | The number of updated/adopted legal acts. | Minimum once in a year | Criteria, procedures, standards of Durable Housing have been amended and a new program has been developed to co-finance the purchase of residential properties for registered IDP families in Tbilisi. Besides, the new normative act also regulates the transfer of living spaces to IDP veterans' families in newly constructed apartment blocks. | Implemented
2.1.2 Implementation of long-term resettlement programs within existing buildings and in order to create new settlements. IDP families will be selected according to the rules, standards and criteria provided by the Minister of Internally Displaced Persons from the Occupied Territories, Accommodation and Refugees of Georgia (hereinafter referred to as "the Minister"). | 2.1.2.1. Purchasing individual houses and apartments, and transferring them into IDP property, including joint funding projects, according to the Guiding Principles, Criteria and Procedures Governing the Process of Durable Housing Allocation adopted by the Ministerial Legal Act. | Number of purchased houses/apartments; Number of transferred/registered houses/apartments to IDPs; Number of IDPs that were accommodated with adequate housing as a result of the project. | 2019: 600 apartments 2020: would be defined by the end of 2019 | 1050 living spaces/apartments have been purchased in the frameworks of rural house program during 2019 | Implemented
| 2.1.2.1. Co-funded resettlement of 50 IDP families registered in Tbilisi by June 1, 2013 (pilot). |  | 2019: 50 apartments 2020: would be defined by the end of 2019 | the pilot program has not been implemented because of stuctural reorganization | has not started yet
| 2.1.2.3. Transferring state owned living units, where IDPs lawfully live into IDP property. | Number of living units transferred into IDP property | 2019: 1500 transferred apartments 2020: 1500 transferred apartments | 812 families have received apartments | Mostly performed
| 2.1.2.4. Purchasing privately owned buildings/apartments that are lawfully occupied by the IDPs and transferring them into IDP ownership | Number of Purchased apartments; Number of transferred apartmetns. | 2019: 50 apartments 2020: 50 apartments | Apartments for 8 families were purchased. | partially implemented
| 2.1.2.5. Building apartment buildings or individual houses according to operating standards, and transferring them into IDP property | Number of built apartment buildings/housees; Number of apartments transferred to IDP property. | 2019: 1,100 apartments 2020: would be defined by the end of 2019 | 1047 apartments were transferred to the IDPs during 2019 | Mostly performed
| 2.1.2.6. Buying of apartments for IDPs in the apartment buildings (block) and transferring into their property | Number of purchased apartments; Number of transferred apartments. | 2019: 800 flats 2020: would be defined by the end of 2019 | In 2019, 548 apartments were purchased for durable housing of IDPs | Mostly performed
| 2.1.2.7. Long-term Resettlement Program for IDP Veterans (Pilot) | following 2.1.2.4. and 2.1.2.5. activities - Resettlement of Vulnerable IDP Families whose Family Members Have Veterans of War for Georgia's Territorial Integrity or Died in the Fight for Georgia's Territorial Integrity | 2019: 180 families 2020: would be defined by the end of 2019 | the pilot program has not been implemented because of stuctural reorganization | has not started yet
| 2.1.2.9. One-off financial assistance to IDP families who bought the property through mortgage before Ministerial Legal Act was adopted and the property is their only living space. | Number of IDP families, who received financial assistance | 2019: 100 families 2020: would be defined by the end of 2019 | the pilot program has not been implemented because of stuctural reorganization | has not started yet
| 2.1.2.11. Accommodating in DHS those IDPs, who live lawfully in the places which are dangerous for their life or health, having increased risk to collapse and/or unfit for living, and closing of the such buildings. | Number of IDPs who received DHS; Number of collapsing or unfit for living buildings; Number of buildings evaluated by an expert | 2019: 350 families 20 closed buildings 2020: 350 families 20 closed buildings | 351 families-31 closed buildings | Implemented
2.1.3. Durable Housing Solution supporting activities | 2.1.3.1. In order to improve IDP living conditions, funding condominium cooperatives of apartment buildings, that have been transferred into IDP property, together with municipalities | Number of funded condominium cooperatives | 2019: 130 condominium cooperatives 2020: would be defined by the end of 2019 | 61 condominium cooperatives have been financed | partially implemented
| 2.1.3.2. Transferring of common spaces into property of condominium cooperatives | Number of spaces transferred into property of condominium cooperatives | 2019: 50 spaces 2020: 50 spaces | 12 spaces were legalized | partially implemented
2.2.1. Improvement of IDP social assistance system | 2.2.1.1. Adapting IDP allowance to their needs | IDP allowance is differentiated according to their social-economic situation | 2019: Consultation with all interested sides 2020: Selection of a model tailored to the needs of IDPs | The law on IDPs has been amended, according to which IDP allowances will not be terminated for persons who have been outside of Georgia for more than three months instead of two months. | partially implemented
| 2.2.1.2. Involving IDP in state social protection programs | Number of IDPs participating in state programs | 2019: monthly 2020: monthly | Information data was updated monthly. 30194 IDPs were registered in database of socially vulnerable people as of December 2019. | Implemented
| 2.2.1.3. Providing IDPs, in urgent/particular needs, with one-off monetary assistance according to elaborated standards | Number of IDPs participating in state programs: Criteria of IDPs in extreme/particular needs, are elaborated and used; Number of IDPs which received assistance; Elaboration of criteria | 2019: 6000 family/person 2020: 6000 family/person | 7895 families/persons were financed | Implemented
| 2.2.1.4. In urgent situations, temporary accommodation of IDPs, according to the Guiding Principles, Criteria and Procedures Governing the Process of Durable Housing Allocation | Number of families who received assistance for the purpose of renting apartment | 2019: 1300 families 2020: 1300 families | 1557 families were financed | Implemented
2.2.2. Addressing access to the livelihoods and economic integration needs of IDPs | 2.2.2.1. Implementation of the IDP Livelihood Strategy Action Plan | IDP Livelihood Strategy and Action Plan are being implemented; IDP Reports are available | 2019: regularly 2020: regularly | 224 persons had opportunity to participate in integration programs during 2019; the cost ammounted 510 000 Gel. | Implemented
2.3.1. Raising awareness and knowledge/understanding of the IDPs and other interested parties, on their rights and services available for them, eligibility/criteria, providing them with an access to the legal consultations, also promotion of their involvement in the Action Plan. | 2.3.1.1. Providing non-governmental organizations, municipalities and media with information related to IDP issues and their solutions | Number of meetings, round tables between the Ministry and partner/non-governmental organizations with the purpose of sharing information | 2019: regularly 2020: regularly | 8 meeting were held with the partner non-governmental organizations during 2019 | Implemented
| 2.3.1.2. Supporting IDP involvement in the elaboration, implementation and revision of the Action Plan. Conducting group meeting with IDPs and participatory assessments. Examining implementation of the Strategy and preparing propositions | Annual evaluation of IDP involvement: - IDP voices are heard; - IDPs consulted on decisions that affect them; - The actions of the Government and other stakeholders are informed by the views of IDPs. | 2019: regularly 2020: regularly | 6 workshops witht the participation of IDPs were arranged. Consultations about the ongoing projects were carried out; the oppinion of IDPs was herd, | Implemented