## Sheet1
Report of Overall Assessment of Resources Required for Implementation of 2017-2018 Action Plan for implementation of IDP State Strategy
Second goal of the state strategy : supporting the dignified living conditions of IDPs and their social integration
Results of the Policy | Activity | Indicator of result | Timeline of implementation (2018 target) | I quarter of 2018 | II quarter of 2018 | III quarter of 2018 | IV quarter of 2018
2.1. Objective: Improving the living conditions of the IDPs by ensuring the durable housing solutions
2.1.1. General Preparatory measures: 1) Updating IDP database; 2) Updating data on social-economic conditions of IDPs; 3) Updating Data on Durable Housing Solution programs. | 2.1.1.1. Regular updating of IDP database according to the legislation | MRA IDP database is updated, available for permitted persons, it functions and information is updated through the segregated data system (sex, age, and region); it contains all the necessary information in order to measure the progress. | Monthly | Data were updated | Data were updated | Data were updated
| 2.1.1.2. Requesting personal details, personal identification documentation, registration address, death, and/or birth of IDPs with the purpose of verification |  | Monthly | Data were updated | Data were updated | Data were updated
| 2.1.1.3. Updating data on beneficiaries enrolled in different social programs, also on various social statuses. | Updated Data | Monthly | Data were updated | Data were updated | Data were updated
| 2.1.1.4. Updating information on IPDs' monthly income according to the legislation. |  | Monthly | Data were updated | Data were updated | Data were updated
| 2.1.1.5. Updating Data on IDPs with disabilities who are beneficiaries of social assistance |  | Twice a year | Data on IDPs with disabilities have been updated according to the documentation submitted during processing DHS applications | Data on IDPs with disabilities have been updated according to the documentation submitted processing DHS applications | Data on IDPs with disabilities have been updated according to the documentation submitted during processing DHS applications
| 2.1.1.6. Regular updating of information about IDP accommodation, and such buildings, which are being or are going to be rehabilitated | Updated Data | Monthly | Data were updated | Data were updated | Data were updated
| 2.1.1.7. Verifying information about real estate registered into property of IDP family members | Information verified | Twice a year | Data have been updated during the process of examining DHS applications | Data have been updated during the process of examining DHS applications | Data have been updated during the process of examining DHS applications
| 2.1.1.8. Identifying unused, state owned non-agricultural land in order to build houses or apartment buildings in various municipalities. | Identifiied land plots for construction in m2 | 0.5 ha | Land plots for construction have been identified in 2017. The identified lands are sufficient for ongoing constructions. | Land plots for construction have been identified in 2017. The identified lands are sufficient for ongoing constructions. | Land plots for construction have been identified in 2017. The identified lands are sufficient for ongoing constructions.
| 2.1.1.10. Revision of IDP accomodation criteria. Procedures, living standarts and other legal acts related to this issue. | The number of updated/adopted legal acts. | Minimum once in a year | The ministerial Decree N320 on Rules of providing accommodation to IDPs was amended in January 5, 2018. According to the amendment, the threshold of amount to fund purchase of IDP apartment was raised. | The ministerial Decree N320 Rules of providing accommodation to IDPs was amended in April 12, 2018 and June 4 2018. | Respective amendments to regulations have been made due to governmental restructuring
| 2.1.2.2. Purchasing individual houses and apartments, and transferring them into IDP property, including joint funding projects, according to the Guiding Principles, Criteria and Procedures Governing the Process of Durable Housing Allocation adopted by the Ministerial Legal Act. | Number of purchased houses/apartments; Number of transferred/registered houses/apartments to IDPs; Number of IDPs that were accommodated with adequate housing as a result of the project. | 1000 apartments | 120 apartments were purchased for the amount of 2,481,200 GEL | 103 apartments were purchased for the amount of 2,212,200 GEL | 205 apartments were purchased for the amount of 4,382,900 GEL
| 2.1.2.3. Transferring state owned living units, where IDPs lawfully live into IDP property. | Number of living units transferred into IDP property | 1500 transferred apartments | Governmental Decree was adopted for 333 families (Governmental Decree #420, adopted on February 16, 2018). Request for 345 families was sent to the Property Management Agency. 409 families registered living spaces into property. | New Governmental Decree was adopted and 370 families registered living spaces into property. | New Governmental Decree was adopted and 163 families registered living spaces into property
| 2.1.2.4. Purchasing privately owned buildings/apartments that are lawfully occupied by the IDPs and transferring them into IDP ownership | Number of Purchased apartments; Number of transferred apartmetns. | 50 apartments | 17 apartments have been purchased in 3 buildings | 29 apartments have been purchased in 1 buildings | 19 apartments have been purchased in 3 buildings
| 2.1.2.5. Building apartment buildings or individual houses according to operating standards, and transferring them into IDP property | Number of built apartment buildings/housees; Number of apartments transferred to IDP property. | 1024 apartments | 40 apartments have been transferred to IDPs in Vasiani settlement | 262 apartments have been transferred to IDPs in Gori and Zugdidi | 10 apartments have been transferred to IDPs in Gori
| 2.1.2.6. Buying of apartments for IDPs in the apartment buildings (block) and transferring into their property | Number of purchased apartments; Number of transferred apartments. | 300 apartments | 40 apartments have been transferred to IDPs living in Tbilisi | 77 apartments have been transferred to IDPs living in Tbilisi | 68 apartments have been transferred to IDPs living in Tbilisi and Marneuli
| 2.1.2.7. One-off financial assistance to IDP families who bought their only living space through mortgage and they are unable to continue paying. | Number of IDP families, who received financial assistance; Respective amendments have been elaborated and adopted by the Ministerial Legal Act | 90 families | 211 applications have been received during the reporting period, and they will be processed in the second quarter. | It was decided, that 211 applications will be funded | 211 IDP families have received financial assistance
2.1.2.8. In order to implement, respective amendments will be elaborated and adopted by the Ministerial Legal Act
| 2.1.2.9. Accommodating in DHS those IDPs, who live lawfully in the places which are dangerous for their life or health, having increased risk to collapse and/or unfit for living, and closing of the such buildings. | Number of IDPs who received DHS; Number of collapsing or unfit for living buildings; Number of buildings evaluated by an expert | 300 families; 18 closed buildings; 50 evaluated buildings. | 40 families have been relocated from CCC into newly built buildings; 3 CCC and/or building not suitable for habitation, have been closed | 155 families have been relocated from CCC; 14 CCC/buildings not suitable for living, have been closed | 67 families have been relocated from CCC; 2 CCC/buildings not suitable for living, have been closed
2.1.3. Durable Housing Solution supporting activities | 2.1.3.1. In order to improve IDP living conditions, funding condominium cooperatives of apartment buildings, that have been transferred into IDP property, together with municipalities | Number of funded condominium cooperatives | 150 condominium cooperative | 29 buildings (1823) families have been funded | 9 buildings (548 families) have been funded | 30 buildings (1906 families) have been funded
| 2..1.3.2. Transferring of common spaces into property of condominium cooperatives | Number of spaces transferred into property of condominium cooperatives | 25 spaces | During reporting period, there were not any spaces in common use that have been transferred into property of condominium cooperatives | During reporting period, there were not any spaces in common use that have been transferred into property of condominium cooperatives | During reporting period, there were not any spaces in common use that have been transferred into property of condominium cooperatives
| Receiving applications of IDPs on lost immovable property that are located on thhe occupied territories as a result of 2008 Russian agression | Number of identified properties; Number of declared properties | 8000 declarations | Preparatory measures have been taken, in order to find necessary resources | Project is underway, and an electronic module has been set up | Project is underway, and in addition to receiving declarations related to properties located on the occupied territories in 2008, digitalization of existing declarations is also underway
2.2. objective: improving social-economic condition of IDPs
2.2.1. Streamlining IDP allowance into unified state system | 2.2.1.1. Adapting IDP allowance to their needs | IDP allowance is differentiated according to their social-economic situation | Implementation of the reform | Meetings with various stakeholders took place. In order to ensure involvement of IDPs in the process, a communication strategy and Action Plan have been elaborated. Necessary statistical data have been updated. | Necessity to modify the existing assistance model was discussed with IDPs during meetings throughout the country | Processing the data and information received from IDPs and various stakeholders, is underway.
| 2.2.1.2. Involving IDP in state social insurance programs | Number of IDPs participating in state programs | Monthly | At the end of I quarter, 30,541 IDPs were beneficiary of the Targeted Social Assistance. | At the end of the II quarter, 30,673 IDPs were beneficiary of the Targeted Social Assistance. | At the end of the III quarter, 29,467 IDPs were beneficiary of the Targeted Social Assistance.
| 2.2.1.3. Providing IDPs, in urgent/particular needs, with one-off monetary assistance according to elaborated standards | Criteria of IDPs in extreme/particular needs, are elaborated and used; Number of IDPs which received assistance; Elaboration of criteria | 5000 families/persons | One-off financial assistance was provided to 721 IDPs | One-off financial assistance was provided to 2094 IDPs | One-off financial assistance was provided to 2657 IDPs
| 2.2.1.4. In urgent situations, temporary accommodation of IDPs, according to the Guiding Principles, Criteria and Procedures Governing the Process of Durable Housing Allocation | Number of families who received assistance for the purpose of renting apartment | 2000 families | 468 families have been provided with rent subsidy | 328 families have been provided with rent subsidy | 334 families have been provided with rent subsidy
2.2.2. Addressing access to the livelihoods and economic integration needs of IDPs | 2.2.2.1. Implementation of the IDP Livelihood Strategy Action Plan | IDP Livelihood Strategy and Action Plan are being implemented; IDP Reports are available | Regularly | Once the new 2018-2019 Action Plan has been adopted, the respective activities have been implemented. | Activities foreseen in the Action Plan are ongoing. Quarterly reports are available. | Activities foreseen in the Action Plan are ongoing. Quarterly reports are available.
2.3. Objective: increasing awareness of IDPs
2.3.1. Raising awareness and knowledge/understanding of the IDPs and other interested parties, on their rights and services available for them, eligibility/criteria, providing them with an access to the legal consultations, also promotion of their involvement in the Action Plan. | 2.3.1.1. Implementation of the Communication Strategy and Action Plan of the Ministry | Activities foreseen in the Communication Strategy and Action Plan are being implemented | Regularly | Activities foreseen in the Strategy are being implemented | Activities foreseen in the Strategy are being implemented | Activities foreseen in the Strategy are being implemented
| 2.3.1.2. Providing non-governmental organizations, municipalities and media with information related to IDP issues and their solutions | Number of meetings, round tables between the Ministry and partner/non-governmental organizations with the purpose of sharing information | Regularly | During the reporting period, meetings took place with the representatives of NGOs. Meetings with the representatives of media, NGO, and municipalities have bene planned. | During the reporting period, meetings took place with representatives of NGOs. Representatives of the ministry took part in televised talk shows. | During the reporting period, meetings took place with representatives of partner NGOs.
| 2.3.1.3. Supporting IDP involvement in the elaboration, implementation and revision of the Action Plan. Conducting group meeting with IDPs and participatory assessments. Examining implementation of the Strategy and preparing propositions | Annual evaluation of IDP involvement: - IDP voices are heard; - IDPs consulted on decisions that affect them; - The actions of the Government and other stakeholders are informed by the views of IDPs. | Regularly | Ministry representatives took part in a participatory assessment organized by the partner organization/ IDPs have been surveyed about ongoing IDP programs. IDP satisfaction level has been assessed during a study. | Meeting took place with IDPs in Zugdidi, Tskaltubo, Kutaisi, Marneuli and Gori. Activities foreseen in the Action Plan have been discussed. Feedbacks from IDPs have been received, and they also filled out questionnaires. | IDP survey results have been processed, and they are being taken into consideration during elaborating the new IDP Action Plan. Representatives of NGOs and various line ministries are involved in the process.
| 2.3.1.4. Informing IDPs about gender issues according to Gender Equality Strategy and Action Plan of the Ministry | Number of implemented activities on gender issues | Minimum two activities in a year | Preparatory measures have been taken to carry out information meetings with IDPs | A training session with IDPs is planned | A partner organization has been contacted in order to jointly carry out the project