## Slide 1: DRG transition plan for Georgia Seminar for piloting hospitals Triin Habicht WHO consultant 11 September, 2018

## Slide 2: Conclusions based on analytical report - 1
SSA’s invoicing data is suitable for introducing DRGs, setting tariff and development of monitoring and reporting system
Key preconditions fulfilled:
  skilled and motivated team
  classifications
  good quality electronic data

## Slide 3: Conclusions based on analytical report - 2
Need for a transition period to assure technical and organizational preparedness of SSA and providers for introducing a DRG system, e.g.
    update the primary classification systems (ICD-10, NCSP)
    provide training on how to use of primary classifications
    develop coding guidelines
    develop a method to set tariffs
    allow providers and the SSA to adapt to the new system

## Slide 4: Steps following the analytical report – 1
Decisions by the Ministry:
  to move to a DRG system and to
  selection of the NordDRG grouper
  duration and phases of the transition period
The roadmap for DRG implementation was developed by end of 2017

## Slide 5: Steps following the analytical report – 2
Internal DRG Working Group was established in 2017 defines key people responsible for implementation
  Core competences: IT, clinical, analytics
  Define their roles in SSA and MOLHSA
  Assure that they have part of their working time dedicated to the DRG implementation
Establishment of the DRG Steering Committee to engage stakeholders is under discussion

## Slide 6: DRG transition phases
1st phase: SSA preparedness
2nd phase: start with minimum 2 big providers to test IT system, to analyze data quality, give feedback to providers, assess implementation risks
3rd phase: phase out to all providers
4th phase: “shadow funding”, preparations and simulations for actual reimbursement based on DRGs

## Slide 7: Core areas for implementation plan
DRG grouper adaption
Transition strategy
IT system preparedness
Data quality
Revision of regulation
Cost weight, base rate and tariff calculation
Reimbursement policy
Monitoring and reporting system
Capacity building
Communication