SCHEDULE 3 - INDICATIVE POLICY MATRIX

The Policy Matrix may be subject to amendments and changes based on the discussions held between AFD and the Borrower.

| Social Welfare Matrix |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Objectives | Responsible Government Entity | Prior action(s) 2018 | Trigger action(s) 2019 | Trigger action(s) 2020 |  | Results (indicators, baseline, target) | Scope of TA |
| Pillar 2. To ensure affordable and quality healthcare and promotion of healthy lifestyle |  |  |  |  |  |  |  |
| Improve effectiveness and efficiency of universal healthcare and other programs | MoLHSA | In the view of improving the effectiveness and efficiency of universal health care, the government has commissioned an external survey to identity groups of population that are not adequately covered and the main gaps of the existing health care system (e.g. geographical disparities, access to drugs and services, increasing costs, challenge in payment mechanisms, diverse quality of treatment, etc.) | Based on the evaluation, the government will elaborate strategic purchasing mechanisms (develop principles of contracting for purchasing services, continue selective contracting ) in order to improve the effectiveness and efficiency of universal healthcare and other related health programs |  | Proposed strategic purchasing mechanisms are piloted and actions are taken to improve the effectiveness and efficiency of universal healthcare, with a particular attention to quality of care and cost containment methods By June 2020 - New tarification on cardio surgery and emergency services is implemented - New contracting mechanism of primary health care services is started By December 2020 - Draft of health care system development strategy and action plan are developed - Payment mechanisms (ratification) on Neurosurgery, ophthalmology and otorhinolaryngology services is implemented. - Preparatory work on DRG implementation process is continued in order to start piloting in 2021 and national wide implementation in 2022 | OOP on drugs: - Baseline (2016): 64% - Target (2021): 58% General government expenditure on health as percentage of current health expenditures (GGHE-D as percentage of CHE) - Baseline (2016): 38% - Target (2020): 40% | - effectiveness and efficiency of universal healthcare - quality of care - cost containment mechanisms |
| Strengthen the Mental Health Services |  | The government has commissioned a study, technically supported by WHO, to analyse current mental health services and patient rights protection mechanisms, with respect to international best practices and standards. The study also proposes recommendations on how to improve the current model and provide better services to the population. | Pioneer initiatives are implemented in line with the promotion of deinstitutionalization and the development of community based services (aligned with the national strategy of mental health adopted in 2014 by the Decree of Government of Georgia N762). Elaborated monitoring mechanisms for protection of Human rights is mental health institutions (public and private) |  | The Government of Georgia has prepared a mental health legislation according to EU legislation (the proposed legislation has been validated by GoG/Minister ) By June 2020, draft amendments will be elaborated By December 2020, the draft law will be finalized and validated by the government | Budget dedicated to mental illnesses - Baseline (2017): 16,000,000 GEL - Target (2020): increase 20% Ensuring continuity of time-keeping outpatient services after hospitalization - Baseline (2017): 37% - Target (2020): 50% | - EU mental health care and legislation |
| Support the COVID-19 Emergency Response and Health Systems Preparedness |  |  |  |  | Emergency COVID-19 Response: The national health system is able to provide immediate support to enhance disease detection capacities through increasing surveillance capacities, provision of technical expertise, strengthening laboratory and diagnostic systems to ensure prompt case finding and local containment. Health Care Strengthening: The national health system strengthens essential health care service delivery to provide the best care possible for affected population. | Target 7 (number) of public and private laboratories able to detect Covid-19 infected population by PCR method Target 3732 of beds capacities dedicated to Covid-response 967) of intensive care unit beds dedicated to severe cases |  |