Report of Action Plan 2019 for Implementation of the State Strategy for Livelihood of IDPs

| # Chapter 1: GOVERNANCE |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| ## 1. Coordination, management and monitoring mechanism |  |  |  |  |  |  |  |
| a) Steering Committee (LIMC) |  |  |  |  |  |  |  |
| Policy outcomes | Activity | Indicator | Term of implementation | I quarter of 2019 | II quarter of 2019 | III quarter of 2019 | IV quarter of 2019 |
| Strategic management and monitoring of implementation of the Action Plan | The Steering Committee (SC) monitors and guides the implementation of the LAP | 2 meetings annually | 2019: II, IV quarters | TEG meeting took place, which examined new housing projects | No meeting took place | TEG meetings took place, as well as with representatives of IDP initiative groups, which discussed IDP housing and social assistance issues | Meeting is being planned in the first part of 2020 |
| b) Revision of the Action Plan |  |  |  |  |  |  |  |
| Policy outcomes | Activity | Indicator | Term of implementation | I quarter of 2019 | II quarter of 2019 | III quarter of 2019 | IV quarter of 2019 |
| Revision of the Action Plan if needed | Revision the Action Plan with the involvement of stakeholders | Minimum 1 meeting annually with stakeholders | 2019: II, IV quarters | No amendments were made | No amendments were made | No amendments were made | 2020-2021 draft Action Plan was elaborated |
| c) Information and Management Systems |  |  |  |  |  |  |  |
| Policy outcomes | Activity | Indicator | Term of implementation | I quarter of 2019 | II quarter of 2019 | III quarter of 2019 | IV quarter of 2019 |
| Effective functioning of institutional database on livelihood programs | 1. Availability on the webpage of the information about livelihood program providers and livelihood programs | Database is accessible on the Livelihood LEPL website | 2019: II, IV quarters | Information on livelihood programs is available on the Agency's website | Information on livelihood programs is available on the Agency's website | Information on livelihood programs is available on the Agency's website | Information on livelihood programs is available on the Agency's website |
|  | 2. Identify information needs for programming and targeting livelihood interventions | Research plan is developed on the basis of the Geostat survey Identified research studies completed | 2019: IV quarter: Identified research studies completed | Studies have been identified and been planned in order to elaborate livelihood programs for IDPs | IDPs have been surveyed on the phone | Data of the survey have been processed | Findings of the study was used in elaborating 2020-2021 Action Plan. Focus group discussions with IDPs took place |
|  | 3. Analysis of the results of Geostat surveys | Research results are processed according to the following variables: education, agriculture, access to land, livelihood / employment | 2019: III quarter | Data have been processed in order to implement IDP assistance projects | Data have been processed in order to implement IDP assistance projects | Geostat data was used in preparing survey report | Statistical data was used in elaborating the Action Plan |
| ## 2. Communication |  |  |  |  |  |  |  |
| a) Information Campaigns |  |  |  |  |  |  |  |
| Policy outcomes | Activity | Indicator | Term of implementation | I quarter of 2019 | II quarter of 2019 | III quarter of 2019 | IV quarter of 2019 |
| Providing timely and efficient information about IDPs on livelihood programs | 1. Information meetings on livelihood programs by the employees of the LEPL, in the framework of field visits in the IDP settlements. | At least 10 information campaign | IV quarter 2019 | 5 information campaigns have been carried out on livelihood programs | 4 information campaigns have been carried out about livelihood programs | 3 information meetings took place during reporting period | 2 information meetings took place during reporting period. In total, 14 information campaign was carried out in 2019. |
|  | 2. Informing IDPs on livelihood programs by volunteers through facetoface meetings. | 6,000 information materials are desiminated in the year; 40% of informed IDPs are women. | IV quarter 2019 | Activity is planned in the following quarter | Activiy is planned in the followind quarter | Applications of volunteer candidatures have been received. Trainings of volunteers and IDPs are planned in the following quarter | Volunteers informed 4910 families (14,460 IDPs) during the door-to-door information campaign (among the informed IDPs 53.3% were women). |
|  | 3. Livelihood forums across the country, where in one spance are represented livelihood implementing agencies and organization. | At least 3 livelihoods forum in different regions of Georgia | 2019: II, IV quarters | To be implemented in the III and IV quarter | To be implemented in the III and IV quarter | Livlihoods forum was organized in Tskaltubo | Livelihoods forums was organized in Gori and Zugdidi. In total, 3 livelihood forums took place in 2019. |
|  | 4. Within the framework of the information campaign, send SMS messages to IDPs about livelihood programs | 3,000,000 short text messages are sent to IDPs on different programs of livelihood in the year | 2019: II, IV quarters | During the reporting period 244,933 short message was sent on State livelihood programs. | During the reporting period 766,219 short messages were sent out on State livelihood programs. | During the reporting period 211,144 short message were sent on State livelihood programs. | During the reporting period 71,744 short message were sent on State livelihood programs. In 2019, 1,294,040 message were sent in total. |
|  | 5. Equip the Agency regional offices with appropriate information dissemination tools | 2000 information dissemination materials prepared and distributed to MRA regional offices and Services providers. | 2019: I – IV quarters | The Agency has announced a tender to print information materials | The Agency territorial representations were provided with the necessary information materials | The Agency territorial representations were provided with the necessary information materials | The Agency territorial representations were provided with the necessary information materials |
| b) Inter-Sectoral-Referral System |  |  |  |  |  |  |  |
| Policy outcomes | Activity | Indicator | Term of implementation | I quarter of 2019 | II quarter of 2019 | III quarter of 2019 | IV quarter of 2019 |
| Effective functioning of the Ministry services in the direction of livelihood programs | Training of the Ministry hotline and Recception Center, as well as municipalities and other representatives of service suppliers on livelihood programs. | Employees of the hotline and IDP Reception Center are trained on livelihood programs; Representatives of municipalities and service providers are trained, at least once a year | 2019: I quarter | Information on livelihood program was provided to for the staff of the Hotline and Reception Center | Information on livelihood program was provided to for the staff of the Hotline and Reception Center | Information on livelihood program was provided to for the staff of the Hotline and Reception Center | The staff of the newly created IDPs, Livelihoods, and Ecomigrants Agency, including personnel of the Reception Center, have been trained about livelihood programs |
| # Chapter 2: Promoting employment |  |  |  |  |  |  |  |
| ## 1. Employment through state programs |  |  |  |  |  |  |  |
| a) Access to Job/Career counselling |  |  |  |  |  |  |  |
| Policy outcomes | Activity | Indicator | Term of implementation | I quarter of 2019 | II quarter of 2019 | III quarter of 2019 | IV quarter of 2019 |
| IDP employment rate growth | 1. Professional training and retraining of job seekers and promoting IDP engagement into qualification raising state programs | 7% of the places of the SSA “Job- seeker’s Training and Requalification State Programme” to start in 2016 are provided to IDP | 2019: I – IV quarters | During the reporting period, 455 persons attended the course, and among them 32 were IDPs (out of which, 22 were women). | During the reporting period, 884 persons attended the course, and among them 58 were IDPs (out of which, 41 were women). | During the reporting period, 1420 persons enrolled the course, and among them 98 were IDPs (out of which, 66 were women). 1254 persons graduated successfully, and among them 79 were IDPs, out of which 59 are women. During the second stage, 1037 persons enrolled and among them 108 were IDPs, out of which 71 were women. The course is ongoing. | In 2019, 2674 persons have been enrolled in the program, among them 200 (7.4%) are IDPs. Women make up 68.5%. |
|  | 2. Encourage the involvement of IDPs in the state program of employment promotion services development | 10% of people engaged in the state program of employment promotion services development are IDPs | 2019: II, III quarters | To be implemented in the second quarter | 1420 persons enrolled in the training and requalification program, and among them 98 were IDPs (out of which 66 were women). The training process is ongoing. | As of the end of third quarter, 1311 job seekers took part in the group consultation trainings. Among them 96 are IDPs, out of which 67 are women. | As of December 10, 2019, 1711 job seekers took part in the group consultation trainings. Among them 123 are IDPs (7.1%), out of which 83 (67.4%) are women. |
| ## 2. Self-employment promotion program |  |  |  |  |  |  |  |
| Access to trade tools |  |  |  |  |  |  |  |
| Policy outcomes | Activity | Indicator | Term of implementation | I quarter of 2019 | II quarter of 2019 | III quarter of 2019 | IV quarter of 2019 |
| Promotion of self-employment of IDPs | Promotion of self-employment of IDPs, who graduated specific professional courses by purchasing working tools | About 50 funded beneficiaries, 40% of which are women; In cooperation with the Ministry of Education and Science of Georgia and other partner organizations, self-employed professions are identified | 2019: II quarter | 101 self-employment professions have been identified. Admission of applications started in March | Applicants to be funded have been selected | 50 applicants are waiting to be funded | 50 applicants are waiting to be funded |
| # Chapter 3: EDUCATION AND TRAINING |  |  |  |  |  |  |  |
| ## 1. VET programs |  |  |  |  |  |  |  |
| a) Access to VET |  |  |  |  |  |  |  |
| Policy outcomes | Activity | Indicator | Term of implementation | I quarter of 2019 | II quarter of 2019 | III quarter of 2019 | IV quarter of 2019 |
| Professional training of IDPs and improved opportunities for employment in the labor market | Facilitate the enrolment of IDPs in VET | Among the enrolled at least 6% are IDPs | 2019: I – IV quarters | The registration period will start in April 8 | During the spring admission period, 2617 IDPs have been enrolled (among them 128 are women) | Statistics of enrolled IDPs are being verified | In the state VET programs, 5105 persons have been enrolled and among them 479 are IDPs (9.3%) |
| Support of IDP students enrolled in vocational education institutions | Provide transportation of all IDP students who have been enrolled in the state professional educational institutions | Number of all IDPs with need who have been enrolled in state professional educational institutions; 40% of funded IDPs are women | 2019: I – IV quarters | Statistics of the Spring admission session will be available in the second quarter | As of June, applications are being accepted | In total 177 beneficiaries have been enrolled. Among them 96 are women and 81 men. | In 2019, 222 beneficiaries have benefited of transportation subsidies. Among them 113 are women (50.9%) and 109 men. |
| # Chapter 4: ACCESS TO LIVELIHOOD PROGRAMS |  |  |  |  |  |  |  |
| ## IDPs’ involvement in livelihood programs |  |  |  |  |  |  |  |
| a) Access to State Funded Agro-programmes |  |  |  |  |  |  |  |
| Policy outcomes | Activity | Indicator | Term of implementation | I quarter of 2019 | II quarter of 2019 | III quarter of 2019 | IV quarter of 2019 |
| Increase participation of IDPs in the state program of agro-insurance | Promoting the involvement of IDPs in the Agricultural Project Management Agency Agro Insurance Program | At least 300 IDPs are involved in the State Program of Agro Insurance | 2019: I – IV quarters | As of March 22, 2019, agro-insurance program has not been approved | Memorandum on cooperation is going to be concluded | Memorandum on cooperation is going to be concluded | As the memorandum was not concluded, the Agency does not have information |
| b) Livelihood grants |  |  |  |  |  |  |  |
| Policy outcomes | Activity | Indicator | Term of implementation | I quarter of 2019 | II quarter of 2019 | III quarter of 2019 | IV quarter of 2019 |
| 1. Supporting integration of accommodated IDPs | Implementing of a grant program for IDPs which have been accommodated under “Purchasing housings for IDPs program” (Rural Housing) | Needs of IDPs have been identified, respective grant program has been elaborated and 10 IDPs households have been funded | 2019: I – IV quarters | Study was conducted in order to identify needs. 4 priority directions have been identified | Program hass been elaborated and applications are being admitted (deadline is June 20) | 14 IDPs to be funded have been selected | 14 projects have been selected. 1 beneficiary was selected and 13 IDPs are waiting to be funded |
| 2. Support agricultural initiatives of IDPs | Funding of agricultural initiatives of IDPs | Funding of agricultural initiatives of IDPs | 2019: I – IV quarters | Applications are being admitted as of March | Applications have been processed and beneficiaries selected | 15 IDPs have been selected to be funded | 15 IDPs have been funded and greenhouses built |
| c) Creating cooperatives by IDPs |  |  |  |  |  |  |  |
| Policy outcomes | Activity | Indicator | Term of implementation | I quarter of 2019 | II quarter of 2019 | III quarter of 2019 | IV quarter of 2019 |
| Increase of awareness of IDPs about creation of programs and cooperatives and joining Cooperatives planned by LEPL "Agricultural Cooperative Development Agency" (ACDA) | Informing IDPs on creating and joining cooperative, as well as on procedures to join the programs developed by LEPL "Agricultural Cooperative Development Agency" | At least two information campaigns annually | 2019: I – IV quarters | Information campaigns will be conducted in the second and third quarters | Information campaign was not conducted during the reporting period and it is being planned in July | One joint event was organized (the ACDA was dissolved and it was absorbed by the Agriculture Development Agency) | Representatives of ACDA participated in 3 events organized by the Agency |
| d) Business Start-up Support Project |  |  |  |  |  |  |  |
| Policy outcomes | Activity | Indicator | Term of implementation | I quarter of 2019 | II quarter of 2019 | III quarter of 2019 | IV quarter of 2019 |
| Increase participation of IDPs in MSE program | Promoting the involvement of IDPs in the SME state program | 4% of those who are involved in micro and small entrepreneurship program are IDPs | 2019: I – IV quarters | Data will be available in the II quarter | The program was not implemented yet | The program was not implemented yet | It is not known when the program will relaunch |