## ActionPlan
Sector Priorities | The resettlement of IDPs and eco-migrants is ensured and they independently maintain and improve decent housing and livelihoods. They are integrated into host communities, have access to financial, social and material resources, and their livelihoods are enhanced and durable. IDPs and eco-migrants are not dependent on state aid and their self-sufficiency has been achieved.
Goal 1: | The purpose of the livelihood strategy is to improve the social and economic situation of IDPs and eco-migrants |  |  |  |  | Connection with Sustainable Development Goals (SDGs) |  |  |  | 11
Impact indicator: 1.1 | Raising the standard of living - reduced number of IDPs and eco-migrants involved in the Targeted Social Assistance program | [5 empty] | Basic | Target |  | Source of confirmation
[8 empty] | Intermediate | Final
[6 empty] | Year | 2019 | 2022 | 2025 | Data from the LEPL Social Service Agency;
[6 empty] | Indicator | 10.7% | 10% | 9%
Objective 1.1: | Establishing a coordination mechanism for effective management of the livelihoods sector
Outcome Indicator 1.1.1: | A coordination mechanism has been set up and the reports are avaliable | [5 empty] | Basic | Target |  | Source of confirmation
[8 empty] | Intermediate | Final
[6 empty] | Year | 2019 | 2022 | 2025 | IDPs, Eco-Migrants and Livelihoods Agency LEPL
[6 empty] | Indicator | 0 | 6 | 12
Risk: | Reorganization of the Ministry structure; Frequent changes of representatives of the Steering Committee member organizations
Activity |  | Activity Output Indicator |  | Source of confirmation | Responsible Authority | Partner agency | Implementation time | Budget | Source of Financing
[9 empty] | State budget |  | Donor |  | Deficiency
[9 empty] | Amount | Code | Amount | Organization
1.1.1 | Managing and monitoring activities of the Action Plan by the Steering Committee; Developing recommendations as needed | 1.1.1.1 | Steering Committee is convened at least twice a year | Steering Committee minutes | IDPs, Eco-Migrants and Livelihoods Agency LEPL | Ministry of Internally Displaced Persons from the Occupied Territories, Labor, Health and Social Affairs of Georgia | 4th Quarter 2021 | Administrative resource | 0 | 27 01 07 | 0 | N/A | 0
1.1.2 | Training of the Ministry's Hotline and IDP Reception Center, as well as municipalities and representatives of livelihood programs providers | 1.1.2.1 | Employees of the Hotline and IDP reception center are trained / trained in livelihood programs; Representatives of the municipality and service providers are trained at least once a year | Report of the IDPs, Eco-Migrants and Livelihoods Agency LEPL | IDPs, Eco-Migrants and Livelihoods Agency LEPL | Ministry of Internally Displaced Persons from the Occupied Territories, Labor, Health and Social Affairs of Georgia; Local municipalities | 4th Quarter 2021 | Administrative resource | 0 | 27 01 07 | 0 | N/A | 0
Objective 1.2: | Increasing the competitiveness of beneficiaries in the labor market
Outcome Indicator 1.2.1: | Increase in the number and percentage of IDPs and eco-migrants enrolled in state vocational programs; | [5 empty] | Basic | Target |  | Source of confirmation
[8 empty] | Intermediate | Final
[6 empty] | Year | 2019 | 2022 | 2025 | LEPL - Education Management Information System Data; LEPL - State Employment Promotion Agency Data; the IDPs, Eco-Migrants and Livelihoods Agency LEPL
[6 empty] | Indicator | 7.5% | 8.5% | 10%
Risk: | Low interest rates for vocational education courses;
Activity |  | Activity Output Indicator |  | Source of confirmation | Responsible Authority | Partner agency | Implementation time | Budget | Source of Financing
[9 empty] | State budget |  | Donor |  | Deficiency
[9 empty] | Amount | Code | Amount | Organization
1.2.1 | Involving IDPs and Eco-Migrants in State Program for Job Seekers Professional Retraining and Qualification | 1.2.1.1 | Number of IDPs and Eco-Migrants Involved in State Program for Job Seekers Professional Retraining and Qualification | LEPL - State Employment Promotion Agency Data | LEPL - State Employment Promotion Agency | IDPs, Eco-Migrants and Livelihoods Agency LEPL | 4th Quarter 2021 | 2020: 152 000; 2021: 152 000 | 304 000 | 27 06 05 | 0 | N/A | 0
1.2.2 | Incolving the IDPs and eco-migrants in the State Program for the Development of Employment Support Services | 1.2.2.1 | The number of IDPs and eco-migrants involved in the State Program for Development of Employment Support Services | LEPL - State Employment Promotion Agency Data | LEPL - State Employment Promotion Agency | IDPs, Eco-Migrants and Livelihoods Agency LEPL | 4th Quarter 2021 | 2020: 14 200; 2021: 14 200 | 28 400 | 27 06 05 | 0 | N/A | 0
1.2.3 | Facilitate enrollment of IDPs and eco-migrants in state vocational education institutions | 1.2.3.1 | Number of Enrolled in Public Vocational Education Institutions | Data from LEPL -Education Management Information System | Ministry of Education, Science, Culture and Sport of Georgia | IDPs, Eco-Migrants and Livelihoods Agency LEPL | 4th Quarter 2021 | 2020: 660 000; 2021: 660 000; | 1 320 000 | 27 06 05 | 0 | N/A | 0
1.2.4 | Providing transportation of all IDP and Eco-Migrant students in need who are studying atstate vocational education institutions. | 1.2.4.1 | Number of all IDPs and eco-migrants in need of being financed for studying at state vocational education institutions; 40% of the sponsored are women | Report of the IDPs, Eco-Migrants and Livelihoods Agency LEPL | IDPs, Eco-Migrants and Livelihoods Agency LEPL | N/A | 4th Quarter 2021 | 2020: 100 000; 2021: 100 000 | 200 000 | 27 06 05 | 0 | N/A | 0
Objective 1.3: | Implementation of IDPs and Eco-Migrant Income Generation Programs
Outcome Indicator 1.3.1: | Increase in the total number of IDP and eco-migrant families involved in programs implemented by the Agency | [5 empty] | Basic | Target |  | Source of confirmation
[8 empty] | Intermediate | Final
[6 empty] | Year | 2019 | 2022 | 2025 | Reports of LEPL IDPs, Eco-Migrants and Livelihoods Agency
[6 empty] | Indicator | 250 | 20% | 30%
Risk: | Funding cuts; Ineffective management of funded projects;
Activity |  | Activity Output Indicator |  | Source of confirmation | Responsible Authority | Partner agency | Implementation time | Budget | Source of Financing
[9 empty] | State budget |  | Donor |  | Deficiency
[9 empty] | Amount | Code | Amount | Organization
1.3.1 | Promoting self-employment for IDPs and eco-migrants by providing them with working tools | 1.3.1.1 | Up to 50 beneficiaries are funded, among them 40% are female; By cooperation with the Ministry of Education, Science, Culture and Sport of Georgia and other partner organizations Self-employment professions with high demand are identified | IDPs, Eco-Migrants and Livelihoods Agency LEPL | IDPs, Eco-Migrants and Livelihoods Agency LEPL | Ministry of Education, Science, Culture and Sport of Georgia, LEPL State Employment Promotion Agency, LEPL Education Management Information System | 4th Quarter 2021 | 2020: 100 000; 2021: 100 000 | 200 000 | 27 06 05 | 0 | N/A | 0
1.3.2 | Promoting of the integration process of IDPs and eco-migrants by providing grants | 1.3.2.1 | Needs are identified; A need-based grant program has been developed; 10 households are funded | IDPs, Eco-Migrants and Livelihoods Agency LEPL | IDPs, Eco-Migrants and Livelihoods Agency LEPL | N/A | 4th Quarter 2021 | 2020: 100 000; 2021: 100 000; | 200 000 | 27 06 05 | 0 | N/A | 0
1.3.3 | Support of IDPs and Eco-migrants by providing greenhouse program | 1.3.3.1 | Mnimum 15 projects are funded | IDPs, Eco-Migrants and Livelihoods Agency LEPL | IDPs, Eco-Migrants and Livelihoods Agency LEPL | USAID Project Zrda Georgia | 4th Quarter 2021 | 2020: 200 000; 2021: 200 000 | 200 000 | 27 06 05 | 200 000 | USAID/ZRDA | 0
1.3.4 | Increasing access to livelihoods for vulnerable IDPs - a pilot project | 1.3.4.1 | Mnimum 200 Initiative are funded | IDPs, Eco-Migrants and Livelihoods Agency LEPL | IDPs, Eco-Migrants and Livelihoods Agency LEPL | LEPL Social Service Agency | 4th Quarter 2020 | 2020: 500 000 | 500 000 | 27 06 05 | 0 | N/A | 0
Objective 1.4: | Awareness of IDPs and eco-migrants on various livelihood programs, promoting their involvement in these programs;
Task Outcome Indicator 1.4.1: | Increasing the number of IDPs and eco-migrants involved in state programs; | [5 empty] | Basic | Target |  | Source of confirmation
[8 empty] | Intermediate | Final
[6 empty] | Year | 2019 | 2020 | 2025 | The data of LEPL "Enterprise Georgia" and NNLP Agricultural and Rural Development Agency and the report of the LEPL Agency for IDPs, Eco-Migrants and Livelihoods Assistance
[6 empty] | Indicator | 2504 | 7% | 15%
Risk: | The lack of applicants for participation in government programs, low quality of projects sand low competitiveness; lack of material or technical resources required for co-financing.
Activity |  | Activity Output Indicator |  | Source of confirmation | Responsible Authority | Partner agency | Implementation time | Budget | Source of Financing
[9 empty] | State budget |  | Donor |  | Deficiency
[9 empty] | Amount | Code | Amount | Organization
1.4.1 | Holding information meetings on livelihood programs into IDPs and eco-migrant settlements | 1.4.1.1 | Minimum 10 informational meetings annually | Report of the IDPs, Eco-Migrants and Livelihoods Agency LEPL | IDPs, Eco-Migrants and Livelihoods Agency LEPL | N/A | 4th Quarter 2021 | Administrative resource | 0 | 27 01 07 | 0 | N/A | 0
1.4.2 | Informing IDPs and Eco-Migrants about door-to-door livelihood programs, by volunteers | 1.4.2.1 | 6,000 informational materials are distributed annually; At least 40% of the informed population is female | Report of the IDPs, Eco-Migrants and Livelihoods Agency LEPL | IDPs, Eco-Migrants and Livelihoods Agency LEPL | USAID/ZRDA | 4th Quarter 2021 | 2020: 25000; 2021: 25000 | 0 | N/A | 50000 | USAID/ZRDA | 0
1.4.3 | Livelihood Forums throughout Georgia | 1.4.3.1 | At least 3 livelihood forums in different regions of Georgia | Report of the IDPs, Eco-Migrants and Livelihoods Agency LEPL | IDPs, Eco-Migrants and Livelihoods Agency LEPL | Partner organizations specified in the strategy and action plan | 4th Quarter 2021 | Administrative resource | 0 | 27 01 07 | 0 | N/A | 0
1.4.4 | Sending short text messages (SMS) to IDPs and eco-migrants about livelihood programs within the information campaign | 1.4.4.1 | 3,000,000 short text messages annually | Report of the IDPs, Eco-Migrants and Livelihoods Agency LEPL | IDPs, Eco-Migrants and Livelihoods Agency LEPL | N/A | 4th Quarter 2021 | 2020: 8000; 2021: 8000 | 16000 | 27 06 05 | 0 | N/A | 0
1.4.5 | Provide authorized agency staff with the tools needed to disseminate information | 1.4.5.1 | About 2,000 copies of livelihood information materials are transmitted to the territorial divisions of the Agency | Report of the IDPs, Eco-Migrants and Livelihoods Agency LEPL | IDPs, Eco-Migrants and Livelihoods Agency LEPL | N/A | 4th Quarter 2021 | Administrative resource | 0 | 27 01 07 | 0 | N/A | 0
1.4.6 | Information on livelihood programs is published on the Ministry's website | 1.4.6.1 | Information is avaiable at the web page of MoIPDsLHSA | Web Page Of MoIDPsLHSA | MoIDPsLHSA | IDPs, Eco-Migrants and Livelihoods Agency LEPL | 4th Quarter 2021 | Administrative resource | 0 | 27 01 01 | 0 | N/A | 0
1.4.7 | Production and distribution of informational material on livelihood programs | 1.4.7.1 | 10 000 booklets are produced and distributed annually | Report of the IDPs, Eco-Migrants and Livelihoods Agency LEPL | IDPs, Eco-Migrants and Livelihoods Agency LEPL | N/A | 4th Quarter 2021 | 2020: 15 000; 2021: 15 000 | 30 000 | 27 06 03 01 | 0 | N/A | 0
1.4.8 | Encouraging Involvement of IDPs and eco-migrants in the programs of LEPL Enterprise Georgia | 1.4.8.1 | Number of IDPs and Eco-Migrants Involved in the Program | LEPL "Enterprise Georgia" | IDPs, Eco-Migrants and Livelihoods Agency LEPL | N/A | 4th Quarter 2021 | 2020: 510 000; 2021: 510 000; | 1 020 000 | 24 07 02 | 0 | N/A | 0
1.4.9 | Involving IDPs and Eco-Migrants in State Program of NNLP Agricultural and Rural Development Agency | 1.4.9.1 | Number of IDPs and Eco-Migrants Involved in Agency's Program | NNLP Agricultural and Rural Development Agency | IDPs, Eco-Migrants and Livelihoods Agency LEPL | N/A | 4th Quarter 2021 | 2020: 480 750; 2021: 480 750; | 961 500 | 31 05 | 0 | N/A | 0