## General
Georgia Emergency COVID-19 Response
Thresholds for Procurement of Goods, Works and Non-Consulting services:
Procurement Method | Procurement | Prior Review
1 - Goods
ICB: | >US$1 Mil | As indicated in respective sheets for Goods, Works and Consulting Services
NCB: | ≤ US$1 Mil
SH: | <US$100 K
DC: | None
2- Works
ICB | >US$10 Mil
NCB | ≤ US$10 Mil
SH | <US$200 K
DC
Thresholds for Selection and Employment of Consultants:
Procurement Method | Procurement | Prior Review
3 - Consulting Services Firms |  | As indicated in respective sheets for Goods, Works and Consulting Services
QCBS
QBS
FBS
LCS
CQS | ≤US$300,000
DC
4 - Consulting Services Individuals
IC
DC

## Procurement plan for COVID19
| Date | 2020-04-27
# | Description | Implementation Entity | Type | Procurement Approach | PQ | PR | Packs | Cost (Estimate GEL) | Cost (Estimate USD) | IBRD Financing | Actual Cost (GEL) | Issue of REOI | Issue of BD/ITQ/RFP | Bid/Proposal Opening | Eval done - NO issued | Contract Signed | Contract Start | Contract Finished | Note
Component 1:EMERGENCY COVID19 RESPONSe
Goods/Works/Non-Consultin Services
1 | PPE | MoH | Goods | Open/Shopping/Direct | N | Y | Single or Multiple | 32044000 | 10000000 | 4500000
2 | Procurement of Equipment for hospitals | MoH | Goods | Open/Shopping/Direct | N | Y | Single or Multiple | 54314580 | 16950000 | 7627500
3 | Procurement of Motorcycle for Ambulance first responders | MoH | Goods | Open/Shopping/Direct | N | N | Single or Multiple | 4806600 | 1500000 | 675000
3 | Procurement of fully Equipped Ambulances | MoH | Goods | Open/Shopping/Direct | N | Y | Single or Multiple | 8011000 | 2500000 | 1125000
4 | Procurement of Diagnostic Supplies | MoH | Goods | Open/Shopping/Direct | N | Y | Single or Multiple | 16022000 | 5000000 | 2250000
5 | Procurement of Equipment for Emergency Control Center | MoH | Goods | Open/Shopping/Direct | N | Y | Single or Multiple | 8972320 | 2800000 | 1260000
| Procurement of ICT goods for public health facilities | MoH | Goods | Open/Shopping/Direct | N | N | Single or Multiple | 961320 | 300000 | 135000
| Procurement of Moto Vehicles for Infectios Control Monitoring Center | MoH | Goods | Open/Shopping/Direct | N | N | Single or Multiple | 961320 | 300000 | 135000
6 | Minor repairs of public health facilities | MoH | CW | Shopping/Direct | N | N | Single or Multiple | 6408800 | 2000000 | 900000
[7 empty] | Sub-Total USD of Goods, Works and Non-Consulting Services |  | 41350000 | 18607500
Consulting Services
8 | Training and Assistance | MoH | CS | QBS | N | N | 1 | 961320 | 300000 | 135000
9 | Procurement Consultant | MoH | CS | IC | N | N | 1 | 169192.32 | 52800 | 23760
10 | Project Manager | MoH | CS | IC | N | N | 1 | 230716.8 | 72000 | 32400
11 | Financial Consultant | MoH | CS | IC | N | N | 1 | 192264 | 60000 | 27000
12 | Enviromental Specialist | MoH | CS | IC | N | N | 1 | 123048.96 | 38400 | 17280
13 | Social Specialist | MoH | CS | IC | N | N | 1 | 123048.96 | 38400 | 17280
14 | Operating Costs * | MoH | N/A | N/A | N/A | N/A | N/A | 97734200 | 30500000 | 13725000
[6 empty] | Sub-Total (USD) of Consulting services |  |  | 31061600 | 13977720
[6 empty] | Total of Component |  |  | 72411600 | 32585220
*Operating costs refer to Quarantine and mild case management in non-medical settings; Global budget to public and private facilities to ensure preparedness;Costs of case management and treatment
Price Convertion Rate, Date and Source:
| USD/GEL: | 3.2044
| 2020-04-27 | https://www.nbg.gov.ge/index.php?m=2&lng=eng