- Project Overview

| Country: | Georgia |
| --- | --- |
| Full Project Name: | Georgia Emergency COVID-19 Response Project |
| Total Finance ($): | 180 M |
| Project Number: | P173911 |
| Summary of Project Development Objectives | To prevent, detect and respond to the threat posed by the COVID-19 pandemic in Georgia |

- The Project will have three components as outlined below:

- Component 1 - Emergency COVID-19 Response

  - Sub-component 1.1: Case Detection and Confirmation

  - Sub-component 1.2: Health System Strengthening for Case Management

- Component 2 - Enabling health measures to contain the COVID-19 outbreak through temporary income support for poor households and vulnerable individuals

- Sub-component 2.1: Scale up of the Targeted Social Assistance program for extreme poor households

- Sub-component 2.2: Temporary cash transfers for informal workers

- Sub-component 2.3: Temporary unemployment benefits for formal workers

- Component 3 - Project Management and Monitoring

Component 1: Emergency COVID-19 Response (EUR 66.35 million, US$ 71.85 million equivalent)

Sub-component 1.1: Case Detection and Confirmation (EUR 16.1 million, US$ 17.7 million equivalent)

- This sub-component will help to strengthen public health laboratories and epidemiological capacity for early detection and confirmation of cases.  It will support the strengthening of diseases surveillance systems and the capacity of the selected public health laboratories to confirm cases by financing medical supplies and equipment. It will include personal protection equipment (PPE) and hygiene materials, COVID-19 test kits, laboratory reagents, polymerase chain reaction equipment, and specimen transport kits.

Sub-component 1.2: Health System Strengthening for Case Management (EUR 50.0 million, US$ 54.1 million equivalent)

- The Project aims to contribute to the strengthening of health system preparedness, improve the quality of medical care provided to COVID-19 patients, and minimize the risks for health personnel and patients. These objectives will be achieved through the procurement of essential medical goods, rapid conditioning of designated public health facilities, the financing of COVID-19 related treatment costs. This sub-component will also provide equipment, drugs and medical supplies. The Project will finance PPE and hygiene materials for health workers and other staff who may be at high risk of exposure to COVID-19, including individuals working in quarantine facilities and border posts. In addition, this sub-component will support capacity improvements in designated public facilities. This sub-component will finance intensive care units (ICUs) and beds in the designated public hospitals, as well as minor repairs, such as remodeling ICUs and increasing the availability of isolation rooms, and other capacity needs to improve service delivery for COVID-19. The Project will also finance case management and treatment of COVID-19 patients in public and private facilities by supporting the reimbursement of claims by the SSA for COVID-19 related services. To ensure sustainability, the Project will support consulting services to revise the payment methods for health care services, including tariff setting for COVID-19.  It will also finance compensation in the form of a global budget to public and private facilities for idle capacity and ensure standby readiness to provide COVID-19 care. This sub-component will support case management for non-severe cases in non-medical settings (e.g. hotels temporarily rented for this purpose) for those individuals who cannot self-isolate at home and will finance ambulances to support urgent transportation of patients across the hospital network to designated reference facilities.

Component 2.  Enabling health measures to contain the COVID-19 outbreak through temporary income support for poor households and vulnerable individuals (EUR 99.6 million, US$ 107.85 million equivalent)

Subcomponent 2.1:  Scale up of the Targeted Social Assistance (TSA) program for extreme poor households

- This sub-component will finance the natural expansion of the TSA program to support households negatively impacted by the health measures adopted to contain the outbreak and the resulting economic downturn. By design, the program targets extreme poor households based on a Proxy Means Test scoring formula which is partially shock responsive. It is expected that about 35,000 new households will apply and be eligible to the TSA program in a scenario where 20 percent of formal wage workers will lose their jobs and 20 percent will probably lose their jobs, and where wage workers staying in their jobs will see their labor income reduce by 20 percent. The benefit amounts remain the same. The implementation of this sub-component will rely on the existing mechanism by which the SSA will determine and verify the eligibility and contract with Liberty Bank to make payments. Application procedures and all payments are already cash-free and the implementation processes have been already simplified and adapted to minimize the risk of contagion in compliance with the regulations on social distancing.

Subcomponent 2.2: Temporary cash transfers to informal workers

- This sub-component will support the introduction of a temporary (cash) benefit targeted to vulnerable households dependent on informal and occasional work. The temporary benefit will be on-demand and provide a flat benefit of about GEL 150 (around US$48) per month per family for a period up to 6 months, in addition to the social assistance benefits they receive (child benefits and other small benefits administered at the municipal level). Informal workers in vulnerable households will be identified through the existing scoring formula used to target the TSA (and other social benefits) but based on higher eligibility threshold than the one currently used for the TSA (households normally ineligible to receive TSA). Households without formal sector employees and which declare to have no source of income, including no TSA nor social pensions, will be eligible. Simulations on HIES 2018 show that about 120,000 households are expected to apply (assuming a take up of 80 percent of eligible households in a scenario where 20 percent of wage employment is loss). The eligibility determination and verification processed will be carried out by SSA in accordance with the existing system and in compliance with regulations on social distancing.

Subcomponent 2.3: Temporary unemployment benefits for formal workers

- This sub-component will support the introduction of a temporary unemployment assistance benefit for formal wage workers who lose their jobs because of containment measures taken due to COVID-19 and who do not receive TSA nor the temporary cash benefit. A flat benefit of 200 GEL (US$63) per month will be provided to private sector workers who are laid off as a result of COVID-related restrictions and economic lockdown of non-essential businesses. The benefit amount is commensurate to the cost of living: the monthly social pension is set at 220 GEL (US$70) per person per month (old age pension) as a comparison. The duration of the unemployment assistance benefit is for a period up to 6 months. Assuming that 20% of wage workers are laid off (conservative estimates), between 50,000 and 130,000 individuals are expected to be dismissed and eligible for this benefit. The Revenue Service will compile a list of laid off workers based on companies’ declarations and on the cross-verification with the payroll income database. The Revenue Service will submit the list of unemployed and their bank account details to SSA who will further verify eligibility (eligible unemployed individuals must not be beneficiaries of the TSA and the temporary cash benefit).  SSA will proceed with the payment to respective bank accounts as provided by the Revenue Service.

- Funds allocated to Component 2 of the Project would not be sufficient to address all needs of vulnerable individuals in the country. As such, the Government will use its own resources and potentially funds from other development partners.

Component 3.  Project management and monitoring.

- This component will support project implementation for the overall administration of the Project, including procurement, financial management, as well as regular monitoring and reporting on project implementation progress (and required fiduciary assessments). A Project Implementation Unit (PIU) will be established within 30 days of Project Effectiveness in MoIDPLHSA relying on existing government structures and staffing At least four consultants will be hired to cover the PIU key functions given the overwhelming scope of response to COVID-19 and the urgency of actions to be taken by all parties. These include consultants for procurement, financial management, social and environmental safeguard, and a consultant to support the overall coordination, monitoring, and evaluation of the Project activities. Other consultants can also be hired as needed during the Project implementation. As such, the MoIDPLHSA will be responsible for the overall administration, fiduciary functions, environmental and social aspects, communication and outreach for both components 1 and 2.

- Overview of Country, Borrower and Marketplace

- Operational Context

- Governance aspects

- Georgia is an independent democratic republic. Two regions, namely Abkhazia and Samachablo are conflict-affected and occupied by Russian armed forces. No particular limitations in terms of legislation or use of State-Owned Enterprises (SOEs) are envisaged. The government of Georgia has initiated an effective multi-sectoral response to COVID-19. In January 2020, the government adopted Decree #164 on “Approval of Measures to Prevent the Possible Spread of the New Coronavirus in Georgia and Approval of an Emergency Response Plan for Cases Caused by COVID-19” (amended on April 1, 2020, with the GoG Decree #625) and established a national multi-sectoral committee. Under the Operational Response Plan, approved by the government of Georgia, each line ministry and government entity has clearly defined roles and responsibilities at every stage of COVID-19 response. From January 31, 2020, Georgia adopted the case definition of the COVID-19 and intensified epidemiological surveillance throughout the country. On March 2, 2020, the Government Reserve Fund allocated 1 million GEL ($358,358) to the MoIDPLHSA to respond to the challenge of the new coronavirus in Georgia. The government has also scaled up its communication efforts by establishing a unified hotline and an informational platform StopCov.ge - a web site available in five languages with all necessary governmental links and related information.

- To ensure the preparedness of the health system to address the pandemic, the government has identified a list of designated public and private facilities to provide treatment to COVID-19 patients. In addition, seven public laboratories have been designated for testing. Given that more than 85 percent of health facilities in Georgia are privately owned, the government has decided to leverage the capacity of the private facilities, while at the same time strengthening the public facilities to fill the critical gaps. All diagnostic, laboratory, and treatment costs of the COVID-19 patients are covered by the government of Georgia. In addition, following the approach adopted in other countries, such as Germany, the government has introduced a temporary  transfer to public and private hospitals in the form of a global budget to ensure standby readiness and compensate facilities for losses in revenue due to COVID-19.

- Economic Aspects

- Georgia is an upper-middle-income country with Gross Domestic Product (GDP) per capita of US$4,785 in 2019, and a population of approximately 3.7 million people (World Development Indicators, 2018). Over the past decade, Georgia’s economy has grown robustly at an average annual rate of 4.5 percent. This was despite numerous shocks, including the global financial crisis of 2007-08, the conflict with the Russian Federation in 2008, and the drop-in commodity prices since 2014 that has impacted key trading partners

- Prior to the global outbreak of COVID-19, Georgia’s recent economic reforms have favored economic growth and poverty reduction. The outlook for the Georgian economy was positive, and GDP growth was expected 4.3 percent in 2020. The Georgian economy picked up pace in the first half of 2019, was growing at 4.9 percent and accelerating to 5.1 percent by the end of the year. While domestic demand was supported by higher consumption, investment contracted due to the completion of several infrastructure projects and declining foreign direct investment (FDI). Net exports improved considerably, reflecting slowing imports and the increased re-export of used cars and copper ores. On the supply side, all sectors, except mining and electricity production, positively contributed to growth. Coupled with a system of targeted social transfers, economic growth helped to nearly halve the poverty rate from 37.4 percent in 2007 to 20.01 percent the national poverty line in 2018, and to improve the income and living conditions of the bottom 40 percent of the population. The unemployment rate declined to 12 percent in 2019, helping to lower the poverty rate (measured at the national poverty line) to 20.1 percent.  However, the country now faces significant domestic and external downside risks, and the growth projections are now challenged by the larger global downturn arising from the COVID-19. Georgia’s GDP growth is expected to decline, and risks to economic growth include greater than expected sluggishness in trading partners’ economies, weaker than expected domestic demand, slower growth in tourism revenues, and tighter liquidity in global financial markets, including the impact of lockdowns and the shuttering of businesses due to COVID-19 in the country. In addition, the drop in domestic economic activity, foreign investment and exports, combined with the regional and global economic slowdown have led depreciation of the Georgian Lari by 13 percent in March 2020 (IMF), and rising prices of consumer prices, and making pressures on foreign exchange reserves in the country.

- Sustainability Aspects

- Nowadays, environmental policies are receiving increasing attention from Georgian policy and decision makers, recognizing that sustainable development is about a profound change of policies that drive systemic transformation of production, consumption, and behavioral patterns. The list of the country’s environmental challenges is long. Current policies and instruments lack the rigor to effectively reduce pressures on natural assets and protect public health from poor environmental quality.

- Georgia’s environmental legal framework is well developed and covers key aspects of environmental protection legislation. In conjunction with the provisions of the EU-Georgia Association Agreement, Georgia has started to harmonize the legal basis concerning environmental management and, most important, to integrate environmental concerns into other policy areas.

- Georgia made some significant progress forward in creating an enabling environment for gender equality in the past years. In 2015, the Government of Georgia responded favorably to the introduction of the Sustainable Development Goals (SDGs), which replaced the MDGs. The government showed a high level of support to the prioritization of all 17 of the SDGs, including SDG 5 on gender equality, and the development of nationally relevant indicators is currently under way.

- Technological Aspects

- There are no limitations in terms of technological aspects identified. Majority of local population has a free access to the internet, television and radio. Therefore, there is no limitation in terms of information transfer if necessary.

Key Conclusions

- The effects of pandemic include social and economic instability. Therefore, the current operational context imposes a substantial risk to the project implementation.

- Client Capability and PIU Assessment

- Project Implementing Agency

- The designated implementing agency for the project is the Ministry of Internally Displaced Persons from the Occupied Territories, Labour, Health and Social Affairs of Georgia (MoIDPLHSA) which is formally accountable for the health of the population, oversight of the health system, the quality of health services, as well as for managing the social protection and employment programs of the Government of Georgia. Ministry acts within the framework of the legislation of Georgia, including Decree #473 of the Government of Georgia of September 14, 2018 on “Approval Statute of the Ministry of Internally Displaced Persons from the Occupied Territories, Labour, Health and Social Affairs of Georgia”. MoIDPLHSA will be responsible for the fiduciary and technical aspects as well as the operational implementation, in close coordination with the Ministry of Finance (MoF). The Social Service Agency (SSA) is a state subordinated institution under the administration of MoIDPLHSA, and responsible for purchasing publicly financed health services in the country, implementing social services and programs and for supporting the most vulnerable social groups. SSA serves approximately 2.5 million Georgian citizens (about 60 percent of the population).

- The project will be implemented using the existing institutions and capacities, which are deemed adequate to assure a smooth operation and oversight. The implementation arrangements for Component 1 will involve MoIDPLHSA within its healthcare function, together with SSA and in coordination with the National Center for Disease Control (NCDC) and the State Procurement Agency. The MoIDPLHSA will conduct centralized procurement of lab equipment, test kits, equipment, and supplies for the hospitals. As a purchasing agency, the SSA will reimburse the providers for COVID-19 related services. Activities conducted by the MoIDPLHSA will be coordinated when relevant with the NCDC, which is at the forefront of epidemic response. Component 2 will be implemented by the MoIDPLHSA within its social protection function and through the SSA, together with the Revenue Service of the MoF. Specifically, the SSA will be in charge of (i) determining and verifying the eligibility to the TSA, emergency benefit and temporary unemployment benefits and (ii) making the payments to beneficiaries of Component 2 through their personal bank accounts (unemployment benefits) and through special accounts at the Liberty Bank and connected bank cards (for TSA and emergency benefits).  No payment is envisioned to be cash-based.

- A Project Implementation Unit (PIU) will be established within 30 days of the Project effectiveness comprising existing staff from MoIDPLHSA, SSA, MoF, State Procurement Agency, Treasury, and the NCDC and consultants hired under the project. The PIU will be led and coordinated by MoIDPLHSA.  Several key consultant positions will be needed given the overwhelming scope of response to COVID-19 and the urgency of actions. These include consultants for procurement, financial management, social and environmental safeguard, and a consultant to support the overall coordination, monitoring, and evaluation of the Project activities. Other consultants can also be hired as needed during the Project implementation. The PIU, to be established under MoIDPLHSA, will need to be adequately be staffed for Financial Managment and procurement functions including accounting, reporting, budgeting and funds flow, internal controls as well as social and environmental aspects.

- Monitoring and evaluation activities will be the responsibility of the PIU. The PIU will: (a) monitor project implementation; (b) collect data and information related to the PDO and intermediate indicators; and (c) prepare progress reports by coordinating with related departments at the MoIDPLHSA, MoF, and other implementing agencies.  Progress reports will cover compliance with the planned project activities, the updated Procurement Plan, progress on the achievement of indicators as defined in the Results Framework; and progress on the Environmental and Social Framework (ESF). The PIU will submit these reports to the World Bank on a semi-annual basis. The roles and responsibilities, as well as the methodology, will be described in the Project Operations Manual (POM).

- Need for hands-on support

- Procurement is regulated in accordance with the Law of Georgia on “State Procurement”. Procurement unit is responsible for carrying out state procurement procedures. Based on the necessities defined by the structural unites, the procurement unit prepares plan of procurement, which is approved by the order of the Minister and submitted to the State Procurement Agency through electronic system.

- Currently, Covid-19 procurement project management team comprises: Head of Administration; Head of procurement unit; Full time staff members of the procurement unit – 2; Head of International relations Division; Full time staff members of the legal department – 2. Some representatives are familiar with the Bank’s procurement guidelines and regulations. None of the existing staff members have the experience of the World Bank funded projects operations.

- Reporting procedures are conducting according to the Law of Georgia on “State Procurement” through electronic system.

- While the implementing agency has vast experience in conducting the procurement of required goods and services under the national procurement regulations, it lacks the recent track of the procurement under Bank financed projects. Therefore, for the procurement of initial needs will be provided by the Bank to the Borrower during the Project cycle as follow: (i) provision of draft technical requirements and specifications, as requested by the MoIDPLHSA; (ii) assistance to the implementing agency in the drafting of procurement documents; and (iii) advices on evaluation procedures, including participation as observers during contract negotiations, only on clarifying matters related to the Bank procurement regulations .

- Bank Facilitated Procurement (BFP). Under HEIS, the Bank, at the Borrower’s request, may also provide proactive assistance in accessing existing supply chains through BFP, meaning: (i) conduct extensive market engagement and survey to identify available stock of the agreed list of critical medical consumables and equipment needed in the quantities specified; (ii) assist the implementing agency in negotiating prices, delivery terms, and other contract conditions with identified suppliers; (iii) draft final award letters and/or contracts adapted to specific market conditions, on a fit-for-purpose basis and ensuring consistency with the Bank’s procurement framework; (iv) provide additional hands-on support in contracting to outsource logistics.

- Contract management capability and capacity

- Contract Management Unit. The MoIDPLHSA does not have a special unit to conduct management of the contract. Considering the thematic topics of the procured goods/service, the relevant person is designated for this purpose.

- Inspection of the delivery of the goods. Each agreement on state procurement includes supervision of the agreement by the relevant person or team defined by the procurer in advance in order to supervise (delivery terms, quantity and quality of the goods) implementation of the agreement.

- Supervision of the works. During procurement of the construction works, there are relevant employees in the Ministry who are involved in planning, implementation and supervision of the construction works. After completion of the project, in some cases, independent expert’s conclusion could be used.

- Monitoring. Procurement monitoring is conducted by the State Procurement Agency.

- Payment. In general, the payment is done on time, based on the terms of the contract.

- Complaints management and dispute resolution systems

- Disputes are settled by the Dispute Resolution Council established according to the Law of Georgia on “State Procurement” and through addressing the Georgian courts

- The MoILHSA and Project Management Unit shall follow the procurement related complaints strictly in accordance with WB Regulations for Borrowers.

Key Conclusions

- The MoILHSA does not have an experience in procurement under World Bank financed projects. While the ministry will receive an extensive technical support from the Bank, it is essential to provide intensive training for the procurement team. It is recommended that the dedicated Procurement consultant will be hired for the project.

- Market Analysis

- Market sector dynamics

- Before outbreak of COVID-19, the MoIDPLHSA was procuring part of the essential inventories for the public hospitals using the consolidated tenders under the national procurement regulations. Other goods and services were purchased by open and/or national tenders governed by national procurement laws using e-Procurement system of Georgia. Shortly after outbreak, the local suppliers experienced the shortage of the critical supplies, which automatically annulled the existing framework agreements.

- Local Market Capacity. Considering pandemic situation, the demand on personal protective equipment is very high and local market only satisfies minimum requirements (around 5 percent). Therefore, the replenishment of the stock is carried out by imported goods.

- Market analysis. To the extent possible, the MoIDPLHSA conducts the market analysis exercises.

- This section provides an overview of details of a market analysis summary for the supply of critical medical products required to respond the COVID-19 outbreak. The analysis identifies the main market segments, the major suppliers for each segment and supply chain risks. Informed by this analysis, procurement options and actions are outlined to help address market supply issues.

- The supply of medical products required to respond to the COVID-19 outbreak is consolidated in five separate market segments:

    - Personnel Protective Equipment

    - Medical Device Equipment

    - Medical Consumables

    - Chemicals

    - Vehicles

As well as manufacturers who act as suppliers, there are also distributors, procurement agents and wholesalers who operate in this market. This analysis focuses on the OEM (Original Equipment Manufacturers).

- Personnel Protective Equipment (PPE) -Many products in this category are impacted by surging demand from the public for protective equipment e.g. masks. Normally, the majority buyers in this market are in the health sector, rather than the general public. Therefore, this supply market is not geared-up to respond to mass demand from the general public. Generally, across the market, backlogs on orders are running at 4 to 6 months. Production of PPE items have been significantly shifted from the U.S. to Mexico who are experiencing 100% utilization rates (capacity is full), and this is expected to continue for the next 4 to 6 months. Distribution is a through a mixture of supply from manufacturers and wholesalers. The U.S. represents the largest buyer, followed by Europe. Both these geographies have domestic manufacturers, but the marketplace is dominated by Chinese suppliers (due to lower cost of production).  Other geographies have rapidly expanding local manufacturing base offering low-cost product lines.

- Surgical Masks - China is the main producer of surgical marks, accounting for approximately 50% of worldwide capacity. Other supplier countries include India, Thailand, Malaysia, Japan, Mexico, US, Korea and several European countries.

- Surgical Gloves - The distribution of manufacturing capacity for surgical gloves is more diversified than surgical masks. Though China does produce significant amounts of gloves, the greatest production capacities are in Malaysia, Thailand and Indonesia. Distribution is a through a mixture of supply from manufacturers and wholesalers.

- Surgical Gowns - Disposable surgical gowns are preferred more than reusable surgical gowns. The disposable surgical gowns segment dominates the market with approximately 68-70% of market share. This is a highly globalized market with main manufacture in Europe, Asia and North America.

- Scrubs - North America and Europe are the largest medical protective clothing markets due to major market players being domiciled in these regions.

- Goggles -The market is highly consolidated due to the presence of a few global suppliers and numerous local manufacturers in different parts of the world. Key manufacturers in this market are based in the USA and Europe, with some local manufacturers present mostly in Asia Pacific region.

- Respirator Fit Testers - The USA holds significant market share from the sales of respirator fit testers due to stringent government regulations and standards enforced by United States Department of Labor.

- Oxygen Concentrator -The USA is the leading supplier of Oxygen Concentrators followed by Europe then China. Oxygen concentrators can be complex to buy and subject to many local regulations.

- Tubes (Lab Equipment / Laboratory Glassware) -The market is dominated by a number of key suppliers mainly from North America and Europe due to the bigger demand of downstream applications. In 2017, these two regions took 62.04% of global laboratory glassware consumption in total.

- Portable Ventilators -The global ventilators market is highly consolidated with 5 companies accounting for more than half of the global market share. Portable ventilators can be complex to buy and subject to many local regulations.

- Pulse Oximeter - North America is the largest supplier of pulse oximeters, with a production market share nearly 46% in 2015. Asia is the second largest supplier of pulse oximeters with a production market share nearly 33% in 2015.

- Laryngoscope - The market is highly fragmented with many suppliers, with Europe and North America suppliers considered the leading companies supplying Laryngoscopy technology.

- Ultrasound -The global Ultrasound market is dominated by 5 main suppliers that represent 90% of market supply. Ultrasound can be complex to buy and subject to many local regulations.

- Bio-Hazard Bags - North America is the largest bio-hazard bag market at present followed by Europe. This is mainly due to stringent government regulations regarding waste disposal, an aging population and large amounts of bio-hazard waste generated.

- Chlorine - The USA, Canada, Brazil, Japan, China and India are major producers of chlorine.

- Ambulances -The USA is the largest supplier of emergency ambulances, with a production market share of approximately 30%, while Europe is the second largest supplier with a market share of approximately 25%. Ambulances are complex to buy and subject to many local regulations.

## Price Analysis

- Price benchmark information is in the public domain for a number of medical products as detailed below. This type of information can be used to support Borrowers in establishing how much of premium is being charged due to increased demand.

| PPE Product | Price Median ($) |
| --- | --- |
| Exam Gloves | $6.55 |
| Isolation Gowns | $49.50 |
| Respirators | $10.52 |
| Shoe Covers | $49.50 |
| Surgical Masks | $55.00 |

## Use of Alternatives

- VENTILATOR - Many COVID-19 patients will require mechanical ventilation. However, a shortage of ventilators has led to an increased risk of patient fatality.

- Use of Consumer-Grade Obstructive Sleep Apnea Devices May Supplement Ventilator Supply during Shortage [ECRI Exclusive Hazard Report] - Devices intended for obstructive sleep apnea (OSA) may be used as a temporary measure for low-acuity patients while intensive care, non-invasive ventilators, and devices cleared for other preferred therapies are in a critical shortage.

- MECHANICAL VENTILATOR - Anesthesia Units Can Be Repurposed to Provide Ventilatory Support for Critically Ill Patients, as Long as Precautions Are Taken [ECRI Exclusive Special Report]

- N95 RESPIRATOR - Use expired N95 FFRs for healthcare delivery. FDA approved the use of expired FFRs on March 28, 2020; Use imported, non NIOSH-approved FFRs that are similar to NIOSH-approved FFRs:

Current Strategies and Market Outreach

- For the time being, the MoIDPLHSA experiences major challenges in obtaining the vital inventory to fight the pandemic. The ministry exercises on-the-spot procurement of the supplies, as well as utilizes an external mediator support, such as diplomatic corps of Georgia.

- Currently, Government of Georgia develops incentives for industry to rapidly respond to the supply needs and start and/or increase production, such as face masks, gowns, protection suits, disinfectant solutions etc.  Newly established state enterprise plans to hand over the Ministry 4 million face masks.

- WHO has provided the Ministry with the following PPE: Examination gloves M, L, XL – 10000 pair, Protective goggles – 200 unit, Face masks FFP2 – 200 unit, Surgical mask – 10 000 unit, Gown L, XL – 1400 unit.

- Financial

- The proposed Project would be implemented over a period of two years for a total Bank financing of US$80 million of which US$17.6 million equivalent from the FTCF IDA allocation, US$62.4 million equivalent from IBRD, and US$100 million from the AIIB.

- Indicative Activity and Equipment List with Tentative Costing for Component 1

| Component 1: Emergency COVID 19 response | Year 1 | Year 2 | Total |
| --- | --- | --- | --- |
| Sub-Component 1: Case Confirmation |  |  |  |
| Equipment, diagnostic supplies (including lab reagents and testing kits), infection protection and transportation for laboratories | $17,850,000 |  | $17,850,000 |
| Total Subcomponent Cost (US$) | $17,850,000 |  | $17,850,000 |
| Sub-Component 2: Health System Strengthening |  |  |  |
| Infection protection supplies | $13,000,000 |  | $13,000,000 |
| Equipment and minor repairs to strengthen public facilities | $10,000,000 |  | $10,000,000 |
| Quarantine and mild case management in non-medical settings | $7,000,000 |  | $7,000,000 |
| Global budget to public and private facilities to ensure preparedness | $7,000,000 |  | $7,000,000 |
| Costs of case management and treatment | $16,000,000 | $500,000 | $16,500,000 |
| Consulting services (e.g. training, payment systems) | $500,000 |  | $500,000 |
| Total Subcomponent Cost (US$) | $53,500,000 | $500,000 | $54,000,000 |
| Total Component Cost (US$) | $71,350,000 | $500,000 | $71,850,000 |

- Procurement Options

- World Bank Procurement interventions should focus at three levels:

- Support Borrowers by providing access to contractual arrangements that ensure supply, are easy to use, efficient and effective and provide cost protection.

- Engage with industry through Pandemic Supply Chain Network to develop solutions that prioritize supply based on need, remove barriers to distribution, effectively manage cost and facilitate increased production.

- More detailed market analysis, supported by industry experts/specialist medical sector consultants, to identify other sources of supply, benchmark data on prices and monitor trends.

- Based on the above, possible procurement related options are:

- Lever existing arrangements with UN partners e.g. UNOPS. Accessed through UNFPA -This has the benefit of fast implementation, low integrity concerns, good VFM and low risk. It provides access to UNOPs stocks and levers their existing supply frameworks and purchasing influence/power.

- Borrower’s use their own existing supply arrangements with health providers (in effect the Bank guarantees funding) - It is common for most countries to have existing supply agreements for medical equipment/consumables and stocks held locally. This has the benefit of fast implementation and the Borrower retains full ownership.

- If possible, through Global Pandemic Supply Chain Network (PSCN)/WHO negotiate a Framework arrangement for supplies with main manufacturers/ distributors - The procurement approach should be direct negotiation with main manufacturers/distributors with the greatest capacity/distribution network (see Annex 1). A traditional, open competitive approach or spot buying is discounted due to the emergency situation and supply shortages (suppliers are unlikely to competitively tender when they can sell everything they have/can make directly with minimal costs to them of that sale and higher profit margins). Another option is that another PSCN member agency leads the procurement such as WHO, UN etc.

- Independent Procurement Support and Supply Chain Analysis

Key Conclusions

- Global supply market characterizes with high uncertainty. The market situation is most likely to worsen before starting to improve. The Industry and governments are currently mobilizing to boost supply and put measures in place to stop speculation and stock piling. WHO is working with governments, industry and the PSCN to boost production and secure stock allocations for critically affected and at-risk countries.

- Expediting UN agencies support.

- Procurement Risk Analysis

| Risk Description | Likelihood | Impact | Overall risk | Description of Mitigation | Risk Owner |
| --- | --- | --- | --- | --- | --- |
| Supply Shortages/out of stock | 5 | 5 | 25 | Direct contracting with suppliers who has enough goods based on market analysis. | MoF, MoH |
| Cost Increase | 3 | 4 | 12 | Deep market analysis. | MoF, MoH |
| Potential procurement delays: Experience with the past and on-going projects in the country show frequent procurement delays due to poor procurement planning and lack of appropriate market analysis. | 5 | 5 | 25 | Careful procurement planning based on the market analysis and realistic scheduling; advanced preparation of technical specifications or TORs; close Bank supervision and monitoring, particularly from the country offices. Usage of RFQ method without thresholds limitations, decreasae of the time for bids or quotations submission and usage only post review approach for all packages. | MoF, MoH |
| Manufacturer Shutdowns | 5 | 5 | 25 | Market analysis to determine manufacturers who is still working and based on the virus free territory. | MoF, MoH |
| Inadequate contract management and lower-than-required quality of procured equipment | 5 | 5 | 25 | Contracting team will be created for managing contracts. More emphasis and training on appropriate contract management; regular physical inspections by Bank supervision mission. | MoF, MoH |
| Perceived high level of corruption as measured by Transparency International. Overall procurement environment is unsuitable for effective procurement. | 3 | 5 | 15 | Bank Anticorruption Guidelines will be enforced. Close supervision by the Bank staff. | MoF, MoH |
| Transportation Disruption | 5 | 5 | 25 | Market analysis to determine manufacturers who is still working and based on the virus free territory. Discuss with neighbored countries possibility of transit. | MoF, MoH |
| Sudden exhaustion of the vital inventory | 4 | 5 | 20 | Inventory control mechanism, such as Burn Rate Calculator | MoF/ MoH |

- Procurement Objective

- Secure and obtain vital supplies.

- Ensure that purchased goods, works and services are fit for purpose.

- Keep implementation delays low through appropriately planned and monitored procurement.

- Procure products at competitive market prices.

- Ensure that right quantities of required products, conforming to specified quality levels, are delivered to intended locations in a timely manner.

- Protect legitimate business interests of suppliers, contractors, and consultants with a view to creating and maintaining confidence of the market in the purchaser which is necessary in the long-term interests of the purchaser.

- Ovoid transportation disruption and minimize administrative burdens of supply delivery.

- Recommended Procurement Approach for the Project

- Overall there are few major procurements under this project, with current thinking on procurement summarized below:

- Supply of the PPE to for different end users.

- Procurement of equipment for PHC and/or hospitals.

- Procurement of fully equipped ambulances.

- Procurement of necessary material and technical equipment for case management.

- The Project will support the renovation and equipping of intensive care units (ICUs).

- Minor repair works in boxed chambers.

Recommended Procurement Approach for the Project

- Contract and Estimated Cost: Procurement of PPE  (Goods) - USD 11,900,000

Procurement Approach Options

Option 1 Procurement of goods through open bidding

Option 2 Procurement through UN agency

Option 3 Direct Selection

Option 4 Bank Facilitated Procurement

The urgency of the need should determine the most appropriate approach.

- Contract and Estimated Cost: Procurement of equipment for PHC and/or hospitals (Goods) USD 11,900,000

Procurement Approach Options:

Option 1 Procurement of goods through open bidding

Option 2 Procurement through UN agency

Option 3 Direct Selection

Option 4 Bank Facilitated Procurement

- Contract and Estimated Cost: Procurement of ambulances (Goods) USD 5,400,000

Procurement Approach Options:

Option 1 Procurement of goods through open bidding

Option 2 Procurement through UN agency

Option 3 Direct Selection

Option 4 Bank Facilitated Procurement

- Contract and Estimated Cost: Diagnostic Supplies (Including Lab reagents and testing kits) (Goods) - USD 1,000,000

Procurement Approach

Option 1 Procurement of goods through open bidding

Option 2 Procurement through UN agency

Option 3 Direct Selection

Option 4 Bank Facilitated Procurement

- Contract and Estimated Cost: Equipment for Emergency Control Center (Goods) – USD2,800,000

Procurement Approach

Option 1 Procurement of goods through open bidding

Option 2 Direct Selection

- Contract and Estimated Cost: Minor repairs and remodeling (works) – USD2,000,000

- Identified contracts and estimated cost for retroactive financing:

| Item | Contract | Cost (US$) |
| --- | --- | --- |
| PPE | Multiple | 5,600,000 |
| Hospital Equipment and Transportation | Multiple | 500,000 |
| IT Software and hardware | Multiple | 136,000 |

Preferred arrangement for low value, low risk activities (if applicable)

| Activity | Category | Estimated cost | Procurement arrangement |
| --- | --- | --- | --- |
| Multiple Goods | Goods | 100,000 | RFB, RfQ, DS |
| Project Management | Goods and Consulting services | 300,000 | IC, Competitive selection of individual consultants |
| Training or Assistance | Consulting servicers | 500,000 | QBS, Least Cost |

Summary of PPSD to be inform the Bank’s preparation of the PAD

| Contract Title, Description and Category | Estimated Cost US$ and Risk Rating | Bank Oversight | Procurement Approach/Competition: National International Open Limited Direct | Selection Methods: Pre/Post qualification SPD (RFP/RFB) Competitive Dialouge Framework Agreement E-Reverse auction QCBS/QBS etc. Negotiation BAFO | Evaluation Method: Rated criteria (VfM) Lowest evaluated cost |
| --- | --- | --- | --- | --- | --- |
| PPE (Goods) | 11,900,000 | POST | Open Limited Direct | Single or multiple contracts Post-Qualification, RFB | Lowest evaluated cost |
| Procurement of equipment for PHC and/or hospitals (Goods) | 11,900,000 | POST | Open Limited Direct | Single or multiple contracts Post-Qualification, RFB | Lowest evaluated cost |
| Procurement of fully equipped ambulances (Goods) | 5,400,000 | POST | Open Limited Direct | Single or multiple contracts Post-Qualification, RFB | Lowest evaluated cost |
| Diagnostic Supplies | 1,000,000 | POST | Open Limited Direct | Single or multiple contracts Post-Qualification, RFB | Lowest evaluated cost |
| Equipment for Emergency Control Center (Goods) | 2,800,000 | POST | Open Limited Direct | Single or multiple contracts Post-Qualification, RFB | Lowest evaluated cost |
| Minor repairs and remodeling | 2,000,000 | POST | Open Limited Direct | Single or multiple contracts Post-Qualification, RFB | Lowest evaluated cost |

## Annex

There are a number of providers opening up their platforms to help those in need identify sources of PPE.

scoutbee: https://lnkd.in/gYferRC

Thomas: https://lnkd.in/gbNGkFq (no login required)

Tealbook: https://lnkd.in/gp9b-4N (will send you the list and contacts)

SAP Ariba: https://lnkd.in/gbv5aBU

GEP Worldwide: https://lnkd.in/gpagjWP

Coupa Software: https://lnkd.in/gCEndDd

Bonfire Interactive: https://lnkd.in/gwmS5W8

ConnXus: https://lnkd.in/gZeC5tq

SourceDay: https://lnkd.in/gaT-2gZ

For extensive list of suppliers, CDC website could also be accessed free of charge:

CDC Center of Disease Control and Prevention: https://www.cdc.gov/niosh/

Please note this annex of manufacturers is not exhaustive and is based on agile internet research.

SURGICAL MASKS

Main manufacturers:

Below is a A-Z list of the main manufacturers of surgical mask products identified, with  their Head Office Location, however manufacturing is usually globalized, much of which is in China.

- 3M, St. Paul, MN, USA

- Foss Performance Materials (includes Nexera Medical Inc), Hampton, NH, USA

- Honeywell (includes GlaxoSmithkline, Sperian Respiratory Protection, LLC), Santa Ana, CA, USA.

- Kimberley Clark, Irving, TX, USA

- Makrite, New Taipei, Taiwan

- Prestige Ameritech, Richland Hills, TX, USA

- Shanghai Dasheng, Shanghai, China

- Shanghai Gangkai, Shanghai, China

SURGICAL GLOVES

Main manufacturers:

Below is a A-Z list of the main manufacturers of surgical gloves identified, with their Head Office Location (where found), however manufacturing is usually globalized:

- Anhui Haojie Plastic and Rubber Products Co. Ltd, Anhui, China

- Ansell Healthcare, Melbourne, Australia

- Asma Rubber Products Pvt. Ltd., Kakkanad, Kerala, India

- B. Braun Melsungen AG, Melsungen, Germany

- Cardinal Health, Ohio, USA & Dublin, Ireland

- DACH Schutzbekleidung, Rastaat, Germany

- Globus, Pennsylvania, USA

- Halyard Health, Inc. Georgia, USA

- Hartalega Holdings Bhd, Kuyala Lumpur, Malaysia

- Hutchinson Medical, Massachusetts, USA

- Kanam Latex Industries Pvt. Ltd., Tamil Nadu, India

- Kossan Rubber Industries BHD, Selangor, Malaysia

- Kurian Abraham Private Limited (KAPL), Tamil Nadu, India

- Medline Industries, Northfield, IL, USA

- Molnlycke Health Care AB, Gothenburg, Sweden

- Motex Group, Taipei, Taiwan

- Paul Hartmann AG, Heidenheim, Germany

- Rubberex Corporation, Berhad, Malaysia

- Semperit AG Holding, Vienna, Austria

- Shangdong Yuyuan Latex Gloves, Shangdong, China

- Shijiazhuang Hongray Group, Shijiazhuang, China

- Supermax Corporation, Berhad, Malaysia

- Top Glove Corporation Bhd,  Shah Alam, Malaysia

- Vulkan Medical AS, Hradek na Nisou, Czech Republic

Surgical Gowns

Main Manufacturers:

Below is a A-Z list of the main manufacturers of surgical gowns identified, with their Head Office Location (where found), however manufacturing is usually globalized:

- 3M, St Paul, Minnesota, USA

- 3Teks, Baspinar, Turkey

- Ahlstrom-Munksjo, Helsinki Finland

- Alan Medical, Paris, France

- Azid Bonz GmbH, Herrenberg, Germany

- Berner International GmbH, Elmshorn, Germany

- Cardinal Health, Ohio, USA & Dublin, Ireland

- Cardiva Integral Solutions, Malaga, Spain

- DACH Schutzbekleidung, Rastaat, Germany

- Egypt for Medical Clothes – MEDIC, Cairo, Egypt

- Endochoice, Georgia, USA

- Exact Medical, New York USA & Nieuwkuijk, the Netherlands

- Franz Mensch, Buchloe, Germany

- FULLSTAR NON-WOVEN PRODUCTS, Wuhan, China

- GrupA Medical Products, Izmir, Turkey

- Halyard Health, Georgia, USA

- Hogy Medical, Japan

- Hygeco International Products, Garges-lès-Gonesse, France

- Johnson and Johnson, New Jersey, USA (HQ)

- Landau Uniforms Inc, Mississsippi, USA

- Leboo Healthcare Products Limited, Beijing, China

- Lohmann and Rauscher, Rengsdorf, Germany & Vienna, Austria

- Medline Industries, Illinois, USA

- Molnlycke Health Care, Gothenburg, Sweden

- Neomedic Ltd, Hertfordshire, UK

- Paul Hartmann, Heidenheim, Germany

- Pidegree Medical Technology, Guangzhou, China

- Pluritex, Fidenza, Italy

- PRIMED Medical Products, Edmonton, Canada

- Priontex, Cape Town, Johannesburg, Durban & Port Elizabeth, South Africa

- Rays SpA, Osimo, Italy

- Safetec of America, New York, USA

- SFERAMED Healthcare Lda, Lisbon, Portugal

- Sino-Fan Ltd, Jiangsu, China

- TIDI Products, Wisconsin, USA

- Timo d.o.o., Ajdovščina, Slovenia

- Vogt Medical Vertrieb, Karlsruhe, Germany

- Vygon, Blunsdon St Andrew, UK

- Wujiang Evergreen, Jiangsu, China

SCRUBS

Main Manufacturers:

Below is a A-Z list of the main manufacturers of scrubs identified, with their Head Office Location (where found), however manufacturing is usually globalized:

- 3M, St Paul, Minnesota, USA

- Algrimia Medical. Inc., Hong Kong, China

- Barco Uniforms, California, USA

- Biolene, Buenos Aries, Argentina

- Cardinal Health, Ohio, USA & Dublin, Ireland

- Cardiva Integral Solutions, Malaga, Spain

- Halyard Health, Georgia, USA

- Holtex, Holmfirth, UK

- Landau Uniforms Inc, Mississsippi, USA

- Leboo Healthcare Products Limited, Beijing, China

- Lydias Uniforms, Michigan, USA

- Medica Europe BV, Oss, Netherlands

- Medline Industries, Illinois, USA

- Molnlycke Health Care, Gothenburg, Sweden

- Otix Medical, Hong Kong, China

- Priontex, Cape Town, Johannesburg, Durban & Port Elizabeth, South Africa

- Probody Medical ApS, Haderslev, Denmark

- Rays SpA, Osimo, Italy

- Sino-Fan Ltd, Jiangsu, China

- SMTEK Technology Development LTD, Hong Kong, China

- Steris Healthcare, Ohio, USA

- Thermo Fisher Scientific, Massachusetts, USA

- Tshimbunda Trading (PTY) LTD, Gauteng, South Africa

APRONS

Main Manufacturers:

Below is a A-Z list of the main manufacturers of aprons identified, with their Head Office Location (where found), however manufacturing is usually globalized. This list excludes manufacturers of lead aprons used in radiology:

- Akzenta, Chiasso, Switzerland

- Alexandra, Bristol, UK

- Ascott, Staffordshire, UK

- Azid Bonz GmbH, Herrenberg, Germany

- Berner International GmbH, Elmshorn, Germany

- Body Products, Frechen, Germany

- Connscience LLC, Ohio, USA

- Dastex, Muggenstrum, Germany

- Eloi Podologie, Paris, France

- HPC Healthline, London, UK

- Hygeco International Products, Garges-lès-Gonesse, France

- Neomedic Ltd, Hertfordshire, UK

- Pidegree Medical Technology, Guangzhou, China

- Rays SpA, Osimo, Italy

- Renol, Brussels, Belgium

RESPIRATOR FIT TESTERS

Main Manufacturers:

Below is a A-Z list of the main manufacturers of respirator fit testers identified, with  their Head Office Location (where found), however manufacturing is usually globalized:

- 3M Company, St Paul, Minnesota, USA

- Allegro Industries, Piedmont, South Carolina, USA

- American Airworks, Sophia, West Virgina, USA

- Envirocon Instrumentation, Johannesburg, South Africa

- Honeywell International Inc, Santa Ana, CA, USA.

- Levitt-Safety Ltd, Calgary, Canada

- Moldex Metric Inc. Culver City, California, USA

- Sensidyne, LP, St Petersburg, Florida, USA

- TSI, Occupational Health Dynamics, Shoreview, Minnesota, USA

GOGGLES

Main manufacturers:

Below is a A-Z list of the main manufacturers of goggles identified, with  their Head Office Location (where found), however manufacturing is usually globalized:

- 3M Company, St Paul, Minnesota, USA

- Ansell Ltd, Melbourne, Australia

- BolleSafety, East Sussex, UK

- GF Health Products, Atlanta, Georgia, USA

- Heinz Herenz Medizinalbedarf GmbH, Hamburg, Germany

- Honeywell International Inc, Santa Ana, CA, USA.

- Narang Medical Limited, New Delhi, India

- Palmero Healthcare, Stratford, Connecticut, USA

- TIDI Products, Neenah, Wisconsin, USA

- Uvex Safety Group, Furth, Germany

OXYGEN CONCENTRATOR

Main manufacturers:

Below is a A-Z list of the main manufacturers of medical oxygen concentrators identified, with  their Head Office Location (where found), however manufacturing is usually globalized:

- AVIC Jianghang, Jiangsu, China

- Beijing North Star, Beijing, China

- Chart (Airsep), Amherst, NY, USA & Cleveland, USA

- Drive Medical, NY, USA

- Foshan Kaiya, Guangdong, China

- GCE Group, Malmo, Sweden

- Inogen, CA, USA

- Inova Labs (ResMed), Austin, TX, USA

- Invacare, OH, USA

- Philips Respironics, Amsterdam, Netherlands

- Precision Medical, Pennsylvania, USA

- Teijin, Osaka, Japan

Tubes (Lab Equipment / Laboratory Glassware)

Main manufacturers:

Below is a A-Z of Laboratory Glassware manufacturers identified with their Head Office Location (where found), however manufacturing is usually globalized (NB: Whilst Laboratory Glassware covers many products, this includes tubes):

- Acumen Labware, Haryana, India

- BOECO, Hamburg Germany,

- Corning Incorporated, Corning, New York, USA

- Eagle Laboratory Glass Company, Painesville, Ohio, USA

- Glassco Group, Haryana, India

- Haimen Shengbang Lab Consumable Instrument Co., Ltd, Jiangsu, China

- Jencons Glass Industries, Gujurat, India

- Kahotest Citotest Labware Manufacturing Co.,Ltd, Jiangsu, China

- M. V. Scientific, Gujurat, India

- Paul Marienfeld GmbH & Co. KG, Konigshofen, Germany

- Pioneer Scientific Instrument Corporation, Kolkata, India

- Rose Scientific Ltd., Edmonton, Canada

- SciLabware Limited, Stoke-on-Trent, UK

- Scientific Apparatus Maunfacturing Company, Mumbai India

- Sichuan ShuBu Group, Chongzhou, China

- Shanghai Heqi Glassware Co., Ltd, Shanghai, China

- Tianbao Glass Instruments, Beijing, China

PORTABLE VENTILATORS

Main Manufacturers:

Below is a A-Z of portable ventilator manufacturers identified with their Head Office Location (where found), however manufacturing is usually globalized:

- Air Liquide, Shanghai, China

- Breas, Gothenburg, Sweden

- Demcon Macawi, Best, Netherlands

- Drager, Lubeck, Germany

- Magnamed, Sao Paulo, Brazil

- Meditec, Harrow, UK

- Medtronic, Dublin, Ireland (Bank has a contact, Trevor Gunn)

- Oxivent, Ankara, Turkey

- Philips, Amsterdam, Netherlands

- ResMed, Cleveland, USA

- Weinmann, Hamburg, Germany

PULSE OXIMETER

Main Manufacturers:

Below is a A-Z of pulse oximeter manufacturers identified, with  their Head Office Location (where found), however manufacturing is usually globalized:

- Contec, Hebei, China

- GE Healthcare, Chicago, IL, USA

- Heal Force, Hong Long, China

- Jerry Medical, Shanghai, China

- Konica Minolta, Tokyo, Japan

- Masimo, CA, USA

- Medtronic, Dublin, Ireland (Bank has a contact Trevor Gunn)

- Mindray, Shenzen, China

- Nihon-Kohden, Tokyo, China

- Nonin Medical, Minneapolis, MN, USA

- Philips, Amsterdam, Netherlands

- Smiths Medical, Minneapolis, MN, USA

- Solaris, San Francisco, CA, USA

LARYNGOSCOPE

Main Manufacturers:

Below is a A-Z of laryngoscope manufacturers identified, with  their Head Office Location (where found), however manufacturing is usually globalized:

- Hangzhou Yuha Medical Optical Tech, Hangshou, China

- Hersill, Madrid, Spain

- HUM, Lunen, Germany

- Jiangsu Maslech Medical, Jiangsu, China

- Kawe, Asperg, Germany

- Lorien Industries, Sialkot, Pakistan

- Luxamed, Baluburen, Germany

- Marshall Airway Products, Radstock, UK

- Meber, Fontanini, Italy

- Opticlar Vision, Poole, UK

- Oscar Boscarol, Bolzano, Italy

- Penlon, Oxford, UK

- Royax, Cestlice, Czech Republic

- Rudolf Riester, Jungingen, Germany

- Shenzen Tianlang Medical Equipment, Shenzhen, China

- Sklar Instruments, Pennsylvania, USA

- Smiths Medical, Minneapolis, MN, USA

- Sturdy Industrial, New Taipei, Taiwan

- Surtex Instruments, New Malden, UK

- Timesco, Basildon, UK

- Truphatek International, Netanya, Israel

- Vadi Medical Technology, Taoyuan, Taiwan

- Vision Scientifics, Wetland, MI, USA

- Welch Allyn, New York, USA

- Xohai Medica, Sialkot, Pakistan

Ultrasound

Main manufacturers:

Below is a A-Z list of the main manufacturers of ultrasound technology identified, with  their Head Office Location (where found), however manufacturing is usually globalized:

- Analogic Corporation, USA

- Chison, China

- Edan, Sunnyvale, CA, USA

- Esaote S.p.A, Italy

- FUJIFILM Holdings Corporation, Japan

- GE Healthcare, Chicago, IL, USA

- Hitachi Medical Corporation, Japan

- Koninklijke Philips, Amsterdam, Netherlands

- Mindray Medical International Ltd, China,

- Samsung Electronics Suwon, South Korea

- Siemens Healthcare, Munich, Germany

- Sonoscape, China

- Toshiba Medical Systems Corporation, Tokyo, Japan

Bio-Hazard Bags

Main Manufacturers:

Below is a A-Z list of the main manufacturers of medical oxygen concentrators identified, with their Head Office Location (where found), however manufacturing is usually globalized:

- BioMedical Waste Solutions, LLC, Port Arthur, Texas, USA

- Clean Harbors, Inc., Norwell, Massachusetts, USA

- Daniels Sharpsmart, Inc., Chicago, Illinois, USA

- REMONDIS Medison GmbH, Lunen, Germany

- Republic Services, Inc. Phoenix, Arizona, USA

- Sharps Compliance, Inc., Houston, Texas, USA

- Stericycle, Inc., Lake Forest, Illinois, USA

- Suez Environnement S.A. La Defense (Paris) France

- Veolia Environnement S.A. Aubervilliers, France

- Waste Management, Inc., Houston, Texas, USA

CHLORINE

Main Manufacturers:

Below is a A-Z list of the main manufacturers/producers of chlorine identified, with their Head Office Location (where found), however manufacturing is usually globalized:

- BASF SE, Ludwigshafen, Germany

- Dow Chemical Company, Midland, Michigan, USA

- Formosa Plastics Corporation, Kaohsiung, Taiwan

- Hanwha Chemical Corporation , Seoul, South Korea

- Ineos Group Ltd, London, UK

- Occidental Petroleum Corporation, Houston, Texas, USA

- Olin Corporation, Clayton, Missouri, USA

- PPG Industries, Pittsburgh, Pennsylvania, USA

- Tata Chemicals Limited, Mumbai, India

- Tosoh Corporation, Tokyo, Japan

Ambulances

Main Manufacturers:

Below is a A-Z list of the main manufacturers of ambulances identified, with  their Head Office Location (where found):

- American Emergency Vehicles, North Carolina, USA

- Braun Industries, Ohio, USA

- DEMERS, Ohio, USA

- Life Line Emergency Vehicles, Iowa, USA

- Marque Ambulance, Florida, USA

- MEDICOP medical equipment, Slovenia

- Miesen, Bonn, Germany

- OrientMEd International FZE, Dubai, UAE

- Paramed International, Dubai, UAE

- Wheeled Coach, Florida, USA

Note:

Sample collection and diagnostics is generally at a single country level, so this segment does not have a global market to speak of.

- Contract and Estimated Cost:

- Procurement Approach (select from options and complete table below):

| Attribute | Selected arrangement | Justification Summary/Logic |
| --- | --- | --- |
| Specifications | Conformance/Performance |  |
| Sustainability Requirements | Yes/No |  |
| Contract Type | - Traditional - Design and Build - Design, Build, Operate, Maintain - Design and Build – Turnkey or Prime Contractor - EPC and EPCM - Other:_____________________ |  |
| Pricing and costing mechanism | - Lump Sum - Performance based contracts - Schedule of Rates / Admeasurement - Time and Materials - Cost Plus |  |
| Supplier Relationship | - Adversarial/Collaborative |  |
| Price Adjustments | - None, fixed price - Negotiated - Percentage |  |
| Form of Contract (Terms and Conditions) | - State any special conditions of contract |  |
| Selection Method | - Request for Proposals (RFP) - Requests for Bids (RFB) - Requests for Quotations (RFQ) - Direct Selection |  |
| Selection Arrangement | - Competitive Dialogue - Public Private Partnerships (PPP) - Commercial Practices - United Nations (UN) Agencies - e-Reverse Auctions - Imports - Commodities - Community Driven Development - Force Accounts - Framework Agreements - Cross Project Opportunities |  |
| Market Approach | - Type of Competition - Open - Limited - International - National - No Competition – Direct Selection - Number of Envelopes/Stages - Single Envelope - Two Envelopes - Single Stage - Multi Stage - BAFO (Yes/No) - Negotiations (Yes/No) |  |
| Pre / Post Qualification | - Pre-Qualification - Post-Qualification - Initial Selection |  |
| Evaluation Selection Method | - Quality Cost Based Selection (QCBS) - Fixed Budget Based Selection (FBS) - Least Cost Based Selection (LCS) - Quality Based Selection (QBS) - Consultant’s Qualifications Based Selection (CQS) - Direct Selection |  |
| Evaluation of Costs | - Adjusted Bid Price - Life-Cycle Costs |  |
| Domestic Preference | Yes / No |  |
| Rated Criteria | List the type of criteria to be used (mandatory/desired) |  |

- Preferred arrangement for low value, low risk activities (if applicable)

| Activity | Category | Estimated cost | Procurement arrangement |
| --- | --- | --- | --- |

- Summary of PPSD to be inform the Bank’s preparation of the PAD

Particularly Rukhi hospital, which is located near Abkhazia and serves a large internally displaced population.

With a score of less than 65,000.

The average monthly TSA transfer is estimated to be 283 GEL per household, nearly three quarters of their average aggregate monthly consumption, estimated at 384 GEL (HIES 2018).

ECRI Exclusive Hazard Report - https://assets.ecri.org/PDF/COVID-19-Resource-Center/COVID-19-Clinical-Care/COVID-Alert_Sleep-Apnea-Devices.pdf

ECRI Exclusive Hazard Report - https://assets.ecri.org/PDF/COVID-19-Resource-Center/COVID-19-Clinical-Care/COVID-Alert_Repurpose-Anesthesia-Units.pdf

COVID-19 – ECRI Exclusive Hazard Report - https://assets.ecri.org/PDF/COVID-19-Resource-Center/COVID-19-Clinical-Care/COVID-Alert-N95-Shortage-Strategies.pdf

CDC recommended spreadsheet of supply management - https://www.cdc.gov/coronavirus/2019-ncov/hcp/ppe-strategy/burn-calculator.html