European Neighbourhood Program for Agriculture and Rural Development (ENPARD, Phase III)

2017-2020

Total Budget: 77.5 mln Euro

EUR 44,500,000 for budget support

EUR 33,000,000 for complementary support

| Specific Conditions: indicators (to be achieved by the end of the specified year), sources of verification and baselines for disbursements |  |  |  |
| --- | --- | --- | --- |
| 2017 | 2018 | 2019 | 2020 |
| Priority Area 1 – Economy and competitiveness |  |  |  |
| Condition 1 - Increased competitiveness of agriculture |  |  |  |
|  | Indicator 1.1.1 The actual expenditure outturn is at least 70% of the approved budget expenditure of the annual (2018) Rural Development Action Plan (RDAP) for agricultural cooperatives. (maximum amount: €1,000,000) | Indicator 1.1.2 At least 100 active agricultural cooperatives supported through public funds between 01.01.2017 and 31.12.2019. (maximum amount: €1,000,000) Status – Fully Achieved During 2017-2019 years, 139 new agricultural cooperatives were financed in the frame of state programs supporting agricultural cooperatives, implemented by the Agricultural Cooperatives Development Agency | Indicator 1.1.3 At least 15% increase in land amelioration supported with public funds between 01.01.2017 and 31.12.2020 compared to baseline value. (maximum amount: €1,300,000) Status – ongoing No problem detected to achieve indicator |
|  | Baseline value (2017): Validated percentage (%) of actual expenditure outturn for 2017 will be available after the year is completed. | Baseline value (2016): 100 active agricultural cooperatives supported through public funds in 2016. | Baseline value (2016): 14,375 ha of ameliorated land completed with public funds in 2016. |
|  | Source of verification: Ministry of Agriculture (MoA)-published annual report for 2018; official Budget execution report for 2018 published and submitted to Parliament according to Georgian legislation, providing evidence of compliance with indicator 1.1.1. | Source of verification: MoA-published annual report for 2019 providing evidence of compliance with indicator 1.1.2. | Source of verification: MoA-published annual report for 2020 providing evidence of compliance with indicator 1.1.3. |
| Condition 2 - Increased income of rural households |  |  |  |
|  | Indicator 1.2.1 The actual expenditure outturn is at least 70% of the approved budget expenditure of the annual (2018) RDAP for Small and Medium Enterprises (SMEs) support in rural areas. (maximum amount: €1,000,000) | Indicator 1.2.2 At least 3,000 active SMEs in rural areas supported through public funds between 01.01.2017 and 31.12.2019. (maximum amount: €1,000,000) Status – Fully Achieved In 2017-2019, by LEPLs “Enterprise Georgia” and Georgia’s Innovations and Technologies Agency, in rural areas, 3,745 small and medium enterprises (SMEs) were supported by public fund | Indicator 1.2.3 At least additional 2,000 graduated beneficiaries in rural areas enhanced entrepreneurial skills through trainings supported by public funds between 01.01.2017 and 31.12.2020, out of which at least 500 achieved increased sales and at least 40 set up new active SMEs. (maximum amount: €1,300,000) Status – ongoing Due to recent COVID 19 crisis we need to modify this indictor |
|  | Baseline value (2017): Validated percentage (%) of actual expenditure outturn for 2017 will be available after the year is completed. | Baseline value (2016): 2,049 active SMEs in rural areas supported through public funds by 31.12.2016. | Baseline values (2016): 200 new graduates from Georgian Innovations and Technology Agency (GITA) trainings in rural areas supported with public funds by 31.12.2016. |
|  | Source of verification: Implementing agencies under Ministry of Economy and Sustainable Development (MoESD) for 2018; official Budget execution report for 2018 published and submitted to Parliament according to Georgian legislation, providing evidence of compliance with indicator 1.2.1. | Source of verification: Official reports of implementing agencies under MoESD for 2019 providing evidence of compliance with indicator 1.2.2. | Source of verification: Official reports of implementing agencies under MoESD for 2020 providing evidence of compliance with indicator 1.2.3. |
| Priority Area 2 – Social conditions and living standards |  |  |  |
| Condition 1 - Improved rural infrastructure |  |  |  |
|  | Indicator 2.1.1 The actual expenditure outturn is at least 70% of the approved budget expenditure of the annual (2018) RDAP for rural infrastructure support. (maximum amount: €1,000,000) | Indicator 2.1.2 New or upgraded public infrastructure completed in at least 1,150 rural settlements by 31.12.2019. (maximum amount: €1,000,000) Status – Fully Achieved During 2017-2019, new infrastructure projects were implemented in 1,655 rural settlements. | Indicator 2.1.3 At least 35% increase of the population in rural settlements with access to new or upgraded public infrastructure completed between 01.01.2017 and 31.12.2020 compared to baseline value. (maximum amount: €1,300,000) Status – ongoing No problem detected to achieve indicator |
|  | Baseline value (2017): Validated percentage (%) of actual expenditure outturn for 2017 will be available after the year is completed. | Baseline value (2016): 600 rural settlements with new or upgraded public infrastructure completed with public funds by 31.12.2016. | Baseline value (2016): 900,000 people in rural settlements with access to new or upgraded public infrastructure completed by 31.12.2016. |
|  | Source of verification: Ministry of Regional Development and Infrastructure (MRDI)-published annual report for 2018; official Budget execution report for 2018 published and submitted to Parliament according to Georgian legislation, providing evidence of compliance with indicator 2.1.1. | Source of verification: MRDI–published annual report for 2019 providing evidence of compliance with indicator 2.1.2. | Source of verification: MRDI–published annual report for 2020 providing evidence of compliance with indicator 2.1.3. |
| Condition 2 - Improved skills development and local population engagement |  |  |  |
|  | Indicator 2.2.1 The actual expenditure outturn is at least 70% of the approved budget expenditure of the annual (2018) RDAP for Vocational Education and Training (VET)/skills development support. (maximum amount: €1,000,000) Status - completed | Indicator 2.2.2 At least 5% increase of beneficiaries in rural areas graduated from modular Technical and Vocational Education and Training (TVET) courses designed in participation with employer leading to improved skills for employability between 01.01.2018 and 31.12.2019 compared to baseline value. (maximum amount: €1,000,000) Status – Fully Achieved 474 beneficiaries (baseline value) were graduated from modular Technical and Vocational Education and Training (TVET) courses in rural areas between 01.01.2017 and 31.12.2017. 4,571 beneficiaries were graduated from modular Technical and Vocational Education and Training (TVET) courses in rural areas in 2018-2019. | Indicator 2.2.3 At least 100% increase of enrolled students on Work Based Learning (WBL) TVET courses in rural areas that involve employers in assessment process between 01.01.2018 and 31.12.2020 compared to baseline value. (maximum amount: €1,300,000) Status – ongoing No problem detected to achieve indicator |
|  | Baseline value (2017): Validated percentage (%) of actual expenditure outturn for 2017 will be available after the year is completed. | Baseline value (2017): Validated number of graduates in rural areas from modular TVET courses between 01.01.2017 and 31.12.2017. | Baseline value (2017): 54 enrolled students on WBL TVET courses in rural areas between 01.01.2017 and 30.06.2017. |
|  | Source of verification: Ministry of Education and Science (MoES)- published annual report for 2018; official Budget execution report for 2018 published and submitted to Parliament according to Georgian legislation, providing evidence of compliance with indicator 2.2.1. | Source of verification: Official MoES- reports / VET database for 2019 providing evidence of compliance with indicator 2.2.2. | Source of verification: Official MoES- reports / VET database for 2020 providing evidence of compliance with indicator 2.2.3. |
| Priority Area 3 - Environmental protection and sustainable management of natural resources |  |  |  |
| Condition 1 - Improved forest and natural resources management |  |  |  |
|  | Indicator 3.1.1 The actual expenditure outturn is at least 70% of the approved budget expenditure of the annual (2018) RDAP for the sustainable management of forests in compliance with the Rules of Development and Approval of Forest Management Plans. (maximum amount: €400,000) Status - completed | Indicator 3.1.2 At least 6 new Forest Management Plans (FMPs) are formally adopted in compliance with the Forest Code of Georgia between 01.01.2017 and 31.12.2019. (maximum amount: €500,000) Status – Fully Achieved In 2017-2019, by LEPLs National Forest Agency and Agency of Protected Areas, with the EU support, 9 new Forest Management Plans (FMPs) were formally adopted in compliance with the Forest Code of Georgia. | Indicator 3.1.3 At least 17% increase in forest area managed between 01.01.2017 and 31.12.2020 on the basis of FMPs adopted in compliance with the Forest Code of Georgia compared to baseline value. (maximum amount: €750,000) Status – ongoing Due to recent COVID 19 crisis we need to modify this indictor |
|  | Baseline value (2017): Validated percentage (%) of actual expenditure outturn for 2017 will be available after the year is completed. | Baseline value (2016): 10 FMPs formally adopted in compliance with existing Georgian regulations by 31.12.2016. | Baseline value (2016): 10% of forest areas in Georgia managed through FMPs by 31.12.2016. |
|  | Source of verification: Ministry of Environment and Natural Resources Protection (MENRP)-published annual report for 2018; official Budget execution report for 2018 published and submitted to Parliament according to Georgian legislation, providing evidence of compliance with indicator 3.1.1. | Source of verification: MENRP-published annual report for 2019 providing evidence of compliance with indicator 3.1.2. | Source of verification: MENRP-published annual report for 2020 providing evidence of compliance with indicator 3.1.3. |
|  | Indicator 3.2.1: The actual expenditure outturn is at least 70% of the approved budget expenditure of the annual (2018) RDAP for the sustainable management of the System of Protected Areas of Georgia. (maximum amount: €400,000) Status - completed | Indicator 3.2.2 At least 3 new Protected Areas (PAs) are formally added to the System of PAs of Georgia between 01.01.2017 and 31.12.2019. (maximum amount: €500,000) Status – Fully Achieved In 2017-2019, 5 new Protected Areas (PAs) are formally added to the System of PAs of Georgia. | Indicator 3.2.3 At least 50% of the territorial units within the System of PAs of Georgia have by 31.12.2020 Management plans developed in compliance with the Law of Georgia on the System of Protected Areas compared to baseline value. (maximum amount: €750,000) Status – ongoing No problem detected to achieve indicator |
|  | Baseline value (2017): Validated percentage (%) of actual expenditure outturn for 2017 will be available after the year is completed. | Baseline value (2016): 88 PAs formally added to the System of PAs of Georgia by 31.12.2016. | Baseline value: 45% of territorial units within the System of PAs of Georgia with Management plans in compliance with the Law by 31.12.2016 |
|  | Source of verification: MENRP-published annual report for 2018; official Budget execution report for 2018 published and submitted to Parliament according to Georgian legislation, providing evidence of compliance with indicator 3.2.1. Status - completed | Source of verification: MENRP-published annual report for 2019 providing evidence of compliance with indicator 3.2.2. | Source of verification: MENRP-published annual report for 2019 providing evidence of compliance with indicator 3.2.3. |
| Priority Area 4 – Rural development governance |  |  |  |
| Condition 1: Effective governance for the implementation of the rural development strategy |  |  |  |
| Indicator 4.1.1 The National Rural Development Action Plan (RDAP) 2018-2020 is costed and reflected in the Basic Data and Directions (BDD) document submitted by the Government to the Parliament by 31.12.2017. (maximum amount: €2,000,000) Status - completed | Indicator 4.1.2 The actual expenditure outturn of the costed RDAP for 2018 is at least 70% of the approved budget expenditure of the year 2018 from RDAP (2018-2020) (maximum amount: €2,000,000) Status - completed | Indicator 4.1.3 The actual expenditure outturn of the costed RDAP for 2019 is at least 75% of the approved budget expenditure of the year 2019 from RDAP (2018-2020) (maximum amount: €2,000,000) Status – Fully Achieved The actual expenditure outturn of the costed RDAP for 2019 is at approximately 123 % of the approved budget expenditure of the year 2019 from RDAP (2018-2020) | Indicator 4.1.4 The actual expenditure outturn of the costed RDAP for 2020 is at least 80% of the approved budget expenditure of the year 2020 from RDAP (2018-2020) (maximum amount: €2,000,000) Status – ongoing Due to recent COVID 19 crisis we need to modify this indictor |
| Baseline value (2017): National RDAP 2017 is costed and has been reflected in the BDD document | Baseline value (2017): Validated percentage (%) of actual expenditure outturn for 2017 will be available after the year is completed. |  |  |
| Source of verification: publication of (i) the BDD published and submitted to the Parliament by 31.12.2017, and (ii) a report, in Georgian and English languages, providing evidence of compliance with indicator 4.1.1. | Source of verification: Official Budget Execution report for 2018, in Georgian and in English languages, published and submitted to Parliament according to Georgian legislation, providing evidence of compliance with indicator 4.1.2. | Source of verification: Official Budget Execution report for 2019, in Georgian and in English languages, published and submitted to Parliament according to Georgian legislation, providing evidence of compliance with indicator 4.1.3. | Source of verification: Official Budget Execution report for 2020, in Georgian and in English languages, published and submitted to Parliament according to Georgian legislation, providing evidence of compliance with indicator 4.1.4. |
| Indicator 4.2.1 National RDAP 2018-2020 presented to stakeholders and media by the Inter-Agency Coordination Council (IACC) for rural development. (maximum amount: €2,000,000) Status - completed | Indicator 4.2.2: Qualitative and quantitative results of the implementation of the RDAP for 2018 are overall in line with the results set for 2018 in the RDAP (2018-2020). (maximum amount: €2,000,000) Status - completed | Indicator 4.2.3: Qualitative and quantitative results of the implementation of the RDAP for 2019 are overall in line with the results set for 2019 in the RDAP (2018-2020). (maximum amount: €2,000,000) Status – Fully Achieved There are three objectives per each Strategic priority area, hence, 9 objectives (12 objective indicators). In 2019, 7 indicators (1.1.1, 1.1.2, 1.2, 1.3, 2.2, 3.1.2, 3.3.2) out of 12, were fulfilled at more than 100%. 3 indicators (2.3, 3.2, 3.3.1) were fulfilled at 100%, 2 indicators (2.1, 3.1.1) were fulfilled at 89% and 96 %. | Indicator 4.2.4: Qualitative and quantitative results of the implementation of the RDAP for 2020 are overall in line with the results set for 2020 in the RDAP (2018-2020). (maximum amount: €2,000,000) Status – ongoing Due to recent COVID 19 crisis we need to modify this indictor |
| Baseline value (2016): National RDAP 2017 officially approved and presented to stakeholders and media. | Baseline value (2017): Validated results of the implementation of the National RDAP for 2017 will be available after the year is completed. |  |  |
| Source of verification: publication in the government website, in Georgian and in English languages, of the IACC-approved National RDAP 2018-2020, and the subsequent presentation to stakeholders and to the media of the main results expected (i) by end-2018, (ii) by end-2019 and (iii) by end-2020, respectively, providing evidence of compliance with indicator 4.2.1. | Source of verification: publication in the MoA website, in Georgian and in English languages, of the IACC-approved annual report specifying qualitative and quantitative achievements during 2018 implementation of the RDAP, providing evidence of compliance with indicator 4.2.2. | Source of verification: publication in the MoA website, in Georgian and in English languages, of the IACC-approved annual report specifying qualitative and quantitative achievements during 2019 implementation of the RDAP, providing evidence of compliance with indicator 4.2.3. | Source of verification: publication in the MoA website, in Georgian and in English languages, of the IACC-approved annual report specifying qualitative and quantitative achievements during 2020 implementation of the RDAP, providing evidence of compliance with indicator 4.2.4. |
| Total Amount: 7mln Euro Fully Disbursed: 7 mln Euro | Total Amount: 11.8 mln Euro Fully Disbursed: 11.8 mln Euro | Total Amount: 12 mln Euro Indicators will be assessed by December 31, 2019 Assessment mission expected in May, 2020 Full Disbursement expected by September 2020 | Total Amount: 13.7 mln Euro |