## TOTAL
| Cost estimate (USD) | Outstanding amount (USD) |  | 6000000 | retroactive
Component 1. Emergency COVID-19 Response and Component 3. Project Management and Monitoring | 41500000 | 35937073.6
Component 1. Emergency COVID-19 Response
GOODS | Cost estimate (USD) | ACTUALS (contracted) | Remaining funds | UNCOMITTED | Planed
1. Procurement of Personal Protective Equipment | 5000000 | 179820 | 4820180 | 0 | 5000000 | 2000000
2. COVID19/G/DC-06 / Procurement of Hospital Equipment for four dedicated COVID-19 clinics: Rukhi Hospital, Batumi Hospital, Lisi Hospital and Infectious Disease Hospital | 6500000 | 0 | 6500000 | -10000000 | 16500000 | 0
3. COVID19/G/RFQ-03 / Procurement of Motorcycle for ambulance first responders with helmets | 1500000 | 0 | 1500000 | 202913.9701 | 1297086.0299 | 500000
4. COVID19/G/RFQ-01 / Procurement of fully equipped Ambulance car C type - Intensive Care Mobile Unit (30 Units) | 2250000 | 0 | 2250000 | 0 | 2250000 | 250000
5. COVID19/G/DC-07 / Procurement of Diagnostic Supplies | 25750000 | 8794455.4 | 16955544.6 | 16755544.6 | 200000 | 15750000
6. COVID19/G/RFQ-02 / Procurement of Equipment for Emergency Control Center | 2800000 | 718476 | 2081524 | 2081524 | 0
7. COVID19/G/RFQ-07 / Procurement of ICT goods for public health facilities | 200000 | 0 | 200000 | 154000 | 46000
8. COVID19/G/RFQ-04 / Procurement of motor vehicles for Infectious Control Monitoring Center | 200000 | 0 | 200000 | -185369.6803 | 385369.6803
9. Equipment for Primary Care Facilities | 3000000
SUM | 47200000 | 9692751.4 | 34507248.6 | 9008612.8897 | 25678455.7103
WORKS | Cost estimate (USD) | ACTUALS (contracted) | Remaining funds | UNCOMITTED | COMITTED
COVID19/CW/RFB-01 / Repair works of public health facilities | 1000000 | 0 | 1000000 | 704627.7048 | 295372.2952 | 1000000
SUM | 1000000 | 0 | 1000000 | 704627.7048 | 295372.2952
3750000
CONSULTANCY SERVICE | Cost estimate (USD) | ACTUALS (contracted) | Remaining funds | UNCOMITTED | COMITTED
| 300000 | 9375 | 290625
| 300000 | 9375 | 290625
quarantine | 5000000
preparedness | 5000000
cost of case | 13500000 |  | 47500000
| 23500000 |  | 24000000 | 23200000
Component 3. Project Management and Monitoring
CONSULTANCY SERVICE Component III | Cost estimate (USD) | ACTUALS (contracted) | Remaining funds | UNCOMITTED | COMITTED
| 300000 | 160800 | 139200
| 300000 | 160800 | 139200
SUM | 72300000 | 9862926.4 | 35937073.6

## WORKS I
Request for Bids
Activity Reference No. / Description: | In-Process | Loan / Credit No. | Component | Review Type | Category | Market Approach | Prequalification (Y/N) | Procurement Process | Evaluation Options | Estimated Amount (US$) | COMITTED | High SEA/SH Risk | Procurement Document Type | Process Status | Activity Status | Draft Pre-qualification Documents |  | Specific Procurement Notice |  | Amendments to Pre-qualification Documents | Opening / Minutes of Pre-qualification |  | Pre-qualification Evaluation Report |  | Draft Bidding Documents |  | Specific Procurement Notice |  | Invitation to Providers |  | Amendments to Bidding Documents | Bid Submission / Opening / Minutes |  | Bid Evaluation Report and Recommendation for Award |  | Notification of Intention of Award |  | Signed Contract |  | Contract Amendments | Contract Completion |  | Contract Termination
[16 empty] | Planned | Actual | Planned | Actual | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Actual | Planned | Actual | Actual
COVID19/CW/RFB-01 / Repair works of public health facilities | No | IBRD-91130 | Emergency COVID-19 Response | Prior | Works | Open - National | N | Single Stage One Envelope |  | 1000000 |  |  |  | Pending Implementation | Cleared | [9 empty] | 2020/06/22 |  | 2020/06/27 |  |  |  |  | 2020/08/08 |  | 2020/09/07 |  | 2020/09/21 |  | 2020/10/12 |  |  | 2021/04/10
Kutaisi Emergency Coordination and Emergency Assistance Center | [9 empty] | 0 | 230000
O.Chkhobadze Disabled and Elderly Medical Rehabilitation Clinical Center | [9 empty] | 0 | 65372.2952
Tbilisi
TOTAL | [9 empty] | 0 | 295372.2952

## GOODS I
|  | Activity Reference No. / Description: | In-Process | Loan / Credit No. | Component | Review Type | Category | Market Approach | Estimated Amount (US$) | COMITTED | High SEA/SH Risk | Procurement Document Type | Process Status | Activity Status | Draft Request for Quotations |  | Specific Procurement Notice |  | Invitation to Supplier / Contractor |  | Amendments to Request for Quotations | Receive Quotations |  | Comparison of Quotations |  | Notification of Intention of Award |  | Signed Contract |  | Contract Amendments | Contract Completion |  | Contract Termination
[15 empty] | Planned | Actual | Planned | Actual | Planned | Actual | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Actual | Planned | Actual | Actual
2.1 | Infection protection supplies | 1.COVID19/G/DC-05 Procurement of Personal Protective Equipment | No | IBRD-91130 | Component 1. Emergency COVID-19 Response | Prior | Goods | Direct selection | 5000000 | 0 |  |  | Pending Implementation | Cleared | 2020/06/14 |  | 2020/06/19 |  | 2020/06/19 |  | 2020/07/03 |  | 2020/07/24 |  |  | 2021/01/20
|  | Goggles, protective | [5 empty] | Direct | 179820 | 0
[9 empty] | 0 | 0
TOTAL | [8 empty] | 179820 | 5000000
2.1 | Costs of case management and treatment | 2. COVID19/G/DC-06 / Procurement of Hospital Equipment for four dedicated COVID-19 clinics: Rukhi Hospital, Batumi Hospital, Lisi Hospital and Infectious Disease Hospital | No | IBRD-91130 | Emergency COVID-19 Response | Prior | Goods | Direct | 16500000 |  |  |  | Pending Implementation | Cleared | 2020/06/15 |  | 2020/06/20 |  | 2020/06/20 |  | 2020/07/04 |  | 2020/07/25 |  |  | 2021/01/21
|  | Rukhi Republic Hospital | [6 empty] | 0 | 0
|  | Batumi | [6 empty] | 0 | 0
|  | Tbilisi Infectiouse Disease Hospital | [6 empty] | 0 | 0
|  | Chkhobadze medical centerr in Kutaisi | [6 empty] | 0 | 0
|  | ICU of the Infectiouse LG Hospital in Kutaisi | [6 empty] | 0 | 0
|  | Sachkhere Hospital | [6 empty] | 0 | 0
|  | ICU of the unuverity hospilat | [6 empty] | 0 | 0
TOTAL | [8 empty] | 0 | 16231524
2.1 | Equipment and minor repairs to strengthen public facilities | 3. COVID19/G/RFQ-03 / Procurement of Motorcycle for ambulance first responders with helmets | No | IBRD-91130 | Emergency COVID-19 Response | Post | Goods | Limited | 1500000 |  |  |  | Pending Implementation | Cleared | 2020/06/15 | [6 empty] | 2020/07/04 |  | 2020/07/11 |  | 2020/07/25 |  | 2020/08/15 |  |  | 2021/02/11
|  | Motorcycle for ambulance first responders with helmets | [7 empty] | 1297086.0299
TOTAL | [8 empty] | 0 | 1297086.0299
2.1 | Equipment and minor repairs to strengthen public facilities | 4. COVID19/G/RFQ-01 / Procurement of fully equipped Ambulance car C type - Intensive Care Mobile Unit (30 Units) | No | IBRD-91130 | Emergency COVID-19 Response | Prior | Goods | Limited | 2500000 |  |  |  | Pending Implementation | Cleared | 2020/06/15 | [6 empty] | 2020/07/04 |  | 2020/07/11 |  | 2020/07/25 |  | 2020/08/15 |  |  | 2021/02/11
|  | Intensive Care Mobile Unit (30 Units) | [7 empty] | 2250000
TOTAL | [8 empty] | 0 | 2250000
1.1 | Equipment, diagnostic supplies (including lab reagents and testing kits), infection protection and transportation for laboratories | 5. COVID19/G/DC-07 / Procurement of Diagnostic Supplies | No | IBRD-91130 | Emergency COVID-19 Response | Prior | Goods | Direct | 10000000 |  |  |  | Pending Implementation | Cleared | 2020/06/15 |  | 2020/06/20 |  | 2020/06/20 |  | 2020/07/04 |  | 2020/07/25 |  |  | 2021/01/21
|  | COVID19/G/DC-01 / Procurement of Rapid COVID-19 Test Cassette | Yes | IBRD-91130 | Component 1. Emergency COVID-19 Response | Post | Goods | Direct | 504400 |  |  |  | Signed | Cleared | 2020/05/28 | 2020/05/13 | 2020/06/02 | 2020/05/13 | 2020/06/02 | 2020/05/17 | 2020/06/16 | 2020/05/17 | 2020/07/07 | 2020/05/17 |  | 2021/01/03
|  | COVID19/G/DC-04 / Procurement of Standard COVID-19 Antigen Tests | No | IBRD-91130 | Component 1. Emergency COVID-19 Response | Post | Goods | Direct | 612200 |  |  |  | Signed | Cleared | 2020/06/12 | 2020/06/12 | 2020/06/13 | 2020/06/12 | 2020/06/13 | 2020/06/16 | 2020/06/20 | 2020/06/18 | 2020/06/21 | 2020/06/19 |  | 2020/07/21
|  | COVID19/G/DC-08 / Procurement of In Vitro Diagnostic Medical Device (cobas) | No | IBRD-91130 | Emergency COVID-19 Response | Post | Goods | Direct | 493980 |  |  |  | Under Implementation | Cleared | 2020/06/12 | 2020/05/22 | 2020/06/13 | 2020/06/19 | 2020/06/13 |  | 2020/06/20 |  | 2020/07/11 |  |  | 2021/01/07
|  | COVID19/G/DC-09 / Procurement of Qiagen RNA Mini Kit | No | COFN-C1670,IBRD-91130 | Component 1. Emergency COVID-19 Response | Post | Goods | Direct | 338708 |  |  |  | Signed | Cleared | 2020/06/25 |  | 2020/06/30 |  | 2020/06/30 |  | 2020/07/14 |  | 2020/08/04 |  |  | 2021/01/31
|  | COVID19/G/DC-10/Thermos Scientifics COVID-19 tests | yes | COFN-C1670,IBRD-91130 | Component 1. Emergency COVID-19 Response |  |  | Direct | 5685100 |  |  |  | Signed | Cleared
|  | COVID19/G/DC-11/Nucleic Acid Diagnostic Kit | yes | COFN-C1670,IBRD-91130 | Component 1. Emergency COVID-19 Response |  |  | Direct | 600000
|  | COVID19/G/UN-01 / Procurement of Xpert (R) Xpress SARS-CoV-2 Diagnostic Test Kits | No | COFN-C1670,IBRD-91130 | Emergency COVID-19 Response | Post | Goods | Direct | 478240.4 |  |  |  | Signed | Cleared | 2020/06/25 |  | 2020/06/30 |  | 2020/06/30 |  | 2020/07/14 |  | 2020/08/04 |  |  | 2021/01/31
|  | Laboratory Supplies COVID19/G/RFQ-05 | No | IBRD-91131 | Emergency COVID-19 Response |  |  | RFQ | 81827 |  |  |  | Under Implementation
|  | Rapid antigen antibody tests for tourist-active zones | [7 empty] | 200000
TOTAL | [8 empty] | 8794455.4 | 200000
|  | 6. COVID19/G/RFQ-02 / Procurement of Equipment for Emergency Control Center | No | IBRD-91130 | Emergency COVID-19 Response | Prior | Goods | Open - National | 2800000 |  |  |  | Pending Implementation | Cleared | 2020/06/18 |  | 2020/06/23 |  | 2020/06/23 |  |  | 2020/07/07 |  | 2020/07/14 |  | 2020/07/28 |  | 2020/08/18 |  |  | 2021/02/14
|  | COVID19/G/DC-02 / Procurement of Critical Care Ventilators and Related Services | Yes | IBRD-91130 | Emergency COVID-19 Response | Post | Goods | Direct | 405000 | 0 |  |  | Signed | Cleared | 2020/05/28 | 2020/05/04 | 2020/06/02 | 2020/05/11 | 2020/06/02 | 2020/05/19 | 2020/06/16 | 2020/05/21 | 2020/07/07 | 2020/05/21 |  | 2020/08/31
|  | COVID19/G/DC-03 / Procurement of Mobile Emergency Ventilators and Related Services | Yes | IBRD-91130 | Component 1. Emergency COVID-19 Response | Post | Goods |  | 313476 | 0 |  |  | Signed | Cleared | 2020/05/28 | 2020/05/13 | 2020/06/02 | 2020/05/14 | 2020/06/02 | 2020/05/19 | 2020/06/16 | 2020/05/20 | 2020/07/07 | 2020/05/20 |  | 2020/08/31
Radio sistems
TOTAL | [8 empty] | 718476 | 0
|  | 7. COVID19/G/RFQ-07 / Procurement of ICT goods for public health facilities | No | IBRD-91130 | Emergency COVID-19 Response | Post | Goods | Open - National | 300000 |  |  |  | Pending Implementation | Cleared | 2020/06/15 |  | 2020/06/20 |  | 2020/06/20 |  |  | 2020/07/04 |  | 2020/07/11 |  | 2020/07/25 |  | 2020/08/15 |  |  | 2021/02/11
|  | Computers | [7 empty] | 46000
Camera
Camera of the patient's salon
Tablets for ambulances
TOTAL | [8 empty] | 0 | 46000
|  | 8. COVID19/G/RFQ-04 / Procurement of motor vehicles for Infectious Control Monitoring Center | No | IBRD-91130 | Emergency COVID-19 Response | Post | Goods | Open - National | 300000 |  |  |  | Pending Implementation | Cleared | 2020/06/05 |  | 2020/06/10 |  | 2020/06/10 |  |  | 2020/06/24 |  | 2020/07/01 |  | 2020/07/15 |  | 2020/08/05 |  |  | 2021/02/01
|  | 15 motor Motor Vehicles for Infectious Control Monitoring Center | [7 empty] | 385369.6803
TOTAL | [8 empty] | 0 | 385369.6803
Note on C44: Nino Gvenetadze: it can be defined to move in emergancy contol center

## CS I
Quality Based Selection (QBS)
Activity Reference No. / Description: | In-Process | Loan / Credit No. | Component | Review Type | Category | Market Approach | Estimated Amount (US$) | COMITTED | Process Status | Activity Status | Terms of Reference |  | Expression of Interest |  | Evaluation of Expression of Interest and Short List of Consultants |  | Short List and Draft Request for Proposals |  | Request for Proposals as Issued |  | Amendments to Request for Proposals |  | Opening of Technical Proposals / Minutes |  | Evaluation of Technical Proposals |  | Combined Evaluation Report and Draft Negotiated Contract |  | Notification of Intention of Award |  | Signed Contract |  | Contract Amendments | Contract Completion |  | Contract Termination
[11 empty] | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Actual | Planned | Actual | Actual
COVID19/CS/QBS-01 / Training and technical assistance to MoLSHA | No | IBRD-91130 | Emergency COVID-19 Response | Post | Consultant Services | Open - International | 300000 |  | Pending Implementation | Cleared | 2020/06/05 |  | 2020/06/26 |  | 2020/07/26 |  | 2020/08/09 |  |  |  | 2020/08/09 |  | 2020/09/06 |  | 2020/10/06 |  | 2020/11/05 |  | 2020/11/19 |  | 2020/12/10 |  |  | 2021/12/10
COVID19/CS/CDS-02 / Technical Assistance for post crises COVID-19 strategy for Health Sector - Assistant Consultant | No | COFN-C1670,IBRD-91130 | Emergency COVID-19 Response | Post | Consultant Services | Direct | 3125 |  | Pending Implementation | Cleared | 2020/06/25 |  | 2020/06/28 |  | 2020/06/28 |  | 2020/06/28 |  | 2020/07/03 |  | 2020/07/03 |  | 2020/07/03 |  |  | 2020/07/28
COVID19/CS/CDS-01 / Technical Assistance for post-crises COVID-19 strategy for Health Sector - Lead Consultant | No | COFN-C1670,IBRD-91130 | Emergency COVID-19 Response | Post | Consultant Services | Direct | 6250 |  | Pending Implementation | Cleared | 2020/06/25 |  | 2020/06/28 |  | 2020/06/28 |  | 2020/06/28 |  | 2020/07/03 |  | 2020/07/03 |  | 2020/07/03 |  |  | 2020/07/28
TOTAL | [6 empty] | 9375

## CS COMP.III
Individual Consultant Selection
Activity Reference No. / Description: | In-Process | Loan / Credit No. | Component | Review Type | Category | Market Approach | Estimated Amount (US$) | Process Status | Activity Status | Terms of Reference |  | Expression of Interest |  | Evaluation of Expression of Interest and Short List of Consultants |  | Justification for Direct Selection |  | Invitation to Identified / Selected Consultant |  | Draft Negotiated Contract |  | Notification of Intention of Award |  | Signed Contract |  | Contract Amendments | Contract Completion |  | Contract Termination
[10 empty] | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Actual | Planned | Actual | Actual
PIU | [6 empty] | 300000
COVID19/CS/INDV-01 / Procurement Manager | No | IBRD-91130 | Project Management | Post | Consultant Services | Open | 36000 | Signed | Cleared | 2020/05/25 | 2020/05/08 | 2020/06/08 |  | 2020/07/08 | 2020/06/05 |  |  | 2020/07/13 | 2020/05/21 | 2020/08/03 | 2020/06/16 | 2020/08/17 | 2020/06/16 | 2020/09/07 | 2020/06/16 |  | 2021/03/06
COVID19/CS/INDV-05 / Social Standards Specialist | No | IBRD-91130 | social specialist | Post | Consultant Services | Open | 19200 | Under Implementation | Cleared | 2020/05/25 | 2020/05/08 | 2020/06/08 |  | 2020/07/08 |  |  |  | 2020/07/13 |  | 2020/08/03 |  | 2020/08/17 |  | 2020/09/07 |  |  | 2021/03/06
COVID19/CS/INDV-02 / Financial Manager | No | IBRD-91130 | Financial manager | Post | Consultant Services | Open | 30000 | Under Implementation | Cleared | 2020/05/25 | 2020/05/08 | 2020/06/08 |  | 2020/07/08 |  |  |  | 2020/07/13 |  | 2020/08/03 |  | 2020/08/17 |  | 2020/09/07 |  |  | 2021/03/06
COVID19/CS/INDV-06 / Environmental Standards Specialist | No | IBRD-91130 | enviromental Specialist | Post | Consultant Services | Open | 19200 | Signed | Cleared | 2020/05/25 | 2020/05/08 | 2020/06/08 |  | 2020/07/08 | 2020/06/05 |  |  | 2020/07/13 | 2020/05/21 | 2020/08/03 | 2020/06/16 | 2020/08/17 | 2020/06/16 | 2020/09/07 | 2020/06/16 |  | 2021/03/06
COVID19/CS/INDV-04 / Health Specialist | No | IBRD-91130 | Health specialist | Post | Consultant Services | Open | 30000 | Signed | Cleared | 2020/05/25 | 2020/05/08 | 2020/06/08 |  | 2020/07/08 | 2020/06/05 |  |  | 2020/07/13 | 2020/05/21 | 2020/08/03 | 2020/06/16 | 2020/08/17 | 2020/06/16 | 2020/09/07 | 2020/06/16 |  | 2021/03/06
COVID19/CS/INDV-03 / Procurement Specialist | No | IBRD-91130 | Procurement specialist | Post | Consultant Services | Open | 26400 | Signed | Cleared | 2020/05/25 | 2020/05/08 | 2020/06/08 |  | 2020/07/08 | 2020/06/05 |  |  | 2020/07/13 | 2020/05/21 | 2020/08/03 | 2020/06/16 | 2020/08/17 | 2020/06/16 | 2020/09/07 | 2020/06/16 |  | 2021/03/06
160800