## Methodology
Annex 4. Methodology for piloting the disability assessment in Samtskhe Javakheti region
Activities | Status of Activity | Starting Date/Period | Duration/completion date | Resources | Key areas for consideration/Risks | Project activity
Development of methodology for piloting of disability assessment in Samtskhe Javakheti region
Functional assessment instrument & social profile instrument (for adult and children): Translation in English and analysis of first versions transmited by UNICEF | Done | May-June | 2 month | Yannick Deimat, Andrei Tretyak | discussed during the seminar 1-2 July | A111
Functional assessment instrument & social profile instrument (for adult and children): Transmission of last version after aproval | Has not started | July-August | 2 month | UNICEF / GASW | last version should ne ready by the end of July 2019 | A111
Functional assessment instrument & social profile instrument (for adult and children): Translation in Armenian/Russian | Has not started | July - August | 2 month | Natalia GAMGEBELI | in order to be understood by local comunities in Samtskhe Javakheti | A111
Translate in English and adapt the job descriptions of the functional assessment specialists and case managers for children and adults. | Done | July 2019 | July 2019 | Natalia GAMGEBELI | Agree the job descriptions with the MoIDPOTLHSA | A111
Organisation of 2 days seminar in Tbilissi in order to agree the methodology of piloting | Done | July 2019 | July 2019 | MoIDPOTLHSA, UNICEF, EF (Yannick Deimat, Andrei Tretyak) | seminar 1-2 July organised in Tbilissi | A111
Update the detailed workplan | In progress | July 2019 | July 2019 | Yannick Deimat, Andrei Tretyak |  | A111
Recruitment of a local expert to assess local needs and coordonate the experimentation. | In progress | July-August | 7 WD | Local expert (Maguli Shaghashvili) | First mission to Samtskhe Javakheti 22/07; Report in English by mid-August | A111
Development of terms and conditions of coopeartion with GASW (Recrutement, training and follow-up of local staffs) | In progress | July-August | 2 month | Keti Gigineishvili, Andrei Tretyak |  | A111
Piloting of assessment instruments in Samtskhe Javakheti region
1 day workshop in Akhaltsikhe to present the functionak model of disability assessment and to discuss the methodology of the testing phase with local authorities | In progress | July 2019 | 1 day | MoIDPOTLHSA, UNICEF, GASW (Keti Gigineishvili), EF Maguli Shaghashvili, Audrius Bitinas, Yannick Deimat, Andrei Tretyak. | 22/07 in Akhaltsikhe. Meeting with the focus persons in the municipality, the evaluation centers and the GASW | A112
Publication of the job descriptions of the functional assessment specialists and case managers for Samtskhe Javakheti region | In progress | July 2019 | 22 July 2019 | Natalia GAMGEBELI | With deadline 5 of September. 4 functional assessment specialists; 4 case managers and 3 Coordinating doctors will be recruted in Samtskhe Javakheti region
Translate, adjust and consolidate the training program and materials for the specialists | Has not started | July 2019 | September 2019 | Audrius BITINAS, Natalia GAMGEBELI with GASW and UNICEF | UNICEF has shared the training material with AFD/Expertise France. Two training sessions about personal rehabilitation for PWD and management of social evaluation of patients will be added to the original training.
Creating the recruitment commission and proceeding to interviews | Has not started | September 2019 | September 2019 | Expertise France; local authorities; GASW | 9-11 of September 2019
Contract with the functional assessment specialists and case managers and equip them with 8 tablets | Has not started | September 2019 | September 2019 | Expertise France; GASW
Provide the initial trainings to the specialists in Akhaltsikhe | Has not started | September 2019 | November 2019 | Expertise France; GASW with local experts | 16 of September - 16 of November
Provide trainings to the medical doctors involved in the disability status determination. | Has not started | September 2019 | 1 month | Yannick Deimat/ Medical expert??? | Trainings will raise awareness of the medical doctors to promote functional assessment within the pilot. Delivering information and training to medical centers staff; Promote their participation in the pilot of the system - compare the health conditions of the claimants to the results of the functional assessments | A112
Organise exchange of experience between Adjara and Samtskhe Javakheti region | Has not started | November 2019 | December 2019 | UNICEF/Expertise France | Transport costs covered
insure the necessary spece for FAS and CM into medical centres | Has not started | November 2019 | December 2019 | UNICEF/Expertise France
Provide the professional supervision/coaching to the functional assessment specialists and to case managers | Has not started | November 2019 | December 2020 | Expertise France; GASW
Insure the necessary spece for FAS and CM for reegular meetings of specialists | Has not started | November 2019 | December 2019 | UNICEF/Expertise France
Organisation of regular meetings (At least once a month) | Has not started | November 2019 | December 2020 | Expertise France; GASW
Process the data entered in web host | Has not started | November 2019 | December 2020 | Local experts | The electronic data collected by functional assessment specialists and case managers shall be extracted so they can be analysed by a statistician and a specialist of handicap scales.
Policy initiatives and evaluation of the interim and final results of the pilot
Definition of data necessary for policy impact assessment based on the results of piloting in the two Georgian regions. | In progress | May-June 2019 | 2 month | Michel Villac and Yannick Deimat |  | A113
Development of dictinary of data | Has not started | August 2019 | September 2019 | Michel Villac and Yannick Deimat
3 month of collected data analyzed. Andrei, Michel and one specialist of handicap scale | Has not started | January 2020 | January 2020 | Michel Villac, Andrei Tretyak and one specialist of handicap scale | 15 days/international experts | A113
Mid-term of collected data analyzed. | Has not started | April 2019 | April 2019 | Michel Villac, Andrei Tretyak and one specialist of handicap scale | 15 days/international experts | A113
Impact assesment. 2 missions. | Has not started | November 2020 | December 2020 | Michel Villac and Andrei Tretyak | 15 days/international experts | A113
Develop the set of indicators for monitoring and evaluation of the pilot process. Evalution will include the feedback from adults with disabilities, parents of children with disabilities and children with disabilities | Has not started | November 2020 | December 2020 | Team Leader, Michel Villac, Yannick Deimat and another expert
The simulation model will be developed based on pilot data of the two regions. | Has not started | September 2020 | December 2020 | Michel Villac/Yannick Deimat/International expert |  | A113
This analysis will be the result of the results of the three evaluations realized throughout the project. | Has not started | September 2020 | December 2020 | Michel Villac/Yannick Deimat/International expert |  | A113
Establish the regional group composed by the representatives of the Ministry of Health and Social Affairs of Samtskhe Javakheti region, the city of Borjomi, three health institutions, Disabled Persons Organizations, Social Service Agency,etc. | Has not started | September 2019 | 1 month | Team Leader | In order to introduce the project, a meeting was organized by MoIDPOTLHSA in April 2019 with these institutions. Representatives from these institutions shall be part of the institutional steering group to be created. | A112
Arrange the regional group meetings to support and assess the pilot in Samtskhe Javakheti region. | Has not started | September 2019 | December 2020 | Team Leader | The institutional streering group shall meet 3 times throughout the project: When the experimentation starts, for mid-term and final evaluations. | A112
Arrange the regular working group meetings to evaluate the assessment process - instruments, interviewing process, feedback from the respodents | Has not started | October 2019 | November 2019 | MoIDPOTLHSA/Expertise France/UNICEF/GASW |  | A112
Prepare a report on piloting note according to the findings of the pilot process - analyze who will be included and excluded in the system, the administrative costs of the new system; establishment of indicators | Has not started | November 2019 | December 2019 | Expertise France |  | A112
Communication and public awareness
Prepare/adjust the brochures explaining a role of functional assessment and pilot | Has not started | August 2019 | September 2019 | Local experts |  | A112
Prepare written consents for the respondents | Has not started | August 2019 | September 2019 | Local experts |  | A112
Meetings with Disabled Persons Organizations, associations of parents of children with disabilities, service beneficiaries | Has not started | September 2019 | December 2019 | Local experts |  | A112