ROLLING WORK-PLAN No 1 TO TWINNING GRANT CONTRACT Twinning Project “Improving the standards of employment conditions/relations as well as health and safety at work in Georgia“ Twinning number: GE 17 ENI OT 02 19 WORK-PLAN AND BUDGET FOR THE PERIOD: 7 October - 30 May 2020

Contracting Authority

Delegation of the European Union to Georgia

38 Nino Chkheidze ST.

0102 Tbilisi, Georgia

General remark:

This Initial Work Plan issues from the Twinning Proposal “Improving the standards of employment conditions/relations as well as health and safety at work in Georgia”, which is an Annex 02b of the Twinning Grant Contract No. ENI/2019/409 - 668, taking into consideration rules of the Twinning Manual (revision 2017 - update 2018) and its Annex C15: Template for rolling work-plan.

According to the Twinning Manual (revision 2017 - update 2018), Section 5.2, the key initial task of the Project is elaboration of the initial work-plan, which is considered the first rolling work-plan covering at least the first six months. This initial rolling work-plan is the basis for the effective and timely implementation of the whole project. It stipulates detailed description of particular project activities, methods of their implementation, indicators, human resources and timing saturation.

ARTICLE 1: Objective

The Member State Project Leader Mr. Branislav Ondruš and the Beneficiary Project Leader Mrs. Tamila Barkalaia hereby notify the Contracting Authority of the detailed work-plan and budget of the above-mentioned Twinning Grant Contract for the 7-month period from 7 October through 30 May 2020.

ARTICLE 2: Tasks (Inputs)

Budget Heading - RTA and related expenses

Sub-heading RTA

Sub-heading RTA Assistant (s)

Indicators and benchmarks agreed:

-  timely and correct implementation of project activities in accordance to initial work plan

ensured

-  administrative management and mission backstopping, as well as translation and

interpretation services ensured by RTA assistants

Budget Heading – Horizontal costs

Sub-heading Work plan preparations and Steering Committees

Sub-heading Communication and Information

Sub-heading

Indicators and benchmarks agreed:

- Initial WP is prepared and signed

- SCM is conducted to TW regulations

- Communication and visibility plan are prepared and annexed to the IWP (see Annex 1)

The first Project Steering Committee meeting will be held on 28th November 2019 in accordance with the instructions of the actual Twinning Manual. This initial rolling work-plan will be discussed and approved at the PSC meeting

The second PSC meeting is planned in March 2020, presenting the results of quarterly period 28th November – 27th February 2020, and approving the extended work-plan of the next 3 months.

The initial rolling plan has been prepared during the initial period.

Budget Heading – Horizontal costs

Sub-heading Communication and Information

Indicator(s) and benchmark(s) agreed: Work plan plus Communication and Visibility plan preparation

Budget Heading - Mandatory Results / Components

Component 1: Approximation of primary and secondary legislation related to Labour Law, Gender Equality, and Occupational Safety and Health in accordance with the Union acquis

Indicator/benchmark agreed

- Number of the Tables of Concordance prepared for the Labour Law acquis, including aspects of labour inspection system;

- List of amendments to be made in the Georgian primary and secondary labour legislation specified with explanatory notes;

- List of amendments to be made in the Georgian primary and secondary legislation on Gender Equality acquis specified with explanatory notes;

- Share of staff from relevant public institutions who are fully informed on regulatory and fiscal impact of changes in labour law and gender equality acquis;

- Availability of quality checked translation of the OSH acquis with clear technical terminology (if necessary);

- Availability of the Tables of Concordance prepared for the OSH acquis, including aspects of labour inspection system;

- Available list of amendments to be made in the Georgian primary and secondary OSH legislation specified with explanatory notes;

- Share of staff from relevant public institutions who are fully informed on regulatory and fiscal impact of changes in OSH acquis.

Activity 1.1.1: Aligning Georgian legal framework on labour law, including aspects of labour inspection system, amended in compliance with the Union acquis

Method

The objective of this activity is providing support of the BC staff and relevant stakeholders to the transposition of the provisions of the relevant EU Directives in the field of labour legislation into a national legislation.

During preparation of the initial work-plan the current state of play related to the approximation of EU directives to be covered by the TW project during its implementation has been discussed between the representative of the BA, Ms. Lika Klimiashvili, Head of the Labour and Employment Policy and Collective Labour Disputes Division and with RTA and both Component Leaders. Almost all EU directives in the field of labour law which should be aligned in 2018 and 2019 as per AA/DCFTA has already passed through the transposition process thanks to the support of new ILO project for improving legislative reforms in areas of labour law and OSH.

Moreover, the draft amendments of the labour code are currently available in the Georgian language and with support of donor community the public discussions were launched on 22 October 2019. A consultation process was initiated by the Georgian Parliament through a set of round tables presenting new legal and institutional mechanisms being introduced into the Labour Code of Georgia.  Different donors have facilitated an ongoing consultation process through organising thematic discussions of norms related to the individual chapters of the amended labour code.

To support the EUD in elaboration of its position/messages and approach to the labour code´s discussions a comprehensive assessment of proposed amendments of the Labour Code of Georgia will be conducted during the implementation of the initial work plan by the short term experts with the aim to ensure the scope of their alignment to the relevant EU acquis and supporting Georgian authorities in inclusive discussion and approval process.

Taking into consideration the current state of play as described above, there is only one EU Directive left from the package of 8 EU Directives (to be adopted in 2018 – 2020 as per AA/DCFTA) which has not been transposed and will be dealt with during the implementation of this initial work plan:

- 91/383/EEC supplementing the measures to encourage improvements in the safety and health at work of workers with a fixed-duration employment relationship or a temporary employment relationship.

This activity will be focused on applying the general concept of transposition process, in accordance with the following pattern:

- The process of setting up of formal or non-formal Technical Working Group (standardised or flexible approach) will be discussed at the first working group meeting focused on the alignment of the first directive to be implemented. The STE will join the working groups proposed by the beneficiary and will support them in any phase of the process.

- Survey of Georgian legislation comparing if there are any provisions similar to those of the respective EU Directive.

  - Research of national legislation, comparing if there are any provisions similar to the relevant Directive, recording the findings into the Initial Comparative Table, which enable to analyse wording of particular provisions of EU Directive with text of various up-to-date national regulations and analyse the compliance (concordance).

  - Developing the list of primary and secondary legislation related to labour and other laws that should be revised.

  - Assessing the degree of compliance of existing primary and secondary legislation of Georgia with EU standards and requirements in the relevant field of law. According to the structure of missing provisions, it can be recommended to ensure transposition of respective directive either through revision and amendment of existing national regulation or through development of a new regulation.

- Introductory meeting of TWG – provided technical and legal information for WG members on the topic of respective directive, and introduction of EU best practice. During this meeting also the structure, concept and content of new Regulation (if needed) proposed by the TW expert is discussed. Drafting the first proposal of the text of the amendment of particular laws on the basis of comparative analysis of current legislation and a discussion at the 1st meeting and implementing good practice. This introductory workshop of the Technical Working Group will be focused on:

  - Providing basic information on the procedure of transposing process, principles of respective EU Labour Law Directive, technical and legal base of the topic of directive, results of comparative analysis and a proposal of the concept, structure and content of a new regulation (if needed), or amendments of the current law.

  - Based on the assessment, at the 2nd TWG meeting the text of the first draft - article by article in the Georgian language would be verified. The development of the amended text or a new regulation/amendments of the law will be discussed, fine-tuned and completed by the TWG during the 2nd or 3rd TWG meeting ensuring the inclusive progress and in agreement with corresponding stakeholders. Finalisation of the text, verification from the technical point of view and terminology. The English final version shall be fine-tuned by the twinning experts.

  - Team of BC experts will assist in elaboration of the accompanying documents, such as explanatory notes, regulatory and fiscal impact assessments, ‘Table of Concordance’, compliance with international legal standards, and other documents according to the Georgian legislative rules.

- STE will provide support throughout the consultation and approval process of the relevant legislation in the Georgian Parliament (e.g. assessment of new proposals and changes, suggestions of alternatives).

- During the whole transposition process the participation of following departments, institutions and partners are considered essential in the implementation of this activity: MoIDPLHSA - Labour and Employment Policy and Collective Labour Disputes Division; Labour Conditions Inspecting Department; representatives of social partners; representatives of donors; the Tripartite Social Partnership Commission (TSPC);

Moreover, additional missions will be allocated to the development of the Assessment Report and will cover the following EU Directives to be adopted in 2018, 2019 and 2020 as per AA/DCFTA:

- 91/533/EEC on an employer's obligation to inform employees of the conditions applicable to the contract or employment relationship

- 1999/70/EC concerning the framework agreement on fixed-term work concluded by ETUC, UNICE and CEEP

- 97/81/EC concerning the Framework Agreement on part-time work concluded by UNICE, CEEP and the ETUC - Annex: Framework agreement on part-time work

- 2002/14/EC establishing a general framework for informing and consulting employees in the European Community - Joint declaration of the European Parliament, the Council and the Commission on employee representation

- 2001/23/EC on the approximation of the laws of the Member States relating to the safeguarding of employees' rights in the event of transfers of undertakings, businesses or parts of undertakings or businesses

- 98/59/EC on the approximation of the laws of the Member States relating to collective redundancies

- 2003/88/EC concerning certain aspects of the organisation of working time

Resources

- Member State human resources needed: 8 MS experts, 75 WDs / 15 missions

- Beneficiary administration human resources: all together around 20; staff of the Labour and Employment Policy and Collective Labour Disputes Division of MoIDPHLSA, Labour Conditions Inspecting Department, Technical working group members; social partners and other relevant stakeholders; specialists/ experts from the relevant institutions on the topic

- Other resources: Translation of amendments of the Labour Code, 100 pages

Activity 1.2.1: Analysis / Assessment of current legal framework on non-discrimination and gender equality including aspects of Labour Inspection System, in order to amend it in compliance with the EU aquis

Method

The objective of this activity is providing support of the BC staff and relevant stakeholders to the transposition of the provisions of the relevant EU Directives in the field of non-discrimination and gender equality legislation into a national legislation.

During preparation of the initial work-plan the current state of play related to the approximation of EU directives to be covered by the TW project during its implementation has been discussed between the representative of the BA, Ms. Lika Klimiashvili, Head of the Labour and Employment Policy and Collective Labour Disputes Division and with RTA and both Component Leaders. All EU directives in the field of non-discrimination and gender equality which should be aligned in 2018 and 2019 as per AA/DCFTA have already passed through the transposition process thanks to the support of new ILO project for improving legislative reforms in areas of labour law, non-discrimination and gender equality and OSH.

Moreover, the draft amendments of the labour code are currently available in the Georgian language and with the support of donor community the public discussions were launched on 22 October 2019. A consultation process was initiated by the Georgian Parliament through a set of round tables presenting new legal and institutional mechanisms being introduced into the Labour Code of Georgia.  Different donors have facilitated an ongoing consultation process through organising thematic discussions of norms related to the individual chapters of the amended labour code.

To support the EUD in elaboration of its position/messages and approach to the labour code´s discussions a comprehensive assessment of proposed amendments of the Labour Code of Georgia will be conducted during the implementation of the initial work plan by the short term experts with the aim to ensure their alignment to the relevant EU acquis and supporting Georgian authorities in inclusive discussion and approval process.

Taking into consideration the current state of play as described above, there are only 2 EU Directive left from the package of 6 EU Directives (to be adopted in 2018 – 2020 as per AA/DCFTA) for which the scope of the transposition has to be assessed and will be dealt with during the implementation of this initial work plan:

- 2004/113/EC implementing the principle of equal treatment between men and women in the access to and supply of goods and services

- 79/7/EEC on the progressive implementation of the principle of equal treatment for men and women in matters of social security

Moreover, additional missions will be allocated to the development of the Assessment Report and will cover the following EU Directives to be adopted in 2018, 2019 and 2020 as per AA/DCFTA:

- 2000/43/EC implementing the principle of equal treatment between persons irrespective of racial or ethnic origin

- 2000/78/EC establishing a general framework for equal treatment in employment and occupation

- 2006/54/EC on the implementation of the principle of equal opportunities and equal treatment of men and women in matters of employment and occupation

- 92/85/EEC on the introduction of measures to encourage improvements in the safety and health at work of pregnant workers and workers who have recently given birth or are breastfeeding (tenth individual Directive within the meaning of Article 16(1) of Directive 89/391/EEC).

This activity will be focused on applying the general concept of transposition process, in accordance with the following pattern:

- The process of setting up of formal or non-formal Technical Working Group (standardised or flexible approach) will be discussed at the first working group meeting focused on the alignment of the first directive to be implemented. The STE will join the working groups proposed by the beneficiary and will support them in any phase of the process.

- Survey of the Georgian legislation comparing if there are any provisions similar to those of the respective EU Directive.

  - Research of national legislation, comparing if there are any provisions similar to the relevant Directive, recording the findings into the Initial Comparative Table, which enable to analyse the wording of particular provisions of the EU Directive with text of various up-to-date national regulations and analyse the compliance (concordance).

  - Developing the list of primary and secondary legislation related to labour and other laws that should be revised.

  - Assessing the degree of compliance of the existing primary and secondary legislation of Georgia with EU standards and requirements in the relevant field of law. According to the structure of missing provisions, it can be recommended to ensure transposition of the respective directive either through revision and amendment of the existing national regulation or through development of a new regulation.

- Introductory meeting of TWG – provided technical and legal information for WG members on the topic of respective directive, and introduction of EU best practice. During this meeting also the structure, concept and content of new Regulation (if needed) proposed by the TW expert is discussed. Drafting the first proposal of the text of Regulation on the basis of comparative analysis of current legislation, a discussion at the 1st meeting and implementing good practice. This introductory workshop of the Technical Working Group will be focused on:

  - Providing basic information on the procedure of transposing process, principles of the respective EU non-discrimination and gender equality directive, technical and legal base of the topic of directive, results of comparative analysis and a proposal of the concept, structure and content of a new regulation (if needed), or amendments of the current law.

  - Based on the assessment, at the 2nd TWG meeting the text of the first draft - article by article in the Georgian language would be verified. The development of the amended text or a new regulation will be discussed, fine-tuned and completed by the TWG during the 2nd or 3rd TWG meeting ensuring the inclusive progress and in agreement with the corresponding stakeholders. Finalisation of the text, verification from the technical point of view and terminology. The English final version shall be fine-tuned by the twinning experts.

  - Team of BC experts will assist in elaboration of the accompanying documents, such as explanatory notes, regulatory and fiscal impact assessments, ‘Table of Concordance’, compliance with international legal standards, and other documents according to the Georgian legislative rules.

- STE will provide support throughout the consultation and approval process of the relevant legislation in the Georgian Parliament (e.g. assessment of new proposals and changes, suggestions of alternatives).

- During the whole transposition process the participation of the following departments, institutions and partners are considered essential in the implementation of this activity: MoIDPLHSA - Labour and Employment Policy and Collective Labour Disputes Division; Labour Conditions Inspecting Department; representatives of social partners; representatives of donors; the Tripartite Social Partnership Commission (TSPC);

Resources

- Member State human resources needed: 3 MS experts, 25 WDs / 5 missions

- Beneficiary administration human resources: all together around 20; staff of the Labour and Employment Policy and Collective Labour Disputes Division of MoIDPHLSA, Labour Conditions Inspecting Department, Technical working group members; social partners and other relevant stakeholders; specialists/ experts from the relevant institutions on the topic

- Other resources: 0

Activity 1.3.1: Aligning Georgian legal framework on Occupational Health and Safety, including aspects of Labour Inspection System, amended in compliance with the Union acquis:

Method

The objective of this activity is providing support of the BC staff and relevant stakeholders to the transposition of the provisions of the relevant EU Directives in the field of non-discrimination and gender equality legislation into a national legislation.

During preparation of the initial work-plan the current state of play related to the approximation of EU directives to be covered by the TW project during its implementation has been discussed between the representative of the BA, Mr. Beka Peradze, RTA Counterpart and the Head of the Labour Inspecting Conditions Department and Mr Levan Abashidze and with RTA and both Component Leaders. Out of total number of 15 OSH Directives to be implemented in the period of 2018 – 2022, 2 of them have already been aligned to.

Taking into consideration the current state of play, there are 4 EU Directives from the package of 15 EU Directives (to be adopted in 2019 – 2020 as per AA/DCFTA) which have been identified as a priority to be transposed and will be dealt with during the implementation of this initial work plan:

- 89/656/EEC on minimum safety and health requirements for the use of personal protective equipment

- 92/58/EEC on minimum requirements for the provision of safety and health and/or health sign at work.

The Assessment Report ongoing in act. 1.1.1 and 1.1.2.  will cover in this activity the following EU Directives to be adopted in 2019 as per AA/DCFTA:

- 89/391/EEC on the introduction of measures to encourage improvements in the safety and health of workers at work (EU Framework Directive)

This activity will be focused on applying the general concept of transposition process, in accordance with the following pattern:

- The process of setting up of formal or non-formal Technical Working Group (standardised or flexible approach) will be discussed at the first working group meeting focused on the alignment of the first directive to be implemented. The STE will join the working groups proposed by the beneficiary and will support them in any phase of the process.

- Survey of Georgian legislation comparing if there are any provisions similar to those of the respective EU Directive.

  - Research of national legislation, comparing if there are any provisions similar to the relevant Directive, recording the findings into the Initial Comparative Table, which enable to analyse wording of particular provisions of EU Directive with text of various up-to-date national regulations and analyse the compliance (concordance).

  - Developing the list of primary and secondary legislation related to labour and other laws that should be revised.

  - Assessing the degree of compliance of existing primary and secondary legislation of Georgia with EU standards and requirements in the relevant field of law. According to the structure of missing provisions, it can be recommended to ensure transposition of the respective directive either through revision and amendment of existing national regulation or through development of a new regulation.

- Introductory meeting of TWG – provided technical and legal information for WG members on the topic of respective directive, and introduction of EU best practice. During this meeting also the structure, concept and content of new Regulation (if needed) proposed by the TW expert is discussed. Drafting the first proposal of the text of Regulation on the basis of comparative analysis of current legislation, a discussion at the 1st meeting and implementing good practice. This introductory workshop of the Technical Working Group will be focused on:

  - Providing basic information on the procedure of transposing process, principles of the respective EU non-discrimination and gender equality directive, technical and legal base of the topic of directive, results of comparative analysis and a proposal of the concept, structure and content of a new regulation (if needed), or amendments of the current law.

  - Based on the assessment, in the 2nd TWG meeting the text of the first draft - article by article in Georgian language would be verified. The development of the amended text or a new regulation will be discussed, fine-tuned and completed by the TWG during the 2nd or 3rd TWG meeting ensuring the inclusive progress and in agreement with corresponding stakeholders. Finalisation of the text, verification from the technical point of view and terminology. The English final version shall be fine-tuned by the twinning experts.

  - Team of BC experts will assist in elaboration of the accompanying documents, such as explanatory notes, regulatory and fiscal impact assessments, ‘Table of Concordance’, compliance with international legal standards, and other documents according to the Georgian legislative rules.

- STE will provide support throughout the consultation and approval process of the relevant legislation in the Georgian Parliament (e.g. assessment of new proposals and changes, suggestions of alternatives).

- During the whole transposition process the participation of the following departments, institutions and partners are considered essential in the implementation of this activity: MoIDPLHSA - Labour and Employment Policy and Collective Labour Disputes Division; Labour Conditions Inspecting Department; Technical and Construction Supervision Agency (TCSA), MoESD; The Tripartite Social Partnership Commission (TSPC); Representatives of social partners;

Resources

- Member State human resources needed: 4 MS experts, 60 WDs /12 missions

- Beneficiary administration human resources: around 30; Staff of the Labour Conditions Inspecting Department of MoIDPHLSA, Technical working group members; social partners and other relevant stakeholders

- Other resources: Translation of Directives and relevant texts, 40 pages

Component 2: Capacity building, inter-institutional cooperation, and awareness raising of relevant state authorities and private sector for full implementation of amended legislation in labour law, gender equality and OSH

Indicator/benchmark agreed

- Functional review of the relevant state authorities to implement changes, including human and financial resources, administrative structures and equipment needed;

- Training needs analysis and plan of the whole staff of beneficiary department and representatives from other relevant institutions listed;

- Share of BA staff who received training to implement necessary changes and the representatives from other relevant institutions listed;

- Number of labour inspectors who are trained more to become ‘trainers’ with full knowledge and competency in implementing the new laws;

- Plan for improving institutional operations and procedures of the relevant state authorities to support their pilot implementation, each with clear competences and coordination roles;

- Number of written operational guidelines, manuals and procedures required to implement all changes, explaining all steps of implementation to the relevant staff;

- Number of OSH online Glossary and Risk Assessment checklists and their dissemination to relevant parties;

- Number of elaborated promotional materials and public information campaigns in printed and online media, TV and other tools;

- Share of private companies (i.e. both employers and workers) which are informed and number of citizens reached out on the new rules and changes made in labour legislation;

- Proposal for a structure of inter-institutional cooperation and working procedures, with a review of existing options;

- Working groups operational with team members from relevant institutions with a clear mandate and their continuous involvement in the “Technical Working Group” and “Coordination Group”.

Activity 2.1.1. Assessment of the administrative structures and institutional capacities of the beneficiary and relevant stakeholders and improvement of their inter-institutional operation

Method

The objective of this activity is focused on mapping and assessment of the administrative structures and the institutional capacities of the beneficiary including relevant stakeholders with the aim to improve their inter-institutional cooperation and capacity building for full implementation of amended legislation in the field of labour, non- discrimination and labour equality.

The assessment will be presented in the form of functional review, main purpose of which is to pave the way to improvement of inter-institutional cooperation and capacity building to be ready for the full implementation of approximation process. In particular, to determine the strategic goals that would affect the human resources involved in approximation process, to understand the current regulatory environment regarding the human resources in public service and modify management process (including human, financial resources, administrative structures and equipment, if needed).

Stages and steps to be followed in conducting the functional analysis:

- desk research to overall understanding of the public administration reform process in Georgia so that we could place our analysis and recommendations in an appropriate context;

- practice of general operational and human resource management functions at all levels (vertical and horizontal);

- initial workshop with the relevant representatives of the BC and stakeholders;

- elaboration of methodological approach and tool for collection of relevant information;

- semi-structural interviews will be prepared and conducted with the different management staff levels with the purpose to gather new information from different staff representatives and to validate collected data;

- training needs analysis will be part of this assessment as well;

- if appropriate, on-line questionnaire will be prepared using google instrument;

- analysing and processing the gathered information/data;

- elaboration of Functional Review Report with a set of recommendations for management/administrative, financial resources and operational changes including the scenario for possible institutional arrangements;

- workshop will be organized with the purpose to share and discuss with the representatives of BC and relevant stakeholders from central level the draft recommendations, scenarios for possible institutional arrangements formulated in the Action Plan.

Resources

Member State human resources needed: 5 MS experts, 55 WD/11 missions

- Beneficiary administration human resources: around 30; Staff of the Labour Conditions Inspecting Department of MoIDPHLSA, staff of the Labour and Employment Policy and Collective Labour Disputes Division of MoIDPHLSA; social partners and other relevant stakeholders

- Other resources: 0

Activity 2.1.2. Training needs analysis and strengthening the institutional capacity of the beneficiary and relevant stakeholders

Method

By signing the AA/DCFTA Georgia has to adapt to an enormous number of changes in a very short time. Civil servants are faced with the constantly changing or new regulatory framework which needs implementation and enforcement, as well as new demand from the growing private sector. These challenges can only be met if the staff (civil servants) are highly qualified and constantly updating their qualification. The functional review conducted within activity 2.1.1. will be complemented by the training need analysis (TNA), focused on defining the performance gap. This is what has to be filled by training and enables beneficiary to make informed decisions regarding the training and develop programs for both the management and staff in order to meet any organizational needs and requirements in the execution tasks related to full implementation of the (to be) amended legislation.

The training plan covering the beneficiary staff and representatives of the relevant institutions will be developed with each individual institution.

Resources

Member State human resources needed: 5 MS experts, 35 WD/ 7 missions

- Beneficiary administration human resources: Staff of the Labour Conditions Inspecting Department of MoIDPHLSA, social partners and other relevant stakeholders

- Other resources: translation of the directives (to be calculated)

Activity 2.1.3

Delivery of Training of Trainers of the labour inspectors

Method

- The activity is focused on the development of a specific Training Programme for labour inspectors to cover the immediate current need for enforcement of new legislation and implementation of new working methods and instructions. The developed training programme will be based on the principle of Training of Trainers and follow-up training for labour inspectors. Good practice examples confirm that inspectors shall be trained in their mother language, by local trainers to ensure better understanding which finally will contribute to the sustainability of the project outcomes after the completion of the project.

- The rationale of this ToT is to train general trainers for all presented themes, nevertheless it is a possibility to continue in specialisation on selected topics, according to the interest and experiences of particular inspectors-trainers.

- The candidates for trainers will be identified through the preliminary screening process using some broad criteria for their selection. The success of the Training of Trainers will depend on the candidates’ professional and social skills, and their readiness for training. The following set of criteria for the selection process might be proposed for consideration: a) Qualifications and experience, b) Technical knowledge, c) Personal characteristics and skills.

- Trainers of labour inspector will obtain training materials for delivering their training (curricula and PPTs).

- The course will be complemented by examinations of Trainers of Inspectors, and awarding by certificates .

- At least 8 initial follow-up training courses for labour inspectors, delivered by the new trainers will be mentored by trainers of trainers.

- MS trainers will train a group of selected of maximum 10 labour inspectors. The course will consist of 30 days in the period of 8 months), covering training skills, technical issues, legislation issues, and organisational issues, as well as practical exercises and case studies of OSH procedures (the training model can be modified according to the recommendations and the needs of beneficiary). The training courses will be complemented by individual study of related documents and legislative acts.

- During this initial working plan period the training will cover first 10 days of ToT training

Resources

Member State human resources needed: 3 MS experts, 45 WD/ 9 missions

- Beneficiary administration human resources: 10 trainers; Staff of the Labour Conditions Inspecting Department of MoIDPHLSA, social partners and other relevant stakeholders

- Other resources: 0

Activity 2.1.4. Delivery of comprehensive training programmes to improve the institutional capacities of the beneficiary and relevant

Method

- New harmonised OSH legislation, new methodologies and guidelines, as well as new challenges for acting of beneficiaries’ staff involved in the approximation process as well as for labour inspectors require to provide specific broadly designed training with the aim of equal implementation, performance and enforcement.

- Currently, a recruitment process of new inspectors is ongoing and the initial training for at least 60 new inspectors was indicated as a high priority by the beneficiary. The initial training for newly hired inspectors will be organized in the period of February – May, and advanced training for 25 inspectors already working as inspectors will be organized during the same period as well.

- Our team is prepared to develop an appropriate specific Training Programme covering current and new adopted legislation, and some inspection working methods.

- The Training Programme (curriculum) will be developed by the project team using permanent feedback of the MoIDPLHSA, labour inspection management and the working groups involved in the process.

- The following tentative training modules for initial/refreshment training could cover the following topics:

- General skills:

Communication skills

Time management skills

- Legal framework:

OSH Framework

Risk assessment for undertakings and for Labour Inspectors (monitoring check lists)

Workplace, Work equipment, PPE

Working time and leave

Working time and flexible pattern of work

Anti-discrimination and equal treatment agenda

Technical reglaments, already existing, new and forthcoming

- Sectors to be covered:

    - Construction

    - Service

    - Mining

    - Metallurgy

    - HORECA

- Advanced and systematic training:

  - Theory training to be agreed during the TNA

  - Exam /test about theory training

  - On site practice / visits with veteran BC labour inspectors

  - Feedback

  - Exam / test on practical training

  - Global sum up exam / test including (theory, practice, administrative issues, etc.)

- Trainings will be delivered each last weeks of February, March, April/May.

Resources

Member State human resources needed: 5 MS experts, 65 WD / 13 missions

- Beneficiary administration human resources: Staff of the Labour Conditions Inspecting Department of MoIDPHLSA,

- Other resources: 0

Activity 2.2.1. Development of the relevant guidelines, labour inspection manuals, checklists and other tools to improve the institutional operations and procedures focused on precise implementation of newly adopted legislation

Method

The success of labour inspection performance depends on a good management, clear instructions, strict rules and standardised procedures. All processes shall be described and available for all inspectors and other relevant staff involved in the implementation of the newly adopted legislation. Therefore, suitable manuals and guidelines are essential.

During these implementation period we will focus on development of operational guidelines and the check lists of the prioritised OSH Directives to be implemented and adapted to Georgian legal framework:

- Directive 89/656/EEC on minimum health and safety requirements for the use by workers of personal protective equipment at the workplace

- Directive 92/58/EEC on minimum requirements for the provision of safety and/or health signs at work.

Resources

Member State human resources needed: 4 MS experts, 40 WD / 8 missions

- Beneficiary administration human resources: Staff of the Labour Conditions Inspecting Department of MoIDPHLSA, social partners and other relevant stakeholders

- Other resources: 0

Activity 2.2.2. Preparing and implementing public information campaign aiming to raise awareness among the project among key stakeholders, public, private sector and civil society

Method

- Public awareness raising campaigns are an effective tool for increasing awareness of the private sector and citizens (companies, employers and workers) about legal changes, new requirements and practices, promoting occupational safety and health at the workplaces, increasing of awareness and motivation of employers and employees, as well as building a positive attitude of public. The project team attaches significance to this activity due to its comprehensive coverage and possibility of effective influence.

- In order to ensure the targeted information will reach the target groups during the public information campaign we envisaged to implement look for results of surveys implemented  by some institutions. If there are no similar sources available a simple google electronic questionnaire can be elaborated and disseminated to recipients. The questionnaire will provide us a feedback about the current situation, what type of messages should be communicated to the different target groups and what are the most requested channels for communication. Having this initial information, we can develop the concept note for the preparation of campaign to be discussed with the BC.

- The campaign programme will be developed in cooperation with a working group nominated by the LCID, involving also social partners and other stakeholders. It is an intention to combine a topic of the official EU OSHA Campaign with presentation of new Georgian harmonised legislation, promotion of work culture and positive attitude to safety and health at work.

- The campaign programme will be proposed in the following areas:

- Information about legal changes, new requirements and good practice for different target groups -  companies, employers and workers

- Delivering of the OSHA campaign materials (hangers, leaflets, brochures, posters)

- An event remembering 28 April – World OSH Day

- Organizing debates in TV and Radio

- Broadcasting a TV spot for promotion OSH

- Development of leaflets and brochures on promotion OSH and their dissemination

- Visits of at least 3 companies as a good OSH practice – with media

- Press releases

- The activities will be coordinated with the ILO and social partners.

Resources

Member State human resources needed: 3 MS experts, 60 WD/12 missions

Beneficiary administration human resources: Staff of the Labour Conditions Inspecting Department of MoIDPHLSA, social partners and other relevant stakeholders

- Other resources: 4 500,- Eur (purchasing the broadcasting time on TV, radio)

Activity 2.2.3. Conducting study visits to Member states, focused for transfer of good practices on organisation and management of labour inspection

Method

- Any organised study visits are always the most effective forms of transfer of good practice and experiences. Planned study visit to an EU Member State is aimed at bringing new ideas and challenges for those who are building the Labour Conditions Inspecting Department.

- During that 7-month period, we are planning to organize a study visit for a group of 8 - 10 persons to Estonia

- The aim of the study visit will be to introduce them the system and organisation of Labour inspectorates in Estonia, especially their inspection policies, organisational structures, management methods, human resources policy, methods of planning, inspection methods, information system, training system, implementation of ESAW/EODS, and other issues interested by beneficiary.

- The complex programme of the study visit will be drafted together with the Georgian partners and agenda of the study visit will be discussed and agreed with LCID.

- After the study visit an evaluation in a form of “Study Visit Report” will be prepared and follow up exercise will be conducted by all participants.

Resources

Member State human resources needed:

- Beneficiary administration human resources: 5 BC experts, 1 interpreter

- Other resources: 0

ARTICLE 3: Risks

Specify/update the internal conditions related to the project that must be fulfilled to guarantee efficient and timely implementation and achievement of results.

| Risk | Corrective measures/ Mitigation |
| --- | --- |
| Unexpected national and international policy or jurisdiction changes affecting the objectives of the project, e.g. slowdown of structural reforms | Continuous policy monitoring in order to react early in project governance. Close and regular exchange between project partners. |
| Inadequate commitment and support from decision making level in particular with regard to adoption of amended legislation, draft acts, guidelines and procedures | Close and regular exchange between project partners, in particular PL, JPL and RTA. Involvement of (MoIDPHLSA) decision-makers in workshops, consultations and presentations of output. |
| Unsuccessful beneficiary administration´s reorganization | Close and regular cooperation and communication between project partners. Regular Project Steering Committee meetings to inform on upcoming changes and if needed agree on actions to be taken. |
| Delay in implementation of project activities | Sufficient human and technical resources allocated in BC and MS administrations. Sound and joint planning of initial work plan. |

ARTICLE 4: Schedule

| Project Month 2019/20 | October | Nov | Dec | Jan | Feb | March | April | May |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Horizontal costs |  |  |  |  |  |  |  |  |
| Steering Committee |  |  |  |  |  |  |  |  |
| Component 0 |  |  |  |  |  |  |  |  |
| Activity 0.1 Kick-off |  |  |  |  |  |  |  |  |
| Component 1 |  |  |  |  |  |  |  |  |
| Activity 1.1.1 |  |  |  |  |  |  |  |  |
| Activity 1.1.2 |  |  |  |  |  |  |  |  |
| Activity 1.1.3 |  |  |  |  |  |  |  |  |
| Component 2 |  |  |  |  |  |  |  |  |
| Activity 2.1.1. |  |  |  |  |  |  |  |  |
| Activity 2.1.2. |  |  |  |  |  |  |  |  |
| Activity 2.1.3. |  |  |  |  |  |  |  |  |
| Activity 2.1.4. |  |  |  |  |  |  |  |  |
| Activity 2.2.1. |  |  |  |  |  |  |  |  |
| Activity 2.2.2. |  |  |  |  |  |  |  |  |
| Activity 2.2.3. |  |  |  |  |  |  |  |  |

ARTICLE 5: Human Resources

| Member State or Beneficiary | Name | Present position | Employer | Years of experience | Education | Specialist knowledge | BC experience | Languages |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Slovakia 1 | JOSEF TOMAN | Director of the Legal department of the MoLSAF | Ministry of Labour, Social Affairs and Family, Slovakia | 17 | Comenius University of Bratislava | - Expert in industrial relations policy and practice; - Labour law and employment legislation, social dialog and collective bargaining; - Long-lasting experience with the transposition and implementation of the EU and the EP regulations and directives in the field of employment and social policy, social dialog and collective bargaining into the Slovak legislation | Slovak, English German | Serbia, Croatia, Romania, |
| Slovakia 2 | MAROS PALIK | Chief lawyer for labour relations | Regional Development Agency Senec-Pezinok, Slovakia | 16 | Faculty of Law, Comenius University, Bratislava, Slovak Republic | - Legal assistance in the field of labour law, labour law relations, individual and collective, anti-discrimination law - Legal analysis of labour legislation, anti-discrimination legislation and its alignment with the EC Directives related to labour relations acquis - Analysis of the labour code, occupational health and safety, employment, antidiscrimination, wage regulations and commitments arising from collective agreements, undeclared work - Member of the working group for amendment of the labour legislation in terms of undeclared work ( employment contract, fixed term part-time contract, atypical form of contracts, and development of the deterrence measures) | Slovak, English German | Georgia, Serbia |
| Slovakia 3 | IVAN MAJER | Advisor and Trainer | National Labour Inspectorate | 40 | Technical University, Faculty of Mechanical Engineering Kocise | - Profound knowledge, skills and experiences on occupational safety and health, prevention principles, risk assessment, - safety management, organisation of safety and health services, implementation of OSH legislation, OSH policies and OSH expertise | Slovak, English, Russian | Serbia, Croatia, Albania, Romania, Albania, Croatia, Kosovo, Turkish Cypriot Community, Turkey, Ukraine, Tunisia |
| Slovakia 4 | LAURENCIA JANCUROVA | Senior Inspector and the representative of Focal Point for European Agency for Health and Safety at Work | National Labour Inspectorate | 25 | Technical University, Faculty of Mining Engineering, Slovakia | - Profound experience in safety and health at work, prevention protection, risk management - unifying and rationalising of working methods of the labour inspectorates, - preparation of conceptual materials, programme materials and draft measures for improving the situation in the area of labour protection - development inspection manuals and instructions - implementation of OSHA activities at the national level | Slovak, English, Russian | Croatia, Albania, Romania, Albania, Croatia, Turkish Cypriot Community, Turkey, Ukraine, Tunisia |
| Slovakia 5 | Luba Pavlovova | Director/trainer | Regional Development Agency, Slovakia | 29 | Master in Engineering | - Highly experienced in implementing activities related to raising public awareness, management of several public campaigns - public awareness campaigns – preparation and implementation - development of the radio and TV spots, short documentary films, professional debate, round tables - training of trainers | English French Bulgarian Russian Serbian Croatian Czech Macedonian | Jordan, Croatia, Serbia, North Macedonia, BiH Romania Bulgaria Azerbaijan Albania Turkey Georgia |
| Slovakia 6 | Lubica turner | Trainer/methodologist | Regional Development Agency, Slovakia | 25 | Academic diploma MA in Education and Linguistics | - Extraordinary knowledge and professional skills in elaboration of training methodologies and evidence-based learning - Excellent trainer recognised at EU-level - Proven twinning experience in ToT in Serbia | English Serbian Croatian/Bosnian Russian French Macedonian | North Macedonia Croatia Monte Negro Jordan Serbia, Georgia |
| Croatia 7 | KRISTINA BALENOVIC | Legal Counsellor Specialist | Ministry of Labour and Pension System, Zagreb | 10 | Faculty of Law, Zagreb | - Knowledge and experience in necessary administrative structures and institutional capacities for the implementation of the relevant acquis | Croatian (native), English, Bosnian, Serbian, Slovene ,Spanish | Serbia, Montenegro Ukraine Portugal Slovenia |
| Croatia 8 | TOMISLAV MARKOTA | Legal Counsellor | National Labour Inspectorate, Zagreb | 10 | Faculty of Law, Zagreb | - Knowledge and practical experience in working in the EU approximation field | Croatian (native), English, Italian | Serbia, Montenegro |
| Hungary 9 | TAMAS BERKY | Management Counsellor | Regional Development Agency Senec-Pezinok, Slovakia | 19 | Corvinus University, School of Management, | - Extensive experience in training needs analysis (TNA), development of competency systems and competency based training and education programmes, as well as development of curricula, training methodology support, training delivery and evaluation | English Spain | Georgia Serbia Croatia Romania |
| Croatia 10 | ZDRAVKO MURATTI | Dep. Director of OSH Department | Ministry of Labour and Pension System, Zagreb | 32 | Faculty of Mechanical Engineering and Naval Architecture, Zagreb | - Proven working experience in alignment of the Croatian OSH legislation with EU acquis, - Knowledge and experience of drafting OSH legislation, including regulatory impact assessment, costing and inter-institutional coordination, - preparation of conceptual materials, programme materials and draft measures for improving the situation in the area of labour protection, developing good practice solutions for strengthening capacities to protect workers’ health, reducing of work relate accidents, - Member of the Focal Point EU-OSHA, - drafting opinion on legal OSH provisions; provide explanations to workers, employers, trade unions and employers association; monitoring judicial practice in OSH issue; providing opinion on drafts and proposed regulations form other government bodies. | English | Croatia |
| SPAIN 11 | concepción pascual lizana | Team Leader Labour and Social Security Inspector | Labour and Social Security Inspectorate of Spain State Agency. (Ministry of Labour, Migrations and Social Security) | 34 | Law degree | - Transposition of EU Directives on OSH. - Occupational Safety and Health. - Labour relations. - Social Partners. - 2008 – 2012 Director National Institute Safety and Health at Work (INSST) of Spain. - EU OSHA governing board member. - ACSH member. | English French | Ecuador |
| SPAIN 12 | consuelo manchón garcía | Labour and Social Security Inspector | Labour and Social Security Inspectorate of Spain State Agency. (Ministry of Labour, Migrations and Social Security) | 20 | Political Science and Sociology | - Occupational Safety and Health. - Labour relations. - Social Partners. - 2007 – 2019, Chief OSH Unit Labour and Social Security Inspectorate, Albacete. - 2005 – 2007, Associate professor, Law Universidad Castilla – La Mancha. Teacher LSSI School. - 2009, external consultor ILO, “enhancing LI effectiveness”, FYR Macedonia. - 2010, SLIC exchange, OSH, Romania. - 2011, Speaker “OSH inspection visit”, ITC ILO, Turin Italy. - 2014-2015, project coordinator, ILO “increasing workplace compliance through LI”, Vietnam. - 2015, Speaker “risks assessment OSH”. - 2016, OSH and LI, Panama. | English | Sweden. Cape Verde Mexico |
| SPAIN 13 | JUAN MARTÍN GARCÍA ALLOZA | Labour and Social Security Inspector | Labour and Social Security Inspectorate of Spain State Agency. (Ministry of Labour, Migrations and Social Security) | 34 | - Law degree - Postgraduate courses. - Superior Technician on OSH. | - Occupational Safety and Health. - Labour relations. - Social Partners. - 1990 -1996, 2015 – 2016, Associate professor, Law Valencia University - Teacher LSSI School - 1987, training LI. Bolivia - 1996, Training OSH LI, Bolivia. - 1997, training OSH LI, Bolivia. - 2000, TU worker’s, Guatemala. - 2005, Labour mediation and conciliation, ILO, Bolivia. | English | Colombia El Salvador Bolivia |
| SPAIN 14 | MARÍA MERCEDES TEJEDOR AIBAR | Head International Relations Department | National Institute Safety and Health at Work (INSST) of Spain. Ministry of Labour, Migrations and Social Security. | 23 | Industrial engineer. Ecomonics degree. Master in OSH. Auditor in OSH. | - Transposition of EU Directives on OSH. - Occupational Safety and Health. - Labour relations. - Social Partners. - EU OSHA governing board alternate member. - ACSH alternate member. - PEROSH. | English French | EU OSHA governing board alternate member. |
| SPAIN 15 | marta zimmermann verdejo | Head Research and Information Department. | National Institute Safety and Health at Work (INSST) of Spain. Ministry of Labour, Migrations and Social Security. | 33 | Degree in Medicine and Surgery Postgraduate specialization Epidemiology and Public Health. Master degree in Public health Degree in design and statistics methodology for health sciences. Master degree in field of Epidemiology Training programs. | - Transposition of EU Directives on OSH. - Occupational Safety and Health. - Labour relations. - Social Partners. - Spanish strategy for safety and health at work. - Surveys on working conditions. - Work relates accidents, occupational diseases. - Epidemiological reports. - Scientific steering group PEROSH. - External expert EUROFOUND. | English | EUROFOUND. |
| SPAIN 16 | RAQUEL CALVERAS AUGÉ | Labour and Social Security Inspector | Labour and Social Security Inspectorate of Spain State Agency. Generalitat Cataluña. | 31 | Law degree | - Occupational Safety and Health. - Labour relations. - Social Partners. | English French | STE TW Romania, |
| SPAIN 17 | JAIME ADMETLLA RIBALTA | Labour and Social Security Inspector | Labour and Social Security Inspectorate of Spain State Agency. Generalitat Cataluña. | 34 | Law degree | - Occupational Safety and Health. - Labour relations. - Social Partners. | English | Czech Republic, Romania, |
| SPAIN 18 | Gabriela Beltran Fernandez | Labour and Social Security Inspector | Labour and Social Security Inspectorate of Spain State Agency. (Ministry of Labour, Migrations and Social Security) | 37 | Degree in Law | - In accordance to European acquis and Spanish Legal framework, on site Labour and Social Security Subinspector activities, task of control at the working sites in all areas with relevant competences - Occupational Health and Safety OHS (Factories, Entreprises,Building construction sector, on-site inspectionvisits, campaigns sector ),talks with representatives of social agents, workers, workers’ representatives, Trade Unions, employers’ associations, within the occasion of labour conflicts, strikes, layoffs, etc. - Antidiscrimination, gender equality, Gender Pay Gap, | English French Italian Arab | EU ILO |
| SPAIN 19 | Tomas Criado Navamuniel | Labour and Social Security Inspector | Labour and Social Security Inspectorate of Spain State Agency. (Ministry of Labour, Migrations and Social Security) | 10 | Law degree Universidad Complutense de Madrid, Madrid (Spain) | - Compliance with social legislation, advising, reporting, assessment, mediation or interaction with workers and entrepreneurs’ representatives, - Good command and deep knowledge of the European Acquis in the fields of OSH, Labour Law, Social Security, Labour Migration, Equality, Undeclared Work and Labour Relations. | English French Romanian | Romania Albania Panama |
| SPAIN 20 | JOSÉ IGNACIO MARTÍN FERNÁNDEZ | Labour and Social Security Inspector. International Relations Unit. | Labour and Social Security Inspectorate of Spain State Agency. (Ministry of Labour, Migrations and Social Security) | 20 | Law degree Jean Monnet Course on European legal Culture | - Transposition of EU Directives on OSH. - ILO Conventions and Regulations. - Technical counsellor ILC 2018 ILO “ending violence and harassment in the world of work”. - ILO legal officer, CEACR 2016. - Occupational Safety and Health. - Labour relations, Social Partners, EU Strategy on OSH. - Spanish strategy for safety and health at work. - SLIC European Campaigns. - SLIC working groups. - SLIC LI exchange programs. - Psychosocial risks. - IMI system. Posting of workers. - ECPW, EPAUW, working groups. - EUROFOUND governing board alternate member. - Teacher LSSI School. - Teacher National Institute Public Administration. - Teacher master access to legal practice. | English French Portuguese Italian Russian | see CV. |
| Estonia 21 | Eva Põldis | Adviser in Working Life Development Department, Work Environment Unit | Ministry of Social Affairs of Estonia | 4 years in the field of OSH | Master´s degree in economics | - Knowledge and experience of drafting labour legislation (with focus on OSH), including regulatory impact assessment and inter-institutional coordination. - Experience in developing strategy documents and implementation guidelines. - Knowledge and experience working on legal approximation issues, particularly Union acquis. - Knowledge and experience of developing public consultations, information campaigns and awareness raising. - Good command of written and spoken English. - Good computer literacy (word, excel, power point). | English | Member of the Advisory Committee on Safety and Health, Member of Baltic Sea Network of Occupational Health and Safety |
| Estonia 22 | Silja soon | Head of Supervisory Department | Labour Inspectorate of Estonia | Since 1995 | Medical doctor | - Occupational health and safety - Occupational hazards and their effect to the health | English | Member of SLIC working groups (Chemex, Long Latency, Enforcement) |
| Estonia 23 | Seili Suder | Working Life Development Department, Head of Work Environment | Ministry of Social Affairs of Estonia | Since 2005 | Magister Juris degree in law at the University of Tartu, where she is currently also pursuing a doctorate degree. | - 14 years of professional experience in the field of labour legislation (both individual and collective labour law and OSH), 2 years of it in the Labour Inspectorate of Estonia - knowledge and experience of drafting labour legislation (labour law, OSH) - knowledge of relevant EU legislation and other international instruments (European Social Charter and ILO conventions, labour law, OSH) - working experience on EU legislation and practical law enforcement issues in Member States - experience in developing strategy documents, implementation guidelines, operational/ procedural manuals and instruction handbooks - Knowledge and experience of developing public consultations, information campaigns and awareness raising. - Good command of written and spoken English. - Good computer literacy (word, excel, power point). - Member of the working party on Occupational Safety and Health Signs Directive 92/58/EEC (special working party in the Advisory Committee on Safety and Health at Work). | English | Finland, Ireland |
| Estonia 24 | Mariliis Proos | Working Life Development Department, Head of Employment Relations | Ministry of Social Affairs of Estonia | Since 2002 | Degree equal to bachelor’s degree in law | - 17 years of professional experience in the field of labour legislation (both individual and collective labour law and labour dispute resolution), 4,5 years of it in the Labour Inspectorate of Estonia and 4,5 years in trade union - knowledge and experience of drafting labour legislation - knowledge of relevant EU legislation and other international instruments (European Social Charter and ILO conventions) - working experience on EU legislation, ILO instruments and practical law enforcement issues in Member States - experience in developing strategy documents, implementation guidelines, operational/ procedural manuals and instruction handbooks - experience in industrial relations (industrial actions, collective bargaining) - knowledge and experience of developing public consultations, information campaigns and awareness raising. - Member of the Advisory group for the European Labour Authority - Member of the European Commission Committee of Experts on Posting of workers and subgroup on the transposition of directive 2018/957/EU. | English | Participation experience in the working group meetings of the Council of European Union. Presidency of EU. |
| Austria 25 | Manuela HARGASSNER-DELPOS | Senior Specialist | Austrian Federal Ministry of Labour, Social Affairs, Health and Consumer Protection | 25 | University of Vienna/Social Sciences Faculty (Vienna, Austria) | Training methodologist, Training of trainers Soft skills Gender Mainstreaming implementation | English German | Czech Republic Azerbaijan |

ARTICLE 6: Budget

BUDGET to be annexed

<

The Member State PL

[signature]________________________________

[date]____________________________________

The Beneficiary Country PL

[signature]________________________________

[date]____________________________________