Technical Assistance 
to the Social Welfare system in Georgia

Technical Assistance 
to the Social Welfare system in Georgia

March 2019

Human capital & Social development Department

Social Protection & Decent Work Unit

TABLE OF CONTENTS

1.	Relevance of the technical assistance proposal in the Georgian social context	6

1.1	Recent socio-economic developments in Georgia	6

1.2. 	Snapshot of vulnerable groups facing poverty in Georgia	7

1.3	Health in Georgia: improving population access to sustainable services	10

1.4	Mental healthcare profile of Georgia	11

1.5	Objectives of the technical assistance financed by AFD	12

2	Work Approach	13

2.1	Project Methodology	13

2.2	Project Team	14

3	Project implementation methodology	17

3.1 	Enhancing social support to vulnerable groups	18

3.1.1	Improving the support to peoples with disabilities (PWD) by developing functional/social model of assessing and granting disability status in line with the UN Convention on the Rights of Persons with disabilities	18

3.1.2	Support to implement the second phase of deinstitutionalization	22

3.1.3	Establish new services for children in street situation to protect their rights and promote their integration	25

3.2	Ensure affordable and quality healthcare	27

3.2.1	Improve the effectiveness and efficiency of universal healthcare and other programs	27

3.2.2	Strengthen the public Mental Health Services	31

3.3	Reinforcing the efficiency of resources allocated to IDP needs	33

3.4	Cross-cutting issues	35

3.4.1	Improving the evidence-based monitoring and evaluation of social policies	35

3.4.2	Capacity-building	38

3.5	Closing phase	43

LIST OF ACCRONYMS

AFD		Agence Française de Développement

CSO		Civil Society Organization

CWD		Children with Disabilities

DRG		Diagnosis-Related Group

IDP		Internally Displaced Person

IT		Information Technology

MOLHSA		Ministry of IDPs from the Occupied Territories, Labour, Health and Social Affairs

PHC		Primary Healthcare

PCG		Project Coordination Group

PWD		People with Disabilities

SSA		Social Service Agency

TA		Technical Assistance

TSA		Targeted Social Assistance

WB		World Bank

WD		Working Day

WHO		World Health Organization

# Relevance of the technical assistance proposal in the Georgian social context

## Recent socio-economic developments in Georgia

One can observe a better and substantial economic growth in 2017 in Georgia compared with two previous years, thanks to tourism, foreign direct investments and remittances from the diaspora. Numerous jobs were created in diverse sectors. However, growth was not limited to those items and prices for basic necessities went up, meaning a less affordable lifestyle for vulnerable groups : electricity tariffs rose by 27,5% in July 2016, healthcare (+6,9%), food (vegetables +25%, fruit and grapes +16%, cheese and eggs +9,3%).

Aggregate government spending is projected to reach 11,4 billion GEL in 2018 (+9,7% increase from 2017). However, public expenditures on healthcare and social protection decreased from 2016 to 2017. It is worth noting that social protection expenditure is the largest spending item in the state budget (24,6% in 2017, or 6,7% of GDP), and especially pensions.

Approximately 20% of the general population is living under the relative poverty line (60% of median consumption corresponding to 177.1 GEL/month), with a marked difference between rural and urban areas. The country is overall better off when compared to 2013-figures, but worrisome for vulnerable groups.

Source: UNICEF (2018), “The Welfare Monitoring Survey 2017 Summary”

## 1.2. 	Snapshot of vulnerable groups facing poverty in Georgia

According to main observers, vulnerable groups are socio-economic groups with significantly lower income than the general population: People With Disabilities (PWD), Internally Displaced Persons (IDP), homeless persons and children in street situation.

Socio-economic conditions of PWD

The number of PWD in Georgia is accounted by the Ministry of IPDs from the Occupied Territories, Labour, Health and Social Affairs (MOLHSA), in charge of defining and monitoring social policies for PWD. In February 2016, according to official figures, 123 957 individuals received a disability pension (3,3% of the population). However, the official definition of disability may exclude people with a lesser degree of disability. On a global scale, PWD have higher poverty rates (41,2%), lower educational achievements (6% are illiterate, Rate of PWD with master or equivalent is half of the general population), and lower labour force participation than the general population. PWDs affect economically and socially a whole family/household: caregiving is mostly done by a family member (mothers especially) and more often than not doesn’t allow the caregiver for a sustained economic activity.

As the World Bank puts it in its 2017 report on “Social Exclusion and Inclusion in Georgia: A Country Social Analysis”, “[e]xclusion and invisibility of PWD is a result of multiple mutually reinforcing barriers”.

Source: The World Bank (2017), “Social Exclusion and Inclusion in Georgia : A Country Social Analysis”

The entire life of PWD is affected by their conditions. Equally worrisome is the situation of children with disabilities (CWD): they are only 9 integrated classes for CWD in Georgia. Approximately 6000 CWD go to school and there are 1300 teachers trained to teach CWD. Out of 2084 public schools in Georgia, 263 have ramp access. The collaboration between Ministry of Education, Science, Culture and Sport and the MOLHSA aims at integrating day centres into public schools. Guides and extra funding are allocated to schools with CWD.

Transitions into adult life and independence for young adults with special needs is very difficult. There is still much discrimination in employment even though a set of laws exists to fight it. Law enforcement can be difficult in those situations.

Children in street situation

It is very difficult to have sound and consistent data about the number of children living and/or working in the streets as the issue deals with many changing individual situations: for instance some children are temporarily in the streets or moving seasonally, or are just below 16, making it hard to count them as children. Most recent studies in Georgia have focused on a qualitative assessment of children in street situation rather than a quantitative assessment. However, Non-Governmental Organizations such as Caritas estimate that around 2, 500 children are living and working in the streets of Georgia. Most children living and working in the streets are in an urban setting, where economic activity is thriving (e.g. along the Black Sea coast during tourism season).  Their situation is worrisome because of the long-term impact for people missing education and basic human development opportunities for their future. More often than not, the poverty trap affects street children. Root causes of the problem needs to be addressed.

According to UNICEF (Report “Children living and working in the streets of Georgia” published in July 2018), street children can be divided in subgroups:

- Homeless children and youth (of the street): Youth/children who live and work in the streets, unaccompanied by adults while in the street, and without protective care from parents. They may stay in touch with parents on occasion.

- Unaccompanied children in the street, sleeping at home: Children who spend most of their daytime hours working or otherwise engaging in economic activities in the street, unaccompanied by adults, but who are provided for with food and/or resources by a parent on a regular basis, and who themselves contribute with income to the family.

- Street children of mobile street families: Children that accompany or are accompanied by adults who are also street workers, and who work, but do not sleep, in the streets.

- Children of homeless families: Children of homeless families are similar to children of mobile street families, but they do not return to a home at night.

There is an ethnic dimension to the phenomenon but it cannot be understood in ethnic terms only. There is a predominance of Romani speakers (of Moldavan Roma descent) and Azerbaijani Kurds among street children of mobile street families.

The main challenges concerning street children are as follows

- Outreach of Azerbaijani Kurdish families who do not see any reward in cooperating with the state or local services (many avoid registering birth, do not seek formal documentation and identification papers, do not enrol children to school and do not apply for social support). Children are often taking part in income generating activities with their parents

- Limited educational opportunities, lack of future employment prospects and bad appearance and hygiene (hindering their socio-economic integration in everyday life). The National Program of Social Rehabilitation and Childcare by MOLHSA is tackling these issues with day-care centres for street children

- Vulnerability to physical, emotional and sexual violence from caretakers and other street youth. Most street children do not have access to either education or medical services beyond emergency care.

Internally Displaced Persons: from a status-based social allowance to a needs-based pension

Internally Displaced Persons from the conflicts in Abkhazia (1992 -1993) and South Ossetia (2008) represent approximately 7% of the population of Georgia. They are a very heterogeneous group since some succeeded in reintegrating socio-economic life after leaving the regions. However, poverty rate among this group is very high with circa. 43,3 % living under poverty line.

Many IDPs are located in adjacent areas of the border zones of the self-declared independent states and major cities (75% of IDPs live in urban areas due to the housing and economic opportunities). Most of them came from rural areas and were not able to maintain their traditional livelihoods. 38% still inhabit collective centres where living conditions are substandard: IDPs who still live in non-rehabilitated collective centres away from the capital are one of the most marginalized sub-group: most of them were displaced during the 1990s and the Abkhazia conflict when the State response to housing was not as effective as the one in 2008.

The Government introduced a benefit of GEL 45/month/IDP for individuals earning less than GEL 1,250/month. The main challenges are twofold:

- Socio-economic challenges: housing and living conditions; unemployment (low qualifications due to a low socioeconomic status and low-skilled jobs) especially for males as women tend to accept low-skills jobs.

- Budgetary issues: the government benefit for IDP is status-based and the status is hereditary. It means that more and more people will receive the benefit unconditionally. There is a need to smoothly switch from a status-based governmental benefit to a needs-based benefit in coordination with other social benefits, notably the Targeted Social Allowance (TSA). Political communication is required as the issue and status of IDP is a sensitive topic and needs to be maintained.

## Health in Georgia: improving population access to sustainable services

86% of the population in Georgia is covered by the universal healthcare program. Despite this figure, the universal state healthcare introduced in 2013 providing basic medical services is facing many challenges:

- Share of governmental spending on healthcare in overall healthcare expenditures is significantly lower (at 37,2% in 2016) compared to the least limit of 40% recommended by WHO, meaning that the population has to cover a considerable amount of costs on medical care itself (“out-of-pocket” expenditures is high) and that public medical infrastructures face many challenges;

- 61,2% of all health expenditures in 2016 are private health expenditures, be it out-of-the pocket expenses (91% of the private health expenditures) or through a private health insurance (5,6% of the private health expenditures and growing), i.e.  the Universal Healthcare Program covers 3.2 million people, while 530, 000 are on private,corporate or government schemes ;

- Access to affordable health services (especially in rural areas); corporate, employer sponsored or private insurance is more common in urban areas than it is in rural areas.

- Cost of medicine and medical acts: in an UNICEF survey, 27% of household reported buying medicine to be their main problem. Average expenditures on medication increased significantly across consumption quintiles. Drug production and prices as well as prices of medical acts are under-regulated.

## Mental healthcare profile of Georgia

Mental health covers many different situations, from chronic depression to severe mental disabilities. Whereas some mental health problems can be bearable on an everyday life, severe mental disabilities for individuals affect their family and livelihoods of the household. Mental health is still a stigma for many families. People living with mental disorders in Georgia face a lack of care and, as a recent WHO report and the Georgian Ombudsman put it, lack of human and compassionate treatment.

Since 1995, the number of inpatient psychiatric beds has decreased significantly from 5000 to 1490, but outpatient and community mental health care has not been developed enough to compensate. For inpatient care, there are 9 specialized institutions and three departments (with 30-bed units) within general hospitals. From 2006 till 2011 circa. 2,5% of public health expenditures were allocated to mental health. This amount dropped to 1,7% for the period 2012-2018 and 2.1% in 2019 according to the Ministry of Finance.

There is a strong link between mental health problems, social exclusion and poverty. Poor conditions and treatment in mental health institutions due to a lack of qualified personnel, inappropriate therapeutic environment, and low-quality treatment. The academic offer for aspirant doctors are limited:  as a result, there are very few mental health specialists (lack of motivation: Tbilisi enrolls only 2 to 3 new residents in psychiatry each year). A new residency program in child psychiatry opened in 2016 in the medical university. The National Institute of Mental Health (now Center for Mental Health and Prevention of Addiction) for research activities is the main research actor on those issues and covers the whole mental health scope, with an emphasis on posttraumatic stress disorders and other stress-related disorders.

In 2013, the “National Concept on mental health” for inpatient care, community-based services, balance between pharmacological treatment and psychological therapies adopted by the Parliament of Georgia. The “National strategy and action plan for years 2015-2020” tries to find a balance between preferences of people with mental disorder and family and community interests; and a balance between methods of prevention, treatment and rehabilitation.

It is important to get more qualitative information and data regarding mental health and social protection in Georgia, especially sex-disaggregated data and gender statistics covering demography, health, employment and education. Together with the beneficiary, the project team will mainstream gender into its activities in i) getting updated sex-disaggregated data, and ii) addressing specific issues and needs of PWD of both genders, people living with mental health disorders and internally displaced people.

## Objectives of the technical assistance financed by AFD

The technical assistance (TA) aims at providing the Ministry of IDP from the Occupied Territories, Labour, Health and Social Affairs and its partners with tools to face the above-mentioned challenges for vulnerable groups and health-related costs.

The technical assistance will mobilize long-term and short-term expertise to accompany change in those areas, support institutions and CSOs in their policies and programs and train relevant stakeholders to standards.

TA will also support evidence-based monitoring and improved data systems in order to improve public policies in targeting root-causes of social issues.

# Work Approach

The project will be implemented in close collaboration with the relevant Georgian authorities. It is proposed to establish a Project Coordination Group (PCG), at the beginning of the project in agreement with AFD, in order to support the smooth implementation of the project and to ensure a better cooperation between the main Project’s stakeholders (Project Team, AFD and Beneficiary Institutions).

The PCG will ensure that project activities meet their objectives and that its implementation progresses consistently with the ongoing social protection reforms. AFD and the MOHLSA will oversee the implementation of the project and may request adjustments to its methodology.

The PCG will be chaired by a representative from the MOLHSA and will be composed of representatives of the technical assistance direct beneficiaries (MOHLSA, SSA).The Project Team Leader should be part of the PCG and other members of the project management team may participate as observers in the PCG. Representatives of AFD and Expertise France may participate to the PCG in order to coordinate the Project Team activities.

In complex Technical Assistance projects, it is usual to make adjustments to the annual work plan before the end of the covered period. It is proposed to organize 4 meetings of the PCG, one every 6 months, in order to analyse the progress in implementing the planned activities and, if necessary, to propose adjustments. In case of necessity, the PCG could hold additional meetings at the request of one of this member.

The PCG’s responsibilities will include the following:

| - Examining the half year progress reports, providing advice on project activities and recommending new direction when appropriate. | - Providing full access to all the information regarding the overall project context, necessary for the launching and the management of the project activities |
| --- | --- |
| - Facilitating overall project implementation. | - Identifying and suggesting to the project management potential synergies between its mission and other relevant initiatives. |

## Project Methodology

The project’s activities will include three complementary pillars:

- Pillar 1: Enhancing social support to vulnerable groups

- Pillar 2: Ensuring affordable and quality healthcare

- Pillar 3: Support to optimizing resources allocated to IDP needs

The three pillars address different needs expressed by the Georgian authorities for improving the social welfare while making its financing sustainable from a fiscal point of view.

Activities presented in this document will need to be further refined at the start of the project with AFD and the beneficiary institutions, taking into account the work already done, analysing the existing reports produced on behalf of the Georgian authorities. Existing methodologies and programs of other donors will also be taken into account, e.g. the pilot project conducting with UNICEF for implementing the functional/social model of PWD in the Adjara region.

An inception phase of 1 to 2 months will allow to use as much as possible what has been already produced and avoid overlapping, as well as mainstream gender in the different activities proposed. At the end of the inception phase, the Project Team will submit, during the first meeting of the Project Coordination Group (PCG) an Inception report together with annual work plan, based on the activities proposed below.

The annual work plan will propose to the members of the Project Coordination Group priority areas of intervention, concrete activities, duration, and period of implementation and methods of intervention.

Proposed activities could be:

- Technical assistance on specific thematic with the mobilization of national, regional or international experts

- Advisory services directly provided by the project team

- Studies

- Organization of trainings

- Organization of workshops, seminars or conferences

- Organization of Study tours

When preparing the annual work plan, the Project Team will discuss the most suitable method for the implementation of the various activities with the concerned direct beneficiaries. In this task, Expertise France will accompany the Project Team making proposals based on similar activities already implemented in other countries.

## Project Team

The success of the project will rely on the setting up of a permanent multidisciplinary project team in Tbilisi, in charge of technical, administrative, financial and logistical aspects.

The different members of the project team proposed by Expertise France will ensure the effective implementation of various activities envisaged through the following missions:

- Identification of the needs of the contracting authority and beneficiary institutions

- Development and adjustments of annual work plans

- Procurement and contracting activities (including drafting terms of reference and tender documents)

- Supervision of the contracts execution

- Technical and administrative support as well as the logistical aspects of technical missions (transport, accommodation, catering, ...), organization of workshops or working meetings, steering committees or study tours.

- Preparation of the technical and financial reports

- Administrative, financial and contractual management of the Project

The recruitment of the project team will be the responsibility of Expertise France which will apply its own internal procedures. However, in order to ensure the adequacy of the profiles of the Team Leader, the Team Leader Assistant (TL) and experts (international or local), CVs of potential candidates will be submitted for approval to the MoLHSA and AFD.

Paris office

Tbilisi office

Quality Control Expert

Team Leader / Expert in Social Protection

Expert in coordination with French institutional partners

Backstopping

Project assistant / Translator / Interpreter

The Tbilisi Office

The technical team

- Team leader – expert in social protection

Based within the premises of the Ministry, he/she will supervise the whole project, be a member of the PCG, and lead most of the activities of Component 1, 2 and 3 in coordinating international and local experts and follow-ups. The Team Leader will be the main counterpart of the Minister to steer the technical assistance on a day-to-day basis.

His/Her missions:

- Representation of the project in the PCG;

- Strategic interlocutor of MOHLSA/SSA for implementation of project activities;

- Transmission of his/her technical knowledge to the MOHLSA teams;

- Co-redaction with the other members of the team of the annual work plans and overall supervision of effective implementation of activities;

- Drafting of half-year progress reports and presentation during PCG

- Supervising the elaboration of the terms of reference for the various project components;

- Supervising the development of various strategic documents produced within the project components;

- Representation of the project, in close consultation and collaboration with AFD and the beneficiary institutions, with institutional partners;

- Supervision of technical reports produced by short-term experts for the different components.

The administrative and financial team

Project Assistant and Interpreter:

- Permanent support to the technical team;

- Assistance to the Project Coordination Group;

- Support to the logistical organization of the different activities implemented within the framework of the project;

- Interpretation and translation of strategic documents (an extra support of professional translators and interpreters will be considered during activities that bring together many actors or to translate large volumes of documents).

- Management of local contracts and coordination with the Paris office;

- Support to the Project Team for project financial execution under supervision of the Contracting Authority;

- Management of all administrative, contractual and financial aspects of the project in close collaboration with the project coordinator in Expertise France;

The Paris Office

In Expertise France premises

Quality insurance expert

- Permanent quality assurance and control of the project implementation;

- Facilitation of peer-to-peer or institutional cooperation;

- Provision of advice in construction of annual work-plan and half-year progress reports;

- Approval of final version of deliverables before submission to Contracting authorities;

- Participation in some activities of the project related to the increasing of the project visibility and awareness

Expert in capacity development and coordination with French institutional partners

- Administrative and contractual management of the project team based in Tbilisi;

- Follow-up of the respect of contractual obligations with Expertise France and possible contractual modifications (request of addendum, etc.);

- Coordination with AFD headquarters;

- Follow-up of the respect of Expertise France financial and contractual procedures;

- Support in the identification of technical expertise;

- Participation in the launching of tendering procedures and the selection of external service providers;

- Support to the contracting of external service providers;

- Payment of external service providers;

- Accounting and financial control of the project, on the basis of the financial reports, including the feeding and the control of the use of the bank account of the project, and the follow-up of the advances received;

- Consolidation and control of technical and financial reports before sending to the contracting authority;

- Logistical support to activities (installation of the Tbilisi project team, organization of short term expertise missions, organization of study visits in France/Europe);

- Participation, on behalf of Expertise France, in the Project Coordination Group whose schedule will be defined with the project team in Tbilisi, the contracting authority and the beneficiary institutions.

For the effective implementation of the activities, the Project Team will also benefit from a technical, financial and logistical backstopping of Expertise France different departments (financial, human resources, legal, IT, travel, etc....)

# Project implementation methodology

| Activity 0 | Inception phase and launch event |
| --- | --- |
| Objective: | To present the project and its approach to key stakeholders, thus ensuring their motivation and participation |
| Target administration: | MOLHSA, SSA, CSOs, partners |
| Description: | The project’s success depends on the involvement and the collaboration of all stakeholders and the development of a sense of common responsibility among the parties involved. At the onset of the project, there is a need for the creation of a consensus around the project. As well as meeting the different partners and main stakeholders of the project, fine-tuning the project methodology will take place. A kick-off meeting with all relevant stakeholders will be held to gather the representatives of MOLHSA, SSA, AFD, donors, key Departments of the Ministry and local agencies involved in the project, as well as civil society representatives. During the kick-off meeting, the TA team will remind the main objectives and milestones of the project. This event will be the occasion to discuss the content of the inception report to be written by the TA team, notably for: - Clarifications and amendments on the ToRs; - Gender mainstreaming in project activities; - Proposed work plan for completion of the activities in the project - Required commitments of staff and resources from the project partners |
| Deliverable(s): | - Inception report et updated methodology and planning - Gender mainstreaming in project activities - Launch event |
| Input: | Team Leader: 15 WD International experts: 10 WD |
| Timing: | Months 1 - 6 |

## Enhancing social support to Persons With Disabilities

Main activities in the framework of the pillar 1 will concern improving the support to peoples with disabilities (PWD) by developing functional/social model of assessing and granting disability status in line with the UN Convention on the Rights of Persons with disabilities. The Ministry has transmitted to the project team the document “Adapted disability assessment instruments for children and adults” (translated in English).

Necessary information which should be transmitted subject to successful implementation of following activities:

- Report (preferably translated in English) explaining the adaptation and the rationale behind the adaptations of assessment instruments  for children and adults

- Methodology of Adjara A.R Pilot project to test the new functional assessment methodology

| Activity 1.1.1 | Development of methodology for piloting of disability assessment in Samtskhe Javakheti region |
| --- | --- |
| Objective: | Propose a clear methodology shared by the partners for piloting of disability assessment in Samtskhe Javakheti region |
| Target administration: | Ministry of IDPs from the Occupied Territories, Labour, Health, Labour and Social Affairs – Social Affairs Department in charge of PWD ; National Statistics Office (GeoStat); Administration of Samtskhe Javakheti region; CSOs Local administration of Samtskhe Javakheti region and Adjara AR |
| Description: | The disability assessment instrument for adults based on WHODAS 2.0 methodology was translated to Georgian. In partnership with the Ministry, the UNICEF has developed a specific assessment instrument for children based on the WHO’s Model Disability Survey (MDS). The piloting of these two new disability assessment instruments will start in Adjara A.R in March 2019 and should last all the year. Six health institutions are assessing the disability in Adjara AR. UNICEF assist those institutions in recruiting and training of functional assessment specialists in order to form new functional assessment teams. Our project team will propose the methodology of piloting of disability assessment in Samtskhe Javakheti region in line with the methodology used by UNICEF in Adjara AR. In this regards it is necessary to know the basic statistics about disability in both Adjara AR and Samtskhe Javakheti region, as well as in the country. It is important to analyse the existing infrastructure in Samtskhe Javakheti region (which health institutions are assessing disability, their capacities, existing rehabilitation institutions etc.). Our project needs to understand exactly the methodology of UNICEF in Adjara AR (number of the functional assessment specialists to recruit and to train, capacities of functional assessment teams etc) We propose to analyse the possibility to introduce for piloting in Samtskhe Javakheti region an additional tool necessary for evaluation of needs concerning minimum support package for people/children with disabilities. The decision should be made concerning the number of assessment to be made and the solutions to be proposed. The methodology of piloting of disability assessment should be discussed with the administration of Samtskhe Javakheti region as well as with the staff of health institutions assessing disability. |
| Deliverable(s): | - Methodology for piloting the disability assessment in Samtskhe Javakheti region is drafted and approved by the beneficiary; - Electronic versions of administration of the instrument's scores are is ready for implementation - Database for data treatment is established - 1 day workshop is organised in Borjomi in order to discuss the methodology with local authorities |
| Input: | Team Leader: 10 WD Senior International experts: 25 WD |
| Timing: | Months 1-3 |

| Activity 1.1.2 | Piloting of assessment instruments in Samtskhe Javakheti region |
| --- | --- |
| Objective: | Carry out a test for implementation of new disability assessment instruments in Samtskhe Javakheti region |
| Target administration: | Ministry of IDPs from the Occupied Territories, Labour, Health, Labour and Social Affairs – Social Affairs Department in charge of PWD ; Local administration of Samtskhe Javakheti region and Adjara AR; local health institutions |
| Description: | Based on agreed methodology of pilot assessment, the project will start the preparation to piloting in Samtskhe Javakheti region. The assessment will be organised on the level of primary or secondary evaluation of the PWD by specialised medical institutions in order to assess the differences in assessment methodologies. The project will use the job descriptions of the functional assessment specialists for children and adults developed by UNICEF and approved by the Ministry. Following tasks will be realised: - Adapt the training program and materials for the specialists based on Adjara experience - Define the number of the functional assessment specialists according to the data of existing health institutions in Samtskhe Javakheti region - Assist in recruitment of functional assessment specialists in Samtskhe Javakheti region - Provide the initial trainings to the specialists in Borjomi - Provide trainings to the medical doctors involved in the disability status determination. - Provide the professional supervision/coaching to the functional assessment specialists and medical doctors involved in the disability status determination. |
| Deliverable(s): | - Trainings are organised; - Some PWD are evaluated according to new assessment instruments ; - Report on piloting is drafted; - Anonymous database is established |
| Input: | Team Leader: 40 WD Senior International experts: 60 WD Local experts: 245 WD |
| Timing: | Months 4-16 |

| Activity 1.1.3 | Policy impact assessment based on the results of piloting in two Georgian regions and best international practices in implementing the functional/ social model for evaluation of disability |
| --- | --- |
| Objective: | Formulate evidence-based analysis and recommendations in order to implement and mainstream the functional/social model in Georgia |
| Target administration: | Ministry of IDPs from the Occupied Territories, Labour, Health, Labour and Social Affairs – Social Affairs Department in charge of PWD ; National Statistics Office (GeoStat); Other public institutions; Local authorities; SCOs |
| Description: | Based on the results of piloting in Ajara AR and Samtskhe Javakheti region, international and local experts will draft a report with evidence-based analysis and recommendations for implementation assessing and granting disability status with the functional/social methodology in Georgia. In this regards, the same information systems and databases should be used in both region in order to analyse the results. Gender dimension of disability should be taken into consideration in this analysis. In this report an impact assessment about actual population of PWD will be made: who will not be considered as disabled with new assessment instruments, who will remain considered as disabled, how many new categories will be considered as disabled, etc. The simulation model will be constructed based on experiences of both regions and different policy decisions will be considered (level of benefits, basic social services package, and additional services). The main conclusion of this report will be presented and discussed with the Ministry, UNICEF and other relevant stakeholders. Special part of analysis will be devoted to connection between the results of social/functional assessment and health condition / medical diagnosis (proof of functional limitation, disability etc.). |
| Deliverable(s): | - Public policy impact assessment report (including gender dimension) is drafted; - Simulation model is developed based on pilot data of two regions; - Analysis of connection between the results of social/functional assessment, environmental assessment and health condition / medical diagnosis (proof of functional limitation, disability etc.). |
| Input: | Team Leader: 20 WD Senior International experts: 55 WD Local experts: 60 WD |
| Timing: | Months 12-20 |

| Activity 1.1.4 | Proposal for minimum support package for people/children with disabilities |
| --- | --- |
| Objective: | Formulate the basic services which can be guaranteed to PWD / CWD in Georgia in line with the functional/social model and available resources |
| Target administration: | Ministry of IDPs from the Occupied Territories, Labour, Health, Labour and Social Affairs – Social Affairs Department in charge of PWD ; Other public institutions; Local authorities; SCOs |
| Description: | Based on the simulation model, the project team will propose different options related to the minimum package necessary to support people/children with disabilities. This package should be composed of disability benefit, cost of homecare, cost of day-care, cost of institutional care, cost of compensations for adaptation of external environment including home and working place etc. Special recommendations will be formulated regarding involvement of different stakeholders (healthcare, social services, rehabilitation, other public institutions, local authorities, SCOs) with clear distribution of roles. The results of analysis should be presented to the broader public, involving main stakeholders and CSOs representing the PWD. Based on this broad discussion the project team will develop the methodology of assessment of capacities of different service providers which can be involved in the implementation of social model in Georgia. Clear criteria should be established in order to select the valuable partners and reinforce their capacities. |
| Deliverable(s): | - Different options for minimum support package for people/children with disabilities including their pricing - Recommendations on involvement of different stakeholders (Ministry, other public institutions, local authorities, SCOs) with clear distribution of roles; - Development of methodology of assessment of capacities of different service providers |
| Input: | Team Leader: 20 WD Senior International experts: 60 WD Local experts: 100 WD |
| Timing: | Months 12-20 |

| Activity 1.1.5 | Support in drafting a realistic Action Plan for implementation of assessing and granting disability status with functional/social methodology in Georgia |
| --- | --- |
| Objective: | Support mainstreaming the functional/social model in Georgia |
| Target administration: | Ministry of IDPs from the Occupied Territories, Labour, Health and Social Affairs – Social Affairs Department in charge of PWD ; SCOs |
| Description: | Based on the public policy impact assessment, discussions with the Ministry, PWDs and CSOs, international and local experts will draft an Action Plan in order to plan the transition from medical to functional/social model of assessing and granting disability status in Georgia. This action plan should include detailed costs of the scale up and the reform for the entire territory of Georgia. This Action plan should present a comprehensive timeline for the implementation of social model of disability in Georgia, highlighting clear stages, defining necessary conditions to move on to the following stages etc. This Action plan should be discussed with main stakeholders and involving the CSOs representing PWD. |
| Deliverable(s): | - Proposal of Action Plan for implementation of transition from medical to functional/social model of assessing and granting disability status in Georgia including cost of the scale up and the reform; - Organisation of debates involving professionals and PWD |
| Input: | Team Leader: 25 WD Senior International experts: 30 WD Local experts: 60 WD |
| Timing: | Months 20-24 |

| Activity 1.1.6 | Support in implementation of awareness raising campaigns and consultations about implementation of functional/social model in Georgia |
| --- | --- |
| Objective: | Raise awareness about differences between medical and social models of disability Reinforce the rights of PWD in social, professional and political life and assessment of inclusive policies for everyday life of PWD |
| Target administration: | Ministry of IDPs from the Occupied Territories, Labour, Health and Social Affairs – Social Affairs Department in charge of PWD ; Other public institutions; Local authorities; SCOs |
| Description: | Together with the Ministry and CSOs, international and local experts analyse of the existing awareness raising campaigns of the Ministry and CSOs and draft recommendations for future campaigns aiming at reinforcing the visibility and rights of PWD. Three workshops involving the Ministry, local authorities, CSOs, PWDs, employers are organized in Tbilisi and in two regions to be selected. |
| Deliverable(s): | - Organisation of 3 thematic round tables involving different stakeholders - Communication strategy about difference between medical and social models of disability |
| Input: | Team Leader: 15 WD Senior International experts: 30 WD Local experts: 60 WD |
| Timing: | Months 4-24 |

| Activity 1.1.7 | Study visit |
| --- | --- |
| Objective: | Study international experience in implementation of functional/social model |
| Target administration: | Ministry of IDPs from the Occupied Territories, Labour, Health and Social Affairs – Social Affairs Department in charge of PWD ; Local authorities of Ajara AR and Samtskhe Javakheti region; |
| Description: | One study visit will be organises in order to analyse an international experience in implementation of functional/social model |
| Deliverable(s): | - Organisation of study visit for 6 officials to France - Report of study visit |
| Input: | Team Leader: 10 WD Senior International experts: 10 WD 6 officials during 6/7 days to France |
| Timing: | Months 12 |

## 3.2	Ensure affordable and quality healthcare

## 3.2.1	Improve the effectiveness and efficiency of universal healthcare and other programs

Necessary information for successful implementation of this component:

- Results of external survey to identity groups of population that are not adequately covered and the main gaps of the existing health care system (e.g. geographical disparities, access to drugs and services, increasing costs,  challenge in payment mechanisms, diverse quality of treatment, etc.)

- Report of the MOLHSA presenting the strategic purchasing vision and road map

| Activity 2.1.1 | Define standard operating procedures for the implementation of performance-based contracting, especially to primary health care |
| --- | --- |
| Objective: | To set up standard operating procedures for the implementation of performance-based contracting, especially to primary health care |
| Target administration: | Ministry of IDPs from the Occupied Territories, Labour, Health, Labour and Social Affairs – Health Department |
| Description: | This activity is devoted to develop performance based contracting methodology for the Ministry based on best European practices, including performance indicators and quality indicators. Expertise France will present best European practices in performance based contracting on Primary Health Care, secondary outpatient, inpatient care levels To develop understanding what regards rationale to introduce performance based contracting in Georgia, especially to primary health care To contribute to creation of a vision of optimal contracting methodology and practical steps required to move from the present situation towards the vision. |
| Deliverable(s): | - Standard operating procedures for the implementation of performance-based contracting, especially to primary health care are drafted |
| Input: | Team Leader: 5 WD Senior International experts: 25 WD Local experts: 20 WD |
| Timing: | Months 6-18 |

| Activity 2.1.2 | Analyse the functioning of IT in the health sector (E health) |
| --- | --- |
| Objective: | Improve the efficiency of using information technologies in the health financing |
| Target administration: | Ministry of IDPs from the Occupied Territories, Labour, Health, Labour and Social Affairs – Health Department |
| Description: | This activity is devoted to analyse national legislative and normative framework related to the architecture standards, technical standards and legislative acts, regarding information management and personal data protection in Georgia. Overview of international best practice must be provided. Existing utilisation of IT in the health sector, and the current eHealth regulations in Georgia must be analysed. The objective is also to overview security aspects, individual data storage, beneficiaries’ and health care suppliers’ identification and procedures and protocols for digital information dissemination. Furthermore it is important to identify and define the quality requirements to e-Health system and its performance. Architecture standards, technical standards and respective normative acts approved by the international eHealth SDOs (standard development organizations) and SMOs (standards maintenance organizations) as well as best practices of other countries must be analysed in a context of applicability to Georgia |
| Deliverable(s): | - Report of functioning of IT in the health sector (E health) and recommendations for improvement |
| Input: | Team Leader: 5 WD Senior International experts: 30 WD Local experts: 40 WD |
| Timing: | Months 6-18 |

| Activity 2.1.3 | Study visit |
| --- | --- |
| Objective: | Study international experience in implementation of health financing and healthcare management in France |
| Target administration: | Ministry of IDPs from the Occupied Territories, Labour, Health and Social Affairs – Health Department |
| Description: | One study visit will be organises in order to analyse an international experience in healthcare management and health financing |
| Deliverable(s): | - Organisation of study visit for 6 officials to France - Report of study visit |
| Input: | Team Leader: 10 WD Senior International experts: 10 WD 6 officials during 6/7 days to France |
| Timing: | Months 18 |

## 3.2.2	Strengthen the public Mental Health Services

Necessary information for successful implementation of this component:

- National strategy of mental health adopted in 2014 by the Decree of Government of Georgia, (translated in English)

- WHO reports on mental health in the Caucasus and the special report on Georgia

| Activity 2.2.1 | Development of the roadmap for implementation of deinstitutionalization and the development of community based services in line with recommendations of WHO report |
| --- | --- |
| Objective: | Support deinstitutionalization process for Mental Health Services in Georgia |
| Target administration: | Ministry of IDPs from the Occupied Territories, Health, Labour and Social Affairs – Health Department |
| Description: | This activity is devoted to draft a roadmap for implementing deinstitutionalization. TA will analyse national legislative and normative framework related to the technical standards and legislative acts regarding mental healthcare. Overview of international best practices will be provided. Detailed roadmap for implementation of deinstitutionalization and the development of community based services should take into account the capacities existing in Georgia. This roadmap should present a gradual improving of services with special emphasis on community based services, day-care and home-based services, without reducing abruptly the capacities of existing institutions. The priority should be given rather on gradual transformation of existing institutions. |
| Deliverable(s): | - Support for establishing the roadmap for implementation of deinstitutionalization and the development of community based services in line with recommendations of WHO report - Development of operational models including detailed analysis of staffs needs and costing of organisation of services - Workshop on best practices |
| Input: | Team Leader : 20 WD Senior International experts: 30 WD Local experts: 50 WD |
| Timing: | Months 1-6 |

| Activity 2.2.2 | Elaboration of monitoring mechanisms for protection of Human rights in mental health institutions (public and private) |
| --- | --- |
| Objective: | Provide MOLHSA with a toolbox for monitoring and enforcing Human rights in mental health institutions |
| Target administration: | Ministry of IDPs from the Occupied Territories, Health, Labour and Social Affairs – Health Department |
| Description: | TA will make an overview of international best practices and propose indicators and monitoring mechanisms for protection of Human rights in mental health institutions (public and private) as well as reporting and whistle-blowing. TA will meet with relevant stakeholders to decide and mainstream monitoring in their work. Qualified staff in hospitals will take part in awareness-raising workshops on human rights for people living with mental health conditions, and will be trained on human rights in mental health institutions and whistle-blowing mechanisms. |
| Deliverable(s): | - Mechanisms and tools for protection of Human rights in mental health institutions (public and private) On-the-job training of qualified staff on use of monitoring tools and reporting mechanisms |
| Input: | Team Leader : 20 WD Senior International experts: 30 WD Local experts: 30 WD |
| Timing: | Months 6-12 |

| Activity 2.2.3 | Recommendations on legal framework for mental health care in line with best EU practices and training |
| --- | --- |
| Objective: | Improve quality of life of people living with mental health problems |
| Target administration: | Ministry of IDPs from the Occupied Territories, Health, Labour and Social Affairs – Health Department |
| Description: | Based on available data and existing policies, TA will meet with different stakeholders to draft recommendations on how to improve mental healthcare. |
| Deliverable(s): | - Recommendation for improving of legal framework for mental health care in line with best EU practices |
| Input: | Team Leader : 20 WD Senior International experts: 20 WD Local experts:70 WD |
| Timing: | Months 12-24 |

| Activity 2.2.4 | Study visit |
| --- | --- |
| Objective: | Study international experience in management of mental health and implementing WHO guidelines |
| Target administration: | Ministry of IDPs from the Occupied Territories, Labour, Health and Social Affairs – Social Affairs Department in charge of health and mental health ; |
| Description: | One study visit will be organises in order to analyse an international experience in implementation of mental health care |
| Deliverable(s): | - Organisation of study visit for 6 officials to France (or another relevant country) - Report of study visit |
| Input: | Team Leader: 10 WD Senior International experts: 10 WD 6 officials during 6/7 days to France (or another relevant country) |
| Timing: | Months 12-24 |

## 3.3	Reinforcing the efficiency of resources allocated to IDP needs

| Activity 3.1 | Formulation of recommendations for housing and livelihood improvements of vulnerable IDPs |
| --- | --- |
| Objective: | Support the Ministry in addressing the housing and livelihood issues of vulnerable IDPs |
| Target administration: | Ministry of IDPs from the Occupied Territories, Health, Labour and Social Affairs – IDP Department |
| Description: | Identification of the vulnerable IDPs (for ex. with a vulnerability score between 100, 001 and 200, 000 according to the TSA vulnerability index) and their vulnerabilities thanks to a multi-analysis of the different tools of SSA (TSA benefits) and the IDP Livelihood Agency, as well as CSOs and representative of IDPs and field visits to CSOs and resettled households. Elaboration of recommendations for the programs of the IDP Livelihood Agency targeting vulnerable IDPs. |
| Deliverable(s): | - Report and recommendations on i) the resettlement providing information on the number of people/ families resettled and resettlement solution ; ii) livelihood issues (socio-economic integration) |
| Input: | Team Leader: 25 WD International experts : 15 days Local experts: 35 WD |
| Timing: | Months 10-18 |

| Activity 3.2 | Analysis of budgetary impact of different solutions for reform of IDP benefits |
| --- | --- |
| Objective: | Switching from a IDP status-based government benefit to a needs-based benefit |
| Target administration: | Ministry of IDPs from the Occupied Territories, Health, Labour and Social Affairs – IDP Department |
| Description: | Together with the relevant stakeholders (MOHLSA, MOF), international and local social policy experts and statisticians/economists gather data and present different budgeted reform scenarii. |
| Deliverable(s): | - Report and recommendations with different budgeted scenarii |
| Input: | Team Leader: 25 WD International experts: 10 days Local experts: 35 WD |
| Timing: | Months 18-20 |

| Activity 3.3 | Organisation of workshop about best options for Georgia, including a benchmark of other countries' experiences in management of IDP issues |
| --- | --- |
| Objective: | Present and exchange different experiences and lessons-learnt from relevant countries regarding IDP issues to decision-makers and facilitate debate/conversation between different interest groups |
| Target administration: | Ministry of IDPs from the Occupied Territories, Health, Labour and Social Affairs – IDP Department |
| Description: | A one-day conference is organized by Expertise France and a CSO specialised in mediation/facilitation in order to present to relevant stakeholders (representatives of IDPs, IDP Livelihood agencies, municipalities hosting IDPs) with a benchmark of other countries in IDP management (housing issues and socio-economic integration). Together with the Ministry, the TA will choose a mediator/facilitator for this conference/workshop. The relevant countries include Balkan states, Eastern Europe, North Africa and Turkey but other might be added. Prior to the conference, guests will have received relevant information regarding IDP policies. A debate will then be moderated by the mediator in order to raise IDP issues. |
| Deliverable(s): | 1-day conference workshop with benchmark presentations of relevant experiences (ex. Balkan states, Eastern Europe, North Africa and Turkey, etc.) 1-day mediation with the different stakeholders |
| Input: | Team Leader: 25 WD International experts: 15 days Local experts: 35 WD |
| Timing: | Months 20-24 |

## 3.5	Closing phase

The ‘Closing Phase’ of the project refers to activities that aim to hand-over the formal responsibilities from the TA team experts to the local counterparts and to ensuring sustainability and visibility of the project’s results. However, our project philosophy is to ensure an on-going consultative and joint responsibility-driven process to maximise long-term sustainability. This will be done during the last month of project duration.

| Activity 5 | Closing phase |
| --- | --- |
| Objective: | Prepare for demobilization, ensure ownership of deliverables |
| Target administration: | MOHLSA |
| Description: | The Closing Phase will consist of the following activities: 1. Preparation of a final project publication. 2. Demobilization of experts, equipment and facilities; verification and transfer of project files and closure of administrative formalities 3. Preparation and submission of the Final Report We suggest that at the end of the assignment the Consultant will prepare a Final Project Publication, which will summarise the major achievements and lessons learned, and include proven guidelines, methodologies and instruments which are useful for replication of similar type of project activities. The Final Project Publication will be disseminated as a hardcopy and CD-ROM formats and it can be uploaded on the project website to raise further public awareness. The responsible expert for this activity will be the TA Team Leader. The Team Leader will coordinate the demobilisation of experts, equipment and other project facilities, and verification and transfer of any files belonging to the project to the MoLHSA and Contracting Authority. In addition, we propose that the TL will arrange final briefing meetings with the counterparts from the relevant bodies and AFD. A closing event will also help disseminate information and deliverables to the relevant stakeholders and ensure their ownership. The team leader will bear the main responsibility of the preparation of the project’s Final Report. This report will summarize the projects achievements and list the recommendations made by the experts. In the continuity of interim reports, special emphasis will be put on how to ensure the sustainability of the results achieved. |
| Deliverable(s): | Final Report Closing event |
| Input | Team Leader: 25 WD Senior international experts : 15 WD |
| Timing | Month 24 |

Annex 1 Working days distribution

Laws concerning PWD are the following : Law on the Elimination of All Forms of Discrimination; Labour Code of Georgia; Law on the Social Protection of Persons with Disabilities; Law on Social Assistance of Georgia; Law of Georgia on Secondary Education and the National Education Plan

Main findings and figures come from :

- Geostat and National Health Account (2016) and NHA results (2012-2016)

- https://databank.worldbank.org/data/reports.aspx?source=world-development-indicators

- Tengiz Verulava and Tamar Maglakelidze, Health Financing Policy in the South Caucasus: Georgia, Armenia, Azerbaijan, Bulletin of the Georgian national academy of sciences, vol. 11, no. 2, 2017

- A.Jorbenadze, A. Zoidze, D. Gzirirshvili, G.Gotsadze, Health Reform and Hospital Financing in Georgia, Ministry of Health of Georgia; Curatio Medical Group, Tbilisi, Georgia

United Nations Children’s Fund (UNICEF), The Well-Being of Children and their families in Georgia, Georgia Welfare Monitoring survey fifth stage 2017, June 2018, prepared by Analysis and Consulting Team (ACT)

Advances in Psychiatry, published by Afzal Javed, Kostas N. Fountoulakis, Springer 2018