## AP 2020 Germany
Activity | Implementer | Partners | timeframe
1. Developing Infromation Materials and handouts for regional and local (self-)government for pre-selection of the initial caseload | IOM | Deputy Minister of Labor Migrtion, Division on labor Migrants Issues, Emplpoyment Agency | by 19-24 Feb
2. Planing meetings in the regions with the regional authorities - State representatives in Adjara, Guria and Samegrelo | Ministry of Labor; |  | 2020-02-24
3. Information and awareness raising meeting with Guria Governor and Mayors | IOM Tbilisi, IOM Batumi field office; Employment Support Agency | Adjara Government and Adjara Employment Agency | 2020-03-03
4. Working Meeting with the IOM Batumi field Offices | IOM Tbilisi, IOM Batumi field office; |  | 2020-03-03
5. Information and awareness raising meetings with the Adjara Employment agency | IOM Tbilisi and IOM Batumi field Office | Adjara Employment Agency | 2020-03-04
6. Information and awareness raising meetings with Samegrelo- ZS Governor and mayors in Zugdidi | IOM Tbilisi, Poti Field office | Labor Ministry, Employment Support Agency | 4 or 5 March
7. Working meeting with Poti field office | IOM Tbilisi |  | 2020-03-05
8. Meeting with the Mayors representatives in the territorial-admin units in Guria | IOM Batumi Office | Guria governor, mayors | 10-11 March
9. Meeting with the Mayors representatives in the territorial-admin units in Samegrelo | IOM Poti and IOM Kutaisi | Samegrelo governor, mayors | 10-11 March
10. Initial inventory of persons interested in seasonal employment in Germany | Adjara Employment Agency and local authorities in Samegrelo and Guria and Poti collecting and sending to IOM field offices in Batumi and Poti (also provided to Tbilisi by IOM field offices) |  | 16 March Adjara; - 20 March For Samegrelo - 20 March for Guria
11. Provision of vacancies from the German BA | Ministry of Labor and Employment Support Agency | German BA and employers | 20 March onward
12. Informing, Inviting to the IOM field offices and starting actual registration of potential migrant workers |  |  | 24 Mar -10 Apr
13. Selection of first cohort of vacancy relevant candidates | Labor Ministry, Employment Agency and IOM |  | From 25 March onward in parallel to regitration process
14. Provision of infromation about the selected candidate to the german BA accrodingto the provided form | IOM offices filling and submitting to employment Agency; Employment Agency sending to the German BA |  | 6 April onward
15. German Employers contacting workers for labor contract and work permit related issues | Labor Ministry |  | TBD
16. Pre-Departure Orientation Trraining for those selected | IOM |  | TBD
17. Pre-embarkation support to departing migrants (information about the travel tickets, insurance, bank info etc.) | IOM |  | TBD