| Activities | Target Group | Targeted # PoC (direct & indirect) | Impact Indicators | Stakeholders responsible | Timeframe | Budget required |
| --- | --- | --- | --- | --- | --- | --- |
| PoC verification exercise including livelihood assets; PoC focus groups; Survey instrument | All PoCs 16-59 in Tbilisi and main rural areas |  | Extent Economic and Social Integration Realized | Propose use of regional research organization, such as CRCC. | 2019-2020 |  |
| Stakeholder meeting to review strategy conducted and feedback incorporated | Key external stakeholders engaged in planning process: Public Sector, NGOs, and Private Sector |  | Extent Economic and Social Integration is realized | Direct partners: Government (Refugees counterpart); Ministry of IDP, Labour, Health and SA; | Q3 2019 |  |
| PoCs are included in programming of government and other development actors; including mainstreaming into programs that do not accept non-citizens | Youth; women; PoCs (16-59) |  | Extent social and economic integration is realized | Partners: MOLHSS, MIA, Ministry of Education; Enterprise Georgia; World Bank, UNDP, GIZ, and others |  |  |
| Establish individual economic integration plan for targeted PoCs; Through social counsellors, register job-seekers via Worknet. Actively followup with PES on job-matching performance. Refer job-seekers to NGOs with internships and job-matching programs | Unemployed, poor, skilled refugees (18-59 years of age) living in Tbilisi |  | Extent persons of concern have formal access to work opportunities in host country | MOLHSA, Public Employment Service “Worknet”; Integration support services partner (“Integration Centre”; Open House?) |  |  |
| Refugees have access to adult-centric learning of Georgian language at appropriate level with no more than 15 students per class. (English and Russian) | UNHCR recognized refugees |  | Extent persons of concern have formal access to work opportunities in host country | Jhvania Language School; Ministry of Education |  |  |
| Introduce to ENTERPRISE GEORGIA for participation in business development programming. | Recently arrived; Skilled refugees (18-59) with prior business experience and some financial capital |  | Extent persons of concern have formal access to work opportunities in host country | Enterprise Georgia (or equivalent) |  |  |
| Vocational institutions are identified; reduced or waived fees are negotiated. PoCs sign completion commitment as part of individual integration plan. | PoCs who through acquisition of new skills can be matched with the labour market; focus on Youth (15-24) and women (15-59) |  | Extent persons of concern have formal access to work opportunities in host country | To be identified; Minister of Education; Ministry of Labour |  |  |