## AP 2020 Germany
Action PLan on Employment in Germany
| Activity | Implementer | Partners | timeframe
1 | Planing meetings in the regions with the regional authorities - State representatives in Adjara, Guria and Samegrelo | Ministry of Labor; |  | 2020-02-28
2 | Developing Infromation Materials and handouts for regional and local (self-)government for pre-selection of the initial caseload | IOM | Deputy Minister of Labor Migrtion, Division on labor Migrants Issues, SESA | 2020-03-05
3 | Information and awareness raising meeting with the State Representaive in Guria Governor and the Mayors of the Municipalities | Ministry of Labor; State Employment Support Agency (SESA) | IOM | 2020-03-09 | 15:00
4 | Information and awareness raising meeting in Batumi with Government of Autonomous Republic of Adjara and the Mayors of the Municipalities | Ministry of Labor; SESA | IOM | 2020-03-10 | 10:00
5 | Information and awareness raising meetings with the Adjara Employment Agency, counselors of SESA (5 people) , IOM field staff (2 people) | IOM | Adjara Employment Agency; SESA | 2020-03-10 | 15:00
6 | Information and awareness raising meeting in Zugdidi with the State Representaive in Samegrelo- ZS Governor and the Mayors of the Municipalities | Ministry of Labor; SESA | IOM | 2020-03-11 | 10:00
7 | Meeting with the representatives of the Mayor in the aministative units in Guria | IOM Batumi Office and Guria Employment Agency regional staff (3 Municipalities in 2 days) | State Representarive in Guria; Mayors | 16-17 March
8 | Meeting with the Representatives of the Mayor in the territorial-admin units in Samegrelo | IOM Poti (4 Municipalities in 2days) and 2 regional staff of the Employment Agency from Zugdidi (4 Municipalities in 2 days) | State Representaive in Samegrelo, Mayors | 16-18 March
9 | Initial inventory of persons interested in seasonal employment in Germany | Adjara Employment Agency and local authorities in Samegrelo and Guria and Poti collecting and sending to IOM field offices in Batumi and Poti (also provided to Tbilisi by IOM field offices) | IOM field offices in Batumi, Poti and Kutaisi; SESA | 23 March Adjara; 30 March For Samegrelo and for Guria
10 | Provision of vacancies from the German BA | Ministry of Labor; SESA | German BA and employers | 30 March onward
11 | information materials developed based on the vacancy information and provision to the IOM field offices and Employment Agency staff | IOM | Ministry of Labor; SESA
12 | Inviting the preselected caseload to the IOM field offices, providing detailed Information about vacancies, registering relevant potential migrant workers; Filling in "Application form for a seasonal employment" and "Questionnaire_annex on social insurance" and sending this forms to IOM Tbilisi | IOM field offices in Batumi, Poti and counselors of SESA | SESA | 1 -16 Apr
13 | Selection Panel for selecting the vacancy relevant candidates | Ministry of Labor,SESA and IOM |  | From 22 April onward
14 | Provision of information to the German BA on the selected candidates as per the forms ("Application form for a seasonal employment" and "Questionnaire_annex on social insurance") | Ministry of Labor; SESA | IOM | 27 April onward
15 | German Employers, Employment Support Agency/IOM and selected migrant workers finalizing labor contracting issues | ZAV; BA; | SESA | 15 May - 22 May
16 | Pre-Departure Orientation Trraining for those selected | IOM Tbilisi and IOM field Office in Batumi, Poti, Kutaisi |  | 20 May onward
17 | Pre-embarkation support to departing migrants (information about the travel tickets, insurance, bank info etc.) | IOM |  | 20 May onward