## AP 2020 Germany
Action PLan on Employment in Germany
Activity | Implementer | Partners | timeframe
1. Planing meetings in the regions with the regional authorities - State representatives in Adjara, Guria and Samegrelo | Ministry of Labor; |  | 2020-02-28
2. Developing Infromation Materials and handouts for regional and local (self-)government for pre-selection of the initial caseload | IOM | Deputy Minister of Labor Migrtion, Division on labor Migrants Issues, Emplpoyment Agency | 2020-03-05
3. Information and awareness raising meeting with Adjara Governor | Ministry of Labor; Employment Support Agency | IOM | 2020-03-09
4. Information and awareness raising meetings with the Adjara Employment agency | IOM Tbilisi and IOM Batumi field Office | Adjara Employment Agency | 2020-03-09
5. Information and awareness raising meeting with Guria Governor | Ministry of Labor; Employment Support Agency | IOM | 2020-03-10
6. Information and awareness raising meetings with Samegrelo- ZS Governor and mayors in Zugdidi | Ministry of Labor; Employment Support Agency | IOM | 2020-03-10
7. Working meeting in Batumi withthe IOM Field staff from Batumi, Poti and Kutaisi and 6 staff of the Employment Agency from the regional offces in Guria, Adjara and Samegrelo | Ministry of Labor; Employment Support Agency; IOM |  | 2020-03-11
8. Meeting with the Mayors representatives in the territorial-admin units in Guria | IOM Batumi Office and Guria Employment Agency regional staff (3 Municipalities in 2 days) | Guria governor, mayors | 16-17 March
9. Meeting with the Mayors representatives in the territorial-admin units in Samegrelo | IOM Poti (4 Municipalities in 2days) and 2 regional staff of the Employment Agency from Zugdidi (4 Municipalities in 2 days) | Samegrelo governor, mayors | 16-17 March
10. Initial inventory of persons interested in seasonal employment in Germany | Adjara Employment Agency and local authorities in Samegrelo and Guria and Poti collecting and sending to IOM field offices in Batumi and Poti (also provided to Tbilisi by IOM field offices) | IOM field offices in Batumi, Poti and Kutaisi; Employment Support Agency | 23 March Adjara; 30 March For Samegrelo and for Guria
11. Provision of vacancies from the German BA | Ministry of Labor and Employment Support Agency | German BA and employers | 20 March onward
12. information materials developed based on the vacancy information and provision to the IOM field offices and Employment Agency staff | IOM | Ministry of Labor and Employment Support Agency | 2020-03-24
13. Inviting the preselected caseload to the IOM field offices, providing detailed Information about vacancies, registering relevant potential migrant workers; Filling in "Application form for a seasonal employment" and "Questionnaire_annex on social insurance" and sending this forms to IOM Tbilisi | IOM field offices in Batumi, Poti and the Staff of the Employment Agency | Employment Support Agency | 26 Mar -16 Apr
14. Selection Panel for selecting the vacancy relevant candidates | Ministry of Labor, Employment Support Agency and IOM |  | From 22 April onward in parallel to regitration process
15. Provision of information to the German BA on the selected candidates as per the forms ("Application form for a seasonal employment" and "Questionnaire_annex on social insurance") | Ministry of Labor; Employment Support Agency | IOM | 27 April onward
16.German Employers, Employment Support Agency/IOM and selected migrant workers finalizing labor contracting issues | ZAV; BA; | Employment Support Agency | 15 May - 22 May
17. Pre-Departure Orientation Trraining for those selected | IOM Tbilisi and IOM field Office in Batumi, Poti, Kutaisi |  | 20 May onward
18. Pre-embarkation support to departing migrants (information about the travel tickets, insurance, bank info etc.) | IOM |  | 20 May onward