## Gantt Chart
[9 empty] | 2019 |  |  | 2020 | [9 empty] | 2021 |  |  |  | 2022 |  |  |  | 2023
|  | TOTAL | TL | KE2 | KE3 | JNKE |  | SNKE | Reporting Period 1 | [5 empty] | Reporting Period 2 | [5 empty] | RP 3 |  | RP 4 |  | RP 5 |  | RP 6 |  | RP 7 |  | RP 8
[6 empty] | LT | ST |  | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Q1 | Q2 | Q1 | Q2 | Q1 | Q2 | Q1 | Q2 | Q1 | Q2 | Q1 | Q2
Component 4: Employment Services |  | 1079 | 37 | 460 | 32 | 300 | 0 | 250
4.1 | State Employment Support Agency (SESA) supported in its implementation of the Revised New Service Model (NSM) | 370 | 13 | 160 | 7 | 100 | 0 | 90
4.1.1 | Assessment of current system of the NSM, recommendations | [19 empty] | q |  | q | bar: Reporting Period 1 Feb to Reporting Period 2 Sep
4.1.2 | Institutional development of SESA | [19 empty] | q |  |  |  | q | bar: Reporting Period 1 Mar to Reporting Period 2 Sep
4.1.3 | Develop detailed instructional materials for NSM work methodology | bar: Reporting Period 2 Jun to Reporting Period 2 Sep
4.1.4 | Strategy for improving links with local / regional stakeholders | [23 empty] | q | bar: Reporting Period 2 Jul to Reporting Period 2 Sep
4.1.5 | Guidance for planning, implementing, monitoring and evaluation of measures
4.1.6 | Develop proposals for increasing public awareness of employment services
4.2 | SESA supported in designing and delivering more accessible, effective and comprehensive ALMP measures for all job seekers | 337 | 12 | 150 | 5 | 100 | 0 | 70
4.2.1 | Assessment of current system of ALMP measures | [21 empty] | q
4.2.2 | Proposal for the upgrade and revision of all types of ALMP measures | [23 empty] | q
4.2.3 | Procedures and guidance materials for ALMP measures | [24 empty] | q
4.2.4 | Proposal for revised/redesigned career guidance/ counselling for jobseekers | [24 empty] | q
4.2.5 | Replicable pilot programmes of new ALMP measures
4.3 | Capacity (knowledge and expertise) developed within the ESA staff to provide more effective employment services for jobseekers and employers | 372 | 12 | 150 | 20 | 100 | 0 | 90
4.3.1 | Induction training and TNA of SESA | bar: Reporting Period 2 Sep
4.3.2 | Training plan for staff of SESA and other relevant institutions | [19 empty] | q | bar: Reporting Period 1 Mar; Reporting Period 2 Jul
4.3.3 | Training measures
4.3.4 | Study visit to EU member state(s)
4.3.5 | Exchange of experience with European peers and nationally | bar: Reporting Period 2 Sep
4.3.6 | Coaching scheme and pilot for the staff of SESA and other relevant institutions