## Sheet1
National Human Rights Action Plan 2018-2020
Women's Rights and Gender Equality
15. Establishment of the equality policy and combating discrimination
Goal | Objective | Objective Indicator | Activity | Responsible Agency | Partner Agency | International Recommendations | Deadline | Status | Budget
15.1. Raising awareness and qualifications about the issues related to sexual orientation and gender identity (SOGI) | 15.1.1. Raising awareness about the inadmissibility of discrimination and hate speech against the SOGI vulnerable groups and the hate-motivated crimes | 1. The relevant promotional social campaigns on raising awareness have been conducted through inter-agency cooperation and participation; 2. In the framework of the campaigns, along with the other activities, more than four informational brochures have been issued and published against discrimination and hate speech directed to the SOGI vulnerable groups. 3. The expert assessment has been prepared on extistence of the encouraging stigmatizing opinions, deliberations or/and definitions in the textbooks for the general education. | 15.1.1.1 1. Organizing the inter-agency and public social campaigns on inadmissibility/the negative effects of discrimination and hate speech against SOGI vulnerable groups, hate crimes and promoting tolerance | Administration of the Government; Ministry of Justice; Ministry of Internal Affairs; Ministry of Education, Science, Culture and Sport; Ministry of Internally Displaced Persons from the Occupied Territories, Health and Social Affairs; State Ministry for Reconciliation and Civic Equality; Prosecutor’s Office; Public Institutions | Ministry of Economy and Sustainable Development; Ministry of Finance; Ministry of Foreign Affairs; Ministry of Environmental Protection and Agriculture; Ministry of Defense; Ministry of Regional Development and Infrastructure; Civil Service Bureau | CCPR Rec: 8; UPR Rec: 117.33; UPR Rec: 117.49; ECRI Rec: (§ 67), CERD Rec: (7.b); CCPR Rec: 8; UPR Rec: 117.45 | 2020
|  |  | 15.1.1.2.2. Revision of the textbooks for general education that might contain stigmatizing opinions and/or definitions fostering discrimination | Ministry of Education, Science, Culture and Sport; Administration of the Government |  | UPR Rec: 117.49; UPR Rec: 118.9; CCPR Rec: 8; ECRI Rec: (§ 108); UPR Rec: 117.33 | 2020
| 15.1.2. Enhancing qualifications related to equality, the issues of prohibition of the hate-motivated crimes and discrimination based on SOGI | 1. Prohibition of hate-speech, discrimination (including based on SOGI) and harassment (including based on SOGI) has been laid down in the internal and professional codes of ethics of more than seven institutions; 2. Based on the analysis of the available resources and the needs observed during the activities, the general education module and the guideline principles have been elaborated and implemented; 3. Based on the analysis of the available resources and the needs observed during the activities, the specialized education module and the guideline principles have been elaborated and implemented; | 15.1.2.1. Enshrining the provisions on prohibition of hate-speech, discrimination (including based on SOGI) and harassment (including based on SOGI) in the intstitutional and professional codes of ethics (including in the process of providing public services) | Administration of the Government; Ministry of Justice; Ministry of Internal Affairs; Ministry of Education, Science, Culture and Sport; Ministry of Internally Displaced Persons from the Occupied Territories, Health and Social Affairs; State Ministry for Reconciliation and Civic Equality; Prosecutor’s Office; Ministry of Regional Development and Infrastructure; Civil Service Bureau; Public Institutions | Ministry of Economy and Sustainable Development; Ministry of Finance; Ministry of Foreign Affairs; Ministry of Environmental Protection and Agriculture; Ministry of Defense; | FCNM Rec: Para 59; CCPR Rec: 8; UPR Rec: 117.33; UPR Rec: 117.49 | 2020
|  |  | 15.1.2.2. Mapping of the ongoing activities at the public institutions, as well as the available resources for enhancement of qualifications related to equality, the hate-motivated crimes and SOGI-based discrimination with the aim of unification and its utilization as a unified system | Administration of the Government in cooperation with other institutions |  | UPR Rec: 117.49; UPR Rec: 118.9 | 2020
|  |  | 15.1.2.3. (based on mapping) Elaboration and creation of the analysis-based informational resources/materials for the staff of the relevant institutions on equality issues, inadmissibility/prohibition of the hate-motivated crimes and SOGI-based discrimination | Administration of the Government; Ministry of Internal Affairs; Ministry of Education, Science, Culture and Sport; Ministry of Internally Displaced Persons from the Occupied Territories, Health and Social Affairs; State Ministry for Reconciliation and Civic Equality; Prosecutor’s Office; Civil Service Bureau; Public Institutions | Ministry of Foreign Affairs; Ministry of Economy and Sustainable Development; Ministry of Finance; Ministry of Environmental Protection and Agriculture; Ministry of Regional Development and Infrastructure; Ministry of Defense; Ministry of Justice | CCPR Rec: 8; UPR Rec: 117.33; UPR Rec: 117.49; ECRI Rec: (§ 67); CERD Rec: (7.b); UPR Rec: 117.45 | 2020
|  |  | 15.1.2.4. Distribution of the elaborated informational resources and materials at the relevant public institutions | Administration of the Government; Ministry of Justice; Ministry of Internal Affairs; Ministry of Education, Science, Culture and Sport; Ministry of Internally Displaced Persons from the Occupied Territories, Health and Social Affairs; State Ministry for Reconciliation and Civic Equality; Prosecutor’s Office; Civil Service Bureau; Public Institutions | Ministry of Foreign Affairs; Ministry of Economy and Sustainable Development; Ministry of Finance; Ministry of Environmental Protection and Agriculture; Ministry of Regional Development and Infrastructure; Ministry of Defense; | CERD Rec: (7.b); UPR Rec: 118.9; CCPR Rec: 8; UPR Rec: 117.33; UPR Rec: 117.49; ECRI Rec (§ 67); UPR Rec: 117.45; ECRI Rec: (§ 108) | 2020
|  |  | 15.1.2.5. Implementation of specialized (in-depth) educational module at the relevant public institutions | Administration of the Government; Ministry of Education, Science, Culture and Sport; Ministry of Internally Displaced Persons from the Occupied Territories, Health and Social Affairs | Ministry of Foreign Affairs; Ministry of Economy and Sustainable Development; Ministry of Finance; Ministry of Environmental Protection and Agriculture; Ministry of Regional Development and Infrastructure; Ministry of Defense; | UPR Rec: 118.9; UPR Rec: 117.42 | 2020
| 15.1.3. Prohibition of discrimination in labor and pre-contract relations | 1. The Human resources policies of the public institutions provide a written clause on prohibition of discrimination in pre-contract relations in the vacancy announcements; 2. Inter- agency activities about inadmissibility of discriminatory practices in labor relations and at the workplace have been organized at the public institutions | 15.1.3.1. A written clause about prohibition of discrimination in the pre-contract relations in the vacancy announcements by public institutions | Administration of the Government; Public Institutions |  | UPR Rec: 117.33; ECRI Rec: (§ 108); CCPR Rec: 8; COE CM/Rec(2010)5 | 2020
|  |  | 15.1.3.2. Policy Implementation on prihibition of the discriminatory practices/treatments at the workplace and in labor relations at the public institutions | Administration of the Government; Public Institutions | Ministry of Regional Development and Infrastructure; Ministry of Justice; Ministry of Internal Affairs; Ministry of Education, Science, Culture and Sport; Ministry of Internally Displaced Persons from the Occupied Territories, Health and Social Affairs; Ministry of Economy and Sustainable Development; Ministry of Finance; Ministry of Foreign Affairs; Ministry of Environmental Protection and Agriculture; Ministry of Defense; State Ministry for Reconciliation and Civic Equality; Court; Prosecutor's Office; Civil Service Bureau; | UPR Rec: 117.33; ECRI Rec: (§ 108); CCPR Rec: 8; COE CM/Rec(2010)5 | 2020
15.2. Combating the hate crime | 15.2.1. Realization of the institutional and executive activities eliminating the hate-motivated crimes | 1. The unified and certified education module for the agencies working on hate-motivated crimes has been revamped and implemented; 2. Investigators of the Ministry of Internal Affairs have been retrained; 3. Investigators and prosecutors of the Prosecutor's Office have been retrained | 15.2.1.1. Updating and Implementing the education module with the goal of retraining the investigators working on the hate-motivated crimes | Ministry of Internal Affairs |  | CM/ResCMN(2018)7; FCNM Rec. Para 58 CERD Rec: (7.b) | 2020
|  |  | 15.2.1.2. Revision and refinement of the specialized education module for the prosecutors and investigators of the Prosecutor’s Office working on the hate-motivated crimes | Prosecutor's Office |  | CM/ResCMN(2018)7; FCNM Rec. Para 58 CERD Rec: (7.b) | 2020
|  |  | 15.2.1.3. Functional expansion and enhancement of the hotline for the victims of human trafficking, domestic violence, violence against women and sexual harassment with the objective of reflection of needs of the SOGI vulnerable groups | Ministry of Internally Displaced Persons from the Occupied Territories, Health and Social Affairs; State Foundation for Protection and Assistance of Victims and Individuals Affected by Human Trafficking (later, Agency for Public Care and Assistance of Victims of Human Trafficking) | Ministry of Foreign Affairs | UPR Rec: 118.9. | 2020
| 15.2.2. Producing and maintaining the segregated statistics on the hate-motivated crimes | 1. The synchronized database of statistics has been created based on the unified criteria; 2. Relevant statistics are maintained and are accessible (based on the requests and/or through a website) | 15.2.2.1. Creation of an inter-agency database of statistics based on the unified criteria | Ministry of Internal Affairs; Prosecutor's Office; Court; National Statistics Office of Georgia; Ministry of Internal Affairs | Administration of the Government | ECRI Rec: (§ 48) | 2020
|  |  | 15.2.2.2. Accessibility of the segregated data to the contract monitoring agencies | Prosecutor's Office; Court; National Statistics Office of Georgia | Administration of the Government; Ministry of Internal Affairs; Ministry of Foreign Affairs | ECRI Rec: (§ 48) | 2020
15.3. Improvement of the SOGI specific social and healthcare services | 15.3.1. Study of the current services considering the SOGI particularities | 1. Through the study of the services, taking into account the SOGI specificities, with the objective of improving the quality of such services, the specific recommendations have been developed | 15.3.1.1. Studying (mapping) of the existing social and healthcare services with SOGI particularities in mind | Ministry of Internally Displaced Persons from the Occupied Territories, Health and Social Affairs | Administration of the Government | UPR Rec: 15.1.8.1.; ECRI Rec: (§ 108); CCPR Rec: 8.: UPR Rec: 117.33.(Netherlands); UPR Rec: 117.49. (Brazil). | 2020
|  |  | 15.3.1.2. Elaboration of the specific recommendations and initiation of their implementation with the aim of improvement of the existing social and healthcare services considering the SOGI Specificities | Ministry of Internally Displaced Persons from the Occupied Territories, Health and Social Affairs | Administration of the Government | ECRI Rec: (§ 108); CCPR Rec: 8.: UPR Rec: 117.33.(Netherlands), UPR Rec: 117.49. (Brazil). | 2020
| 15.3.2. Improvement of the healthcare services for the transgender persons | 1. The special protocol for providing the medical services has been developed; 2. The number of the received and reviewed complaints at the agency relevant to provision of the medical services | 15.3.2.1. Development of a special protocol for provision of medical services considering the needs of the transgender individuals, based on the international best practices | Ministry of Internally Displaced Persons from the Occupied Territories, Health and Social Affairs | Administration of the Government | ECRI Rec: (§ 108); CCPR Rec: 8.: UPR Rec: 117.33. | 2020
|  |  | 15.3.2.2. Sensitization of sexual and reproductive healthcare and the psycho-social services with consideration for the needs of transgender individuals | Ministry of Internally Displaced Persons from the Occupied Territories, Health and Social Affairs | Administration of the Government | ECRI Rec: (§ 108); CCPR Rec: 8.; UPR Rec: 117.33 (Netherlands). | 2020
| 15.3.3. Study on the status of rights of the intersex individuals (including an access to the medical services) | 1. The study on the status of rights of the intersex individuals has been conducted | 15.3.3.1. Conducting a study on the status of rights of the intersex individuals | Ministry of Internally Displaced Persons from the Occupied Territories, Health and Social Affairs; Administration of the Government | Administration of the Government | ECRI Rec: (§ 108); CCPR Rec: 8; UPR Rec: 117.33. | 2020
| 15.3.3. Combating discrimination based on sexual orientation and gender identity in a penitentiary system | * This issue is covered by the 2019-2020 Action Plan for Combat Against Torture, Inhumane, Cruel and Degrading Treatment or Punishment |  | Ministry of Justice |  | UPR Rec: 117.49
| 15.3.4. Development of an initial concept of the shelter for SOGI-based vulnerable groups | 1. The needs-assesment study for the crisis center and the shelter for the SOGI-based vulnerable groups, as well as the accessibility to appropriate housing has been conducted; 2. The initial concept for the shelter for SOGI-based vulnerable groups has been elaborated | 15.3.4.1. The needs-assesment study for the crisis center and the shelter for the SOGI-based vulnerable groups, as well as accessibility to appropriate housing | Ministry of Internally Displaced Persons from the Occupied Territories, Health and Social Affairs; Administration of the Government | Ministry of Justice; Ministry of Internal Affairs | ECRI (§ 108); CCPR Rec: 8.; UPR Rec: 117.33.(Netherlands); UPR Rec: 117.49. (Brazil). | 2020
|  |  | 15.3.4.2. Development of the initial concept for a shelter for the SOGI-based vulnerable groups | Ministry of Internally Displaced Persons from the Occupied Territories, Health and Social Affairs; Administration of the Government | Ministry of Justice; Ministry of Internal Affairs | ECRI (§ 108); CCPR Rec: 8.; UPR Rec: 117.33.(Netherlands); UPR Rec:117.49. (Brazil). | 2020