## November 2018
Pilot of the Social Model in Ajara
MoIDPOTLHSA - Ministry of Internally Displaced Persons from the Occupied Territories, Labour, Health and Social Affairs GASW - Georgian Association of Social Workers
| Major Components | Activities | Status of Activity | Starting Date/Period | Duration/completion date | Resources | Responsible unit/ organization | Key areas for consideration/Risks
1 | Functional Assessment Instruments
1.1. | Child assessment instrument | Prepare Geo Version of the instrument | Completed |  |  | Local consultants/ UNICEF's grant | UNICEF/GASW
|  | Description of the scale "severity of disability" | In progress | Started in November, 2018 | First part of January, 2019 | Local consultants/ UNICEF's grant | UNICEF/GASW consultant's team | Without creating the 'descriptive scale' of functional disability -'mild', 'moderate', 'severe', 'profound' will be difficult to start assessment process in Ajara. If a research company is hired in December then the 'descriptive scale' can be developed by the company.
|  | Standardization of the instrument (including the well-defined sample) | Has not started | Will start in December 2018 | 7-8 months | Financial resources of UNICEF | UNICEF will hire the research company | UNICEF's procedures to hire the company will take one month - research proposal, external review, announcement. Creation of the nation-wide instrument might require more financial resouces and time
|  | Prepare the program in Excel for administration of the instrument's scores | Has not started | November-December 2018 | 2 month | IT person will be hired through GASW's grant | UNICEF/GASW | The optimal solution is to create the excel program of scoring together with the research company. If there is a delay in hiring the research company, UNICEF through GASW can hire the IT person
1.2. | Adult assessment instrument - WHODAS 2.0. | Translate Geo Version | Completed |  |  | UNICEF | UNICEF
|  | Prepare the program in Excel for administration of the instrument's scores | Completed | 2018-12-01 | 2018-12-01 | UNICEF | UNICEF | The excel program is created and for better administration of the WHODAS's scores, it is important to upload the program to the webhost.
2 | Human Resources - Functional Assessment Specialists and Medical Doctors
2.1. | Functional Assessment Specialists (FAC) | Develop the job descriptions of the functional assessment specialists for children and adults. Agree the JDs with the MoIDPOTLHSA | Completed |  | October,2018 | UNICEF | UNICEF | It is important to make decision about hiring and preparing the case managers MoIDPOTLHSA
|  | Prepare the training program and materials for the specialists | In progress | November | December 2 | Local consultants will implement this activity through GASW's grant | GASW/UNICEF
|  | Define the number of the functional assessment specialists according to the data of 6 health institutions in Ajara and recruit them | Has not started |  | Beginning of December | UNICEF/local consultants | GASW/UNICEF | The trained specialists will be selceted according to the results of the trainings. Hiring of the case managers will require additional financial resources
|  | Provide the initial trainings to the specialists in Batumi | Has not started | December, 2018 | 2019-01-01 | GASW's grant | GASW/UNICEF
|  | Contract the specialists and equip them with the tablets/computers | Has not started | 2019-01-01 | 2019-01-01 | GASW's grant | GASW/UNICEF
|  | Provide the professional supervision/coaching to the functional assessment specialists | Has not started | 2019-01-01 | 2019-07-01 | GASW's grant | GASW/UNICEF
3 | Role of 6 Health Institutions in Ajara and capacity building of their medical doctors
3.1. | Medical doctors of Health Institutions | Provide trainings to the medical doctors involved in the disability status determination. Trainings will raise awarness of the medical doctors to promote referrals to functional assessment within the pilot | Has not started | 2019-01-01 | 2019-02-01 | GASW's grant | GASW/UNICEF/MoIDPLHSA
|  | Promote their participation in the pilot of the system - compare the health conditions of the claimants to the results of the functional assessments | Has not started | 2019-01-01 | 2019-07-01 | GASW's grant | GASW/UNICEF/MoIDPLHSA
3.2 | Accommodate the functional assessment specialists | Allocate the working space for the FAC | Has not started |  | 2019-01-01 | Health institutions | MoIDPLHSA/Health institutions
|  | Promote the voluntary referrals for the functional assessment | Has not started | 2019-01-01 | 2019-07-01 | N/A | Health Institutions
3.3. | Participate in the pilot | Participate in the working meetings related to piloting of the assessment and new system | Has not started | 2019-01-01 | 2019-07-01 | GASW's grant | GASW/UNICEF/Health Institutions
4 | Filed Work
4.1. | Informing the claimants/respodents | Prepare the brochures explaining a role of functional assessment and pilot | Has not started | 2018-12-01 |  | GASW's grant | GASW and local experts
|  | Prepare written consents for the respodents | Has not started | 2019-01-01 |  | GASW's grant | GASW and local experts
4.2 | Functional Assessment | Ensure the professional supervsion/coaching of the specialists | Has not started | 2019-01-01 | 2019-07-01 | GASW's grant | GASW/UNICEF
|  | Provide the functional assessment and process the data into excel programs | Has not started | 2019-01-01 | 2019-07-01 | GASW's grant | GASW/UNICEF
|  | Carry out interim evaluations of the field work | Has not started | 2019-03-01 | 2019-05-01 | GASW's grant | GASW/UNICEF
5 | Policy initiatives and evaluation of the interim and final results of the pilot
5.1 | Collaboration with ICF team of WHO | Share the standartization plan of the child assessment instrument with WHO team and get their feedback; review the interim and final findings of the pilot | Ongoing process |  |  |  | UNICEF
5.2 | Cooperation with the Health Department | Meeting with the Health Department of MoIDPOTLHSA to discuss the pilot and get their feedback |  |  | 2018-12-01 |  |  | The Deputy Minister and Head of the Social Protection Department will initiatie and facilitate this meeting
5.3 | Institutional steering group at the regional level | Establish the regional group composed by the representatives of the Ministry of Health and Social Affairs of Ajara, six health institutions, Disabled Persons Organizatuions , Social Service Agency and etc. | Has not started | 2019-01-01 | 2019-07-01 | N/A/ | MoIDPOTLHSA/UNICEF/GASW
|  | Ararnge the regional group meetings to support and assess the pilot in Ajara | Has not started | 2019-01-01 | 2019-06-01 | GASW's grant | MoIDPOTLHSA/UNICEF/GASW
5.4 | Local working group of the functional assessment specialists | Arrange the regular working group meetings to evaluate the assessment process - instruments, interviewing process, feedback from the respodents | Has not started | 2019-01-01 | 2019-06-01 | GASW's grant | MoIDPOTLHSA/UNICEF/GASW
5.5 | Monitoring and evaluation of the pilot | Develop the set of indicators for monitoring and evaluation of the pilot process. Evalution will include the feedback from adults with disabilities, parents of children with disabilities and children with disabilities | Has not started | 2018-12-01 | 2019-01-01 | N/A | MoIDPOTLHSA/UNICEF
5.6 | Evaluation of the pilot from perspective of the human rights, CRPD | Define the indicators and provide the interim and final assessment | Has not started | 2019-01-01 | 2019-07-01 | Human Rights Lawer/GASW
5.7 | Report on the pilot | Develop the concept note according to the findings of the pilot process - analize who will be included and excluded in the system, the admin costs of the new system; results on indicators | Has not started | 2019-07-01 |  |  | MoIDPOTLHSA/UNICEF/GASW
6 | Public Awarnerss
6.1. | Raise awarness of persons with disabilities and parents of children with disabilities toward the pilot | Meetings with Disabled Persons Organizations, associations of parents of children with disabilities, service beneficiaries |  |  |  | UNICEF |  | UNICEF/GASW