# ILO – Danida: Inclusive Labour Market for Job Creation in Georgia

# The ILO-MoIDPLSA meeting minutes

| Location: | Ministry of Internally Displaced Persons from the Occupied Territories, Labour, Health and Social Affairs of Georgia, 144, Ak. Tsereteli Ave. Tbilisi 0119 |
| --- | --- |
| Date: | 31.10.2019 |
| Time: | 10:00 – 10:45 |
| Attendees: | Ms. Tamuna Barkalaia, Deputy Minister Ms. Lika Klimiashvili, Head of Labour and Employment Policy and Collective Labour Disputes Division, Policy Department Ms. Tamar Rurua, Chief Specialist, Labour and Employment Policy and Collective Labour Disputes Division, Policy Department Mr. Kinan Bahnassi, Chief Technical Adviser, ILO Ms. Tamar Kheladze, M&E Officer, ILO |

# Agenda items

Overview of the employment support services programming of the ministry

Discuss and agree on ILO-MoIDPLSA work plan in terms of active labour market policies in 2020

| # Action items | # Activities and Status |
| --- | --- |
| Labour Market Assessment: conducting rapid regional labour market assessment to provide analysis on required employment services, potential sector growth and diversification of stagnating sectors, as well as skills needs for seven regions, targeted by the State Employment Services. | Develop ToR for the labour market assessment The ILO will share with the ministry the sample ToR of DANIDA Ukraine, sister project, where the project has helped to establish local employment partnerships (may be replicated in target 9 regions). |
| Improvement and upgrade of Worknet software: upgrading the system Worknet, to produce job placement service, case management, and a well-structured reporting and statistical information for employment services. | -Meeting to be organized with the IT department of the ministry - Develop ToR to define the scope of work required to upgrade the Worknet system. The content of the ToRs to be agreed on with the ministry and to be drafted by the ILO. |