## Gantt Chart
|  | TOTAL | TL | KE2 | KE3 | JNKE |  | SNKE | 2020 | [14 empty] | 2020 | [5 empty] | 2021 |  |  |  | 2022 |  |  |  | 2023
[6 empty] | LT | ST |  | Jan |  | Feb |  | Mar |  |  | Apr |  |  |  | May |  | Jun |  | Jul | Aug | Sep | Oct | Nov | Dec | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3
Component 0: Project Management |  | 207 | 100 | 70 | 22 | 15 | 0 | 0
| Inception Phase, Management and Reporting | 194 | 100 | 62 | 22 | 10 | 0 | 0 |  | q
Component 1: National Sector Reform Policies |  | 475 | 170 | 50 | 46 | 189 | 20 | 0
1.1 | National sector reform policies updated and improved | 239 | 80 | 50 | 0 | 89 | 20 | 0
1.1.1 | Analyse policies, strategies, action plans of the 3 ministries and Youth Agency in skills development and skills matching to identify gaps and propose improvements
1.1.2 | Support the updating and/or improvement of policies, strategies and/or action plans in line with national policy planning framework requirements
a) National VET strategy and action plan
b) Action plan for career education and guidance (general, VET, higher education)
c) National life-long entrepreneurship learning strategy
d) National labour and employment strategy and action plan
e) Action plan for youth services in the context of the revised national Youth Policy and legislation
1.1.3 | Assist MoESCS in surveying geographical coverage of VET by municipality, identifying gaps, and recommending solutions and priorities for expanding availability | [21 empty] | q
1.1.4 | Organize annual thematic workshops/events related to Sector Policy development to present/ discuss relevant Georgian and international experiences and practices | [10 empty] | r q | [17 empty] | r q |  |  |  | r q |  |  |  | r q
1.1.5 | Support strengthening of co-ordinating mechanisms between beneficiary ministries and institutions related to Sector Reform Policy development, implementation and monitoring
1.1.6 | Support implementation/further development of monitoring arrangements for sector strategies/action plans, incl. annual reviews on progress in achieving SRPC targets
1.1.7 | Provide administrative and logistical support to EU missions and expert visits to Georgia related to the SRPC
1.1.8 | Provide short update and progress reports to the EU Delegation related to the SRPC and its implementation
1.2 | Capacities in National Sector Policy development, implementation, monitoring enhanced | 111 | 45 | 0 | 46 | 20 | 0 | 0
1.2.1 | Develop capacity building programme for beneficiaries related to the requirements of national sector policy development, implementation and monitoring, incl.
a) Training in analysis /use of data in evidence-based policy making, incl. EMIS, LMIS
b) Training in financing and costing of action plans
c) Training in monitoring and evaluation of effectiveness of policies/implementation
d) Coaching/mentoring for senior staff in sector policy implementation/ monitoring
e) Training in communicating reforms to stakeholders and the wider public
f) Familiarization/linking with EU networks relevant to particular fields of the SRPC
1.2.2 | Monitor and evaluate progress in capacity building for the project beneficiaries and periodically adjust the programme according to emerging needs | [27 empty] | q |  |  |  | q |  |  |  | q
1.3 | Visibility/communications support for National Sector Policies and services of beneficiaries | 125 | 45 | 0 | 0 | 80 | 0 | 0
1.3.1 | Develop/implement communications and visibility plan incl.measures, tools, events to promote stakeholder engagement and raise public awareness | [8 empty] | q
1.3.2 | Prepare communications and visibility materials to support the project communications and visibility plan
1.3.3 | Support and monitor communications between project beneficiaries and key stakeholders to ensure effective coordination of SRPC-related activities
1.3.4 | Coordinate, support, monitor external communications across all components to raise awareness of SRPC reforms/project results, specifically by:
a) Assisting MoESCS in enhancing awareness of opportunities and attractiveness of VET and LLL though targeted activities and events
b) Increasing public awareness of the youth services, and youth transition and activation measures including social entrepreneurship
c) Generating public awareness of employment services/ALMPs to provide visibility for ESA, advertising services esp. to young people, women, vulnerable groups, NEETs
d) Generating public awareness and visibility of labour market information, including branding of the LMIS web portal
Component 2: |  | 648 | 220 | 40 | 0 | 158 | 80 | 150
2.1 | Enhanced capacity of MoESCS to develop/modernise skills devtt/LLL | 144 | 90 | 0 | 0 | 54 | 0 | 0
2.1.1 | Assist MoESCS in developing legal and financing arrangements to support VET and LLL
2.1.2 | Assist MoESCS in improving access to, and participation in, VET and LLL
2.2 | Enhanced capacity to provide prof. orientation/career guidance | 204 | 60 | 40 | 0 | 54 | 0 | 50
2.2.1 | Assist MoESCS in developing/improving arrangements for career education/guidance
| a) Review current situation, practices and quality in CEG, and capacity of institutions in genera, vocational and higher education to deliver effective services | [17 empty] | q
| b) Prepare proposal/action plan on further development/improvement of career guidance, including institutional arrangements at national, regional and local levels | [22 empty] | q
2.2.2 | Develop capacities in career education and guidance
| a) Develop/pilot training course and materials for teachers in secondary schoolsto take on the career counsellor role, including local partnerships | [27 empty] | q
| b) Review/update existing training module and materials for career managers in VET colleges | [28 empty] | r
2.3 | Enhanced capacity to deliver entrepreneurship education | 300 | 70 | 0 | 0 | 50 | 80 | 100
2.3.1 | Support MoESCS on the lifelong entrepreneurial learning action plan
2.3.2 | Design and pilot training programme for upper secondary teachers on entrepreneurship key competence development within Nat. Curriculum
2.3.3 | Design and pilot an in-service training programme for VET teachers and managers on entrepreneurship key competence development in VET programmes
2.3.4 | Prepare guidance materials for teachers on new learning methods and approaches to enhance entrepreneurship key competence development | [27 empty] | q
2.3.5 | Pilot entrepreneurial experience for students from general secondary education schools and VET colleges, and develop a model for replication in the education system
2.3.6 | Review entrepreneurship learning provision in universities/HE institutions based on a sample survey
2.3.7 | Organize pilots to enhance entrepreneurship learning in universities and disseminate results to the higher education community
Component 3: Youth |  | 684 | 206 | 40 | 0 | 158 | 80 | 200
3.1 | Enhanced capacity of Youth Agency to develop and deliver effective youth services | 211 | 71 | 10 | 0 | 50 | 30 | 50
3.1.1 | Assist the Youth Agency in organizational development, national strategy and action planning, for improvement and delivery of youth services in the regions
3.1.2 | Assess capacity building and support needs of Youth Agency staff and design and deliver a training plan and coaching scheme | [17 empty] | q
3.1.3 | Organize a study visit to EU member state(s) to observe best practices in the field of youth policy and youth services delivery
3.1.4 | Support the Youth Agency in Improving coordination and cooperation arrangements with other agencies and stakeholders
3.2 | Development of Youth Centres supported, including organizational and human capacities | 245 | 65 | 10 | 0 | 50 | 20 | 100
3.2.1 | Organizational capacities of selected Youth Centres in targeted regions assessed, and institutional development and improvement plans prepared | [19 empty] | q
3.2.2 | Capacity building and training needs of youth workers assessed, and appropriate arrangements put in place to ensure their training, qualifications and professionalization
3.3 | Effectiveness of youth services provision improved | 228 | 70 | 20 | 0 | 58 | 30 | 50
3.3.1 | Review current youth activation services delivery and support the Agency in revising/updating, implementing and monitoring youth activation measures across the regions in cooperation with relevant stakeholders | [21 empty] | q
3.3.2 | Review career orientation and guidance services provision for youth across the regions, and support the Agency in revising/developing and piloting more effective services, with guidance materials for planning, implementing, monitoring and evaluating provision | [27 empty] | q
3.3.3 | Review non-formal education and training provision for youth, and support the Youth Agency in developing/improving high quality training courses targeting the employability and social needs of young people in different regions and improving access for vulnerable young people, including key competence development, supported by manuals and materials for planning, developing delivering and monitoring/evaluating training provision | [29 empty] | q
3.3.4 | Review social entrepreneurship measures for youth and support the Youth Agency in developing and piloting innovative approaches to youth entrepreneurship | [28 empty] | q
3.3.5 | Assist the Youth Agency and youth centres in selected regions to increase public awareness of youth services including youth activation measures and social entrepreneurship
Component 4: Employment Services |  | 1079 | 37 | 460 | 32 | 300 | 0 | 250
4.1 | Revised New Service Model (NSM) put in place in the State Employment Support Agency (SESA) at central and regional level | 370 | 13 | 160 | 7 | 100 | 0 | 90
4.1.1 | Assessment of current system of the NSM, recommendations | [12 empty] | q |  |  | q
4.1.2 | Institutional development of SESA
4.1.3 | Develop detailed instructional materials for NSM work methodology
4.1.4 | Strategy for improving links with local / regional stakeholders
4.1.5 | Guidance for planning, implementing, monitoring and evaluation of measures
4.1.6 | Develop proposals for increasing public awareness of employment services | [21 empty] | q
4.2 | More accessible, effective and comprehensive ALMP measures available | 337 | 12 | 150 | 5 | 100 | 0 | 70
4.2.1 | Assessment of current system of ALMP measures | [21 empty] | q
4.2.2 | Proposal for the upgrade and revision of all types of ALMP measures | [25 empty] | q |  | q
4.2.3 | Procedures and guidance materials for ALMP measures | [28 empty] | q
4.2.4 | Proposal for revised/redesigned career guidance/ counselling for jobseekers | [29 empty] | q
4.2.5 | Replicable pilot programmes of new ALMP measures
4.3 | Capacity (knowledge and expertise) developed within the ESA staff to provide more effective employment services for jobseekers and employers | 372 | 12 | 150 | 20 | 100 | 0 | 90
4.3.1 | Induction training and TNA of SESA | [10 empty] | q
4.3.2 | Training plan for staff of SESA and other relevant institutions | [13 empty] | q
4.3.3 | Training measures
4.3.4 | Study visit to EU member state(s)
4.3.5 | Exchange of experience with European peers and nationally
4.3.6 | Coaching scheme and pilot for the staff of SESA and other relevant institutions
Component 5: Information Systems and Analysis |  | 627 | 37 | 60 | 200 | 180 | 0 | 150
5.1 | Data and information systems linked to support evidence-based policy making and implementation | 111 | 0 | 0 | 25 | 36 | 0 | 50
5.1.1 | Analyse the specifications of the main information systems, assess their scope for inter-connectivity, prepare detailed proposals for sharing data | [12 empty] | q | [5 empty] | q
5.1.2 | Provide advisory technical support to the up-grading of the data systems to achieve the necessary linking of main data systems | [27 empty] | q
5.2 | LMIMS portal technically revised and upgraded to increase information content, usability and intranet use by staff | 141 | 0 | 20 | 35 | 36 | 0 | 50
5.2.1 | Develop detailed proposals to upgrade the LMIMS portal (software and hardware) including increased information content and enabling the unemployed to be distinguished from job-seekers | [12 empty] | q |  |  |  | q
5.2.2 | Develop procedure and guidance manuals for use of LMIMS as intranet, as well as for analysis of public employment services data | [27 empty] | q
5.3 | LMIS technically revised and upgraded, providing enriched information content and analytical capacity | 146 | 0 | 20 | 40 | 36 | 0 | 50
5.3.1 | Develop LMIS as a relational SQL database, using administrative digital records from relevant sources | [31 empty] | q
5.4 | Enhanced capacity of MoESD and other users to collect, analyse and disseminate labour market information and monitor labour market developments | 143 | 7 | 20 | 80 | 36 | 0 | 0
5.4.1 | Provide capacity building and support to the LMIS team and other LMIS users | [32 empty] | q
5.4.2 | Support dissemination of LMIS analysis results | [31 empty] | q
5.4.3 | Support Enterprise Georgia in analysing skill needs for SME development in selected sectors and link them with relevant training provision | [36 empty] | q
5.4.4 | Support MoIDPLHSA in carrying out a sector skill needs analysis for the health care sector (within the context of the LMIS) | [27 empty] | q
5.5 | Enhanced capacity of EMIS to support education and training policy making on the basis of evidence-based analyses and policy briefs | 86 | 30 | 0 | 20 | 36 | 0 | 0
5.5.1 | Assess the capacity of the EMIS database to meet the requirements of evidence-based policy making | [16 empty] | q
5.5.2 | Develop capacity of EMIS staff to support evidence-based policy making
Component 6: Monitor Grant Scheme Implementation |  | 250 | 30 | 50 | 0 | 20 | 50 | 100
6.1 | Support grant scheme implementation through the monitoring of grant projects | 230 | 30 | 50 | 0 | 0 | 50 | 100
6.1.1 | Provide technical, implementation and monitoring support to the Grant Scheme
6.1.2 | Support preparation of a compendium of grant projects’ results
Total |  | 3970 | 800 | 770 | 300 | 1020 | 230 | 850