The European Union’s Skills4Jobs Programme in Georgia, Phase 2

Inception Report

Technical Assistance to Skills Development for Matching Labour Market Needs in Georgia

January 2020

(Including revisions made in February 2020 and May 2020)

Project Identification N°:

EuropeAid/39718/DH/SER/GE

The contents of this report are the sole responsibility of the Contractor and can in no way be taken to reflect the views of the European Union.

Inception Report

Technical Assistance to Skills Development for Matching Labour Market Needs in Georgia

January 2020

(Including revisions made in February 2020 and May 2020)

Project Identification N°: EuropeAid/39718/DH/SER/GE

By David Handley, Team Leader, with contributions by Key Experts

Heinrich Duffner and Claus Møller

This Project is implemented on behalf of the European Union

by a Consortium led by GOPA Worldwide Consultants

# Project Details

| Project Title |  | Technical Assistance to Skills Development for Matching Labour Market Needs in Georgia |  |  |
| --- | --- | --- | --- | --- |
| Project ref. no.: | EuropeAid/39718/DH/SER/GE |  | Beneficiary organisation: | EC on behalf CA countries |  |
| Date of contract signature: | 27 August 2019 |  | Contractor’s name, address, telephone & fax numbers and E-mail address: | GOPA Worldwide Consultants Hindenburgring 18 61348 Bad Homburg Germany Phone +49 6172 930-425 Fax: +49 6172 930-440 nikolay.sapundzhiev@gopa.de |  |
| Commencement date: | 03 October 2019 |  |  |  |  |
| Implementation period | 48 months |  | Name of contact person (project director of contractor): | Nikolay Sapundzhiev |  |
| Contract No.: | ENI/2019/409-175 |  | Name of Team Leader: | David Handley |  |
| Total contracted amount (EUR): | EUR 3,711,970.00 |  | Project office address, and Team Leader’s e-mail address: | Ministry of Education, Science, Culture and Sport (MoESCS) 4 Sanapiro Str., 0105 Tbilisi, Georgia david.handley@gopa.de |  |

Contents

Project Details	iv

Contents	v

Abbreviations	vi

1	Introduction	1

1.1	Background to this Report	1

1.2	Activities carried out during the Inception Phase	2

1.3	Brief Project Synopsis	3

2	Issues relevant to Project Design	5

2.1	Overall Objective and Purpose of the Project	5

2.2	Updated analysis of project beneficiaries	5

2.3	Updated analysis of related donor interventions	7

2.4	Key issues relevant to project implementation	10

3	Project Implementation by Component	13

3.1	Component 1 – National Sector Reform Policies	16

3.1.1	Background information	16

3.1.2	Component 1 Implementation	17

3.2	Component 2 – Skills Development and Entrepreneurial Learning	25

3.2.1	Background information	25

3.2.2	Component 2 implementation	27

3.3	Component 3 – Youth	33

3.3.1	Background information	33

3.3.2	Component 3 implementation	34

3.4	Component 4 – Employment Services	40

3.4.1	Background information	40

3.4.2	Component 4 Implementation	43

3.5	Component 5 – Information Systems and Analysis	53

3.5.1	Background information	53

3.5.2	Component 5 Implementation	56

3.6	Component 6 – Grant Scheme	57

3.6.1	Background Information	62

3.6.2	Component 6 Implementation	63

4	Revised Log Frame and Activity Matrix	64

5	Revised Implementation Timetable	86

6	Project Management issues	86

6.1	Resource utilisation	86

6.1.1	Deployment of Key Experts and Long-term Non-Key Experts by Component	86

6.1.2	Non-key Experts	86

6.1.3	Incidental Expenditures	87

6.2	Project Steering Committee	88

6.3	Reporting	89

Annex 1: List of Inception Period Consultation Meetings and Events	91

Annex 2: Revised Implementation Timetable	94

Abbreviations

| AA | Association Agreement |
| --- | --- |
| ADB | Asian Development Bank |
| ALMP | Active Labour Market Policy |
| APF | Accumulated Pension Fund |
| ATF | Analysis Task Force (proposed) |
| BMZ | Federal Ministry for Economic Cooperation and Development (Germany) |
| BS | Budget Support |
| CEG | Career Education and Guidance |
| CVET | Continuing Vocational Education and Training |
| DC dVET | Donor Committee for Dual Education and Training (in Georgia) |
| DM | Deputy Minister |
| DOL | US Department of Labor |
| DVV | Institute for International Cooperation of the German Adult Education Association |
| EaP | Eastern Partnership |
| EBA | European Business Association |
| EMIS | Education Management Information System |
| EQF | European Qualifications Framework for Life-long Learning |
| ESS | Employment Support Services |
| ETF | European Training Foundation |
| EU | European Union |
| EUD | Delegation of the European Union in Georgia |
| EVET | Employment and VET Budget Support programme |
| FabLab | Fabrication Laboratory |
| GCCI | Georgian Chamber of Commerce and Industry |
| GEA | Georgian Employers Association |
| GGF | Good Governance Fund (of the United Kingdom) |
| GITA | Georgian Innovation and Technology Agency |
| GIZ | Deutsche Gesellschaft für Internationale Zusammenarbeit |
| GoG | Government of Georgia |
| GS | Grant Scheme |
| GTUC | Georgian Trade Union Confederation |
| HE | Higher Education |
| HEI | Higher Education Institution |
| HoD | Head of Department |
| IDP | Internally Displaced Person |
| ILO | International Labour Organisation |
| IR | Inception Report |
| IOM | International Organisation for Migration |
| IP | Inception Phase |
| IVET | Initial Vocational Education and Training |
| JNKE | Junior Non-key Expert |
| KE | Key Expert |
| LEPL | Legal Entity of Public Law |
| LLEL | Life-long Entrepreneurship Learning |
| LLL | Life-long Learning |
| LM | Labour Market |
| LMAD | Labour Market Analysis Division (of MoESD) |
| LMI | Labour Market Information |
| LMIMS | Labour Market Information Management System |
| LMIS | Labour Market Information System |
| LT | Long-Term |
| MCA-Georgia | Millennium Challenge Account - Georgia |

| MCC | Millennium Challenge Corporation (of the USA) |
| --- | --- |
| MoESCS | Ministry of Education, Science, Culture and Sports |
| MoESD | Ministry of Economy and Sustainable Development |
| MoF | Ministry of Finance |
| MoIDPLHSA | Ministry of Internally Displaced Persons from the Occupied Territories, Labour, Health and Social Affairs |
| M&E | Monitoring and Evaluation |
| NACE | Nomenclature des Activités Économiques dans la Communauté Européenne |
| NCEQE | National Centre for Educational Quality Enhancement |
| NEET | Not in Employment, Education or Training |
| NQF | National Qualifications Framework |
| NKE | Non-key expert |
| NSM | New Service Model |
| OVI | Objectively Verifiable Indicator |
| PAR | Public Administration Reform (EU Programme) |
| PIC | Personal Identification Code |
| PM | Project management |
| PPP | Public-Private Partnership |
| QA | Quality Assurance |
| QM | Quality Management |
| ROM | Results-Oriented Monitoring |
| SDC | Swiss Agency for Development and Cooperation |
| SDG | Sustainable Development Goal |
| SEN | Special Educational Needs |
| SESA | State Employment Support Agency |
| SME | Small and Medium-sized Enterprise |
| SNKE | Senior Non-key Expert |
| SQL | Structured Query Language (database term) |
| SRPC | Sector Reform Performance Contract |
| SSA | Social Services Agency |
| ST | Short-Term |
| TA | Technical Assistance |
| TAT | Technical Assistance Team |
| TL | Team Leader |
| ToR | Terms of Reference |
| TNA | Training Needs Analysis |
| TPDC | Teacher Professional Development Centre |
| UN | United Nations |
| UNDP | United Nations Development Programme |
| UNFPA | United Nations Population Fund |
| UNIDO | United Nations Industrial Development Organisation |
| UNICEF | United Nations Children’s Fund |
| USAID | US Agency for International Development |
| VET | Vocational Education and Training |
| VNFIL | Validation of Non-Formal and Informal Learning |
| WB | World Bank |
| WD | Working Days |
| YA | Youth Agency |

# Introduction

## Background to this Report

The project “Technical Assistance to Skills Development for Matching Labour Market Needs in Georgia” is the technical assistance component of the second phase of the European Union’s Skills4Jobs Programme in Georgia.

The Terms of Reference (ToR) of the project requires an Inception Report to be submitted not later than 3 months after the start of project implementation, presenting a detailed Implementation Plan for achievement of expected outputs within the set terms and scope of the allocated budget.

According to the ToR: “The Inception report shall consist of (as minimum requirements): project synopsis, situation analysis, project planning for the entire duration of the project, updated log frame, updated detailed project resource planning (HR and incidentals) according to the planned activities, implementation environment and arrangements, risks and assumptions and detailed description of the activities planned for the next reporting period.”

The Inception Report is specifically required to include:

- Review of project purpose, anticipated outputs and planned activities

- To ensure that the project design remains relevant, and to suggest a refocusing of activities where appropriate

- A detailed explication of the project implementation and management strategy

- An Overall and Annual Work Plan

- A revised resource utilization chart, outputs schedules and an updated Project Log frame

- Work Plan for the next reporting period

The Report should also include a mapping of all potential stakeholders, including their roles and the extent of their involvement in project implementation.

The project is implemented by an international consortium led by GOPA Worldwide Consultants (Germany) in partnership with PEM CONSULT (Germany), EPM (Latvia), and Pôle Emploi (France), and there are two full-time key experts – David Handley (Key Expert 1: Team Leader / Skills Development) and Heinrich Duffner (Key Expert 2: Employment Services) – and one part-time key expert – Claus Møller (Key Expert 3: Labour Market Analysis). The three key experts, together with project directors from the Contractor, were mobilized in Tbilisi on 3 October 2019, and a Kick-off meeting for clarification on key project management issues was held at the European Union Delegation on 7 October.

The project was officially launched within the frame of the overall Skills4Jobs programme on 29 October 2019 at an event organized by the Delegation at Community College “Gldani Vocational Education and Training Center”.

Throughout the three-month Inception Phase of the project, the Team Leader and Key Expert 2 conducted intensive consultations with project beneficiaries and key stakeholders, with additional participation by the Key Expert 3 during October 2019. Our review of the ToR, adjustments to the Log Frame, implementation methodology and Work Plans reflect the results and conclusions of these consultations.

The Draft Inception Report, representing our initial conclusions and proposals was submitted to the Delegation on 15 January 2020 and was presented to the first meeting of the Project Steering Committee on 14 February 2020, following which a number of minor amendments were made to the Report.

The draft log frame of the project was shared by the EU Delegation with the EU ROM Eastern Partnership quality assurance team, who recommended a number of adjustments to the Outputs and Indicators in line with current EU best practice, and this Inception Report was modified in May 2020 to reflect the modifications made to the log frame on the basis of advice received..

## Activities carried out during the Inception Phase

According to the ToR, the duration of the Inception Phase was set at 3 months from the starting date of the project, 3 October 2019. However, it may be assumed that it was de facto extended until 14 February, the date of the first Steering Committee when the draft Inception Report was officially presented to project beneficiaries.

During the Inception Phase, detailed preparations were made for the implementation of the project. Activities included a detailed review of all aspects of the project – objectives, expected outputs, activities, deliverables, timeframes etc. – taking into account developments in the country since the ToR were prepared, together with a range of administrative and practical activities necessary to mobilise the project team and ensure a functioning project office.

At an initial Kick-off meeting with the EU Delegation, a range of key points concerning project management and administration were clarified and agreed.

Mobilisation of Experts

The three key experts – David Handley (Team Leader and Key Expert 1 for Skills Development), Heinrich Duffner (Key Expert 2 for Employment Services) and Claus Møller (Key Expert 3 for Labour Market Analysis) – started work in Tbilisi on 3 October 2015 and, for the first few days of the project, were joined by Project Managers Nikolay Sapundzhiev and Elena Friesen from GOPA and by Marita Münks from PEM CONSULT, one of the three other consortium partners.

The TL and KE2 were in Georgia throughout the three-month Inception Phase, whereas the KE3 (who is not full-time) was in Georgia during the first month of the Inception Phase.

Three long-term junior non-key experts were recruited by the third month of the Inception Phase, following an open recruitment procedure which included agreement with the EUD on ToR for each position, public advertisement on two job-search websites (jobs.ge and hr.ge), evaluation of CVs from applicants by the TL and KE2, and interview of short-listed candidates. The following positions were filled:

- Non-key expert in Skills Matching (520 working days): Ana Diakonidze

- Non-key expert in Skills Development (420 working days): Ani Kitiashvili

- Non-key expert in Communications and Visibility (80 working days): Tatia Khubulava

ToR were also drafted for some other non-key expert positions to be filled in the first six months of project implementation.

Project Office

During the Inception Phase of the project, we also set up offices for the project team. For the first two months, the project operated from the Tbilisi office of our project partner, PEM Consult, awaiting the availability of office space provided by project beneficiaries.

On 25 November 2019, after renovation, the project moved its main office provided by the MoESCS (two rooms totalling about 60m2 on the second floor of the former building of the Ministry of Culture).

A second office was set up in a room provided by the MoIDPLHSA on the fifth floor of the ministry (approx. 25m2).

Administrative Staff

At the start of the project, the project administrative staff were recruited, though continuation contracts with existing local employees of our consortium partner, PEM Consult:

- Irakli Khutsianidze (accountant/office manager)

- Gvantsa Tabatadze and Nino Kutateladze (project officers/translators);

Fact-finding and Consultative Meetings with Beneficiaries and Stakeholders

Activities during the Inception Phase activities were mainly focused on an intensive round of fact-finding and consultative meetings with beneficiaries and stakeholders. As well as meetings with senior representatives of beneficiary institutions and key stakeholders, detailed information exchanges took place with the EU-funded Twinning Projects based in MoIDPLHSA and NCEQE, and with international donors and donor-funded projects. The meetings with beneficiaries, stakeholders and donors are listed at ANNEX 1:

The information gathered in these meetings and a number of events attended during the Inception Phase (also listed at ANNEX 1), together with our review of documents, desk research, information from recently contracted NKEs and a number of telephone conversations, have informed our preparation of this Inception Report, including our reorganization of the components of the project and preparation of the revised log frame and implementation timetable.

Communications and Visibility Activities during the Inception Phase

As previously mentioned, the project was publicly launched at an overall EU Skills4Jobs Programme Launch event on 29 October 2019, and there was therefore no need for the project to hold its own launching or dissemination event.

However, following contracting of the NKE in Communications and Visibility, work was started on project visibility, including:

- Preparation of draft visibility and communication strategy;

- Preparation of information leaflet about the project.

## Brief Project Synopsis

The project is an integral part of a Sector Reform Performance Contract on Skills Development and Matching for Labour Market Needs between The European Union and the Government of Georgia, known as the Skills4Jobs Programme, Phase 2.

The ToR defines the overall objective of the project as being to contribute to improving “the employability of women and men in the selected regions of Georgia” and its Purpose, or specific objective, is to “enhance the capacity of the beneficiary ministries and agencies, as well as local communities, to develop, implement, monitor and review skills development and matching policies”.

The main beneficiaries of the project are three ministries (MoESCS, MoIDPLHSA and MoESD), together with a number of subordinate agencies, and the Youth Agency (established in August 2019 as an executive agency under the office of the Prime Minister).  It should be noted that there will be a regional dimension to the project, with a focus particularly on involving regional stakeholders and on piloting measures in selected regions of the country.

The original Terms of Reference (ToR) defined 23 Results, grouped into 5 components: 1) Transversal Tasks, 2) Skills Development, 3) Youth and Entrepreneurial Learning, 4) Skills Matching (Employment Services and Labour Market Analysis, and 5) Support to Grant Scheme Implementation.

During the Inception Phase, we have consulted extensively with the project beneficiaries and, although we are not proposing any major changes to the substantive content of the project, we have reorganized the content into 6 components (comprising 17 Outputs) which we consider to provide a more rational implementation structure for the project.

The structure of the project provides a component focused on supporting overall Sector Reform Policy development and coordination, three components focused on providing TA to specific areas of service delivery (Skills Development, Youth and Employment Services), a component on supporting the development of Information Systems and enhancing capacities to analyse and utilise information in evidence-based policy making, and a component designed to provide support to the monitoring of EU funded grant projects in the areas of skills development and skills matching.

The re-organized structure now proposed is as follows:

COMPONENT 1: NATIONAL SECTOR REFORM POLICIES

- Output 1.1: Updated national sector reform policies drafted

- Output 1.2: Capacities in national sector reform policy development, implementation and monitoring enhanced

- Output 1.3: Enhanced capacity to provide visibility & communications for sector reform policies and specific services provided by beneficiary institutions

Component 2:  Skills Development & ENTREPRENEURSHIP LEARNING

- Output 2.1: Enhanced capacity of the MoESCS to further develop and modernise skills development and LLL systems

- Output 2.2: Enhanced capacity of educational institutions to provide professional orientation and career guidance for learners in general, vocational and higher education

- Output 2.3: Enhanced capacity to deliver entrepreneurship education in general, vocational and higher education and lifelong learning

COMPONENT 3: YOUTH

- Output 3.1 Enhanced capacity of Youth Agency to develop and deliver effective youth services

- Output 3.2: Improved organizational and human capacities to deliver youth services at local level

COMPONENT 4: EMPLOYMENT SERVICES

- Output 4.1: State Employment Support Agency (SESA) supported in its implementation of the Revised New Service Model (NSM)

- Output 4.2: SESA supported in designing and delivering more accessible, effective and comprehensive ALMP measures for all job seekers

- Output 4.3: Capacity (knowledge and expertise) developed within the SESA staff to provide more effective employment services for jobseekers and employers

COMPONENT 5: INFORMATION SYSTEMS AND ANALYSIS

- Output 5.1: Improved integrity and compatibility of data and information systems for evidence-based policy making and implementation

- Output 5.2: Technical revision and upgrading of the Labour Market Information Management System (LMIMS) supported

- Output 5.3: Capacity of Labour Market Information System (LMIS) team enhanced in analysis, survey and anticipation methods

- Output 5.4: Enhanced capacity of EMIS to support evidence-based education and training policy making

- Output 5.5: Enhanced capacity of institutions using LMIS, LMIMS and EMIS data in evidence-based policy making

COMPONENT 6:  GRANT SCHEME

- Output 6.1: Grant scheme implementation supported through the monitoring of grant projects

A table detailing the changes made on a Component by Component basis is set out at the beginning of Chapter 3 below.

# Issues relevant to Project Design

## Overall Objective and Purpose of the Project

This Technical Assistance Project is a component of the overall Skills4Jobs Programme Phase 2, which also includes two Twinning projects (one for the NCEQE and one for the MoIDPLHSA) and a Grant Scheme.

The “Plan for Skills Development and Matching for Labour Market Needs of the EU’s Action Programme 2017 for Georgia” (Skills4Jobs, Phase 2) states that “the need for better matching of skills with labour market demands, as well as for coherent and better skills development system, are identified as key bottlenecks hindering Georgia’s competitiveness and economic development”.

The Overall Objective of the project is defined in the ToR as being to “improve the employability of women and men in the selected regions of Georgia”.

The Purpose (or Specific Objective) of this contract is to “enhance the capacity of the beneficiary ministries & agencies as well as local communities to develop, implement, monitor and review skills development and matching policies”.

From our detailed analysis of the pertaining situation in employment and VET and of the country’s needs and priorities undertaken during the Inception Phase, we see no need to make any changes to these objectives. Indeed, our analysis has confirmed the continuing relevance to these objectives and has served to underline their critical importance to the continuing development of Georgian economy and society.

However, it is necessary to stress that the technical assistance provided is based on the provision of expert advice and capacity building support which can only contribute to achievement of the Overall and Specific objectives. The actual achievement of those objectives remains the responsibility of the project beneficiaries.

As noted in our Technical Proposal, the needs addressed by this project have received considerable donor support, most notably through the previous Sector Reform Performance Contract (SRPC) between the EU and Georgia which supported national reform processes, institutional development and stakeholder cooperation, but impact at meso- and micro-level has so far been limited. This issue is addressed under the new SRPC which, although continuing to support policy development, places an increased emphasis on supporting effective policy implementation, with a special emphasis on targeted regions (Tbilisi, Adjara, Imereti, Kakheti, Kvemo-Kartli, Samegrelo-Zemo Svaneti, Guria, Racha-Lechkhumi and Shida-Kartli).

Furthermore, the project is starting at a very apposite time, not only because of the on-going needs of the three beneficiary ministries for continuing technical assistance, a need to secure greater coordination and synergy at the overall policy level, and the country’s obligation to meet the reform objectives of the new SRPC, but also because of the establishment of two new agencies (the Youth Agency founded in August 2019) and the Employment Services Agency formally established in December 2019). Both will both have important responsibilities throughout all the regions of Georgia and can be supported by the project during the crucial early period of their implementation.

Establishment of the new agencies is among a number of situational changes in the country context since the issuing of the ToR and the submission of the Contractor’s Technical Proposal which are described in the following section of this Report and which need to be addressed in our TA strategy.

Although no changes are proposed to the Overall or Specific Objectives of the project, recent developments and changes in the institutional arrangements inevitably have implications for the expected Outputs of the project and the activities required to achieve those Outputs. Such changes are set out in the Updated Strategy chapter below, and are detailed in the project Log Frame and Implementation Timetable, included in this Report.

## Updated analysis of project beneficiaries

The three ministries targeted as the direct beneficiaries of the TA remain unchanged. They are:

- Ministry of Education, Science, Culture and Sport (MoESCS)

- Ministry of Internally Displaced Persons from the Occupied Territories, Labour, Health and Social Affairs (MoIDPLHSA)

- Ministry of Economy and Sustainable Development (MoESD)

The other direct beneficiary, not listed in the ToR because it was established only in August 2019, is the:

- Youth Agency (an agency directly under the office of the Prime Minister)

In the case of MoESCS, the relevant departments targeted by the project are the VET, General Education and Higher Education Departments, although some activities may involve contact with the Strategy Development Department. Overall project coordination is provided from within the International Relations Department.  It should be noted that the Youth Department, named in the ToR as a beneficiary, no longer exists because its functions were transferred to the new Youth Agency, referred to above.

Relevant agencies linked with the MoESCS which have a direct interest in the project are the TPDC (both General Education and VET Departments), EMIS and, to a lesser extent, the NCEQE.

In the case of the MoIDPLHSA, the relevant department targeted by the project is the Labour and Employment Policy Department. In December 2019, the new Employment Support Agency (SESA) was established as an executive agency of the MoIDPLHSA, and employment support services (ESS) are in the process of being transferred to it from the Social Services Agency, which was named in the ToR as a beneficiary.

In the case of the MoESD, the relevant department targeted by the project is the Economic Policy Department, which includes the Labour Market Analysis Division.

Two agencies under the MoESD – GITA and Enterprise Georgia – will have an involvement in specified project activities respectively related to entrepreneurship learning and SME development.

The establishment of the two new agencies, the Youth Agency and the Employment Support Agency (referred to above), affects only the institutional arrangements of the project partners but implies no changes in respect of the results/outputs as defined by the ToR.

Youth Agency

In August 2019 the new LEPL Youth Agency was founded as a part of the Government’s structural reform plan. The Youth Agency, which reports directly to the office of the Prime Minister, took over the functions of the following institutions:

- Youth Policy Department of the MoESCS

- Children and Youth National Centre

- Youth Development Fund

The main goal of the Youth Agency for the next three years is a comprehensive reform of the youth policy, the main challenge being to close the gaps in the current youth ecosystem. (Definition of youth: 14 - 29 years of age.) The priorities of its work are based on Georgia’s National Youth Policy which aims at:

- developing inclusive and participatory youth policy work on the national and local level through legislative acts and regulations and through supporting the municipal institutions with the formulation and implementation a municipal youth policy;

- creating strategic documents for the development of youth work, volunteerism and youth economy as well as municipal youth centres and youth camps;

- creating high quality non-formal education programmes to develop key competences for Lifelong Learning;

- capacity building of youth organizations, the development of youth workers education and certification programs and the establishment of youth activation services;

- promoting a healthy lifestyle, human rights, tolerance and gender equality.

To achieve these goals the Youth Agency intends to develop a youth policy at national and local level, to implement this policy and coordinate its implementation. The first round of activities will be to allocate the available resources in the Agency, complemented by the elaboration of a three-year reform strategy until February 2020.

The strategy is expected to

- present a concept for youth work;

- establish the application of EU key competencies (non-formal education)

- enhance the qualification of youth workers.

In the third year the function of youth worker should be established as a profession. It is planned to conduct pilots for municipal youth work in some cities, to empower NGOs and work with the National Council of Youth Organisations, a member of the European Youth Forum.

State Employment Support Agency (SESA)

By Resolution No 473 of the Government of Georgia on 10 October 2019 and Order No 01-110/N dated 31.10.2019 of the MoIDPHLSA, the LEPL State Employment Support Agency (SESA) was established. The Agency reports to the MoIDPHLSA and has taken over the functions of the Employment Support Services (ESS) Department of the Social Services Agency (SSA). The objectives, functions, authorities and principles of work of the SSESA are specified in Article 2 of Order No 01-110/N. The Agency is supposed to further implement the New Service Model (NSM) at the national, regional and local levels. It will

- provide the standard mediation services like registration of job seekers and vacancies as well as placement;

- implement Active Labour Market Policy (ALMP) measures and expand their scope;

- administer the Labour Market Information Management System (LMIMS) collecting statistical data and conduct analyses of current and future trends in the Georgian labour market;

- apply and further develop the WorkNet software, a subset of the LMIS, for the registration of job seekers.

Under the previous structure, each of the 69 municipal offices of the SSA had at least 1 person from the ESS Department in charge of employment. However, the new agency is being organised on a regional basis with one city office and 5 district offices in Tbilisi, 9 regional centres and 1 branch in Adjara. The SESA branch office of Adjara is planned to be established in parallel with the already existing Employment Agency of Adjara.

To better adjust the services provided to job seekers and employers to the actual conditions of the labour market the SESA intends to emphasise its work at the local level. An initial focus of the Agency’s work will be on the offices in 7 priority regions, and 2 additional priority regions are planned to be added after 2020.

As with the case of the Youth Agency, the MoIDPLHSA has confirmed that establishment of the SESA does not imply substantive changes in the intended project outputs, but additional activities in the field of organisational development by the TA will be required. This support is relevant regarding two potential risk factors resulting from this reorganisation:

- As the new structure is based on regional offices it needs to be ensured that the provision of services at the lower level of the 69 municipalities will not deteriorate.

- The performance indicator 2.1 of the SRPC requires that by the end of 2019 at least 30% of all SSA/ESS territorial units apply the New Service Model nationwide. It needs therefore to be clarified how this indicator can be redefined with respect to the new structure in order to comply with the conditionalities.

## Updated analysis of related donor interventions

The project ToR and the Consortium’s tender proposal included detailed analyses of other donor interventions that potentially have a bearing on the design and implementation of this project. The objectives of two recently completed projects – the so-called EUVEGE project (“Technical Assistance to VET and Employment Reform in Georgia”) under the previous SRPC, and the MCC-funded ISWD project (“Industry-led Skills and Workforce Development”) implemented by MCA-Georgia were both closely related to those of this project, which should continue to build on their achievements.

The EU Skills4Jobs Programme phase 2 provides two twinning projects in addition to this TA component:

- ” Strengthening capacities for quality assurance and governance of qualifications”: a project providing support to NCEQE from counterpart institutions in Germany and Estonia;

- “Improving the standards of employment conditions/relations as well as health and safety at work in Georgia”: a project providing support to MoIDPLHSA, from counterpart organizations in Slovakia, Spain and Estonia.

The EU PAR Programme (“Support to Public Administration Reform”) aims to improve the quality of service delivery of the public administration, by improving its efficiency, accountability and transparency and enhancing the capacity of the civil service to implement reforms in harmonization with European principles and best practices. Its policy-related support to MoESCS includes supporting the updating of the overall national education strategy.

The EU4Youth Programme (2017-20) fosters the active participation of young people in society and their employability, by developing youth leadership and entrepreneurship through a variety of actions, including capacity building, fellowships, support to policy dialogue, as well as providing grants to organisations active in these areas.

The EU pipeline includes a framework contract-based feasibility study on Georgia’s possible transition towards becoming an ERASMUS+ country, which will be followed by a capacity building technical assistance intervention.

Also in the pipeline is the EU 4 Integrated Territorial Development, a budget support programme aiming to promote a more balanced territorial development and improve living standards and conditions of the population through inclusive, smart and sustainable socio-economic means, by creating a favourable environment and promoting integrated socio-economic development of the four focal regions (Kakheti, Imereti, Guria, and Racha-Lechkumi and Kverno Svaneti).

In addition, the European Training Foundation (ETF) provides on-going policy support to employment and VET, including the Torino Process which, since 2010, has provided evidence-based analyses of human capital development issues and VET policy responses in a lifelong learning perspective in partner countries. Biennial Torino Process country reports identify and analyse challenges to education and training policy and practice that hinder the development and use of human capital, and recommend possible solutions.

In relation to other current international donor-funded initiatives, the following appear to be most significant:

GIZ/BMZ: The GIZ regional project “Private Sector Development in the South Caucasus” continues to support private sector development in region, including TA to VET development based on labour market needs the tourism, construction, wine-production, transport/logistics and ICT sectors. This includes an emphasis on introducing German-style “dual system” apprenticeships, together with teacher and master trainer development. GIZ has also supported introduction of the EFQM excellence quality model in 6 colleges and Georgia’s participation in “WorldSkills”.

Together with the German Federal Ministry for Economic Cooperation and Development (BMZ), the Austrian Development Agency, the Liechtenstein Development Service and the Swiss Agency for Development and Cooperation, GiZ is supporting the Donor Committee for Dual VET (DC dVET) which is supporting Dual VET development and implementation in Georgia.

It should be noted that the German government also funds the embedding of German experts in Georgian institutions This includes a representative of the German Federal Employment Office in the MoIDPLHSA and a representative of the Munich and Upper Bavaria Chamber of Commerce in the GCCI;

UK Good Governance Fund (GGF): During the past two years, projects implemented in partnership with PWC, have included support to the strengthening of public-private partnership in VET, development of short-cycle higher education programmes, and diversified financing of VET and, in partnership with the British Council, support has also been provided to English language teaching within the VET sector. Other GGF support is delivered in collaboration with the World Bank.

World Bank: Currently implementing a 2-year GGF-funded capacity development project “Georgia: Strengthening Teacher Quality in Vocational Education” supporting professional development of VET teachers/managers, with components focused on management development, capacity development for teachers/principals and evidence-based decision making.

One of the components of the project provides support to the upgrading of EMIS with the aim of assisting evidence-based policy-making, and also includes development of a new VET.GE portal intended as a “one-stop shop” for information about VET and employment, linked to other data systems including EMIS.

A 6-year loan-based programme on “Georgia Innovation and Quality”, covering all levels of education, is in the pipeline. This includes a project to be launched before mid-2020 titles “Strengthening Teacher Quality in Vocational Education and Training”

USAID: Active in Georgia for more than 25 years, the objectives of a range of past and present projects include initiatives to stimulate economic growth, develop democratic institutions, improve education, and foster the increased inclusion of minority and disadvantaged people, including the PITA project which is supporting 14 youth centres (including 2 in Tbilisi and 6 in minority areas). There are various other projects at the current time.

The ZRDA Activity (2016-21) promotes inclusive and sustainable economic growth in target regions by promoting Micro, Small, and Medium Enterprises (MSMEs) growth, increasing productivity of rural households, facilitating market linkages between producers and buyers, and promoting local economic development by establishing and strengthening networks. At a small scale the project supports the communities to strengthen their skills through short term trainings in digital marketing, modern farming, and tourism in targeted villages alongside the Administrative Border Line with Abkhazia and South Ossetia.

The Economic Security Program (2019-24) provides technical assistance and cost‐share grants to enhance growth and productivity in the four target sectors (tourism, light manufacturing, creative industries and shared intellectual services).  This assistance helps develop value chains, enhances the viability of micro, small, and medium-sized enterprises (MSMEs), and supports the alignment of the workforce with the needs of industry, through targeted, employer-led trainings to support new or improve their employment in targeted sectors.

Supporting Youth and Women Entrepreneurship in Georgia (YES-Georgia) 2015-2024, supports economic growth and empowers Georgia’s youth and women by encouraging innovation, promoting entrepreneurship, and enhancing youth and women’s employability. The program provides emerging entrepreneurs and professionals with skills development, business training, mentoring, and access to finance.  Supporting Youth and Women Entrepreneurship in Georgia is an extension of the previous USAID program Youth Entrepreneurial Skills for Advancing Employability and Income Generation in Georgia.

USAID is currently working on the design of a new Industry-Led Skills Development Activity. This activity is at an early stage of design but will focus on the elimination of mismatch between labour market needs and job seekers’ skills through the effective and systematic engagement of the private sector. Design of the project will be completed during 2020, with implementation expected to start in 2021.

ADB: A 50m USD loan (“Georgia: Modern Skills for Better Jobs – Sector Development Programme”) with a substantial infrastructure component will also include a 5 or 6-year technical assistance component. A grant-funded preparatory project, which started at the end of 2019, is currently preparing the project, which is likely to include components focused on: Improving quality and relevance of VET (including supporting development of entrepreneurial activities of VET institutions); enhancing private sector participation in VET (including sector councils, outsourcing of VET college management and VET-industry partnerships); and increasing inclusiveness in the VET system (including introducing VET programmes in general secondary schools, gender-inclusive activities, social marketing and an emphasis on disadvantaged groups). The TA component could amount to up to 25% of the total funding, which would make it an exceptionally large TA intervention

KfW: The German development bank is preparing to launch a major infrastructure project (approximately 20m euro to construct a new college in Tbilisi, and it is expected that the initiative will include a TA component to develop staff capacity necessary for the college to become a “centre of excellence”.

DOL: Funded by the U.S. Department of Labor (DOL) Bureau of International Labor Affairs (ILAB), the IMPAQ implemented project is currently implementing the “Strengthening Government Labour Law Enforcement” project. Through this project, the IMPAQ team plans to support the following efforts:

•	adopting laws, regulations, and other legal instruments that are consistent with relevant labour standards;

•	improving the identification and remediation of labour law violations; and

•	improving the prosecution of labour law violations.

The following UN organizations are carrying out activities in Georgia that are also relevant to the project:

- ILO: “Inclusive Labour Market for Job Creation” – a Danish-financed programme, focused on providing TA support to labour laws, labour code, standards and inspections, social partnership, youth entrepreneurship and responsible business conduct.

- UNDP:  Under the Swiss Development-funded project “VET in Agriculture”, wide-ranging and flexible support to the VET sector has included assistance in the areas of integrating general and vocational education, developing formal adult education, strengthening entrepreneurial learning in VET, work-based learning/dual education and training of instructors. Recently the UNDP has been supporting the drafting of by-laws for VET Law implementation;

- UN agencies (UNIDO, UNFPA and UNICEF) are providing support to the Georgian Parliament in developing a new and more comprehensive national youth strategy in compliance with international standards;

- UN Women is supporting a range of UN activities focused on promoting women’s access to employment;

- IOM is carrying activities related to problems of migration including circular migration issues, mediation services and migration-related training for ESS staff, collection of data on migrants.

The following other relevant initiatives should be noted:

- FES (Friedrich Ebert Foundation): This German NGO is currently implementing a pilot model of employment mechanism in the Nadzaladevi district of Tbilisi in cooperation with the SSA. It has supported civic education initiatives and, in 2016, also carried out a Youth Study with the Georgian company ACT.

- We have also noted that World Vision and the Danish Refugee Council have also been implementing various projects in the area of youth participation and youth work in Georgian regions.

- DVV International, having already provided support to the Georgian Adult Education Network and the establishment of 10 adult training centres, is now collaborating with MoESCS to provide German-funded support to adult learning development, including implementation of a range of measures intended to promote adult and lifelong learning.

## Key issues relevant to project implementation

Although there are many potential issues that need to be taken into account when implementing the project, we consider that the following are especially important, in view of their criticality to the achievement of project objectives.

An integrated approach

The project pursues an integrated approach, it aims for closer integration, synergy and consistency between the policies of the ministries and agencies targeted by the TA. This implies fostering increased collaboration and cooperation between them to develop a coordinated approach to the elaboration of strategies and action plans.

This approach is the core issue of Component 1 which is renamed in this report to National Sector Reform Policies. Component 1 plays a transversal role in connecting the other project components. It furthers a coordinated approach and joint policy making through information sharing and establishing coordination mechanisms to achieve synergy effects. Component 1 is also closely linked with the European Union policy agenda and aims to support the Government of Georgia achieving the Budget Support objectives of the SRPC.

It should also be noted that common themes across project components include enhancing inclusiveness and widening of opportunities, improved guidance services for learners across the education system, youth and job seekers, linked information systems, entrepreneurship and an emphasis on a regional dimension, The TA is also required to assist the EU Delegation in monitoring the implementation of the Grant Scheme projects (Component 6) which may also include common themes.

Cross-cutting issues

The project will pursue a coherent approach to cross-cutting issues in specific Components focusing on common themes and links between their Outputs and Activities. It will especially emphasise issues of Gender Equality and Social Integration (GESI) and pay special attention to addressing the needs of all kinds of people in vulnerable situations to receive quality education and skills development. It will also, wherever possible, address environmental issues in line with the “green” approach promoted in Georgia by the EU.

These themes are intrinsically linked with and embedded in the Implementation of project components in various ways, including:

- The need for policy documents and reporting to explicitly address gender and social integration issues and the needs of vulnerable people and communities (Component 1);

- The focus on gender and inclusion of vulnerable people in skills development activities, including measures to improve access to VET, the development of effective guidance provision, and an inclusive approach to development of entrepreneurship learning opportunities (Component 2);

- Development of inclusive youth services and youth activation measures focused on improving opportunities for young people, including NEETs, at a local level (Component 3);

- Development and implementation of improved employment services at a regional level, including active labour market policy measures directed at improving employment opportunities for the unemployed including socially vulnerable groups (Component 4).

These issues will be addressed throughout project interventions, including admission to employment promotions and skills development programmes. Therefore, the deployment of experts will include cross-component working. This concern will be reflected in the planning of all project activities, which will be monitored and evaluated both quantitatively and qualitatively, and the results will be included in project reporting. Moreover, the results should contribute to the development of Sector Reform Policy, as well as following it.

Engagement with industry and regional stakeholders

The project will seek to actively engage industry and regional stakeholders through all project Components. This will serve to address the need to obtain a greater level of involvement of employers in skills development and matching, as well as investing in education and training more generally. Engaging with the private sector is a key thread in Georgian Government policy, promoted by the MoESD in relation to SME development and entrepreneurship and through public-private partnerships (PPP), and the MoESCS has already launched PPP initiatives in VET.

Because the named project beneficiaries are government institutions, project initiatives also need to emphasize private sector engagement in employment (including private education and training providers and employment agencies) and VET in all possible ways. This will require raising private sector engagement and PPP issues wherever appropriate, with efforts to obtain greater involvement of Georgian employers in work-based learning provision, supporting sector skills councils and social partnership mechanisms, and participating in PPP initiatives in employment and VET. Progress will be included in our reporting.

The regional dimension

As emphasised in the ToR, a focus on the regional dimension and the needs of selected regions is of utmost importance for a successful project implementation and for sustainable results. We shall address the problem of regional disparities and seek a more equal balance in opportunities for all. Centrally devised policies and strategies should be adapted to address regional problems and the regional dimension requires targeting local government institutions, the relevant ministries of Adjara institutions and other stakeholders to ensure that they have a voice in strategies to meet the needs of their regions.

Sectoral economic development usually has a mainly regional dimension and there is a need to engage with sector associations to ensure that they have a voice. It should be noted that efforts to develop a functioning social partnership structure have explicitly acknowledged the need to involve civil society as well as employment interests, and the involvement of Georgian (and where necessary relevant international) NGOs will be essential in developing activities in the regions.

NGOs play an important role in local communities, including youth work and support to disadvantaged and marginalized groups. In addition, youth centres are mainly located within municipal offices and Component 3 will especially require engagement with stakeholders at a very local level. In Component 2, activities focused on developing measures to widen access to VET, improving career education and guidance, and piloting entrepreneurship learning will especially require a focus on the needs for communities in different parts of Georgia. In Component 1, support to MoESCS policy-making will include the preparation of recommendations on how to expand VET provision in regions and localities by identifying an expanded number of institutions that may deliver VET programmes in parts of the country where provision is currently limited or even non-existent.

One possible approach to strengthen the regional dimension in Component 4 could be the establishment of Local Partnerships for Employment (LPE) adapting successful examples of some EU member states or accession countries. In addition to the SESA, the social partners and government at local level such a partnership could include NGOs and the municipal youth centre. The focus on the regional dimension as reflected in the structure if the SESA should be complemented by activities that ensure access of clients from the level of municipalities to guarantee at least the same standard of services as were delivered under the previous system. Moreover, it will be necessary to include the activities at municipal level in the implementation of the New Service Model.

Project visibility

The project aims at the highest possible level of project visibility, highlighting success stories, emphasizing the importance of VET and its opportunities for youth and adults, as well as promoting the modernised services of the SESA. Although the volume of college applications indicates increasing interest in VET, there is still a widespread reluctance among the population at large to recognise its benefits, a problem that is exacerbated by the low level of employer engagement.

Making VET the first choice for a majority will be a long process, requiring a sustained investment of time, energy and resources. Linking VET more directly with the labour market provides a key to popularizing VET. Improved guidance services for learners across the education system, for youth and for job seekers will also contribute to raising awareness of the importance of skills development including lifelong learning.

However, the project has a much wider focus than VET. It will include supporting two new institutions – the Youth Agency and SESA – which have still to become known among the wider public, including the building of “trust”, and there is an imperative to ensure visibility for project activities and outputs, not only in Tbilisi, but across the regions of Georgia. Besides the need to communicate policy reforms, specific activities which need to be made visible though our communications include:

- Increased availability and widened access to VET programmes which, themselves, should be more relevant to labour market needs, thus improving the employability of learners, supported by effective guidance services, and including a focus on promoting entrepreneurship;

- Improved and expanded youth services and youth activation measures providing enhanced opportunities and support to young people in all parts of Georgia, through hobbies and sport as well as training, guidance and entrepreneurship promotion;

- Improved and expanded employment services in the regions, including a range of ALMPs intended to support the unemployed and job seekers, including new opportunities for people not currently participating in the labour market, including many women and NEETs;

- Expanded and linked data and information systems intended to support the development and implementation of reform measures in employment, education and training.

Thus, Components 2, 3, 4 and 5 include a range of specific communications activities focused on providing visibility to specific initiatives (such as promoting the attractiveness of VET, providing visibility to youth services, promoting the services of SESA in the regions, and creating public awareness of labour market information), and targeting a range of groups (e.g. students, parents and adult learners, young people, NEETs, job seekers, the unemployed and those not currently participating in the labour market).  In addition, sector reform policies (Component 1) need to be highly visible, to stakeholders and the general public.

However, to provide a coherent and coordinated approach to communications activities across the project, we have proposed an extra output and a range of activities related to project visibility. Both effective internal (with stakeholders) and external (to the general public) communications must be embedded in all project interventions to generate awareness of project achievements, whilst supporting beneficiary ministries in communicating coherent and well-focused messages to stakeholders and the public.

Whilst the above activities will need to be carried out in conjunction with beneficiary institutions, which will be assisted in communicating and promoting their policies, measures and achievements, the objectives and achievements of the project itself, as well as the wider aims of the Skills4Jobs Programme, need to have a high degree of visibility. The communications approach and strategy that we shall adopt will be set out in detail in the project Communications and Visibility Plan, which has already been drafted during the Inception Phase.

All public awareness activities will be in line with EU visibility guidelines and with the Skills for Jobs Phase 2 Programme’s overall visibility plan in tandem with the communication policies of project beneficiaries. Project visibility will also reflect the “green” approach to environmental issues promoted by the EU, including using biodegradable materials, avoiding of waste from over-production of printed materials and avoiding the use of single-use plastics.

# Project Implementation by Component

As noted above, we have reorganised the content of the project into six components. No content proposed in the ToR has been omitted, but we consider that the revised structure of the project provides a more logical framework in which to implement the activities proposed in the ToR. The six Components described in the following pages are as follows:

Component 1: National Sector Reform Policies

Component 2: Skills Development and Entrepreneurship Learning

Component 3: Youth

Component 4: Employment Services

Component 5: Information Systems and Analysis

Component 6: Grant Scheme

To make project implementation more manageable, the number of Outputs has been reduced to 18 from the 23 set out in the ToR, by merging and combining closely related Outputs (formerly referred to as ‘results”) to create broader ones, and the Activities set out in the ToR have also been rationalised, mainly by combining small activities to make larger ones and by creating a hierarchy of sub-activities set out under broader headings.

A summary of the changes from the original ToR, together with comments on possible implications for the allocation of experts’ days is set out in the following table:

| Outputs in New Log Frame | Original “Results” in the ToR | Comment |
| --- | --- | --- |
| COMPONENT 1: National Sector Reform Policies New Output 1.1: Updated national sector reform policies drafted New Output 1.2: Capacities in sector reform policy development, implementation and monitoring enhanced New Output 1.3: Enhanced capacity to provide communications and visibility for sector reform policies and specific services provided by beneficiary institutions | Old Result 1.1 Enhanced capacity of the beneficiaries in national sector policy development, implementation and monitoring Old Result 5.2 Support in policy dialogue Old Result 4.6. Increased public awareness and visibility of SSA/ESS employment services for jobseekers and employers Old Result 4.9. Increased public awareness and visibility of LMIS portal and use of its analytical reports and results | The New Output 1.1 incorporates and extends the scope of the content of the Old Result 5.2, expanding coordination activities and linking policy development more directly with the SRPC and monitoring requirements. It also includes a major new survey activity requested by MoESCS. This unanticipated activity will be demanding in terms of the expert days required and will reduce the available days for any other additional activities that may be defined in the course of project implementation. The New Output 1.2 includes the Old Result 1.1 as well as providing an umbrella for all capacity development activities from other components. The implications for resource allocation are considered to be neutral. The New Output 1.3 is new and reflects the fact that there was no overall output for communications and visibility activities in the original ToR. It also includes all specific visibility Results and activities that were originally in other components (Old Results 4.6 and 4.9 as well as activities from Old Results 2.1 and 3.4). The scope of communications activities beyond those specifically mentioned in the ToR is dependent on the availability of working days not otherwise utilised in other activities. |
| Component 2: Skills Development & Entrepreneurship Learning New Output 2.1: Enhanced capacity of the MoESCS to further develop and modernise skills development and LLL systems New Output 2.2: Enhanced capacity of educational institutions to provide professional orientation and career guidance for learners in general, vocational and higher education New Output 2.3: Enhanced capacity to deliver entrepreneurship education in general, vocational and higher education and lifelong learning | Old Result 2.1. Enhanced capacity of the MoESCS to further develop and modernise skills development and LLL systems Old Result 2.2. Enhanced capacity of the MoESCS and institutions to provide professional orientation and career guidance for learners in general, vocational and higher education institutions Old Result 3.6. Enhanced capacity of the MoESCS and TPDC to design, develop and monitor entrepreneurship key competence development in general and vocational education, and lifelong entrepreneurial learning activities Old Result 3.7. Enhanced capacity of higher education institutions to promote entrepreneurship key competence development in teaching and learning | The New Output 2.1 is much the same as the old one, though with some activities (e.g. related to by-law drafting) reduced in scope and others (related to improving access to LVET/LLL) expanded. The implications for resource allocation are considered to be neutral. The New Output 2.2 is also much the same as the old one, although activities have been re-formulated to reflect beneficiaries’ needs. The implications for resource allocation are considered to be neutral. The New Output 2.3 incorporates both of the two entrepreneurship learning results (previously numbered 3.6 and 3.7). The implications for resource allocation are considered to be neutral. |
| COMPONENT 3: Youth New Output 3.1: Enhanced capacity of Youth Agency to develop and deliver effective youth services New Output 3.2: Improved organizational and human capacities to deliver youth services at local level | Old Result 3.1. Effective delivery of professional orientation and career guidance for the youth outside formal education system Old Result 3.2. Increased variety of high quality non-formal education programmes available and accessible for the vulnerable youth who left formal schooling Old Result 3.3. Improved coordination and collaboration between the Youth Policy Department and youth organisations & youth workers in the design and delivery of youth activation measures Old Result 3.4. Increased public awareness and piloting of social entrepreneurship concept to facilitate youth transition and gain first job experience Old Result 3.5. Capacity (knowledge and expertise) developed within the Youth Policy Department staff to provide more effective youth services, especially for vulnerable youth | Since the original ToR, the Youth Policy Department and existing agencies in the area of youth were combined to create the new Youth Agency, and the Component has been re-designed to reflect this. The Component is now more clearly focused on capacity building, both of the new Youth Agency (through New Output 3.1) and municipal youth centres (and other organizations delivering local youth services), whose functions still need to be more precisely defined (New Output 3.2). Old Results related to youth services (Old Results 3.1, 3.2, 3.4) are now bundled as activities within the New Outputs 3.1 and 3.2, including related capacity building and training In the light of these changes, we anticipate that additional TA inputs and resources could be required, beyond those estimated in the Consortium’s proposal |
| COMPONENT 4: Employment Services New Output 4.1: State Employment Support Agency (SESA) supported in its implementation of the Revised New Service Model (NSM) New Output 4.2: SESA supported in designing and delivering more accessible, effective and comprehensive ALMP measures available for all job seekers New Output 4.3: Capacity (knowledge and expertise) developed within the SESA staff to provide more effective employment services for jobseekers and employers | Old Result 4.1. Revised “employment service model” put in place in the employment offices Old Result 4.2. More accessible and effective ALMP measures available for all job seekers through the revision of existing measures Old Result 4.3. Diversified ALMP measures available for all job seekers through introduction and piloting of non-existent measures Old Result 4.5. Capacity (knowledge and expertise) developed within the SSA/ESS staff to provide more effective employment services for jobseekers and employers | The main differences between the New Output 4.1 and the Old Result 4.1 reflect the shifting of responsibilities for employment services from the SSA to the new SESA and the planned regionalisation of employment services previously provided at municipality level. The latter raises some questions regarding access, which will become clear when the new agency is operational, and which may have some implications for project implementation. The New Output 4.2 combines the Old Results 4.2 and 4.3. The New Output 4.3 remains much the same in terms of content as the Old Result 4.5. The Old Result 4.6 has been incorporated as an activity in the New Output 1.3 and the Old Result 4.4 has been renumbered 5.2 and moved to Component 5. Despite these changes, the implications for TA resource allocation for this Component are considered to be neutral. |
| COMPONENT 5: Information Systems and Analysis New Output 5.1: Improved integrity and compatibility of data and information systems for evidence-based policy making and implementation New Output 5.2: Technical revision and upgrading of Labour Market Information Management System (LMIMS) supported New Output 5.3: Capacity of Labour Market Information System (LMIS) team enhanced in analysis, survey and anticipation methods New Output 5.4: Enhanced capacity of EMIS to support education and training evidence-based policy making New Output 5.5: Enhanced capacity of institutions using LMIS, LMIMS and EMIS data in evidence-based policy making | Old Result 4.4. Labour Market Information Management System (LMIMS) portal technically revised and upgraded to increase its information content, intranet use by the staff, inter-connectivity, and user-friendliness Old Result 4.7. LMIS portal technically revised and upgraded Old Result 4.8. Capacity (knowledge and expertise) developed within the LMIS team for using different skills anticipation tools to collect, analyse and disseminate labour market information, and monitor labour market developments Old Result 4.10. Enhanced capacity of Enterprise Georgia to analyse SME skills needs and link them with relevant training provision Old Result 2.3. Enhanced capacity of EMIS to support education and training policymaking and draft evidence-based analyses and policy briefs | This new Component has been created from a number of Results previously dispersed across different components of the project. During the IP, it became clear that the issue of data sharing between agencies is of crucial importance and extremely complex, and that systems development will require both restricted and public access to data. The Old Result 4.4 has become New Output 5.2 and the Old Result 2.3 has become New Output 5.5 and has been moved to this component. These changes will have neutral implications for resource allocation. The new Output 5.1 was implied but not explicitly stated in the ToR and is clearly an expectation of the beneficiaries. It will involve substantial technical work requiring additional TA inputs not anticipated in the Consortium’s proposal. The Old Results 4.7 and 4.8 have become the New Output 5.3 with an exclusive focus on the LMIS and the MoESD. A New Output 5.5 bundles activities focused on enhancing the capacities of stakeholders and other institutions using LMIS, LMIMS and EMIS data in evidence-based policy making, and also incorporates the Old Result 4.10 as one of the activities. The Result also includes supporting a new survey activity requested by MoIDPLHSA. This Result may therefore also require additional TA inputs not anticipated n the Consortium’s proposal. |
| COMPONENT 6: Grant Scheme New Output 6.1: Grant scheme implementation supported through the monitoring of grant projects | Old Result 5.1. Support and expertise services provided in Grant Scheme component proposals development, project management and monitoring | Old Result 5.1 has become the New Output 6.1 and the scope of the activities has been changed. Although the TA will now be focused only on the monitoring of grant projects, and will exclude the broader support to grant scheme management envisaged in the ToR, we consider that there is a strong possibility that there will be a greater number of projects to monitor and that some of them will be of a longer duration than was estimated in the Consortium’s proposal. We therefore assume that the changes will have neutral implications for resource allocation. |

## Component 1 – National Sector Reform Policies

### Background information

The first component of the project, which was originally titled “Transversal Tasks” has now been re-titled “National Sector Reform Policies”, a title that we consider to express more clearly the aims and content of the component. The Component is focused on increasing capacity of the relevant Georgian institutions to develop, implement and monitor the implementation of national sector policies supported by the EU SRPC programme with the aim of ensuring a more effective and coordinated approach to policy development and implementation.

The Component is targeted on the three ministries named in the ToR (MoESCS, MOIDPLHSA and MoESD), together with subordinate agencies) and with the new Youth Agency, established in August 2019 under the office of the Prime Minister. It is linked with all other components of the project and will provide a primary vehicle for delivery of advisory and capacity building support to SRPC development and implementation by the beneficiaries. The component is thus the strategic driver of the project, impacting on everything else and driving the policy development and implementation process within which the other components will be implemented.

The Component now includes 3 Outputs, following a reorganization of the contents of the TA into a structure that seeks to create greater links between related results and therefore provide a more logical basis for project implementation. The main changes that we have made at the level of Outputs are as follows:

- Old Result 1.1 (“Enhanced capacity of the beneficiaries to further develop and modernize skills development and LLL systems”) has become Output 1.1 “Updated national sector reform policies drafted”, and also includes policy dialogue and monitoring activities previously in the former Result 5.2 “Support to Policy Dialogue”, because of their close links with policy development and improvement. It is focused on policy development and improvement, supporting policy dialogue, and enhancing capacities in sector policy implementation and monitoring. In addition, we have noted that, from the second quarter in 2021, there will be a need to contribute to new programme design.

- All capacity building activities have been moved to the new Output 1.2 which has been named “Capacities in national sector reform policy development, implementation and monitoring enhanced”.

- Output 1.3 is new, and was proposed in the technical proposal at the time of tendering, and reflects the fact that the ToR included requirements for certain communications and visibility measures but did not explicitly specify either a result or any activities leading to the required outcomes. We have named this Output “Enhanced capacity to provide visibility and communications support for sector reform policies and specific services provided by beneficiary institutions”, and we have included it in Component 1 because of the fact that it is transversal in nature and relates to all other components of the project.

It should be noted that, despite a considerable reorganisation of content, no activities from the original ToR have been lost or omitted. However, within each of the Results, some of the original activities have been re-defined though a rationalisation process which has involved combining them into more broadly defined activities, and some of the more narrowly defined activities have been re-grouped as sub-activities.

The Component will be supported jointly by the three Key Experts, David Handley (Team Leader/Skills Development), Heinrich Duffner (Employment Services) and Claus Møller (Labour Market Analysis), with support in Outputs 1.1 and 1.2 from the long-term Non-Key Experts, Ana Diakonidze (Skills Matching) and Anastasia Kitiashvili (Skills Development) and in Output 1.3 from Tatia Khubulava (Communications and Visibility).

### Component 1 Implementation

Output 1.1: Updated national sector reform policies drafted Updated national sector reform policies drafted

Activity 1.1.1:  Analyse the policies, strategies and action plans of the MoESCS, MoIDPLHSA, MoESD (incl. their subordinate bodies), and the Youth Agency in the areas of skills development and skills matching to identify gaps and propose areas for improvement

The collection and analysis of policy and strategy documentation from the beneficiaries of this activity has already begun during the Inception Phase and have contributed to the identification of specific interventions as listed under Activity 1.1.2 below. Nevertheless, this will be an on-going process which will continue throughout the project in conjunction with project beneficiaries and stakeholders, and we anticipate that this will be a pivotal point for both the GoG and the EU.  Attention in the analysis will therefore be paid not only to the substantive content of existing strategy documents, but also to the extent of their compliance with the current requirements of the Administration of the Government of Georgia for sectoral and institutional strategies.

Activity 1.1.2:  Support updating and/or improvement of policies, strategies and/or action plans in line with national policy planning framework requirements

In our Inception Phase meetings, we sought to clarify the expectations of beneficiary ministries and agencies regarding the need for policy development and improvement during the period of the project. As a result, we have identified a need to provide specific support to:

- MoESCS in developing a Strategy and Action Plan for career education and guidance covering general, vocational and higher education, as well as career guidance and counselling for those outside the formal education system:

This will require supporting a working group established by MoESCS (with a coherent approach across the system ensured by the participation of MoIDPLHSA/SESA and the Youth Agency) to develop a strategy and concrete action plan based on an updated and comprehensive career education and guidance concept in cooperation with the three responsible departments of the Ministry.

This task, in accordance with the provisions of the Law on VET, should be completed by the end of 2020.

- MoESCS in developing the national VET strategy and action plan in the context of the overall national education strategy:

This will involve updating the national VET Strategy and Action Plan (currently to 2020) by extending the period of coverage to 2025 or 2026. We understand that this should be done in conjunction with the updating of the country’s overall education strategy which is being supported by the EU PAR programme, and that it will involve advisory support and coordination of a working group established by the MoESCS VET Department.

It is understood that this activity is at the top of the priorities for MoESCS in 2020, with an expectation that it will be completed by the end of the 3rd quarter of the year.

- MoIDPLHSA in updating the national labour and employment strategy and action plan:

The Strategy (to 2023) and Action Plan (to 2021) were adopted on 30 December 2019. In the longer run, and certainly before the end of the project, the time will come when it will be appropriate to review and update it.

We noted also that assistance may be required by MoIDPLHSA in regard to the draft Employment Law, also not yet approved, which is to be worked on further by members of a parliamentary committee. However, it is not yet clear whether this will be necessary.

In addition, it is possible that technical assistance may be required for the drafting of by-laws and other institutional documents related to the work of the SESA and advancement of employment service provision.

- The Youth Agency on developing a strategy/action plan for youth services in the context of the revised national Youth Policy:

The Youth Agency and the Parliament of Georgia, in cooperation with other stakeholders and technical assistance of UN agencies, led by UNFPA, are working on the development of new youth policy concept for 2020-2030, which will be submitted to the Parliament for approval in the 2020 spring session of Parliament. This youth policy concept will become main document determining youth policy development in Georgia for the next ten years.

Based on the youth policy concept that will be adopted by Parliament of Georgia and youth policy document adopted by government of Georgia in 2014, the Youth Agency will elaborate a national cross-sectoral youth strategy 2020-2025 and its action plan for 2020-2023.

The development process of the strategy will start in the spring of 2020 and will finish in the late autumn 2020. This process will be participatory, where the line ministries, civil society organizations and young people will be involved in its development and implementation process. 	Accordingly, the project will assist Youth Agency in this process as well as in its strategic development of youth services related to employment and entrepreneurship.

It has also been noted that the Youth Agency will require some advisory support related to development of a new Law on Youth, although it is not possible at the present time to precisely define the nature of the support that should be provided.

It should be noted that it is likely that other needs will be identified during the process of project implementation and, if so, they will also be incorporated into this list.

In general, the support provided under this Activity will include contributions to working group meetings, comments on drafts and day-to-day advisory support to beneficiary counterparts. If any specific training needs are identified in the course of the TA, short training sessions may be organised. However, it should be noted that Output 1.2 below is intended to cover the capacity building needs of this Component.

All assistance to strategy preparation, including the processes and procedures followed and the structure of draft strategy documents, will comply fully with the requirements set out in the Policy Planning, Monitoring and Evaluation Handbook issued by the Administration of the Government of Georgia in 2019.

Activity 1.1.3: Assist MoESCS in surveying the geographical coverage of VET provision by municipality, identifying gaps related to potential local demand and labour market needs, and recommending solutions and priorities for expanding availability of VET provision through existing institutions and existing or new programmes

During the Inception Phase the MoESCS Deputy Minister for VET requested the project to assist with a study to identify how best to expand the availability of VET provision in parts of the country where access to VET is limited and to increase VET participation. It is understood that this is a very urgent issue and that the assistance should be provided in the early part of 2020, in order to enable MoESCS to make the necessary policy decisions and allocate resources.

The survey is linked with work that is already being carried out by the VET department to introduce VET courses into selected secondary schools. (It is understood that a pilot project currently covers about 600 schools), and which may provide at least some of the required information.

The survey results should identify on a regional basis (i.e. covering 64 municipalities, excluding the five municipalities under Russian occupation) the current availability of VET provision, the potential providers (colleges, schools, university faculties etc.) that could be resourced to provide needed courses, and (on the basis of available labour market information) the courses that should be introduced, adapted or developed in order to meet identified local needs.

According to MoESCS, the research, based on analysis of available demographic, education-related, infrastructure, and local labour market data should investigate and provide answers to the following specific questions:

- What type of educational institution should be established or strengthened in a particular region?

- What type of VET programs (long-term and short-term) will be relevant to a particular region?

- What occupation are in demand and/or which VET programs will be relevant to the specific region?

The focus of the TA will be on working with members of the VET department (and a working group established by MoESCS) to help them to collect and analyse the data, drawing conclusions to enable the making of evidence-based policy decisions. It is not expected that a large amount of new data will need to be gathered, but the work will focus on identifying and working with a very large amount of already available information from a variety of sources in a rather complex analysis.

The results should include recommendations on the most economically viable options open to the MoESCS for expanding VET coverage in all parts of the country.

It should be noted that this activity is potentially extremely resource-intensive and may require the reallocation of some expert working days from less urgent activities.

Activity: 1.1.4: Organize annual thematic workshops/events related to sector reform policy development to present/ discuss relevant Georgian and international experiences and practices

This activity, proposed in the ToR, is part of the SRPC policy dialogue and is intended to stimulate thinking about key policy issues and suggest solutions that may be fed into policy development. In the technical proposal presented by the Consortium, we suggested a number of issues that might be considered, and proposed to organize one event per year. However, our Inception Phase consultations, including discussion with the EUD, have shown that there is an urgent need to go ahead in assisting policy dialogue in a number of areas and it has been proposed that we should organize 2 or 3 workshops in the early part of 2020 to address several immediate needs. In particular, the EUD has requested the project to organize the following events in 2020:

- A workshop on youth work, scheduled to take place on 12 February 2020, examining international good practices in the establishment and functioning of youth centres, and the role and responsibilities of youth workers. This workshop should be organized in close cooperation with the Youth Agency, and should be related to action planning for the further development of youth work and youth measures in Georgia;

- A workshop on embedding key competences (including entrepreneurship) within the National Curriculum and VET, building on work already carried out within the context of the EU PAR programme. This workshop is tentatively scheduled to take place on 14 February 2020 to fit in with the timing of a mission by representatives of the ETF;

- A workshop on social partnership in VET, to explore new approaches following the demise of the National VET Council and the current weakness of social partnership arrangements. This workshop should also take place sometime during the first quarter of 2020.

All three workshops will be held in Tbilisi. The three identified workshops to be held in 2020 are planned as half-day events and will therefore be shorter events than were envisaged at the time of tendering.

Policy Dialogue Workshop topics for the second, third and fourth years of the project will be identified during the course of project implementation and will be proposed to the Project Steering Committee at an appropriate time in conjunction with progress reporting.

Activity 1.1.5: Support the strengthening of co-ordinating mechanisms between beneficiary ministries and institutions related to sector reform policy development, implementation and monitoring

This is a new, on-going and rather ad hoc activity, implied rather than explicitly identified in the ToR,  that we have proposed in order to ensure synergy and consistency in SRPC policy development and implementation between the three beneficiary ministries, the Youth Agency and other relevant agencies and institutions, and is closely related to Activities 1.1.1 and 1.1.6.

For example, there is a need for inter-agency cooperation in the area of youth, covering such issues as education and training, career guidance and counselling, and entrepreneurship, because of potential overlaps between the different players who are targeting young adults, including NEETs, which include MoESCS, MoIDPLHSA, SESA, GITA etc., as well as other stakeholders.

It is our understanding that coordination currently seems to be rather ad hoc rather than systematic, and tends to be related to specific activities or conducted at a personal level, rather than based on a holistic approach. Advice will be provided on possible solutions, and the beneficiaries will be supported in developing cooperative approaches including data and information sharing and coordination activities related to specific activities and interventions of the project.

Activity 1.1.6: Support implementation and further development of monitoring arrangements for sector strategies and action plans, including annual reviews and advisory support to the beneficiary ministries and institutions on achieving targets/performance indicators of the SRPC

This activity is directly linked to the need to ensure compliance with the General Conditions and Variable Tranche Performance Indicators of budget support provided under the SRPC “Skills Development and Matching for Labour Market Needs”.

The assistance should include strengthening the mechanisms employed by the beneficiaries to systematically monitor and self-assess their performance to ensure compliance with the indicators and conditionalities specified in the Contract. Those mechanisms should be reviewed and the beneficiaries should be supported in carrying out systematic performance monitoring.

The project ToR implied that this should be done through an “Annual Review Meeting” organized in the first quarter of each year to discuss progress in achieving target, including a review of data and statistics, action plans and policy measures, and the state of play in implementing reform actions in the policy matrix of the budget support component of the SRPC. In the technical proposal submitted by the Consortium, we followed this approach by proposing a single event involving all the beneficiary ministries.

However, it seems much more likely that the necessary results will be obtained through direct assistance to each of the responsible beneficiary institutions to help them to meet requirements for compliance with budget support conditions and indicators, through advice, capacity building and support to their internal monitoring processes. It is our understanding that the timing of our interventions should be focused on ensuring that the beneficiaries are prepared to demonstrate their progress to the Interim Review Missions of the EU European Neighbourhood Instrument EU-Georgia Annual Action Programme 2017 in May of each year, and to ensure that the necessary actions to ensure compliance are completed by the specified deadlines.

Specific TA activities will therefore be organized with beneficiary ministries to help them meet specified indicators, targets and deadlines specified in the SRPC policy matrix. These imply an alternative way of delivering the TA to that implied in the ToR.

Activity 1.1.7: Provide administrative and logistical support to EU missions and expert visits to Georgia related to the SRPC

This activity was included in the ToR (in the original Result 5.2) in order to assist the EUD in planning, scheduling and organizing visits of EU experts to Georgia to support work in SRPC fields (Skills, VET, LLL, employment and labour market, youth etc.), and involves mainly administrative and logistical support (e.g. in preparing agendas, arranging meetings, organizing local transport etc.)

The logic for including it in the TA project is that the EUD in practice finds it difficult to provide practical support to such visits. However, it will also provide opportunities to forge a closer linkage between the general provision of EU expertise to project beneficiaries in the areas covered by the SRPC and the activities undertaken by the project. The activity will be on-going throughout the project.

Activity 1.1.8: Provide short update and progress reports to the EU Delegation related to sector reform policy development and implementation

This activity (from the former Result 5.2 in the project ToR) is closely related to all other activities of Output 1.1 and is intended to ensure that the EUD is in possession of up-to-date knowledge and information about developments related to the SRPC and the Association Agreement more generally.

Reporting (whenever necessary) will include sharing all important information on progress in policy and legislative development (including key documents) and relevant statistical data, as well as meeting ad hoc information requests by the EUD. The activity will be on-going throughout the project.

Output 1.1: Deliverables and Inputs

| Output 1.1 |  |  |  |
| --- | --- | --- | --- |
| Activities | Deliverables | Inputs (WD) |  |
| 1.1.1 | Proposals for policy development/improvement | TL: KE2: KE3: LT JNKE: ST JNKE SNKE: | 80 50 0 89 20 0 |
| 1.1.2 | Inputs to VET strategy and action plan to 2025 |  |  |
|  | Inputs to career education and guidance strategy and action plan |  |  |
|  | Inputs to the updating of employment/labour market strategy (and possible inputs to legislative development) |  |  |
|  | Inputs to strategy and action plan for youth services, and possibly also to legislation on Youth |  |  |
| 1.1.3 | Assessment report to MES on options for expanding VET provision into all municipalities |  |  |
| 1.1.4 | Agendas/reports of annual thematic workshops |  |  |
| 1.1.5 | Recommendations on inter-ministry/agency coordination arrangements |  |  |
| 1.1.6 | Strengthened SRPC monitoring arrangements |  |  |
| 1.1.7 | Ad hoc meeting schedules for EU expert visits |  |  |
| 1.1.8 | Ad hoc progress reports to EUD |  |  |

Output 1.2: Capacities in sector reform policy development, implementation and monitoring enhanced

1.2.1:  Develop a comprehensive capacity building programme for the beneficiary ministries and institutions for the whole project duration, related to the requirements of national sector policy development, implementation and monitoring

The previous Result 1.1 from the ToR included a significant amount of capacity building for the project beneficiaries in specified fields related to the SRPC, which we have bundled together as sub-activities related to more broadly defined activities.

It should be noted that the list provided in the ToR may not be comprehensive, and we will carry out an analysis of capacity building and training needs with each of the beneficiary institutions to ensure that nothing important has been missed, and the analysis will form the basis for developing an overall training plan which will include modules covering the necessary fields to which the capacity building activities will be directed. The fields specified in the ToR (which may be adjusted by agreement with project beneficiaries during preparation of the programme, are as follows:

- Training in analysis and use of data in evidence-based policy making, including preparation of reports using data from key information sources - EMIS, LMIMS, LMIS etc.: This training will be delivered in the context of Component 5, which includes capacity building support to data users from beneficiary institutions to support the preparation of evidence-based reports and policy documents.

- Training in financing and costing of action plans: This training was specified in the ToR and is thought to be linked with Activity 1.1.2 above, because legislation, strategies and related action plans cannot be adopted and implemented without proper and reliable budget estimates, resulting in poor or limited implementation of various policy measures. The training proposed aims to provide representatives of beneficiary institutions with the tools to more accurately estimate the cost implications of policy measures that may be proposed.

- Training in monitoring and evaluation of SRPC effectiveness of policies and implementation: This training is linked with Activities 1.1.2, 1.1.5 and 1.1.6 above and is intended to address perceived weaknesses in current monitoring and evaluation arrangements and ensure that beneficiaries are better placed to meet the various conditions and indicators of SRPC policy development and implementation. It is understood that some capacity building support in SRPC monitoring and evaluation practices was provided by the previous EUVEGE project during the first phase of Skills4Jobs and the training should seek to replicate as necessary and build upon what has been done already.

- On-site coaching/mentoring for beneficiaries’ senior staff in sector policy implementation/ monitoring: The aim of the coaching, provided day-to-day in the implementation of other project activities is to ensure that SRPC policy implementation is more effectively monitored and evaluated, and that issues related to budget support conditions and indicators are systematically addressed. The caching should follow on from the training provided, and should be on-going throughout the project.

- Training in communicating reforms in skills development and matching to stakeholders and the wider public: This training should cover both the EU visibility requirements (in relation to the SRPC requirements) and development of communications capacities within the beneficiary institutions to effectively communicate policy developments and implementation measures to targeted groups and the general public. From our experience, we know that the PR departments of beneficiary institutions cannot carry out the necessary communications activities alone, and that the training should be provided to a wider group of stakeholders, including those at regional level, who are able to reach out to target groups and the public throughout Georgia. It should be noted that, besides communicating policy developments (Component 1), Components 2, 3 4 and 5 also include activities focused on improving the visibility of specific developments, and this activity will therefore be carried out within the context of the overall Project Communications and Visibility Plan and in relation to specific outputs of the relevant components of the project.

- Familiarization and linking with EU networks relevant to particular fields of the SRPC: Networking and information sharing with international partners is an essential part of the capacity building process, contributing knowledge about relevant and/or comparable experiences and good practices from other countries, and, within the European integration process, the involvement of Georgian institutions in relevant EU networks (e.g. in career guidance, entrepreneurship learning, youth policy) is a “must”. Within the framework of the overall capacity building plan of the project, relevant networks will be identified in relation to various fields of the SRPC and contacts will be facilitated between beneficiary institutions and European networks and counterparts. This activity will be linked especially with the study visits organized through Components 3 and 4, which will provide important opportunities for gaining first-hand contacts with participants in relevant EU networks.

Much of the capacity building under this Output will be delivered through on-the-job coaching and day-to- day advisory support. The following is our provisional estimation of the formal capacity building training events and workshops that will be required (i.e. excluding other capacity building activities.

| C1 | Workshops/ Training | Target group | Breakdown of Workshops/Training events |  |  |  | Participants |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Duration of each event | No. of Events in Tbilisi | No. of Events in regions | Total days | In Tbilisi | In regions | Total person days |
| 1.1.4 | Thematic workshops | Representatives of MoESCS, MoESD, MoIDPLHSA, SESA, Youth Agency, other stakeholders | 0.5 | 8 | 0 | 4 | 240 | 0 | 120 |
| 1.2.1 | Data analysis/use in evidence-based policy making (from ToR) | See details under Component 5 below | See C5 | - | - | See C5 | - | - | See C5 |
|  | Financing and costing of Action Plans (from ToR) | Representatives of MoESCS, MoESD, MoIDPLHSA, SESA, Youth Agency, MoF | 2 | 1 | 0 | 2 | 15 | 0 | 15 |
|  | Monitoring/evaluation of sector reform policies (from ToR) | Representatives of MoESCS, MoESD, MoIDPLHSA, SESA, Youth Agency, MoF | 2 | 1 | 0 | 2 | 15 | 0 | 15 |
|  | Communicating sector reform policy devt. & implementation (from ToR) | Representatives of MoESCS, MoESD, MoIDPLHSA, SESA, Youth Agency | 2 | 1 | 1 | 4 | 30 | 30 | 60 |
|  | Other (depending on TNA) | TBC | 2 | 1 | 0 | 2 | 25 | 0 | 25 |
| Total |  |  |  |  |  | 14 |  |  | 235 |

1.2.2: Monitor and evaluate progress in capacity building for the project beneficiaries and periodically adjust the programme according to emerging needs

Training and other capacity building activities will be implemented according to an overall training plan developed in the first few weeks of the implementation period of the project under Activity 1.2.1 above. Progress and results should be monitored systematically. Each training event/session should be evaluated on the basis of participants’ reactions, and account should be taken of their comments.

Although the capacity building plan should be as comprehensive as possible, it may be assumed that additional training or capacity building needs will arise during project implementation, which should be addressed through adjustments to the programme, involving changes to already planned training interventions or the inclusion of new ones. There should be sufficient flexibility in the training programme to accommodate the need for further or follow-on training to be provided as necessary.

Output 1.2: Deliverables and Inputs

| Output 1.2 |  |  |  |
| --- | --- | --- | --- |
| Activities | Deliverables | Inputs (WD) |  |
| 1.2.1 | Capacity building programme | TL: KE2: KE3: LT JNKE: ST JNKE SNKE: | 45 0 46 20 0 0 |
|  | Reports of individual training and capacity building events, incl. agendas, materials, evaluation reports |  |  |
| 1.2.1 | Evaluation report of capacity building programme |  |  |

Output 1.3: Enhanced capacity to provide visibility and communications for sector reform policies and specific services provided by beneficiary institutions

Activity 1.3.1: Develop and implement a project communications and visibility plan including measures and related tools and events to promote active stakeholder engagement and raise public awareness in compliance with EU visibility requirements

All EU-financed projects are required to develop and implement a project communications and visibility plan, for which a template is provided by the EUD. The project ToR made extensive reference to the need for compliance with EU visibility requirements and included a number of visibility actions related to generating public awareness of specific initiatives undertaken with the beneficiary institutions, but included no specific result or activities specifically related to delivering the communications and visibility outcomes implied in the ToR. As explained above, in the introduction to Component 1, we have therefore proposed the new Output 1.3, under which this activity falls.

All visibility arrangements and materials should conform to the EU visibility requirements set out at https://ec.europa.eu/europeaid/funding/communication-and-visibility-manual-eu-external-actions_en and the  Georgia-specific guidelines at http://eu4georgia.ge/visibility/. Visibility materials will also reflect the “green” approach promoted by the EU, including use of biodegradable materials, care not to produce unnecessarily large quantities of printed materials and avoidance of the single-use plastics.

Preparation of the communications and visibility plan has been started during the Inception Phase and it is expected that it will be delivered together with this Inception Report during January 2020.

In preparing the communications and visibility plan, we have been mindful of the fact that the overall communications and visibility of the Skills4Jobs Phase 2 programme is out-sourced by the EUD, and the scope of the project’s own plan is limited to visibility actions specifically related to the TA component.

The communications and visibility plan should include an up-dated and comprehensive contacts list for project communications.

Activity 1.3.2: Prepare communications and visibility materials to support the project communications and visibility plan

These should include the following:

- Banner for use at communications events

- Brochure(s) and leaflet(s)

- Project web page

- Social media pages etc.

Activity 1.3.3: Support and monitor communications between project beneficiaries and key stakeholders to ensure effective coordination of sector reform policy-related activities

In responding to the ToR, it quickly became clear that effective internal communications and visibility (between the project and the various beneficiaries, as well as between them) will be as important to the success of the project as external communications (with stakeholders more widely, as well as the general public). This activity is closely related to Activity 1.1.5 above and includes developing the tools to facilitate intra-beneficiary coordination and communications, monitoring the effectiveness of cooperation between them, and making the necessary interventions to improve cooperation and coordination. To this end, the project communications and visibility plan includes various mechanisms focused on securing effective stakeholder engagement and cooperation.

Activity 1.3.4: Coordinate, support and monitor external communications across all components of the TA, in order to raise awareness of sector reform policies and project results among stakeholders and the general public

This activity is both generally focused on communicating SRPC reforms to stakeholders and the general public and on communicating specific developments highlighted in the project ToR. It will be carried out with the beneficiary institutions (including both the responsible departments and the institutions’ PR functions).

The external communications activities of the project should include relevant press and media briefings and relevant dissemination events to provide visibility to SRPC and project achievements, according to a provisional timetable (detailed for the first year of implementation and in outline form for subsequent years).

In particular, it should be noted that the activity is closely related to various activities in Components 2, 3 4 and 5 which concern the promotion of opportunities generated by SRPC policy development and implementation supported by the TA provided through the project. Those related activities in the other components will be carried out within the framework provided by the project communications and visibility plan. The activities specifically referred to in the ToR and included in the other components include:

- Assistance to MoESCS in enhancing awareness of opportunities and the attractiveness of VET and LLL among learners and the wider public though targeted activities and events:

This will involve working with the MoESCS VET department, providers (public and private colleges, schools, universities)  and other stakeholders at national level and in the regions to promote developments such as new VET programmes and qualifications, short courses, improved access arrangements etc. with a special emphasis on increasing enrolments, highlighting employability opportunities and targeting NEETs, marginalized communities and vulnerable groups.

- Increasing public awareness of the youth services, and youth transition and activation measures including social entrepreneurship:

This will involve working with the Youth Agency and Youth Centres in targeted regions and municipalities to generate awareness of opportunities for young people, and especially NEETs, provided through the improved range of services and measures provided by the Agency and its local partners.

- Generating public awareness of employment services and ALMPs to provide visibility for the new SESA, advertising their services and targeting young people, women and vulnerable groups including NEETs:

This will involve working with the MoIDPLHSA, the new SESA, its regional offices and partners in the regions to provide public information about opportunities available through the employment services and supported by ALMPS, and promote the benefits to job seekers.

- Generating public awareness and visibility of labour market information, including branding of the LMIS web portal, VET.GE etc.:

This is an activity that seeks to disseminate relevant information both to potential users (i.e. to encourage them to access available information from the LMIS and EMIS portals to meet their needs) and to more generally inform the general public about key labour market issues.

Output 1.3: Deliverables and Inputs

| Output 1.3 |  |  |  |
| --- | --- | --- | --- |
| Activities | Deliverables | Inputs (WD) |  |
| 1.3.1 | Project communications & visibility plan | TL: KE2: KE3: LT JNKE: ST JNKE SNKE: | 45 0 0 80 0 0 |
|  | Comprehensive contacts list |  |  |
| 1.3.2 | Project banner |  |  |
|  | Brochure/leaflet(s) |  |  |
|  | Project web page |  |  |
|  | Social media pages etc. |  |  |
| 1.3.4 | Schedule of external communications events |  |  |
|  | Reports of completed communications events |  |  |
|  | Reports of public disseminations activities organized under Components 2, 3 4 and 5, with related materials |  |  |

## Component 2 – Skills Development and Entrepreneurial Learning

### Background information

The original project ToR provided 3 Results.

Output 2.1 (old Result 2.1) is focused on enhancing MoESCS capacity to further develop and modernize skills development and lifelong learning by:

- Supporting the further development of the legal, regulatory and funding framework for VET;

- Reviewing access to VET and LLL, eliminating barriers and developing measures to increase participation of youth and adults (with an emphasis on early school leavers, NEETs, women and vulnerable groups;

- Developing flexible provision to meet the needs of adult learners and promoting the benefits of VET more generally.

These activities remain the core focus of Output 2.1. However, we have made some adjustments to reflect the outcomes of our fact-finding discussions during the Inception Phase. Besides a re-grouping and some rationalisation of activities defined in the ToR, there is some re-focusing of priorities, which may be summarised as follows:

- The proposed support to secondary legislation preparation for implementation of the VET Law is no longer necessary because other donor projects (UNDP, GIZ, GGF) have already provided the support needed by MoESCS.  In addition, other donor projects (GGF, ADB) have supported development of proposals relating to VET financing and the economic activities of VET institutions. At the time of this Inception Report, no concrete proposals for supporting development of additional by-laws have been put to the project. However, the project will provide support to development of guidelines and regulations on request and as needed;

- On the other hand, it is clear that the need to widen access to VET and LLL and increase participation continues to be a major issue and one of the top priorities of MoESCS. This area of activity will therefore require considerable support from the project. Because it is understood that DVV is now supporting MoESCS in developing lifelong learning provision for adults, the major focus of our activities should be on young people, especially on the early school leaving problem, together with the need to provide NEETs with improved re-entry pathways to VET.

Output 2.2 continues to be focused on career education and guidance (CEG) and the only changes that we have made involve a limited rationalisation and reformulation of activities.

It should be noted that CEG in public and private VET colleges has been quite well supported by previous donor initiatives (including by MCA-Georgia), and that there is already a functioning base on which to build. The biggest challenge is posed by the need to ensure that CEG is provided throughout the secondary education system, in which there are around 2,200 schools, and where it is known that, apart from a few careers information lessons, individual guidance for students is almost universally lacking.

The main contribution of the project is likely to be the provision of support to TPDC in developing and piloting CEG training for teachers and school administrators in order to develop a cadre of career counsellors, together with support to the development of partnerships at local level. In the case of higher education institutions, it is not known how many have functioning career offices or how effective they are, and tis should be one of the lines of enquiry in the situational analysis that should be carried out at the beginning of the implementation of this component.

The original ToR also included support to EMIS in this component as Result 2.3. However, we have moved this to the new Component 5 which brings together the support provided to all the various data systems (including LMIS and LMIMS), which seemed to be a more logical place for it.

Our new Output 2.3 is made up of the activities related to Key Competence Development that were previously located in Component 3 (where they were grouped under two results, formerly numbered 3.6 and 3.7). The new Output 2.3 now groups all activities related to key competence development in general, vocational and higher education. The logic for these changes is as follows:

- Entrepreneurship Key Competences are clearly a part of Skills Development, and are more logically placed in a component that targets other areas of skills development rather than in a component that otherwise targets the improvement of youth services. It should also be noted that there is a potential link between entrepreneurship learning and career education, which is also included in Component 2. Moreover, the activities related to entrepreneurship key competences are focused on supporting MoESCS, TPDC, schools, colleges and higher education institutions, non-formal providers etc., which are the beneficiaries of the other Outputs and activities within Component2;

- Combining separate results from the original ToR covering general and vocational educational education on the one hand, and higher education on the other, has enabled a broader and more holistic Output to be defined, covering the delivery of entrepreneurship key competence across all sectors and levels of education and training.

### Component 2 implementation

Activities under this Component 2 will require the provision of capacity building training to representatives of institutions targeted by the project, and our estimation of the training required under the entire Component is as follows:

| C2 | Workshops/Training | Target group | Breakdown of Workshops/Training events |  |  |  | Participants |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Duration of each event | No. of Events in Tbilisi | No. of Events in regions | Total days | In Tbilisi | In regions | Total person days |
| 2.2.2 | Piloting of CEG training for teachers (2 stages) | Teachers from general education schools (career counsellors) | 2 2 | 2 2 | 0 0 | 4 4 | 40 40 | 0 0 | 80 80 |
|  | Piloting of CEG training for VET provider staff | College career managers | 2 | 1 | 0 | 2 | 25 | 0 | 50 |
| 2.3.2 | Piloting of entrepreneurship training for general ed. teachers (2 stages) | Teachers from general education schools | 2 2 | 2 2 | 0 0 | 4 4 | 40 40 | 0 0 | 80 80 |
| 2.3.3 | Piloting of entrepreneurship training for VET teachers (2 stages) | VET teachers | 2 2 | 1 1 | 0 0 | 2 2 | 25 25 | 0 0 | 50 50 |
| 2.3.5 | Orientation training for implementing entrepreneurship learning pilot | General education and VET teachers | 1 | 1 | 0 | 1 | 20 | 0 | 20 |
| 2.3.5 | Orientation training for implementing entrepreneurship learning pilot (HE) | University teachers | 1 | 1 | 0 | 1 | 10 | 0 | 10 |
| Total |  |  |  |  |  | 24 |  |  | 500 |

Output 2.1: Enhanced capacity of the MoESCS to further develop and modernise skills development and LLL systems

As indicated in the introduction to Component 2, the scope of Activity 2.1.1 below has been reduced, whilst it is expected that Activity 2.1.2 will be a significant area of activity, involving considerable technical assistance.

Activity 2.1.1: Assist MoESCS in developing the legal, regulatory and funding framework for VET and LLL

As previously explained, the specific activities envisaged in the original ToR have already been carried out by other donors, and MoESCS does not have any specific proposals currently on the table which require action by this project at the present time.

However, the VET Department has requested this activity to remain open, because it is anticipated that, during the life of the project, circumstances will arise that will lead the Ministry to request our support in developing guidelines and/or regulations to support the further development of the legal and regulatory framework for VET.

Activity 2.1.2:  Assist MoESCS in improving access to, and participation in, VET and LLL by:

- Reviewing current barriers and factors restricting access of youth, women and vulnerable groups to initial VET, preparing recommendations on how to overcome them, and assisting MoESCS in designing, piloting and implementing appropriate measures:

This is the starting point for work on this activity, and should involve a thorough situational analysis based on documentary desk-research (data from EMIS, GEOSTAT, research reports etc.), consultation with officials, stakeholders and a sample of providers including education and training providers from outside Tbilisi, and (perhaps) focus group discussions with people drawn from target groups (i.e. youth, NEETs, women, vulnerable groups).

The outcome will be a report identifying factors that need to be addressed, together with action-oriented recommendations.

- Assisting MoESCS in designing, piloting and implementing measures aimed at preventing early school leavers and for tracking NEETs:

This sub-activity is closely related to the development of guidance services (under Output 2.2), both in regard to the development of support services for students at risk of “dropping out” and in regard to the tracer studies undertaken to track employment destinations of students graduating from VET courses.

Measures should focus on issues identified in the situational analysis including factors known to affect participation in education and training by young people, especially from vulnerable groups. We anticipate that this activity will lead to a number of identified measures, together with implementation guidelines, which can be piloted in a number of schools.

It will also be linked with initiatives of MES to develop “second chance” educational opportunities for those who left school early.

The guidelines can also be included in the training package for school career counsellors, which will also be developed in the activities under Output 2.2.

- Supporting MoESCS in designing and implementing lifelong learning measures with a special focus on NEETs and adults (including more flexible provision, short courses, partnerships with companies etc.):

This sub-activity will also draw on the results of the situational analysis, and should focus on how delivery systems can be adapted to help adults, including those in employment, to access available learning provision, e.g. by providing greater flexibility through means such as modular delivery, out-of-normal-working-hours classes, computer-based, distance learning and mobile provision, VNFIL credits where the individual can demonstrate some relevant prior learning etc. However, care should be taken not to duplicate anything that is being done by DVV, with which we should cooperate closely, and there should be a special focus on NEETs.

It is likely that the LLL provision that will be of interest to them should include entrepreneurship learning as well as VET courses, and it may be expected that short courses focused on increasing employability in particular economic areas might be more useful to many of them than simply providing access to initial VET programmes.

The measures should include innovative approaches designed to meet specific needs identified in the situational analysis. They should be supported by appropriate implementation guidance materials.

- Assisting MoESCS in actions enhancing public awareness of VET and its attractiveness (linked with Output 1.3 above):

Despite numerous efforts in recent years to promote and popularize VET as well as actions directed at improving both quality and relevance to employment, it is clear that a great many students prefer (or are persuaded by parental or teacher pressure) to opt instead for higher education, which frequently does not lead to employment.

It is understood that this public awareness raising activity represents a continuation of assistance previously provided to MoESCS (including by the previous EVET BS programme TA (EUVEGE) and by MCA-Georgia) to improve the brand image of VET and support awareness raising campaigns. However, it is understood that MoESCS has experienced difficulties in sustaining VET marketing and promotion activities, despite having a budget allocated for this purpose.

The activity should be carried out within the overall communications and visibility framework provided in Output 1.3 above and, rather than being exclusively focused on national campaigns linked with college enrolment deadlines, should include work with providers and other regional stakeholders in order to promote the VET provision available locally.

Output 2.1: Deliverables and Inputs

| Output 2.1 |  |  |  |
| --- | --- | --- | --- |
| Activities | Deliverables | Inputs (WD) |  |
| 2.1.1 | To be defined at a later point in project implementation | TL: KE2: KE3: LT JNKE: ST JNKE: SNKE: | 90 0 0 54 0 0 |
| 2.1.2 | Report/recommendations on VET/LLL access |  |  |
|  | Measures/guidance to combat early school leaving |  |  |
|  | Measures/guidance to improve access to LLL |  |  |
|  | Plan for promoting benefits of VET (national/ regional) |  |  |
|  | Promotional events and materials |  |  |

Output 2.2: Enhanced capacity of educational institutions to provide professional orientation and career guidance for learners in general, vocational and higher education

2.2.1: Assist MoESCS in developing and improving arrangements for career education and guidance by reviewing current situation, practices and quality in career education, guidance and counselling, and the capacity of institutions in general (upper secondary), vocational and higher education to deliver effective services to students:

This sub-activity will involve preparation of a detailed situational analysis report and career education and guidance concept, based on a combination of desk research and consultations with institutions and stakeholders. It should also include visits to a small sample of schools, colleges and universities to assess their career education and guidance provision and their capacity to deliver services. Because the scope of the activity includes general, vocational and higher education, we propose carrying out this activity in close collaboration with a small group made up of a representative of each of the MoESCS departments - VET, general education and higher education.

On the basis of the analysis, which will identify current practices, gaps and deficiencies (compared with international good practices) and capacities, the findings will be used to prepare a Concept Note with recommendations which will be the subject of a stakeholder consultation, at a workshop organized for that purpose.

Note: Work on developing the conceptual approach to career education and guidance will be linked with the development of a national strategy for career guidance under Output 1.1 above. Development of the Strategy and Action Plan will involve supporting a working group established by MoESCS, including representatives of other ministries and agencies including MoIDPLHSA/SESA and the Youth Agency, in order to ensure a coherent national approach to career guidance. Following finalization (on the basis of comments received), the Concept Note, Strategy and Action Plan will be handed over to the three relevant departments of MoESCS for subsequent implementation

Activity 2.2.2: Develop capacities of schools and colleges in career education and guidance:

- In cooperation with TPDC, develop/pilot an in-service training course and materials for teachers in upper secondary schools (if possible based on some of the “new school model” pilot schools) to take on the career counsellor role, including local partnerships with enterprises and colleges:

The MoESCS has requested that this activity should follow after development of the Career Guidance Concept Note, Strategy and Action Plan.

Around 2,200 secondary schools will each be responsible for implementing the new/revised arrangements for career education and guidance, and TPDC will need to implement an intensive programme for teachers in order to prepare them to take on the role of career counsellors, and has suggested the possibility of a two-stage training programme which should be developed and piloted with support from the project. Piloting should involve delivering the training at least twice to different groups of teachers, with the package revised as appropriate on the basis of an evaluation of the pilot.

The activity should also take account of previous CEG-related support provided by MCA-Georgia, which provided a toolkit for development of local education-business partnerships as a source of careers information and a resource to support delivery of career education lessons.

We have noted that the General Education Department of MoESCS is working with 165 specially resourced pilot schools to pilot the “new school model” and it has been suggested that piloting of the teacher training could involve teachers from those schools. On the other hand, it is possible that adding this to the demands of their existing piloting could overload them, and that other schools could alternatively be selected. In any case, development of the programme should involve representatives of the MoESCS General Education Department as well as TPDC. In any case, care will be taken to ensure the participation of teachers from the targeted regions.

Schools involved in the “New School Model” and the vocational schools, located in Tbilisi and the regions, will be identified, providing a network of schools and vocational colleges to be involved in the pilot. TPDC will provide a specific list of schools and vocational colleges.

TPDC has proposed that the training to be offered to teachers and piloted though the project should be organized in two stages, based on basic and advanced modules.

TPDC has also suggested that it will be desirable to link the teacher training in career education and guidance with that in entrepreneurship learning (provided under Output 2.3 below), with peer-to-peer couching used to share experiences among teachers and foster cooperation between teachers across both subject areas in general education and in VET.

- Review and, where necessary, update existing training module and materials for career managers in VET colleges:

A basic training module and toolkit for college career managers was developed by MCA-Georgia and was used in the training of career managers from all public colleges and some private colleges, and was handed over to MoESCS but not to TPDC. We consider that this may be used as a starting point for this activity – it should be reviewed and updated and follow-on training should also be developed to extend the competences of those who have already received basic training.

The up-dated/extended training module(s), together with related materials, guidance, instruments and tools, should be piloted and handed over to TPDC.

Output 2.2: Deliverables and Inputs

| Output 2.2 |  |  |  |
| --- | --- | --- | --- |
| Activities | Deliverables | Inputs (WD) |  |
| 2.2.1 | Situational analysis report (Concept Note) on career education/guidance in schools, colleges, universities | TL: KE2: KE3: LT JNKE: ST JNKE SNKE: | 60 40 0 54 0 50 |
|  | Action Plan for further developing career education/guidance in schools, colleges, universities |  |  |
| 2.2.2 | In-service training course/materials for school career counsellors developed/piloted |  |  |
|  | In-service training course/materials for college career managers up-dated/extended |  |  |

Output 2.3: Enhanced capacity to deliver entrepreneurship education in general, vocational and higher education and lifelong learning

As mentioned in the introduction to Component 2 above, the following activities have been moved from the original Component 3 proposed in the ToR, and two Results originally proposed in the ToR have been combined to produce this single, more broadly-based Output 2.3 covering all sectors and levels of education.

Entrepreneurship is defined in the European Union Council Recommendation on Key Competences as a competence that “refers to the capacity to act upon opportunities and ideas, and to transform them into values for others”.

In 2016, the Entrepreneurship Key Competence Framework (EntreComp) conceptualized entrepreneurship competence in three intertwined competence areas (“Spotting opportunities”, “Resources”, “Into Action”), including 15 smaller competences.

Activity 2.3.1: Support MoESCS in developing a concept note on innovative learning practices in VET in the context of the lifelong entrepreneurial learning strategy:

The MoESCS has established a working group to prepare the Life-long Entrepreneurial Learning (LLEL) Action Plan, and the project is already participating in the working group. Related to this, the MoESCS has asked the project ton prepare a concept note on innovative learning practices in VET, identifying international good practices and recommending those that might usefully be adapted to the Georgian situation, for example by strengthening and improving the use of FabLabs in VET colleges.

Activity 2.3.2: In cooperation with TPDC, design and pilot an in-service training programme for upper secondary teachers on entrepreneurship key competence development within the National Curriculum, based on the relevant EU key competence framework and experience:

Analysis recently undertaken through the EU PAR Programme has shown that efforts to integrate entrepreneurship and other key competences, including digital competence, into the National Curriculum have been limited because of a lack of capacity on the part of teachers to deliver them. (This relates to a general lack of entrepreneurial experience among teachers as well as the fact that entrepreneurial learning has not hitherto been widely taught in higher education courses or teacher training programmes).

Thus, in order to ensure that entrepreneurship key competences are delivered, systematic training of teachers within in-service teacher development programmes should place a high priority on training teachers to deliver entrepreneurship key competence effectively.

Although the activity is mainly focused on entrepreneurship key competence development, there are also references in the ToR  to digital key competence, and the ETF has suggested that this might be addressed though a jointly organised workshop focused on fostering awareness among education and training providers of the EU’s “SELFIE” customizable tool, designed to help schools assess where they stand with learning in the digital age.

In our Inception Phase discussions with TPDC, a two-stage approach to training secondary teachers was suggested, based on a basic or introductory module followed by a more advanced one. The General Education Department had suggested piloting the training with teachers from pilot schools for the so-called “new school model” although a reaction from TPDC was that this could be expecting too much from schools that already have a heavy change-oriented agenda. In any case, care will be taken to ensure the participation of teachers from targeted regions.

The TA should not involve the mass training of teachers, but rather the field testing of the training package that will have been developed. The pilot should involve delivery of the training to at least two groups of teachers, followed by an evaluation of the package and the making of any necessary changes, prior to hand-over to the beneficiary.

Activity 2.3.3: In cooperation with TPDC, design and pilot an in-service training programme for VET teachers and managers on entrepreneurship key competence development in VET programmes, based on the relevant EU key competence framework and experience:

Modular framework VET programmes already include an entrepreneurship module which is taught in all authorised VET programmes.

A training module for teachers delivering entrepreneurship learning in VET programmes was developed by TPDC in conjunction with the EUVEGE project and the ETF, and 185 teachers have already been trained according to the module. However, this is seen only as an introduction to teaching the subject, and TPDC would like to follow it with more advanced training, including embedding entrepreneurship into subject-based teaching in VET, e.g. on a sector basis.  The advanced module should be at the 5th level of the EU EntreComp framework, and teachers trained at this level should also be assisted in developing entrepreneurship competences within programmes targeting different sectors. The following diagram illustrates this approach:

Teaching entrepreneurship as a key competence requires embedding entrepreneurial thinking within modules throughout the VET curriculum. In any case, VET students also have to be prepared for the possibility of self-employment in case they do not succeed in obtaining employment in their chosen field. Because of the need for entrepreneurship key competence learning to be more firmly embedded in the VET curriculum, the work may require the involvement of NCEQE as well as TPDC. The training should aim to provide teachers with appropriate tools and approaches to develop and implement entrepreneurship learning activities within the modules that they are teaching. It should aim to create awareness of international, and especially EU, good practices.

The training should be piloted with teachers from different occupational sectors, and pilot training sessions should aim to involves teachers from all public VET colleges as well as some private colleges. The training should be piloted at least twice with different groups of teachers.

Activity 2.3.4: Prepare guidance materials for teachers on new learning methods and approaches to enhance entrepreneurship key competence development:

This activity is linked with the training programme. The entrepreneurship key competence development materials developed should be used in training teachers, and should also provide a resource pack to be used by teachers in delivering entrepreneurship key competence learning within their teaching programmes.

In their comments on a draft of this report, TPDC stressed the desirability of creating the guides before commencement of training, to provide source material for educators.

TPDC also has suggested that the guides should include the content related to the 5th level of the EntreComp framework and teacher’s competence, sustainable development during vocational teaching etc. The materials may include case studies, video and interactive materials developed with participating providers, as well as ideas for group and individual learning activities which may include games and simulations including learning companies, assignments and projects involving community- and internet-based fact-finding etc. The materials should include examples of how entrepreneurial thinking can be developed within the context of normal teaching activities, whether in mathematics, science subjects or the arts.

Activity 2.3.5: Pilot entrepreneurial experience for students from at least 10 general secondary education schools and VET colleges, and develop a model for replication in the education system:

This activity relates to 2.3.4, and will include assignments, games and simulations developed and organised by teachers and providers including those targeted in the pilot training, with support and assistance provided by the project.

The pilot should involve teachers and schools involved in the teacher training programmes for general education and VET teachers (including institutions and teachers from the targeted regions) and should include use of the learning materials developed in the previous activity. Schools, colleges, subject areas and sectors should be agreed with TPDC. The ToR requires piloting in a total of 10 educational institutions, which we have assumed to be 5 schools and 5 colleges, which will provide a sufficient range of comparative experience from which to draw informed conclusions.

The activity should be implemented during the normal delivery of programmes in the institutions concerned, and should be monitored in order to evaluate the effectiveness of the approaches proposed and the exemplars and materials developed. It may include a simulation involving trading between groups of students in different institutions. If possible, there should be some inter-action between the general and vocational education institutions involved in the pilot.

The experience of the piloting should be reflected in the proposed model, which should be supported by detailed guidelines for users, in order to support replication, and the results should be presented at a stakeholder workshop and widely disseminated to schools and colleges though means possibly including video material.

Activity 2.3.5: Review the quality and availability of entrepreneurship learning provision in universities/ higher education institutions based on a sample survey, using e.g. online/self-assessment, interviews, focus groups

It is thought that, despite various Government-led initiatives, most of the public universities are still not providing courses that seriously address the need for entrepreneurship learning and, as a result of the lack of an entrepreneurial culture, are generally not pro-active in the field, apart from mission statements and some international collaboration projects. Currently available entrepreneurship learning provision at higher education level is almost entirely based on the business studies degree courses offered by a number of private universities. Entrepreneurship key competence development integrated into mainstream higher education provision is thought to be almost non-existent.

These impressions will be tested through a survey of public and private universities (60-70 potential respondents) designed and implemented by the project (on-line questionnaire supplemented where necessary by email/phone questioning), which may be supplemented by more detailed consultation with relevant stakeholders, e.g. GITA, and experts. The conclusions of the survey report will lead to the formulation of recommendations which will be presented to the Higher Education Department of the MoESCS and disseminated to universities through means including a workshop at which the results and recommendations will be presented.

Activity 2.3.6: Develop at least 2 case studies (pilots) to enhance entrepreneurship learning in universities to identify good practices that work in the Georgian context, and disseminate results to the higher education community

Based on the findings of the survey and the related recommendations, two contrasting good practice case studies will be proposed in cooperation with Georgian universities prepared either to participate within the context of an existing pilot project (i.e. building on an already on-going initiatives) or to develop a new initiative on a voluntary basis. Setting this up could be facilitated by MoESCS or GITA.

We should aim at working with at least one public university such as Tbilisi State University (or the Ilia State University which already has a record of innovation in the field), and the other case study might be drawn from one of the private universities, and may include activities focused on using FabLabs and other innovation and technology-based mechanisms as well as adaptation of mainstream degree programmes to include commercialization and business-related content.

We propose disseminating the results and experiences through a second workshop organized on completion of the task, to which representatives of all universities should be invited.

Output 2.3: Deliverables and Inputs

| Output 2.3 |  |  |  |
| --- | --- | --- | --- |
| Activities | Deliverables | Inputs (WD) |  |
| 2.3.1 | Concept paper on innovative learning practices in the context of LLEL | TL: KE2: KE3: LT JNKE: ST JNKE SNKE: | 70 0 0 50 80 100 |
| 2.3.2 | In-service training module on entrepreneurship key competence development for general education teachers |  |  |
| 2.3.3 | In-service training module on entrepreneurship key competence development for VET teachers |  |  |
| 2..3.4 | Report on piloting of entrepreneurship key competence development in schools/colleges |  |  |
|  | Developed model, proposed for replication |  |  |
| 2.3.5 | Report on entrepreneurial learning in universities, with recommendations |  |  |
|  | Workshop report |  |  |
| 2.3.6 | Two case studies of entrepreneurship learning good practices in higher education documented |  |  |
|  | Workshop report |  |  |

## Component 3 – Youth

### Background information

Information about the establishment of the Youth Agency (in August 2019) is provided in our analysis of project beneficiaries above. During the Inception Phase, we had two meetings with management representatives of the Agency, as well as interacting with Agency representatives in other circumstances and, as a result of our fact-finding consultations and related discussion, we have re-formulated the Outputs and activities in this Component.

The original ToR provided for capacity building support to the former (then functioning) MoESCS Youth Department, but, now that the department has been replaced by a new agency with an expanded remit, it is clear that the emphasis paid to institutional and human capacity building must be considerably more than that implied in the ToR, which was focused on training staff to improve specified youth services.

We understand that the Agency expects to be provided with more wide-ranging support in order to become fully effective in planning and leading implementation of youth services throughout the country. However, we have noted that because the Agency was established by amendment to existing legislation providing for the previous Youth Fund, a clearly defined legal basis for the range of youth services to be provided is lacking. We have concluded that a clearly defined Action Plan should be put in place to cover the activities of the Youth Agency in the coming period (based on a bottom-up approach), and the need for a strengthened legislative and budgetary basis for the operations of the Agency should be addressed.

In addition, the Youth Centres around the country which are mainly attached to local municipalities, have very little funding or resources. Although the Agency has limited financial resources, there is a need to up-grade and standardize their services, and the Centres themselves will require considerable capacity building, going far beyond the “improved coordination and collaboration” foreseen in the ToR. Moreover, the Agency is concerned to ensure that Youth Workers employed by the Centres have the necessary professional skills and qualifications to effectively deliver improved youth services and implement appropriate youth activation measures.

The fact that other players are involved in the provision of education, training, guidance and entrepreneurship development activities with young people and adults below the age of 29 means that inter-agency cooperation will also be very important, including with MoESCS, MoIDPLHSA, the SESA, GITA etc.

In the light of the above, we have proposed that the new Output 3.1 should focus on developing the institutional and human capacities of the Youth Agency itself, and that the new Output 3.2 should focus on developing the institutional capacities of Youth Centres and the human capacities of youth workers. In both cases, there is a need to focus on the range of youth services that they need to provide, thus providing the indicative content for capacity building training and other measures that will be developed and implemented.  Implementation support to the various youth services and measures specified in the ToR is now bundled within both Outputs.

It should also be noted that there are important links with activities carried out in other components, and that there is a need to take care to ensure that there is synergy with parallel activities undertaken in other parts of the project. For example, the youth services include:

- Career guidance, which is also supported in Education (general, vocational and higher education institutions) through activities in Component 2 and as part of Employment Services in Component4;

- Youth and social entrepreneurship measures, which potentially relate to entrepreneurship key competence development highlighted in Component 2;

- Implementation of non-formal training courses, which clearly have a parallel in the new and more flexible forms of provision intended to increase access for young people and adults through Component 2, as well as the short re-training courses provided as active employment measures (in the future by the SESA);

- A range of youth activation measures (for unemployed youth) which potentially relate to active employment measures (also to be provided by the SESA).

### Component 3 implementation

The following table sets out our provisional estimation of the formal training (as opposed to on-the-job training or coaching) that will be provided through this Component:

| C3 | Workshops/Training | Target group | Breakdown of Workshops/Training events |  |  |  | Participants |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Duration of each event | No. of Events in Tbilisi | No. of Events in regions | Total days | In Tbilisi | In regions | Total Person days |
| 3.1.2 | Training for YA staff (incl. action planning & org. devt., CG, non-formal courses, entrepreneurship) - 2020 - 2021 - 2022 | Key YA staff (TBC) | 1 1 1 | 5 2 2 | 0 0 0 | 5 2 2 | 20 x 5 20 x 2 20 x 2 | 0 0 0 | 100 40 40 |
| 3.2.2 | Training for Youth Centre staff - CG - NF course dev. - Entrepreneurship | YC Managers/ youth workers | 2 2 2 | 1 1 1 | 1 1 1 | 4 4 4 | 20 20 20 | 20 20 20 | 80 80 80 |
| Total |  |  |  |  |  | 21 |  |  | 420 |

Output 3.1: Enhanced capacity of Youth Agency to develop and deliver effective youth services

Activity 3.1.1: Assist the Youth Agency in organizational development, national youth law drafting, national strategy and action planning, for improvement and delivery of youth services in the regions

As a newly established entity, the Youth Agency will require considerable assistance in its first year or two of operations in order to develop the necessary institutional capacity to carry out its full range of functions.

As mentioned under Component 1 above, assistance to the Georgian Parliament in development of the youth policy concept is being provided by a group of UN agencies. However, the Youth Agency needs to be supported in drafting the National Youth Law; development of national cross-sectoral youth strategy 2020-2025 and its action plan for 2020-2023 for improving Youth services and delivering them across the country (Tbilisi and other targeted regions).

In providing and supporting a range of dedicated youth service across the country, the Youth Agency will also need to establish a high level of inter-institutional cooperation with other agencies and institutions. At governmental level, these will especially include SESA, the MoESCS (VET and general education departments) and municipalities. However, the cooperation should also extend to non-governmental players, including NGOs, community organisations, private employment agencies and employers.

Strategy development and Action planning support will be advisory in nature and will involve project expert(s) in working with counterparts in the Agency to provide required and requested assistance. The assistance will be provided most intensively in the early part of the project, and especially during the preparation of detailed implementation plans for youth services delivery, but will continue on an on-going basis throughout the project.

Activity 3.1.2: Assess capacity building and support needs of Youth Agency staff and design and deliver a training plan and coaching scheme, covering such issues as:

- Strategic and action planning capacity, and organizational development

- Professional orientation and career guidance for youth delivered by youth (information) workers

- Development of non-formal education and training courses for youth

- Social entrepreneurship, youth transition/first job experiences

- Exchanges of experience and good practice on youth policy and service delivery with European peers

At the start of the implementation of TA to the Youth Agency, we will carry out an analysis of the capacity building needs of its staff through a structured interview-based approach, which will lead to the preparation of a training and development plan (i.e. group training where development needs are other than individual, and coaching for individuals to support them in carrying out specific functions. The plan will be submitted to the senior management of the agency for approval.

The issues to be covered may include those listed above, which are based on the range of services specified in the project ToR, although these may be amended in the light of the capacity building needs analysis.

Activity 3.1.3: Organize a study visit to EU member state(s) to observe best practices in the field of youth policy and youth services delivery, including:

- Agreement on destination, institutions to be visited and participants

- In consultation with destination institutions, prepare and agree a programme for the study visit

- Provide logistical support to implementation of the study visit

- Support or facilitate the meetings with representatives of the targeted institutions to ensure that they serve the required purpose and derive maximum benefits for participants

- Facilitate debrief of participants, support preparation of report and arrange workshop to share and disseminate the gathered information and conclusions

To develop the capacity of the SESA staff it will prove useful to enable them to witness in person key concepts and methodology applied in practice abroad. Therefore, the TA in cooperation with the beneficiary will decide on suitable EU member states to be visited. Organised efficiently study visits are excellent tools for learning and turning knowledge into practice. They also allow for establishing networks and relationships that may develop into future sustainable partnerships. The following tasks have to be carried out for a successful implementation of such a visit tour.

- Agreement on destination, institutions to be visited and participants

- In consultation with destination institutions, prepare and agree a programme for the study visit

- Provide logistical support to implementation of the study visit

- Hold an orientation workshop with participants of the study visit

- Support or facilitate the meetings with representatives of the targeted institutions to ensure that they serve the required purpose and derive maximum benefits for participants

Consortium partners are especially well-placed to support visits to Germany, France or Latvia, but we will be guided by the opinions of the Youth Agency as to the most appropriate destination. In this connection, we would recommend visiting a country of equivalent size to Georgia and with some common problems and issues. Other Baltic States including Estonia may also be considered, as well as countries of Southern Europe. It may well be that, through introduction to, and participation in, European Youth networks, other potential destination countries may be identified, and the study visit may provide an opportunity to develop and cement relationships in a way that will support long-term peer-to-peer networking.

Upon completion of the study visit and return to Georgia, the project team will facilitate debriefing and evaluation meetings with the participants of the visit. It will support the preparation of a report to ensure all the parties concerned agree on the necessary follow-up actions. The report will highlight good practice examples collected.

Activity 3.1.4: Support the Youth Agency in Improving coordination and cooperation arrangements with other agencies and stakeholders including local government and organizations in the regions

As a new national agency, the Youth Agency needs to develop close and effective working relationships with regional stakeholders, including the Municipalities, regional offices of the SESA, schools, colleges and universities, NGOs (such as IOM, UNICEF, UN Women, etc.), sector associations and local units of business organisations, together with other actors concerned with youth issues, including NEETs. This will provide a means of disseminating and cascading information, as well as providing important sources of data about the situation pertaining in different parts of the country.

As the project has a regional dimension, we will identify relevant organisations and regional stakeholders in the targeted regions, and shall support the Agency in networking and developing structured activities with them that help to support and sustain local Youth Centres.

Activity 3.1.5: Review current youth activation services delivery and support the Agency in revising/updating, implementing and monitoring youth activation measures across the regions in cooperation with relevant stakeholders

This activity will be based on a situational analysis of current provision and an assessment of the extent to which it reflects the Youth Agency’s vision for the long-term measures to be put in place and the capacity of the system to deliver them. This overall assessment will inform the approach to be adopted to development of individual parts of the package of services and measures (such as work experience, summer jobs, volunteering etc.) to be applied, and the report will include appropriate action-oriented recommendations for service delivery improvement.

Activity 3.1.6: Review career orientation and guidance services provision for youth across the regions, and support the Agency in revising/developing and piloting more effective services, with guidance materials for planning, implementing, monitoring and evaluating provision

As noted in various other places in this report, career orientation and guidance is a common theme in Components 2, 3 and 4, and this activity should be carried out in a way that providers synergy and respects that need for as holistic approach to career guidance delivery as possible across the worlds of education, youth work and employment. Career guidance will be one of the important responsibilities of Youth Centres, and will be aimed mainly at young people who are outside the education system (i.e. out of the coverage of CEG provision of education and training providers) and not registered as job seekers (i.e. not targeted by the regional offices of the SESA). Many, if not most, of those concerned are likely to be NEETs and they will also include young people from socially excluded communities.

The purpose of the guidance is not only to help with job finding, but is to help young people to decide what to do with their lives, form long-term ambitions and access services such as education and training that will help them on their way. This may involve confidence building, self-reflection, skills development (including job hunting, communication and self-employment skills) and advice on how to overcome obstacles and barriers including those created by a lack of financial resources or poverty.

The activity will therefore focus on developing policies and plans that can be put in place by local youth centres together with practical toolkits and guidance materials that youth workers can use in the provision of guidance services. It will also include a plan for monitoring service delivery and identifying areas for improvement, including self-assessment by youth centres, and a reporting mechanism to the youth agency that can be used to support overall monitoring and evaluation of service delivery across all regions.

Activity 3.1.7: Review non-formal education and training provision for youth, and support the Youth Agency in developing high quality training courses targeting employability/social needs and improving access, supported by manuals and materials for planning, delivering and monitoring/evaluating training provision

Delivery of training by Youth Centres is an important service to young people, and includes some vocational skills development as well as training focused more generally on developing life skills and civic values, and drawing on the key competences concept.

Such training should be developed to meet specific needs of individuals and groups, and should especially addressed the needs of young people from disadvantaged backgrounds.

As earlier mentioned in this report, other components of the project (specifically Components 2 and 4) include support to the development of short skills development training courses for youth and adults and, as with guidance services above, care should be taken to ensure that there is much synergy as possible between the different components. The assistance should include providing the Youth Agency and Youth Centres with:

- TNA model to be used in identifying and analysing the training needs of young people;

- A methodology for developing short training courses based on defined objectives;

- Guidance on course delivery;

- A tool for evaluating the results of training provided.

Where necessary, the courses should draw upon and adapt as necessary already available short courses developed through the other components.

Activity 3.1.8: Review social entrepreneurship measures for youth and support the Youth Agency in developing and piloting innovative approaches to youth entrepreneurship

Social entrepreneurship initiatives for youth provide an important means of developing entrepreneurial culture among young people, and are seen as an important element of the youth services to be provided in Georgia. Promoting youth entrepreneurship is an objective of the Europe 2020 strategy, and its Youth on the Move flagship initiative, and Employment and Entrepreneurship are one of the eight fields of action promoted by the EU Youth StrategyDeutsch (de) English (en) español (es) français (fr) italiano (it).

As already noted, entrepreneurship is one of the key competences in the European Reference Framework on Key Competencies for Lifelong Learning. Youth entrepreneurship initiatives, including both economic and social  objectives, provide an important means of fostering an entrepreneurship culture among young people and developing entrepreneurial ideas and skills.

The review will assess the current state of progress, looking at already introduced or completed projects and will identify factors that seem to be important to ensure the effectiveness and success of youth entrepreneurship measures, drawing also on approaches emerging from the LLEL action plan development of the MoESCS and experience from GITA and other institutions implementing projects and initiatives in the field. The conclusions will be supplemented by development of good practice guidelines, that may be piloted in projects implemented by the Youth Agency and selected Youth Centres in targeted regions.

Activity 3.1.9:  Assist the Youth Agency and youth centres in selected regions to increase public awareness of youth services including youth activation measures and social entrepreneurship (linked with Output 1.3)

As a new institution, the Youth Agency urgently needs to create high visibility to its identity in order to get its message across, create public awareness of its role and responsibilities and promote its mission to improve and provide a comprehensive range of youth services across Georgia. This should be coupled with localised campaigns to promote youth services to targeted groups, together with related measures.

Within this activity, assistance will be provided to development of visibility, information and promotional materials, and to the planning of localised campaigns in targeted regions. However, the activity will be implemented within the overall communications and visibility framework provided through Output 1.3.

Output 3.1: Deliverables and Inputs

| Output 3.1 |  |  |  |
| --- | --- | --- | --- |
| Activities | Deliverables | Inputs (WD) |  |
| 3.1.1 | Youth Services Action Plan | TL: KE2: KE3: LT JNKE: ST JNKE SNKE: | 141 30 0 108 60 100 |
|  | Inputs to the Draft Law on Youth |  |  |
|  | Inputs to the National cross-sectoral youth strategy 2020-2025 and its action plan for 2020-2023 |  |  |
| 3.1.2 | Youth Agency Capacity Building Plan |  |  |
| 3.1.3 | Study Visit Programme and Report |  |  |
| 3.1.4 | List of regional stakeholders |  |  |
| 3.1.5 | Review of current youth services provision, incl. youth activation measures, with recommendations |  |  |
| 3.1.6 | Toolkits and guidance for Youth Centres to support delivery and monitoring of career guidance provision |  |  |
| 3.1.7 | TNA model |  |  |
|  | Guidance on developing, delivering and monitoring short courses for youth |  |  |
| 3.1.8 | Youth entrepreneurship guidelines |  |  |
| 3.1.9 | Information and promotional materials |  |  |
|  | Localised campaigns |  |  |

Output 3.2: Improved organizational and human capacities to deliver youth services at local level

Activity 3.2.1: Assess the organizational capacities of selected youth services providers in targeted regions, and support preparation of institutional development/improvement plans to help them in action planning, self-assessment, and increasing the effectiveness of youth services delivery

The starting point for this activity will be an analysis of the capacities of a number of youth service providers including municipal youth centres in different regions, selected in conjunction with the Youth Agency, in order to identify “typical” capacity building needs. Relatively little is known about the current youth centre situation across the country, including the number of functioning youth centres or the scope of their present activities, apart from the fact that they mostly occupy rooms in municipality premises and carry out specific tasks (e.g. hobby or sport-related). Indeed, a Youth Centre concept needs to be more precisely elaborated, taking into account the conclusions of this analysis.

The primary means of data gathering should be the use of a self-assessment questionnaire completed by representatives of each of the centres sampled but, to validate the results, the capacity assessment should also include some on-site visits and structured interviews focused on identifying strengths, weaknesses, opportunities and threats (i.e. SWOT analysis).

The conclusions of the analysis will be fed into development of a template for preparing development and improvement plans for all centres based on a self-assessment process. The Youth Agency will be assisted in developing and applying an approach to monitoring and supporting implementation of the resulting plans.

The focus of the capacity assessment will include analysis of their capacities in the areas of:

- Piloting and implementing career orientation and guidance services provision for young people outside formal education and training, with an emphasis on vulnerable youth and NEETs

- Developing and delivering relevant and high quality short non-formal education and training courses targeted on the needs of young people in their regions, including key competences to support employability and social integration

- Piloting and implementing youth activation measures in cooperation with relevant stakeholders, including piloting/implementing youth transition measures, including social entrepreneurship

Any identified shortcomings in these areas should be addressed in the development and improvement plans of youth centres and supported through the training of youth workers employed by the centres under Activity 3.2.2 below.

Activity 3.2.2: Capacity building and training needs of youth workers (from youth services providers in the regions) assessed, and appropriate arrangements put in place to ensure their training, qualifications and professionalization

Youth workers are thought to come from many different backgrounds and to have become involved in youth work in different ways, e.g. through sport, artistic or cultural activities, family contacts, voluntary work etc. For several years there have been demands to professionalise the occupation, for example through developing a route to qualification through VNFIL. However, a qualification in youth work is still lacking and there is still no standard training programme for youth workers. It is unlikely that many of them have qualifications in social work because of the limited number of qualified social workers in Georgia. In any case, it is normal in other countries for youth work to be regarded as a separate profession, despite the fact that some of the required competences are common to both areas of work. Given that many of them work with children as well as young adults, the lack of a qualified youth worker cohort is a matter of considerable concern. This activity will therefore include:

- A review of the profiles and backgrounds of a sample of youth workers from different regions, and training needs analysis of a “typical” group of youth workers

- A review of typical training and qualifications arrangements for youth workers in the EU

- Definition of occupational standards for youth workers, development of a modular training/qualification programme, identification of appropriate training provider(s), and support to authorization processes

- Development/piloting of procedures for validating prior/non-formal learning of existing youth workers as a step towards qualification

The activity will be carried out in close cooperation with representatives of the Youth Agency, and should also include consultation with a sample of Youth Centre managers. It should also be carried out in cooperation with appropriate VET provider(s) or higher education institution(s) which should be actively involved in developing the learning programme/curriculum, so that the provider/programme may be authorised by NCEQE.

The aim will be to develop a youth worker qualification based on occupational standards reflecting the role and responsibilities of youth workers delivered through a programme provided by authorised VET provider(s). The qualification should be accessible to existing youth workers, with credits obtainable though VNFIL procedures. The outputs of any on-the-job training provided through TA projects etc. should be recognised in the VNFIL process.

Output 3.2: Deliverables and Inputs

| Output 3.2 |  |  |  |
| --- | --- | --- | --- |
| Activities | Deliverables | Inputs (WD) |  |
| 3.2.1 | Capacity assessment report of youth services providers in selected regions | TL: KE2: KE3: LT JNKE: ST JNKE SNKE: | 65 10 0 50 20 100 |
|  | Improvement/development plans of targeted youth services providers |  |  |
| 3.2.2 | Review of existing youth worker profiles |  |  |
|  | Occupational standards for youth workers |  |  |
|  | Authorised training programme in youth work incl. provision for VNFIL credits |  |  |

## Component 4 – Employment Services

### Background information

Statistical overview of LM data

Relevant statistical data on the Georgian labour market come primarily from the National Statistics Office of Georgia (GEOSTAT). The quarterly conducted Labour Force Surveys (LFS) of GEOSTAT are based on a sample of 6,000 households which can be regarded as representative for the entire country, but presumably do not deliver reliable data at the district level. The Labour Market Information System (LMIS) provided by the Ministry of Economy and Sustainable Development (MoESD) obtains its basic data from GEOSTAT. As the MoESD runs no database of its own, it focuses on available data as provided by GEOSTAT, the National Central Bank, WorkNet, and other relevant institutions.

Georgia, Labour Market Data 2012 - 2019

|  | 2012 | 2015 |  | 2016 | 2017 | 2018 | 2019 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Total population, 1,000 persons | 3,739.3 | 3,721.9 |  | 3,728.6 | 3,726.4 | 3,729.6 | 3,723.5 |
| Population > 15, 1,000 persons | 3,057.3 | 3,019.1 |  | 3,009.4 | 3,012.3 | 3,034.3 | 3,031.9 |
| Labour force, 1,000 persons | 2,004.5 | 2,018.0 |  | 1,996.2 | 1,983.1 | 1,939.9 | 1,911.2 |
| Labour force, 1000 persons (m) | 1,068.3 | 1,078.6 |  | 1,083.0 | 1,046.3 | 1,035.3 | n/a |
| Labour force, 1,000 persons (f) | 936.2 | 939.4 |  | 913.3 | 936.7 | 904.6 | n/a |
| Employed, 1,000 persons | 1,659.4 | 1,733.8 |  | 1,717.3 | 1,706.6 | 1,694.2 | 1,690.2 |
| Employed, 1,000 persons (m) | 874.4 | 910.8 |  | 903.1 | 889.3 | 891.1 | n/a |
| Employed, 1,000 persons (f) | 785.1 | 823.0 |  | 814.1 | 817.4 | 803.1 | n/a |
| Unemployed, 1,000 persons | 345.1 | 284.2 |  | 278.9 | 276.4 | 245.7 | 221.0 |
| Unemployed, 1,000 persons (m) | 193.9 | 167.8 |  | 179.8 | 157.1 | 144.1 | n/a |
| Unemployed, 1,000 persons (f) | 151.1 | 116.3 |  | 99.1 | 119.3 | 101.6 | n/a |
| Rates |  |  |  |  |  |  |  |
| Participation rate (%)1 | 65.6 | 66.8 |  | 66.3 | 65.8 | 63.9 | 63.0 |
| Participation rate, m (%) | 77.3 | 77.2 |  | 77.4 | 74.6 | 73.6 | n/a |
| Participation rate, f (%) | 55.9 | 57.9 |  | 56.7 | 58.2 | 55.6 | n/a |
| Employment rate (%)2 | 54.2 | 57.4 |  | 57.1 | 56.7 | 55.8 | 55.8 |
| Employment rate, m (%) | 63.3 | 65.2 |  | 64.5 | 63.4 | 63.4 | n/a |
| Employment rate, f (%) | 46.9 | 50.8 |  | 50.6 | 50.8 | 49.3 | n/a |
| Unemployment rate (%)3 | 17.2 | 14.1 |  | 14.0 | 13.9 | 12.7 | 11.6 |
| Unemployment rate, m (%) | 18.2 | 15.6 |  | 16.6 | 15.0 | 13.9 | 12.8 |
| Unemployment rate, f (%) | 16.1 | 12.4 |  | 10.9 | 12.7 | 11.2 | 10.1 |

1 Labour force / Population >15, 2 Employed / Population >15, 3 Unemployed / Employed, n/a: not (yet) available
Sources: GEOSTAT, LMIS. Gender specific data for 2019 from GEOSTAT spreadsheets are not exactly consistent with the aggregate data presented on its website; respective data of the LMIS end with 2018.

During the period from 2012 to 2019 the population has been relatively stable, decreasing by 0.4 percentage points, whereas the labour force decreased by 4.7 percent. Despite this, the number of employed persons increased by 1.9 percent, corresponding to a 1.6 percentage points increase in the employment rate. At the same time the number of unemployed persons decreased by 36 percent leading to a decrease in the unemployment rate by 5.6 percentage points.

Employment Policy Background

The policy background in the field of labour and employment still being developed and needs completion. Currently there is a National Labour and Employment Policy Strategy and an Action Plan available as well as a Labour Code, and an Employment Law is being drafted.

- National Strategy for the Labour and Employment Policy: A Strategy for the years 2019 - 2023 was prepared by the MoIDPHLSA with some support from the ILO. It is complemented by an Action Plan for the years 2019 - 2021. The Strategy was approved by government on 30 December 2019 and is currently being translated into English.

- Labour Code: The Labour Code is currently under consideration as substantial amendments are regarded as necessary. The draft of September 2019 which was made available to the project proposes several amendments which refer to strengthening the rights of employees regarding discrimination, association rights, health conditions, professional development, parental leaves and maternity as well as the termination of labour contracts. The ILO project Improved compliance with labour laws in Georgia is providing advice on these topics. The EU Twinning project Occupational Safety and Health Legislation advises in this context on issues related to the EU acquis.

- Employment Law: The Ministry is expecting submitting the draft Employment Law to the Parliament for spring session 2020. The TA has access only to an English draft of December 2018. The purpose of the Law is to regulate the activities of institutions in the labour market with the purpose of increasing employment, combatting and preventing long-term unemployment. It also stipulates the rights and obligations of the unemployed persons and employers, and other matters relevant to employment and provides for Active Labour Market Policy measures. The draft law stipulates a national public employment service as well as regional public employment services and proposes regulations for labour market statistics. Moreover, the draft contains relevant definitions of the participants in the labour market relevant for policy making, especially unemployed persons, job-seekers and disadvantaged groups.

Establishment of the Employment Services Agency

As described earlier in this report, the State Employment Support Agency (SESA) is replacing the ESS Department within the SSA as an independent body taking over all its functions. Legal foundation is the Government Resolution № 487 of 10.10.2019 and the Order № 01-110/N by the Minister of MoIDPHLSA.

The process of setting up the Agency is under way: Head of the Agency is the Deputy Minister in charge of the Labour and Employment Department in the Ministry, the Deputy Head has been appointed in January 2020. In accordance with Article 5 of Order № 01-110/N staffing and final structure need to be approved by the Head of the Agency. The planned structure of the SESA is as follows:

Tbilisi City Centre with 5 district service centres in

- Vake-Saburtalo

- Didube-Chugureti

- Gldani-Nadzaladevi

- Isani-Samgori

- Old Tbilisi

9 Regional Centres in

- Imereti (Kutaisi)

- Samegrelo-Zemo Svaneti (Zugdidi)

- Kakheti (Telavi)

- Shida Kartli (Gori)

- Kvemo Kartli (Rustavi)

- Guria (Ozurgeti)

- Samtskhe-Javakheti (Akhaltsikhe)

- Mtskheta Mtianeti (Mtskheta)

- Racha-Lechkhumi, Kvemo Svaneti (Ambrolauri)

Branch of Adjara (Batumi)

The SESA branch office of Adjara is planned to be established in parallel with the already existing Employment Agency of Adjara.

The process of transition is still under way and currently staff is being hired. As of February 2020, the total planned number of staff is 102, thereof 51 civil servants as back office staff and 51 contracted persons. Until now the Director and Deputy Director have been appointed; 34 open positions for contracted employees and 38 for civil servants are expected to be filled during February 2020.

LEPL State Employment Support Agency – Staffing

|  | Planned positions of civil servants | Number | Open |
| --- | --- | --- | --- |
|  | Leadership | 3 | 3 |
| I | Administrative Service | 17 | 10 |
|  | Office of Monitoring, Statistics and Analytics | 7 | 5 |
|  | Financial and Administrative Services | 10 | 5 |
| II | Employment Promotion Department | 17 | 11 |
|  | Employment Programmes Division | 7 | 5 |
|  | Division of job seekers and employers searching and registration | 9 | 5 |
| III | Department of Labor Migration | 14 | 14 |
|  | Division of Labor Migration | 10 | 10 |
|  | Division of International Vacancies | 3 | 3 |
|  | Subtotal | 51 | 38 |
|  | Planned positions of employees under contract | Number | Open |
| 1 | Tbilisi City Centre (including 5 district service centres) | 14 | 8 |
| 2 | Imereti Regional Centre (Kutaisi) | 5 | 5 |
| 3 | Samegrelo-Zemo Svaneti Regional Centre (Zugdidi) | 5 | 4 |
| 4 | Kakheti Regional Centre (Telavi) | 5 | 3 |
| 5 | Shida Kartli Regional Centre (Gori) | 4 | 1 |
| 6 | Kvemo Kartli Regional Centre (Rustavi) | 5 | 5 |
| 7 | Guria Regional Centre (Ozurgeti) | 2 | 1 |
| 8 | Samtskhe-Javakheti Regional Centre (Akhaltsikhe) | 2 | 2 |
| 9 | Mtskheta Mtianeti Regional Centre (Mtskheta) | 2 | 1 |
| 10 | Racha-Lechkhumi, Kvemo Svaneti Regional Centre (Ambrolauri) | 2 | 2 |
| 11 | Branch of Adjara (Batumi) | 5 | 2 |
|  | Subtotal | 51 | 34 |
|  | Total | 102 | 72 |

The contracted positions to be filled are

- Head of Regional Centre	7 positions

- Employment Specialist	13 positions

- Supportive Employment Consultant	16 positions

- Career Guidance Specialist	15 positions

Preliminary assessments and observations with respect to project implementation

The start of the project falls in a transitional period where important political and organisational adjustments take place in the field of employment and labour market policy. The TA sees this is an opportunity for making a relevant impact in this field and contributing to a successful completion of the SRPC.

Adjusted indicator for the Sector Reform Performance Contract (SRPC): The transition to the SESA raises questions of how this indicator can be verified under the new organisational structure. This issue is of utmost relevance for compliance with the conditionalities for Budget Support. The target set for the indicator 2.1 for budget support under the SRPC requires for 2019 that the New Service Model be provided in at least 30% of the territorial units nationwide. This target was reported as met to the Interim Review Mission of the SRPC in December 2019. According to the MoIDPHLSA 21 out of 69 district offices applied the NSM under the old organisational structure.

In view of the new structure of the SESA with 15 regional offices this indicator needs to be reformulated. The project was informed that 8 of them are supposed to apply the New Service Model (NSM). It needs to be clarified how the 21 district offices of the previous ESS are related to the new structure of the SESA.

Access to SESA in remote regions: The transition from the previous structure with 69 offices at the district level to a structure with 15 offices at the regional level raises the issue of how the services previously provided by the local SSA offices will be provided countrywide at the level of smaller municipalities or in remote areas. The current planning is to offer the services on a mobile basis. It has also been agreed with the SSA that its local offices will support the Agency with the registration of jobseekers in the WorkNet. This can obviously be only a provisional solution until the WorkNet has been upgraded and the SESA works independently of the SSA.

Identification of unemployed persons among job-seekers: Currently the SSA/ESS does not differentiate between job-seekers and unemployed. Recipients of Targeted Social Assistance (TSA) are obliged to register as jobseekers in the WorkNet without any further compulsory activation steps. As any individual in Georgia who holds the status of socially vulnerable must register in the WorkNet and create a job seeker’s profile, the number registered as job-seekers increased considerably, when this rule was introduced. However, there is no way to identify how many of them are actually looking for work and count as unemployed, even more so as this rule applies also to those recipients of TSA who are not capable to work at all, e.g. due to health reasons. This is an obstacle to the development of a well targeted employment policy and ALMP measures. The TA proposes to address this issue at the beginning of the implementation phase under Outputs 4.1 and 4.2 which aim at the revision of the NSM and the improvement of ALMP measures.

It is advisable that the new agency works on this basis from its start. The draft Employment Law from December 2018 provides the necessary definitions of unemployed and job-seekers. Currently job-seekers are classified into 4 groups

- Group 1: Employed individuals who are looking for a new job

- Group 2: Unemployed, who possess certain skills and experience and are easy to employ

- Group 3: Individuals who are able to work but require additional support to improve their skills set

- Group 4: Unemployed job seekers belonging to the pool of “hard to employ” individuals, that require significant support and active involvement from the side of SSA

Technically this could be done in the WorkNet registration by adding a variable (unemployed / employed) above the current categories of job-seekers. As individuals under Group 1 are employed, this would apply to Group 3. Regarding Group 4 it has to be decided to what extent they are unemployed or clients, who need assistance from the SSA to overcome social / health problems, before mediation or participation in ALMP measures of the SESA become relevant. The planned upgrading and expansion of the WorkNet with new software would be the suitable occasion for this task. In addition to the already existing modules (employers and jobseekers) further modules (case management, analytical module, digital services for clients, etc.) will be elaborated.

### Component 4 Implementation

The TA project is building on the results of previous projects, mainly the 4-year EUVEGE project concluded in November 2017 and the EU twinning project Capacity Building of the Employment Support Services in Georgia implemented from August 2015 to January 2017. The New Employment Service Model was developed in 2015/2016 with the assistance of these projects.

The SRPC on Skills Development and Matching for Labour Market Needs includes also two twinning projects running in parallel to this project. One of them working on quality assurance of provision and qualifications with the NCEQE and the other one with the MoIDPLHSA to enhance the Georgian Occupational Safety and Health (OSH) legislation.

Activities under this Component will also be coordinated with those of other donors (ILO, UN Women, IOM, GIZ, FES) to create synergies and avoid duplication or contradictory approaches to the issues.

In view of the 4-year time frame of the project and possible new political and economic developments the following outline of planned project activities might need adjustments to upcoming new priorities. The TA will react flexibly to such changes which cannot be anticipated during the Inception Phase.

Output 4.1: State Employment Support Agency (SESA) supported in its implementation of the Revised New Service Model (NSM)

Activities under this Output will be taken up immediately at the beginning of the implementation phase since they are of utmost importance to ensure a successful start of the Agency. As just mentioned, this Output is also relevant with respect to the redefinition of indicator 2.1 of the SRPC.

Activity 4.1.1: Assess how the current system of the NSM has functioned within the different regional centres and district offices of the previous SSA/ESS, main lessons learnt and issues for improvement

The assessment of the previous functioning of the NSM is expected to entail important conclusions for its adaptation within the new SESA:

Assessment Report: To assess the functioning of the new service model (NSM), the following activities will be carried out:

- Carry out desk study of the relevant documents including those of previous projects, gather information on the current and planned structure and staffing of the ESS/SESA, on their work methodology, compile documentary and statistical analysis;

- Hold focus group meetings and structured interviews with MoIDPHLSA and ESS/SESA staff at central and regional level. If possible, representatives of local government, companies and clients will also be included;

- Carry out field visits to selected regional and local offices

The assessment report needs to answer the following questions:

- What exactly is the NSM, which documents are valid? Currently there is a number of single documents from various sources, but there doesn’t seem to exist a coherent description of the new work methodology.

- Where and to what extent/effect has the NSM been put into practice until now?

- Which problems did the implementation face? What are the obstacles for rolling out the new approach to the entire country?

The assessment will form the basis for recommendations on the further development of the new work methodology of the planned SESA.

Recommendations Report: The recommendations will draw the conclusions from the assessment of the work done so far within the ESS and will form the starting point for implementing and developing the NSM in the SESA. They should focus on the following topics that can be tackled immediately:

  - How to improve the services offered, in terms of their range as well as their quality;

  - How to ensure uniformity of availability and provision across the country;

  - How to achieve greater effectiveness and efficiency of delivery;

  - How to provide greater integration with other initiatives (education and training, youth services etc.), and performance measurement and monitoring mechanisms;

  - How to ensure access to services for specific groups (women, youth, long-term unemployed, other hard to employ persons. people in vulnerable situations).

Activity 4.1.2: Advise MoIDPHLSA on the institutional development of the State Employment Support Agency (SESA)

To set up a well-functioning SESA in compliance with the SRPC the TA will further elaborate on the topics as proposed in the Recommendations Report for improvement of the NSM and embed them into a comprehensive plan for institutional development of the SESA. To achieve this the following main tasks will be carried out:

- Define mandate, objectives, functions, strategy, organisational structure (organigram), job descriptions

- Propose a clear division of tasks between administrative functions and mediation (placement or measures) and between the tasks of Employment Specialists and Career Guidance Specialists

- Emphasize the placement function through close cooperation with the employers

- Based on the definition of functions and the local labour market calculate the needed staff size

- Elaborate a roll out plan for replication of well-functioning employment centres

- Develop a plan for Human Resource Development (HRD) and a systematic staff training programme covering all functions (in connection with Output 4.3 Capacity Building)

- Build institutional memory – reporting and filing system – management information system

Other related tasks to the institutional development will be the provision of recommendations for more effective functioning of the SESA with respect to the drafting of national policies and action plans or necessary legislative changes. The TA will also support the exchange of information and cooperation/coordination of activities with other institutions under the Ministry.

The plan for institutional and human resource development should be discussed and adopted by a series of workshops.

Activity 4.1.3: Develop detailed instructional materials for the NSM work methodology

To ensure a country wide unified approach and implementation of the NSM a practical handbook and guidelines need to be drafted for reference of all levels of the new agency. The handbook should have the character of a field manual providing clear-cut instructions on procedures, responsibilities and workflows for all different positions within the SESA free from abstract and theoretical considerations.

The handbook should further serve as the basis for procedures and guidance materials for planning, implementing, monitoring and evaluation of employment services provided (Activity 4.1.5) and for the development of curricula and training materials in the field of HRD (Activity 4.3.2).

Activity 4.1.4: Develop an implementation strategy for improving links with local employers/companies as well as local governments in the regions

To be effective employment policies need to be adjusted to the specific requirements of the region and the local level. For this purpose, the TA will discuss with the Ministry and SESA which regions or sectors are a priority for enhanced employment and labour market policy.

It will be necessary to identify possible partners from the public and private sector (social partners, NGOs) and assess their suitability and willingness to cooperate with the SESA to develop the regional/local economy and labour market.

Local Partnerships for Employment

The TA will inform SESA staff on the specific characteristics of Local Partnerships for Employment (LPE) as a tool for involving local or regional labour market stakeholders in the promotion of employment and consider with them the suitability of this approach in selected regions. As the realisation of a sustainable LPE goes beyond informal meetings with the social partners, it requires careful preparation and involvement of all potential stakeholders. The following steps will be essential:

- Define target area and target group

- Identify and mobilise relevant stakeholders in target areas

- Design methodology for LPE implementation

- Implement strategy

- Elaborate HRD strategy for target area

- Capacity building for LPEs in target areas

- Raise public awareness in target areas

- Regularly review progress

If deemed realistic, the project in close cooperation with the SESA will select one or two suitable regions and organise meetings and workshops with local stakeholders to inform on the different models for the establishment and organisation of an LPE and finally decide on the most appropriate form to be chosen. The piloting of LPE s should be combined with suitable ALMP measures (Output 4.2.).

To identify the most promising regions for replication of successful LPEs analyses prognoses of regional labour markets and should be carried out. In this context it should be ascertained to what extent sophisticated methods of forecasting local/regional labour markets can be applied.

Activity 4.1.5: Develop procedures and guidance materials for planning, implementing, monitoring and evaluation of employment services provided

To complement the handbook should define performance indicators for all functions within the SESA and be complemented by specific and concise guidelines which can serve as a quick reference tool for all SESA employees.

These guidelines should cover registration and profiling of unemployed and job-seekers as well information on their rights and duties, ways of keeping contact with employers to receive information of vacancies and skills demanded. They should also provide guidance on individual and group consulting and give basic information on career guidance and special methods for providing support for various groups of vulnerable people and persons facing particular obstacles in the job market.

Activity 4.1.6: Develop proposals for increasing public awareness of employment services

This activity is closely connected with the activities described above under Output 1.3.

The ESS lacked visibility by their clients, both employers and jobseekers. One reason is the lack of sufficient funding for systematic PR activities. Current activities to raise public awareness are:

- organising job fairs

- holding events with employers

- working with all stakeholders, NGOs, media

- conducting info tours (only twice a year as there are no additional means available for PR)

- using the WorkNet to inform by SMS on new services, job fairs, vacancies

To improve this situation the TA will elaborate a detailed proposal for raising public awareness and visibility of the SESA and its services, addressing both jobseekers and employers. It will agree with the beneficiary an implementation strategy for increasing public awareness of the SESA and its attractiveness for job-seekers and employers

The TA will make its proposals, provide guidance and pilot PR activities within the frame provided by the overall Communications and Visibility strategy and Action Plan under Output 1.3 and, thereby, ensure coherence of message and approach. This will include specific branding measures for the SESA as well as improvement of the accessibility of WorkNet to make it more user friendly and informational to both employers and jobseekers.

The public awareness activities need to be implemented with the relevant PR personnel of MoIDPHLSA and the SESA, who will have ownership over the proposal, implementation strategy, campaign and related materials and events.

- Public information and promotional materials about services

To develop and pilot measures for the use of SESA offices for vacancy reporting and recruitment of workers; to produce promotional materials on their services. These could be publications like

Leaflets containing

- short descriptions of the services and measures provided by the SESA

- instructions for jobseekers about their rights and duties

- information for employers on the support provided in filling vacancies

Target audience: general public, job seekers, employers.

Booklet on ALMP measures (catalogue)

- description of purpose, content and conditions for participation

- short descriptions of the different measures and target groups

- examples of achievements of individual participants

Target audience: key stakeholders, media, NGOs etc.

Occasional TV spots on upcoming events like job fairs could be broadcasted targeting the general public, unemployed, job-seekers, employers and other stakeholders like NGOs.

- Information campaign targeting youth, women and vulnerable groups

The elaborated information campaign needs to be further concretised to reach specific parts of the population, in particular youth (NEETs), women, long-term unemployed, and vulnerable groups like persons with disabilities, minorities or displaced persons. To achieve higher access to employment by these groups the TA will cooperate with other institutions, donors or stakeholders. This includes the Youth Agency, UN Women, IOM and NGOs active in this field.

- Procedures and guidelines for facilitating access for targeted groups

The guidelines developed under Activity 4.1.3 will be complemented by description of procedures and methods that are directed to address specific groups as outlined above and to encourage them to use the services provided by the SESA.

Output 4.1: Deliverables and Inputs

| Output 4.1 |  |  |  |
| --- | --- | --- | --- |
| Activities | Deliverables | Inputs (WD) |  |
| 4.1.1 | Assessment Report | TL: KE2: KE3: LT JNKE: ST JNKE SNKE: | 13 160 7 100 0 90 |
|  | Recommendations Report |  |  |
| 4.1.2 | Institutional Development Plan |  |  |
| 4.1.3 | Handbook on NSM methodology |  |  |
| 4.1.4 | Local employment policy strategy |  |  |
| 4.1.5 | Guidance materials |  |  |
| 4.1.6 | Public awareness strategy |  |  |

Output 4.2 SESA supported in designing and delivering more accessible, effective and comprehensive ALMP measure for all job seekers

The proposed planning of activities under this Output draws on the Assessment of SSA Employment Services and the Review of the State training-retraining program delivered by the EUVEGE project in 2017. The situation seems to be largely unchanged; nevertheless, these studies must be updated by an in-depth review of the current situation and be complemented by statistical data. On this basis the approach to ALMP measures will be revised and refined.

Activity 4.2.1: Assess how the current system of ALMP measures functions within the different regional centres and district offices of ESS/SESA, main lessons learnt and issues for improvement

The current ALMP measures carried out by ESS/SESA are made up of 2 components:

- short-term training and retraining courses and internships;

- wage subsidies for persons with disabilities (PWD) for 4 months (with a minimum of 6 month continued employment) and for youth based on a voucher system.

The TA project will follow up the critical points mentioned in the studies and assess whether or to what extent the proposed recommendations have been adopted. If this is not the case the reason for it needs to be assessed – whether the advice was not suitable or whether other obstacles prevented them from being implemented.

Regarding the Assessment of SSA Employment Services by the EUVEGE project the following topics are relevant:

- Unclear division of tasks leading to duplication of work (e.g. profiling done by employment counsellor only)

- Transition from campaign approach to continuous process of provision of employment services (e.g. organising group sessions)

- Employer contacts done by one person (e.g. employment agent)

- Clear structure of responsibilities and reporting, clear flows of information

- Employment counsellor as first entry point into the system

- Organisation of training courses as proposed in the Assessment of SSA Employment Services by the EUVEGE project

- Financing mechanism adjusted to requirements of the proposed reorganisation of training courses

The Assessment of SSA Employment Services and the Review of the State training-retraining program by the EUVEGE project points at the following topics:

- Job seekers do not undergo proper selection process.

- There is a need for better and updated information regarding the labour market needs, disaggregated at the regional level.

- Employers’ presence needs to increase in the program design.

- In order to increase training providers’ motivation, the criteria for reimbursing the vouchers should change.

- In order to avoid the confusion regarding the prices and content of the courses, SSA should provide as detailed information about the training as possible during the tender procedure.

Overall recommendation:

- shift focus from central to regional level

- include other relevant stakeholders in this process

- training courses should be organized when there are enough job seekers interested, ideally with vacant job opportunities available

The assessment of the current system of ALMP measures will follow the same standard approach as described under Activity 4.1.1. The main purpose will be to

- Carry out desk study of relevant documents to gather information on the current measures and their impact;

- Compile documentary and statistical analysis;

- Hold focus group meetings and structured interviews with MoIDPHLSA and ESS/SESA staff at central and regional level. If possible, representatives of local government, companies and clients will also be included;

- Carry out field visits to selected regional and local offices

Field visits on ALMP measures can be combined with the field visits on the assessment of NSM implementation.

Draft assessment report to answer the following questions:

- Relevance for actual labour market needs

- Effectiveness with respect to the number of participants

- Efficiency regarding the timing and cost of measures

- Impact based on tracer studies, if available

- Sustainability with respect to long-term employment of participants

The assessment will form the basis for recommendations on the further development of ALMP measures.

Activity 4.2.2: Develop a detailed proposal for the upgrade and revision of all types of ALMP measures

Based on the assessment of the current situation the TA will submit to the Ministry and SESA proposals on how to improve the current ALMP measures and propose additional measures. One relevant aspect will be to address local needs. The project experts will also consider to what extent social enterprises can be addressed especially for the employment and skills development of people in vulnerable situations (e.g. ex-prisoners, drug addicts, youth) and scrutinise whether bigger companies can be involved in ALMP measures providing internships, on-the-job training with the purpose of hiring participants after the conclusion of the measure.

Recommendations on current measures will:

- Develop a detailed proposal for revised/ redesigned retraining programmes for unemployed persons and jobseekers both in terms of content and delivery methods in order to get more effective employment results after graduation;

- Develop a detailed proposal for revised/ redesigned employment subsidies and internships for unemployed persons and jobseekers both in terms of content and delivery methods, including linkages with institutions which provide similar services.

With respect to shortcomings of the current measures and the identified needs as described in the recommendations a proposal on a comprehensive system of ALMP measures including new ones will be elaborated with the purpose of:

- Improving the employability of job seekers from different categories of vulnerable groups by developing customised training modules based on key competences, with an emphasis on basic job search, communication and information technology skills;

- Introducing a detailed proposal and pilot self-employment/ entrepreneurship programmes for unemployed persons and jobseekers both in terms of content and delivery methods; including linkages with institutions which provide similar services;

- Introducing a detailed proposal and pilot initiatives related to public works for unemployed persons and jobseekers both in terms of content and delivery methods, including linkages with institutions which provide similar services. Public Works could cover a broad category of infrastructure projects, financed and constructed by the government, for recreational, employment, and health and safety uses in the greater community. They could also include a requirement of providing a certain percentage of training jobs for unemployed job seekers.

The TA aims at developing an approach that to covers all types of ALMP measures, suitable for the needs of the local labour market. If possible, measures will be combined with pilot LEPs (see Activity 4.1.4).

The statistical registration of measures should be in line with the classification as outlined in Eurostat Labour Market Policy Statistics. (See Output 5.2.)

Activity 4.2.3: Develop procedures and guidance materials for planning, implementation, monitoring and evaluation of all types of ALMP measures

To support the upgrading and further development of ALMP measures the TA will draft a handbook and guidelines on the implementation of ALMP measures. These should be a component of the NSM handbook elaborated under Activity 4.1.3.

Activity 4.2.4: Develop a detailed proposal for revised/ redesigned career guidance/counselling for jobseekers both in terms of content and delivery methods, including linkages with institutions which provide similar services

Based on the NSM handbook which outlines the principal methods of career guidance detailed proposals for working with specific groups of clients will be developed. These proposals need to be consistent with the advice provided by public or private institutions, but also complement them where appropriate.

Activity 4.2.5: Make a proposal and organise 1-2 pilot programmes of new ALMP measures for jobseekers, to review the pilots and, based on the experience, to develop a model that can be replicated in the employment support services in the regions

To assess the suitability and practicability of the proposed new ALMP measures one or two pilot programmes covering a subset or combination of the measures will be implemented by the TA. The measures should primarily focus on unemployed persons and not just on job-seekers. The identification of suitable measures for pilot programmes will be done after the overall assessment of the current ALMPs.

To find employers involved in the pilots, a competitive call for proposals may be used. It should also be considered to develop these pilot measures in combination with the piloting of Local Employment Partnerships (see Activity 4.1.4).

These pilots will be thoroughly monitored, reviewed and adjusted to develop from them a model suitable for replication in other parts of Georgia.

Output 4.2: Deliverables and Inputs

| Output 4.2 |  |  |  |
| --- | --- | --- | --- |
| Activities | Deliverables | Inputs (WD) |  |
| 4.2.1 | Assessment report | TL: KE2: KE3: LT JNKE: ST JNKE SNKE: | 12 150 5 100 0 70 |
| 4.2.2 | Recommendations on current measures |  |  |
|  | Recommendations on new measures |  |  |
| 4.2.3 | ALMP procedures and guidance materials |  |  |
| 4.2.4 | Proposal for career guidance |  |  |
| 4.2.5 | 1 – 2 pilots of new ALMP measures |  |  |

Output 4.3: Capacity (knowledge and expertise) developed within the SESA staff to provide more effective employment services for jobseekers and employers

Capacity building constitutes a core task of the TA as it is the main instrument to contribute to the sustainability of the project outputs. Activities under this Output are linked to Activity 4.1.2 on the institutional development of the SESA. All training measures for the new SESA will be carried out in close cooperation with the MoIDPLHSA and SESA.

As the SESA will take up its duties in early 2020 an induction training for all staff is required to ensure the delivery of professional services in accordance with the NSM from the very start of the working of the new agency. The induction training will be implemented as soon as the positions of SESA are filled. It will presumably be preceded by an initial internal training of SESA staff required to make a sufficient number of staff acquainted with the NSM and thereby comply with the condition requested by indicator 2.1 of the SRPC.

Activity 4.3.1: Carry out an induction training and assess training needs of the SESA staff in the field of NSM, implementation of all types of ALMP measures, provision of career guidance and counselling services for jobseekers, and the use of upgraded LMIMS portal

To elaborate a training programme the TA will first carry out a training needs assessment (TNA) which sets the framework and a common starting point for the elaboration of a training plan and the training materials. The TNA will be conducted simultaneously with the induction training. This includes to assess the current state of training, its results and the sustainability of previous training measures, e.g. those implemented by the previous Twinning Project Capacity Building of the Employment Support Services (ESS) in Georgia.

In addition to the desk study of documents of the current training programme and collecting information (evaluations) on previous and current training measures the project will organise focus group meetings and interviews with the current trainers of the Agency and use the field visits to selected regional and local offices (see Activities 4.1.2 and 4.2.1 above) to ask about the state of training. Since previous projects have implemented training measures it will be necessary to identify which ones of the trained persons are still available for the SESA.

The results which will be recorded in a TNA report.

Activity 4.3.2: Design a training plan (short and long term) on all the issues above for the staff of SESA and other relevant institutions which includes:

a) workshops and seminars

b) individual and group trainings

c) job coaching and other tools for capacity development

d) public awareness training about the services provided

To build the capacity of the new SESA the TA will propose a plan for Human Resource Development (HRD) which contains a systematic staff training programme covering all functions of the new Agency. The HRD plan needs to be of a long-term, strategic nature, with continuous adjustments based on the performance of the Agency. The proposed training programme will be designed to

- enable the SESA staff to carry out their tasks successfully and expertly;

- increase their competence dealing with employer and different groups of unemployed and job seekers

- improve their skills in implementing, monitoring and evaluating ALMP measures

- to enable the institution to focus its activities on the specific needs of their region

Training curricula should be drafted for two levels and two stages, basic and advanced. Specialized courses need to be delivered for

- management staff to ensure professional leadership of the agency;

- employment specialists, career consultants and supportive employment consultants to ensure professional services for clients in regional/local offices.

Finally, to develop the internal training capacity of the SESA a specialised training of trainers (ToT) course will be held by the project.

The following table for a training plan for the first year is only a provisional proposal since the exact distribution of staff (civil servants, contractors) according to functions over the organisational units of the SESA is not yet available.

Provisional Plan of Training Measures

| C4 | Workshops/ Training | Target group | Breakdown of Workshops/Training events |  |  |  | Participants |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Duration of each event | No. of Events in Tbilisi | No. of Events in regions | Total days | In Tbilisi | In regions | Total Person days |
| 4.3.1 | Induction | Regional Centres (all), Empl. Promotion Dept. | 2 | 2 | 2 | 8 | 40 | 40 | 160 |
| 4.3.3 a | NSM | Regional Centres (all), Empl. Promotion Dept. | 2 | 2 | 2 | 8 | 40 | 40 | 160 |
|  | Mediation | Employment Specialists | 2 | 1 | 0 | 2 | 20 |  | 40 |
| 4.3.3 b | ALMPs | Employment Specialists | 2 | 2 | 1 | 6 | 40 | 20 | 120 |
| 4.3.3 c | CG | CG Consultants | 2 | 1 | 0 | 2 | 20 | 0 | 40 |
| 4.3.3 d | Vul. groups | Supp. Empl. Consultants | 2 | 1 | 0 | 2 | 20 | 0 | 40 |
| 4.3.3 e | Mon., Stat., Analysis | Mon., Stat., Analysis Dept. | 2 | 1 | 0 | 2 | 10 | 0 | 20 |
|  | LMIMS | Specialists | 2 | 1 | 0 | 2 | 20 | 0 | 40 |
| 4.3.3 f | Inst. Dev/ Mgt. | Managers | 2 | 1 | 0 | 2 | 20 | 0 | 40 |
| 4.3.3 g | ToT | Trainers | 2 | 1 | 0 | 2 | 10 | 0 | 20 |
| Total |  |  |  |  |  | 36 |  |  | 680 |

Activity 4.3.3: Organize training measures based on training plan

Training measures based on the agreed training plan will aim to develop all aspects of knowledge, skills and attitudes of SESA staff. They will make use of standard interactive training methods to deliver an attractive training programme and encourage trainees’ participation through the application of up-to-date interactive learning methods, such as

- Short lecture-style presentations to introduce core topics;

- Visualisation of contents making use of presentations, flip charts and prepared handouts to clarify and re-enforce key messages;

- Emphasis on ‘learning by doing’, ideally using case studies identified by the participants themselves, and the use of simulation games and role plays;

- Group work to encourage the sharing of ideas and skills between participants and to emphasize the importance of teamwork;

- Question and answer sessions to allow participants to raise issues for further explanation;

- Allowing adequate time for groups to provide feedback to the rest of the workshop on completion of set exercises;

- On-hand trainer support to groups working on exercises to ensure that progress is maintained equally.

To achieve a maximum result the training must be organized in such a way that it creates multiplier effects allowing for a cascade of training which can be carried out by the SESA independently form the project. Therefore, training of trainers and mentors will be a crucial part of capacity building for the Agency.

Activity 4.3.4: Organize a study visit to EU member state(s) to observe best practices in the fields of public employment services

To develop the capacity of the SESA staff it will prove useful to enable them to witness in person key concepts and methodology applied in practice abroad. Therefore, the TA in cooperation with the beneficiary will decide on suitable EU member states to be visited. Through its consortium partners the project is well connected with the Latvian State Employment Agency (SEA) and the French public employment service Pôle Emploi. The final decision, however, will be taken in consultation with the beneficiary.

If well prepared and organised efficiently, study visits are excellent tools for learning and turning knowledge into practice. They also allow for establishing networks and relationships that may develop into future sustainable partnerships. The following tasks have to be carried out for a successful implementation of such a visit tour.

- Agreement on destination, institutions to be visited and participants

- In consultation with destination institutions, prepare and agree a programme for the study visit

- Provide logistical support to implementation of the study visit

- Hold an orientation workshop with participants of the study visit

- Support or facilitate the meetings with representatives of the targeted institutions to ensure that they serve the required purpose and derive maximum benefits for participants

Upon completion of study visit and return to Georgia, the project team will facilitate debriefing and evaluation meetings with the participants of the visit. It will support the preparation of a report to ensure all the parties concerned agree on the necessary follow-up actions. The report will highlight the collected examples of good practice.

Activity 4.3.5: Facilitate the exchange of experience and good practice on delivery of modern public employment services with European peers and nationally

The TA will support the SESA to establish communication channels for the exchange of experience within Georgia. One possible topic would be to draw on the previous experience of the Adjara Employment Agency as an independent body.

With the French Pôle Emploi and the Latvian SEA among the project partners the new Agency will be connected from its start with Public Employment Services abroad. In addition to this, international networks like the World Association of Public Employment Services (WAPES) or the European Network of Employment Services can be used for gaining insight into good practices of modern public employment services.

Activity 4.3.6: Develop a coaching scheme for the staff of SESA and other relevant institutions and pilot it after the provision of training programmes

To achieve sustainable results of the training provided to the staff of SESA and possible other institutions involved in capacity building continuous support through complementary measures like coaching is advisable. This would contribute to enhance the quality of their knowledge and skills, strengthen their attitudes and cause a long-term impact on their work.

Output 4.3: Deliverables and Inputs

| Output 4.3 |  |  |  |
| --- | --- | --- | --- |
| Activities | Deliverables | Inputs (WD) |  |
| 4.3.1 | Training needs assessment | TL: KE2: KE3: LT JNKE: ST JNKE SNKE: | 12 150 20 100 0 90 |
| 4.3.2 | Training plan |  |  |
| 4.3.3 | Training measures |  |  |
| 4.3.4 | Study visit |  |  |
| 4.3.5 | Exchange of experience |  |  |
| 4.3.6 | SESA staff coaching scheme |  |  |

## Component 5 – Information Systems and Analysis

### Background information

The LMIS in Georgia is currently based primarily on four sources:

- The LMIS in the MoESD;

- The LMIMS in the MoIDPLHSA;

- The EMIS in the MoESCS;

- GEOSTAT;

The LMIS under the MoESD

Based on an ETF concept note on a Labour Market Information System (LMIS) in Georgia 2014, the current LMIS was established in 2015-2016 under the former Ministry of Health, Labour and Social Affairs, now the MoIDPLHSA. The setting up of the LMIS was supported by the EUVEGE programme. The recommendations of the EUVEGE project constitute a sound basis for implementation of an efficient LMIS, but not all recommendations have yet been implemented.

In mid-2017 the LMIS was transferred from MoIDPLHSA to the MoESD as a special Labour Market Analysis Division (LMAD) under the Economic Policy Department (EPD). Currently the LMAD has a staff of three persons. The MoESD LMAD has produced the following main analyses:

- Annual Labour Market Analysis reports 2017, 2019 and 2019;

- Establishment Skills Survey, 2017;

- Survey on Labour Market Needs in the Tourism Industry, 2018;

- Survey on Labour Market Needs in the Construction Industry, 2019;

The sources of the analysis are primarily:

- GEOSTAT data;

- Ad hoc questionnaire surveys;

- Output tables from the LMIMS under the MoIDPLHSA;

- Data of the Private employment agency HR.GE;

- Data of MoESCS.

So far, no forecasts of the labour market balance on the short- medium- or long term have been produced, but according to the EU SRPC budget support targets and variable performance indicators, the LMAD must provide the documentary evidence in the coming years relating to:

- Variable Performance Indicator 1.1: Availability of information on labour market developments for policy evidence

- Variable Performance Indicator 1.2: Availability of sector specific skills needs

- Variable Performance Indicator 1.5: Availability of national skill anticipation with a 5-year outlook

It should particularly be noted that Variable Performance Indicator 1.5 calls for a further development of the macro-econometric model used by the National Bank of Georgia (NBG) with an additional labour market balance module (which does not exist today), a more specific model like the Local Economy Forecasting Model (LEFM) developed by Cambridge Econometrics and the Warwick Institute for Employment Research or, as a third option, a combination of different quantitative forecast models (prolongation of trends) and qualitative models (Scenario models, expert panels, focus groups etc.)

There is a need to assist the MoESD LMAD to develop and implement sustainable regular labour market balance forecast models and based produce evidence-based policy recommendations for the labour market and VET sector. The project has offered to assist the LMAD elaborate a more comprehensive model based on information from other sources than GEOSTAT which might enhance the quality and depth of analyses to ensure that SBS indicators are achieved.

The LMIMS under the MoIDPLHSA

While the LMIS in 2017 was transferred to the MoESD, the MoIDPLHSA was still responsible for the Labour Market Management Information System (LMIMS) primarily based on the administrative records in the WorkNet portal, which is expected to be transferred from the SSA / ESS to the newly established SESA.

The LMIMS system was supported by the Twinning Project GE/20 ‘Capacity Building of the Employment Support Services (ESS) in Georgia’ 2017 to 2018. The Twinning project produced several high-quality recommendations on updating of the LMIMS and the current project intent to build on these to facilitate implementation and further development of the LMIMS – especially by linking the LMIS to other digital administrative registers – including the EMIS, LMIS and new Accumulated Pension Fund (APF). Linking the LMIMS to the APF will facilitate calculation of employment rates for participants in active employment measures (tracer studies) by using available administrative records instead of resource heavy questionnaire or self-assessment methodologies.

Traditionally, the LMIMS has been designed to manage jobseekers. With the new SESA there is an urgent need to strengthen the facilities for registering enterprises, vacancies and mediations.

A key issue will be ensuring that international standard classifications are used as far as possible (NACE, ISCED, EU classificatory of Active Employment Measures etc). This will facilitate linking the LMIMS to other public and private digital registers and facilitate international comparisons.

As mentioned under Component 4, the project will also assist the MoIDPLHSA introduce the category ‘Unemployed Job seekers’ as an umbrella category above the current 4 categories of job-seekers.

Finally, there is a need to examine the feasibility of linking the LMIMS with other recruitment portals – like the www.jobs.ge, www.hr.ge and others. The current market share of www.worknet.gov,ge is limited, when it comes to vacancies – especially in the higher end of the job hierarchy.

In relation to the SRPC programme, the LMIMS will be the main responsible for delivering documentation statistics for the following variable indicators:

- Indicator 1.3: Availability of information and evidence on job vacancies at local level,2021;

- Indicator 1.4: Employment rate of retrained jobseekers, 2022;

- Indicator 2.2: Number of job intermediations provided by SESA, 2021;

- Indicator 2.4: Number of Job placements brooked by SESA, 2021;

The project will assist the MoIDPLHSA LMIMS section produce the required documentation, including gender-disaggregated data where relevant. It will also assist the MoIDPLHSA further develop the LMIMS portal into a more demand-oriented and user-friendly tool for both services to the jobseekers and the employers and facilitate production of policy and action-oriented analysis of the labour market balance now and in the near future.

The EMIS under the MoESCS

MoESCS has received significant assistance from several donors to develop the VET system and the EMIS. EMIS is already well described and will be further supported by the WB and the ADB Modern Skills for Better Jobs Sector Development Program. The current project will focus on integration of the EMIS with the LMIMS, LMIS and APF digital administrative registers and supporting the EMIS division producing the required documentation for the SRPC variable indicators. In relation to the SRPC programme, the EMIS will have the main responsibility for delivering documentation statistics for the following variable indicators:

- Indicator 3.1: Availability of evidence and analysis on socio-economic indicators of VET students, 2020;

- Indicator 3.3: Number of VET students with special needs, 2020;

- Indicator 3.4: Share of authorised VET providers delivering short term LLL courses, 2021;

- Indicator 3.5: Average completion rate in formal VET programmes, 2022;

- Indicator 4.1: Youth enrolment (15-24) in formal VET qualification programmes in the selected regions, 2021;

- Indicator 4.3: Youth enrolment (15-24) in formal VET qualification programmes nation-wide, 2022;

Indicator 2.5 on ‘Employment rate of young people aged 15 – 29 years with vocational education and training nationwide, 2020’ is the responsibility of GEOSTAT to document, but integration of EMIS and APF would make this task much less costly. The project will assist the EMIS agency to produce the required documentation.

GEOSTAT

GEOSTAT produces labour market and educational statistics in line with international standards. The Labour Force Survey (LFS) is based on a representative sample of approximately 6,000 households answering flexible standardised questionnaire at a regular basis, and the Household Survey is based on a sample size of approximately 4,000. GEOSTAT is not a formal beneficiary of the project, but provides pivotal information to the LMIS, LMIMS and EMIS. The questionnaires used for the LFA and Household Surveys (HHS) all have an obligatory core, that can be supplemented by additional ad hoc questions.

Close cooperation based on information sharing with the GEOSTAT labour market and educational statistics departments will be of the utmost importance for the sustainability and feasibility of the recommendations produced by the project. GEOSTAT will be of pivotal interest to assess the juridical barriers and options for merging public digital registers to generate joint analytical data warehouses using the Personal Identification Code (PIC) for individuals and the VAT code for companies to analyse the labour market balance without jeopardising the regulations on protection of individual and confidential digital data.

Accumulated Pension Fund (APF)

As mentioned, the APF was launched in January 2020 and collects information about all formally employed persons under the age of 40 years. (Involvement of persons under 40 is mandatory, whereas it is currently optional for those over 40). As in other countries, this scheme is expected to be made obligatory until pension age in the future. The APS shares information with the LMIS to monitor the formal employment rate, and offers a possibility of monitoring of graduates from formal education and participants in Active Employment Measures..

### Component 5 Implementation

As explained earlier in this report, Component 5 was created by moving all Outputs and activities from different components off the original ToR to a single component, with the intention of ensuring greater synergy and compatibility between different data and information systems and facilitating the sharing of data for the purpose of evidence-based policy making.

The KE3 (Labour Market Analyst) and other project experts will be located at the main project office in the MoESCS (situated close to the MoESD and LMAD). However, a successful and sustainable implementation of the component requires close cooperation with all stakeholders. It is therefore proposed to establish an Analysis Task Force (ATF) composed of the following representatives:

- The project KE3 and/or the LT NKE on labour market;

- The head of the MoESD LMIS LMAD;

- A representative of the MoIDPLHSA LMIMS;

- A representative of the MoESCS EMIS;

- A representative of the GEOSTAT labour market statistics division;

- A representative of the GEOSTAT educational statistics divisions;

- A representative of the APF register;

- A representative of an appropriate business organisation;

- The EUD programme manager on Labour Market, Migration and Gender;

The AFT group is proposed to meet at least bi-monthly to discuss and solve barriers for further progress. The project will provide the secretarial assistance to the ATF – including agendas and MoM’s.

The basic approach to implementation of the project component is to ensure maximum sustainability by using available data as indicators as far as possible and only embark on costly ad hoc questionnaire surveys when there is no other option. This include an assumption, that one doesn’t need to know everything in detail (Nice to Know), but that imperfect indicators (Need to Know) can provide valuable inputs to the policy decision making process.

The Component involves capacity building training under three of the Outputs. The following is a table setting out our provisional estimation of the formal training (i.e. excluding on-the job training and coaching) that will be required:

| C5 | Workshops/ Training | Target group | Breakdown of Workshops/Training events |  |  |  |  | Participants |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Duration of each event | No. of Events in Tbilisi | No. of Events in regions |  | Total days | In Tbilisi | In regions | Total Person days |
| 5.4.1 a | LMIS user training | MoESD (LMAD) MoIDPLHSA/ESA MoESCS/agencies/EMIS Youth Agency Others | 2 | 2 | 0 |  | 4 | 30 | 0 | 60 |
| 5.4.1 b | LMIS data analysis training | MoESD MoIDPLHSA Other | 2 | 1 | 0 |  | 2 | 15 | 0 | 30 |
| 5.5.2 | EMIS data analysis/evidence-based policy drafting | EMIS staff Other (MoESCS etc.) | 2 | 1 | 0 |  | 2 | 20 | 0 | 40 |
| Total |  |  |  |  |  | 8 |  |  |  | 130 |

Output 5.1: Improved integrity and compatibility of data and information systems for evidence-based policy making and implementation

The project will support the technical inter-connectivity between the information systems, databases and portals relevant for policies promoting skills development and matching.

Activity 5.1.1: Analyse the specifications (technical and content-related) of the main information systems (EMIS, LMIS, LMIMS and the main job search portals), assess their scope for inter-connectivity, and prepare detailed proposals for sharing data between them

During the first 2 quarters of 2020 the project will further develop the concept of establishing an Employment Statistics Resource (relational SQL data warehouse) linking the LMIS with key variables from the LMIMS, EMIS and APF digital registers, which we propose should use the Personal Identification Number (PIN) for individuals (supply side), and Tax numbers for companies (demand side). PIC and Tax codes will be the key variables for merging data, as shown in the diagram below.

Overall structure of the proposed Employment Statistics Resource for analytical purposes

| LMIMS job seeker register: Employment statistics data warehouse - PIC code; - VAT number; - ISCO code; - ISCED code - NACE code - Status code in LMIMS; - ALMM code in LMIMS - School code; - Dates; - Region PIC code; - ISCO code; - ISCED code; - Status; - Region code; - Date; | APF Accumulated Pension Fund Contribution Register: - PIC code; - VAT code; - NACE code; - Region code; - Date |
| --- | --- |
| EMIS student register - PIN code; - ISCED code; - ISCO code; - School code; - Status (enrolled, graduated); - Date; | Other registers (migrants, military service, deceased etc.) - PIN code; - Registered Y/N |

The process will lead to preparation of a Recommendation Report on establishment of an Employment Statistics data warehouse database combining data from the EMIS and LMIMS and other public and private databases for statistical and analytical purposes. The recommended new LMIS will be discussed in the ATF group and submitted for approval in the 2nd SC meeting in the spring 2020.

Activity 5.1.2: Provide advisory technical support to the upgrading of data systems to achieve the necessary linking

The project will support development and piloting of the sharing of data between the main data providers (LMIS, APF, EMIS and LMIMS). Depending on the budget allocated by beneficiaries and the availability of in-house IT development services, the work could be carried out by a contracted IT company. However, it is hoped that the Employment Statistics Resource could be provided through an add-on to an existing database of one of the beneficiaries. It should be noted that technical advice and support could be provided by our consortium partners. The work involved in this activity should include:

- Development of technical specifications including capability for inter-connectivity with other data sources, building on recommendations from previous EUVEGE project

- Providing advisory support to system development

The project will develop capacity by developing and delivering a 3-day training course for key members of the LMIS, LMIMS, EMIS and other relevant teams on how to maintain/update the Employment Statistics data warehouse and generate output tables using statistical software and on-the-job training. Selection of course participants will be made in conjunction with the relevant institutions and based on a Training Need Assessment (TNA).

Output 5.1 Deliverables and Inputs

| Output 5.1 |  |  |  |
| --- | --- | --- | --- |
| Activities | Deliverables | Inputs (WD) |  |
| 5.1.1 | Concept note on establishment of Employment Statistics Resource (data warehouse) | TL: KE2: KE3: LT JNKE: ST JNKE SNKE: | 0 10 30 36 0 80 |
|  | Recommendations report incl. technical specifications for data sharing |  |  |
| 5.1.2 | Report on training (agenda, materials, participants etc.) |  |  |

Output 5.2: Technical revision and upgrading of the Labour Market Information Management System (LMIMS) supported

The LMIMS is primarily based on the administrative WorkNet portal maintained by the SESA and is supposed to be enhanced by additional modules. As mentioned above, additional modules (case management, analytical module, digital services for clients, etc.) in addition to the already existing modules for employers and jobseekers are planned to be elaborated.

Activity 5.2.1: Develop detailed proposals to upgrade the LMIMS portal (software and hardware) including increased information content and enabling the unemployed to be distinguished from jobseekers

In parallel with Activity 5.1.1 the project will assist the MoIDPLHSA LMIMS section upgrade the LMIMS portal in line with the EUVEGE project recommendations. More specifically the project will assist the LMIS section in:

- Introducing the EU classificatory for ALMM and other international standards wherever required;

- Introduction of a category / variable of unemployed in the LMIMS / WorkNet database;

- Facilitation of registration of vacancies and Occupational codes (ISCO);

- Improving the cooperation with alternative recruitment databases like the www.jobs.ge and www.hr.ge;

It is proposed that the upgraded WorkNet will be piloted in selected regions, before and national roll-out is implemented.

In order to facilitate the national roll-out of the upgraded platform, the project will assist the MoIDPLHSA ensure that all local data are transferred regularly to the national LMIMS system data warehouse for statistical purposes.

The activity will lead to preparation of a Recommendation Report on how to upgrade the LMIMS data base – including international classifications of unemployed and Active Employment Measures.

Activity 5.2.2: Develop procedure and guidance manuals for use of LMIMS as intranet, as well as for analysis of public employment services data

This activity, following on from 5.2.1 will involve preparing procedures, manuals and related guidelines on how to use the LMIMS. After approval, it will also include on-the-job training of LMIMS staff based on the procedures and guidelines.

Output 5.2 Deliverables and Inputs

| Output 5.2 |  |  |  |
| --- | --- | --- | --- |
| Activities | Deliverables | Inputs (WD) |  |
| 5.2.1 | Recommendation Report on upgrading the LMIMS database | TL: KE2: KE3: LT JNKE: ST JNKE SNKE: | 0 20 30 36 0 50 |
| 5.2.2 | Guideline on using LMIMS |  |  |
|  | On-the-job training report (specification, results etc.) |  |  |

Output 5.3: Capacity of Labour Market Information System (LMIS) team enhanced in analysis, survey and anticipation methods

Activity 5.3.1: Provide Guidelines and related capacity building to the LMIS team to collect, analyse and disseminate labour market information and monitor labour market developments

Until the LMIS data warehouse is in place the LMIS team will be supported in planning, design, implementation, analysis and dissemination of labour market skills anticipation surveys based on available statistics, enterprise skills survey and relevant qualitative methods.

This will include the drafting and piloting of guidelines relating to data analysis, survey methodology and anticipation methods.

The capacity building will be based on a TNA and tailored to the needs related to required labour market analysis outputs of the LMIS in the coming period. This will include the annual labour market analysis 2020 and 2021, two sector skills anticipation analysis in 2020 and a national skills anticipation forecast for the whole economy in 2021.

The work involved in this activity will include:

- Assess training needs of LMIS team – including skills surveys, training needs analysis of companies, sectoral analysis and medium-term skills anticipation at national level

- Develop and implement training and coaching scheme for relevant staff of MoESD

Activity 5.3.2: Increase public awareness and visibility of the LMIS (linked with Output 1.3)

The project will advise the MoESD LMAD on upgrading the LMIS web portal, including development of technical and design specifications.

The project will also assist the LMIS team to disseminate the results of the analysis to both key stakeholders like the relevant social partners and agencies and to a broader audience highlighting the skills providing a high level of employability, including measures to publicise the results of LMIS surveys in the mass media.

Output 5.3 Deliverables and Inputs

| Output 5.3 |  |  |  |
| --- | --- | --- | --- |
| Activities | Deliverables | Inputs (WD) |  |
|  |  | TL: KE2: KE3: LT JNKE: ST JNKE SNKE: | 0 10 50 36 0 20 |
| 5.3.1 | Draft guidelines for the implementation of LMIS surveys, including: - Sector skills anticipation surveys - Medium term anticipation of skills needs for the whole economy |  |  |
|  | Report on capacity building and training activities for LMAD staff |  |  |
| 5.3.2 | Draft specifications for upgrading LMIS portal |  |  |

Output 5.4: Enhanced capacity of EMIS to support evidence-based education and training policy making

Activities under this result are closely related to Component 1, which requires an increased capacity to produce evidence-based policy and strategy documents from key data sources including EMIS. Since 2017, the EMIS database has been managed by LEPL EMIS, an agency under MoESCS.

It should be noted that GEOSTAT also produces various valuable output tables but without policy recommendations. The LMIS, EMIS and LMIMS should translate these and their own output tables into policy recommendations to facilitate evidence-based decision-making and adjustment of the labour market and VET system to the current and future challenges.

Activity 5.4.1: Assess the capacity of the EMIS database to meet the requirements of evidence-based policy making

There is an expectation that EMIS will not only manage a database providing statistical and other information relating to the education system but will also provide analyses on demand to meet the needs of policy makers. To assess the extent to which the EMIS meets this expectation the TA will

- Review the content of the EMIS databases to identify the availability, relevance and coverage of data required for use in preparing evidence-based analyses (including mapping of data, identification of gaps in data collection etc.), and its scope for inter-connectivity with LMIS and other relevant databases

- Prepare a report for MoESCS with recommendations for the further development of EMIS to address and identified data gaps

Account will be taken of, and in close cooperation with, the support that is being provided to EMIS and VET.GE development by the World Bank (GGF-funded),

Activity: 5.4.2: Develop capacity of EMIS staff to support evidence-based policy making

The EMIS agency will be assisted on an ongoing basis in analysing labour market and educational output tables and elaborate policy and action-oriented recommendations based on the evidence. Currently, the output tables from LMIS, LMIMS and EMIS do not provide sufficiently detailed evidence-based recommendations to meet the needs of policy makers. In cooperation with the management of the MoESD, MoIDPLHSA, MoESCS and other stakeholders like Sector Councils, recommendations for summary and recommendation sections of the analysis reports should be developed.

Sub-activities under this activity are as follows:

- Assess the capacity of EMIS staff to prepare evidence-based analyses, and develop a plan for training and capacity development

- Provide training and on-the-job coaching for EMIS staff in data analysis and reporting

- Support EMIS staff in preparing three analytical reports (on issues related to the SRPC), and develop templates for regular analytical and monitoring reports to be delivered regularly by EMIS

The activity should be closely coordinated with the activities of the parallel WB and ADB projects and may also be carried out in parallel with activities of Output 5.4 above.

Output 5.4 Deliverables and Inputs

| Output 5.4 |  |  |  |
| --- | --- | --- | --- |
| Activities | Deliverables | Inputs (WD) |  |
| 5.4.1 | Review report for MoESCS on content and capacity of EMIS | TL: KE2: KE3: LT JNKE: ST JNKE SNKE | 17 0 25 36 0 0 |
| 5.4.2 | TNA and training/coaching plan |  |  |
|  | Reports of training and coaching provided |  |  |
|  | Templates for SRPC variable indicators 3.1,.3.3, 3.4, 3.5, 4.1 and 4.3 reports |  |  |

Output 5.5 Enhanced capacity of institutions using LMIS. LMIMS and EMIS data in evidence-based policy making

The project will, on an ongoing basis, assist other users to analyse labour market output tables and elaborate policy and action-oriented recommendations based on the evidence. Currently, the LMIS, LMIMS and EMIS have mostly produced output tables with room for the further elaboration and improvement of related policy recommendations.

In cooperation with the management of the MoESD, MoIDPLHSA, MoESCS and other stakeholders like the Sector Councils, recommendations for summary and recommendation sections of the analysis reports should be developed.

GEOSTAT produces several valuable output tables, but without policy recommendations. The LMIS, EMIS and LMIMS should translate these and their own output tables into policy recommendations to facilitate evidence-based decision-making and adjustment of the labour market and VET system to the current and future challenges.

Activity 5.5.1: Assess the capacity of potential users to effectively use data in evidence-based policy

The support should address not only the LMAD team responsible for maintaining the LMIS and managing surveys but all potential users. Mainly these will include staff of the MoIDPLHSA and SESA, EMIS and the MoESCS and its agencies, who require accurate data to plan and deliver provision on a sector and regional basis, as well as bother VET stakeholders. Capacity building will cover the following sub-activities:

- Assess training needs including the fields of skills surveys, training needs analysis (TNA) of companies, sectoral analyses, and medium-term skills anticipation at national level

- Develop and implement short and long-term training plans on all the issues above for the relevant staff of MoESD and other institutions using LMIS

- Develop and implement coaching scheme for the relevant staff of MoESD and other institutions

Activity 5.5 2: Develop and implement training and coaching programme for data users

The purpose of this activity is to ensure that the results of LMIS analyses are known to stakeholders, to enable them to use them appropriately in developing and reviewing policies, strategies and action plans related to employment, education and training and youth. Implementation of the activity will be carried out through two sub-activities:

- Dissemination of results of LMIS analyses to relevant stakeholders through information workshops for those using LMIS data in the design of education, VET and employment services

- Increase public awareness and visibility of the LMIS

The activity will be linked with implementation of the overall Project Communications and Visibility Plan (Output 1.3) which will provide the broad framework within which it will be implemented.

Activity 5.5.3: Disseminate the results of the data analysis to relevant stakeholders through information workshops on use of data for evidence-based policy making

- Develop survey methodology (and finalise after piloting)

- Pilot a skill needs analysis in two selected sectors, including implementation of survey, analysis of results and design of short training courses to meet identified SME skill needs

This activity, included in the original ToR, has been interpreted by the project team as intended to help Enterprise Georgia, an agency under the MoESD in identifying sectors and regions to be targeted in SME development initiatives, by providing information on the potential or small business development related to specific products or services in particular places. The outcomes of the activities should be the development of targeted training provision to help entrepreneurs establish small businesses to meet identified needs.

The activity builds on previous support provided by the ETF which led to 2 sector kills surveys. However, due to staff changes, Enterprise Georgia still lacks capacity to undertake surveys without assistance. The TA will include assisting them in regard to survey methodology and the interpretation of results, and will involve following two sector pilot surveys that they will implement.

Activity 5.5.4:  Support Enterprise Georgia in analysis skills needs for SME development in selected sectors and link them with training provision

- Develop survey methodology (and finalise after piloting)

- Pilot a skill needs analysis in two selected sectors, including implementation of survey, analysis of results and design of short training courses to meet identified SME skill needs

- Provide guidance materials and provide capacity building support on survey implementation/analysis and development of training courses to meet identified SME skills needs

This activity, included in the original ToR, has been interpreted by the project team as intended to help Enterprise Georgia, an agency under the MoESD in identifying sectors and regions to be targeted in SME development initiatives, by providing information on the potential or small business development related to specific products or services in particular places. The outcomes of the activities should be the development of targeted training provision to help entrepreneurs establish small businesses to meet identified needs.

The activity builds on previous support provided by the ETF which led to 2 sector skills surveys. However, due to staff changes, Enterprise Georgia still lacks capacity to undertake surveys without assistance. The TA will include assisting them in regard to survey methodology and the interpretation of results and will involve following two sector pilot surveys that they will implement.

Activity 5.5.5: Support MoIDPLHSA in surveying the health care sector, including the numbers of people qualified and employed in primary health care and hospitals, to identify skills needs and capacity of potential training providers

During the Inception Phase, the First Deputy Minister responsible for health care (MoIDPLHSA) requested assistance in analysing the skill needs of the health care sector. Health care provision in Georgia is private, and health care staff are frequently contracted by multiple clinics and hospitals, which prevents the Ministry from getting a clear picture of the numbers employed, staff shortages and training needs on either an occupational or a regional basis. The Ministry has been advised that this new activity could be carried out as a sector skills analysis within the frame of the LMIS, and it is understood that MoIDPLHSA may request cooperation with MoESD on this matter. Accordingly, the project will provide support in establishing the survey and assistance in interpreting results as necessary.

Output 5.5 Deliverables and Inputs

| Output 5.5 |  |  |  |
| --- | --- | --- | --- |
| Activities | Deliverables | Inputs (WD) |  |
| 5.4.1 | TNA report and linked training plan | TL: KE2: KE3: LT JNKE: ST JNKE SNKE: | 20 20 65 36 0 0 |
|  | Training reports, incl. agendas, materials, participants |  |  |
|  | Coaching plans and reports |  |  |
| 5.4.2 | Dissemination plan |  |  |
|  | Reports of dissemination activities, incl. materials |  |  |
| 5.4.3 | Survey methodology |  |  |
|  | Skill needs analysis (2 pilot surveys) |  |  |
| 5.4.4 | Sector skill needs report for health care sector |  |  |

## Component 6 – Grant Scheme

### Background Information

The Skills4Jobs Action Programme includes “a Grant Scheme aiming at enhancing the employability of target groups in the regions, open to private sector, non-governmental actors and various service providers in education and training, employment and youth. The grants will improve outreach equally for final female and male beneficiaries and vulnerable groups through the development of partnerships and cooperation activities”. (Annex 2 of the Annual Action Programme 2017 Action Document for Skills Development and Matching for Labour Market Needs).

Whilst the TA component tendering process was still on-going, in July 2019, the European Commission launched the publication of a Call for Proposals for a Grant Scheme providing Support to Skills Development and Matching for Labour Market Needs covering three themes: (1) Skills Development; (2) Skills Anticipation and matching; and (3) Youth and entrepreneurial learning. (EuropeAid/164732/DD/ACT/GE, Guidelines for grant applicants).

The overall indicative amount allocated for the Grant Scheme is EUR 7,000,000, made up of:

Lot 1: Support to the development of international partnerships – EUR 2,000,000

Lot 2: Support to the development of local Human Capital Development (HCD) partnerships – EUR 3,000,000

Lot 3: Support to the development of sectoral partnerships – EUR 2,000,000

Any grant requested under this call for proposals must fall between a minimum amount of EUR 300,000 and a maximum amount of EUR 1,000,000. Any grant requested must also fall between a minimum of 50% of the total eligible costs of the action and a maximum of 80%. The duration of projects will be between a minimum of 18 months and a maximum of 36 months.

The scheme provides a two-stage application process, with applicants required to prepare and submit concept notes setting out their project proposals (by 21.10.2019), with short-listed applicants subsequently invited to submit full applications. It is expected that the selection and contracting process will be completed in time for the selected grant projects to start in May 2020.

The ToR for the Technical Assistance component of the programme envisaged the project taking on a wide role in supporting and providing expert services in “Grant Scheme component proposals development, project management and monitoring” and the activities listed in the ToR covering:

- Preparing and implementing an information campaign to promote the grant scheme to potential applicants;

- Conducting training, Q&A and information sessions for shortlisted grant scheme applicants;

- Guiding and monitoring grant scheme implementers through site visits, monitoring reports etc.;

- Facilitating networking among grant implementers through biennial meetings, thematic fora and activities designed to provide visibility for success stories;

- Assisting in public launching and closing events of the grant scheme.

These activities were fully reflected in the technical proposal and original work plan presented by the Consortium at the time of tendering for this TA project.

However, at the Kick-Off Meeting of the project on 7 October 2019, we were informed that, under the rules of the grant scheme (and to avoid possible conflicts of interest). The role of the Technical Assistance team would be limited to providing independent monitoring support on behalf of the EUD to the implementation of grant projects. With this in mind, we have adjusted the definition of Output 6 and the related activities to be carried out in this Component accordingly, as set out in 3.6.2 below.

### Component 6 Implementation

Output 6.1: Grant Scheme implementation supported through the monitoring of grant projects

Activity 6.1.1 Provide technical, implementation and monitoring support to the Grant Scheme

In line with the reduced scope of the TA to be provided, we propose to implement this activity though two sub-activities. However, in the expectation that there may be up to a possible 14 projects implemented in different regions of Georgia (depending on selection decisions and the size of the selected grant projects in relation to the total overall available amount), we consider that, within the available resources, we may be able to provide a deeper and more hands-on monitoring approach than may have been possible if our resources for the Component were spread across a wider range of activity.

The activity, which will be carried out by a senior and a junior NKE experienced in grant scheme monitoring, includes:

- Conducting orientation and training session for grantees on visibility, activity and financial reporting requirements, monitoring arrangements etc. This will help to ensure compliance with Grant Scheme contracting requirements, support delivery of high-quality project outputs and enhance the performance of grantees in project implementation and reporting;

- Guiding and monitoring the implementation of grant projects by checking the inception, progress and final reports of grant projects (including deadlines and deliverables), conducting on-site monitoring visits (timed to fit in with the grantees’ progress reporting deadlines - on at least a six-monthly basis - for the duration of the projects), preparing monitoring reports for the EUD and advising on corrective measures if needed.

The following table shows the information event to be organised under this Output:

| C6 | Workshops/Training | Target group | Breakdown of Workshops/Training events |  |  |  | Participants |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Duration of each event | No. of Events in Tbilisi | No. of Events in regions | Total days | In Tbilisi | In regions | Total Person days |
| 6.1.1 | Orientation training for grantees | Representatives of grant projects | 1 | 1 | 0 | 1 | 15 | 0 | 15 |

Detailed planning for implementation of this activity will be carried out immediately the results of the selection process are known, which will enable identification of the out-of-Tbilisi locations where the activities will be carried out, together with accurate scheduling of training events and monitoring visits.

Activity 6.1.2 Support preparation of a compendium of grant projects’ results, including good practices identified for possible replication

In the course of the monitoring process, we expect that various good practices will be identified, not only with regard to project management and implementation, but especially relating to the lessons learned from projects in the areas of skills development and skills matching, entrepreneurship learning and youth that might help other education and training providers, stakeholders and other actors throughout Georgia in enhancing or improving their provision of education, training or other services, or which may be relevant to further policy or systemic development.

It is quite usual in grant schemes of this kind to collate, publish and disseminate the outcome of grant projects in order to ensure sustainability of results and ensure that good practices developed though projects are widely replicated. The act of preparing such a compendium also helps to focus the attention of grantees on ensuring the quality of deliverables and optimizing results. This issue should be raised at an early stage of grant projects’ implementation, and should be linked with the final reporting and dissemination activities of the grantees.

Output 6.1: Deliverables and Inputs

| Output 6.1 |  |  |  |
| --- | --- | --- | --- |
| Activities | Deliverables | Inputs (WD) |  |
| 6.1.1 | Three orientation/training sessions for grantees in project management, activity and financial reporting, visibility requirements etc. | TL: KE2: KE3: LT NKE: ST JNKE SNKE: | 30 50 0 0 50 100 |
|  | Checking and feed-back on the inception, 6-monthly and final reports of grantees, including checks on deliverables and milestones, expenditure etc. |  |  |
|  | 6-monthly monitoring visits to grant projects, monitoring reports to EUD, incl. recommendations for corrective actions (if any) |  |  |
| 6.1.2 | Compendium of grant projects’ results, incl. identified good practices |  |  |

# Revised Log Frame and Activity Matrix

## Revised Log Frame

|  | Result chain | Indicator(s) | Baseline | Target | Source and means of verification | Assumptions |
| --- | --- | --- | --- | --- | --- | --- |
| Impact: Overall objective | OVERALL OBJECTIVE: (Contribute to) Improved employability of women and men in the selected regions of Georgia | - Proportion of NEETs in the population | 2020 Proportion of NEETs 15-24: 26.9% (male 23.2%, female 31.0%) in 2018 | 2023 Target for proportion of NEETs 15-24, in 2023: <22.8% | GEOSTAT LFS survey (Baseline and targets from Labour & Employment Strategy 2019-2023) | Not applicable |
|  |  | - Women of working age employed / total working age female population | Women’s participation rate: 55.6% in 2019 | Target for women’s participation rate: >63% in 2023 | GEOSTAT LFS (Baseline and targets from Labour & Employment Strategy 2019-2023) |  |
|  |  | - Lifelong learning rate by gender | 0.61% (M 0.68%, F 1.55%) in 2015 | 0.8% (2020), 1.5% with at least 0.5 percentage point increase for women (2022) | GEOSTAT LFS, EMIS (Baseline and targets from Action Document for Annual Action Programme 2017) |  |
|  |  | - Youth drop-out rate from VET | 14% in 2016 | 13% (2020), 11% (2022) | EMIS (Baseline and targets from Action Document for Annual Action Programme 2017) |  |
| Outcome: Specific objective | SPECIFIC OBJECTIVE: (Contribute to) Enhanced capacity of the beneficiary ministries and agencies, as well as local communities, to develop, implement, monitor and review skills development and matching policies | - Status of TA capacity building plans for MoESCS, MoESD, MoIDPLHSA (incl. SESA) and Youth Agency (YA) | 2020 TA capacity building plans not yet defined for the MoESCS, MoESD, MoIDPLHSA/SESA, Youth Agency – to be done by the project | 2023 TA capacity building plans defined, agreed with each beneficiary and fully implemented | Assessment reports of TA capacity building plans for MoESCS, MoESD, MoIDPLHSA (incl. SESA), YA, disaggregated by gender | The enhanced capacities of trained personnel will be effectively utilized in sector reform policy development, implementation and monitoring, and the trained personnel will be retained by the respective institutions |
|  |  | - Status of TA proposals for improving the coordination of policy development, implementation and monitoring for skills development & matching | TA proposals for improved policy coordination not yet defined – to be done by the project (Inter-agency cooperation, apart from consultations on developed policies is now mainly ad hoc) | Improved policy coordination mechanism for skills development/ matching policy development, implementation and monitoring skills development agreed and launched with the responsible institutions | MoUs or other formal agreements for inter-agency cooperation | The Government further maintains and improves the efficiency of inter-agency policy dialogue mechanisms Beneficiaries and targeted stakeholders are prepared to cooperate more closely in the revision/updating of policies, strategies etc. |
|  |  | - Development and implementation status of draft strategies and action plans of the MoESCS, MoIDPLHSA and the Youth Agency related to skills development & matching | Current status of existing strategies/ action plans (VET Strategy, Career Guidance Strategy, Youth Strategy (all 2021-26) not yet prepared; Labour/Employment Strategy 2019-23 approved but not yet implemented) | VET Strategy/AP, Career Guidance Strategy/AP, Youth Strategy/AP and Labour/Employment Strategy have been launched and are annually monitored and reported on by the responsible institutions | Annual reports of MoESCS, MoIDPLHA/SESA, Youth Agency Monitoring reports of implementation of VET Strategy/AP, Career Guidance Strategy/AP, Youth Strategy/AP and Labour/Employment Strategy | The respective roles and responsibilities of beneficiaries and other stakeholders are appropriate for sector reform policy development, implementation and monitoring Appropriate budget and resource allocation provided for Strategy/AP implementation |

| COMPONENT 1: NATIONAL SECTOR REFORM POLICIES |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Outputs – Results | Output 1.1: Updated national sector reform policies drafted | 1.1.1 Status of drafts of updated sector reform policies, strategies and action plans | 2020 Current status of the sector reform strategies that will be supported by the project: - Only the Labour/ Employment Strategy (2019-23) was developed in compliance with the Government’s development and monitoring guidelines - VET strategy (2021-26), CG Strategy (2021-26) and Youth Strategy (2020-25) not yet drafted | 2023 Drafts developed/ updated in compliance with Government development and monitoring guidelines include: - National VET Strategy (2021-26), and Action Plans (2020, with AP updated as necessary) - National Career Guidance Strategy (2021-26) and Action Plan (2020, with AP updated as necessary) - Youth Strategy (2020-25) and Action Plan (2020, with AP updated as necessary) - Labour/Employment Strategy (2019-23) (AP updated as necessary and Strategy updated 2023) | Draft policy documents, Annual progress and performance reports of ministries and agencies BS mission reports | Ministries, agencies and stakeholders including social partners and regional players actively cooperating in development, implementation and monitoring of sector reform policy-related activities The policies are properly funded and resourced |
|  |  | 1.1.2 Status of proposals for improved policy coordination and monitoring | Proposals for improved policy coordination and monitoring have not yet been drafted – to be done by the project | Proposals for improved policy coordination and monitoring have been elaborated and discussed with the beneficiary institutions (2020), with further advice provided as necessary (by 2023) | Records of discussions with beneficiaries, endorsement decision Minutes/reports of inter-agency cooperation meetings related to sector reform policy development, implementation and monitoring | Beneficiary institutions agree to further consider and institutionalise policy coordination proposals |
|  | Output 1.2: Capacities in sector reform policy development, implementation and monitoring enhanced | 1.2.1 Implementation status of TA capacity building programme of the project | 2020 TA capacity building programme not yet existing at start of project – to be developed by the project | 2023 Comprehensive TA capacity building programme developed and agreed (2020), and completed (by 2023) Beneficiaries advised and supported to help them to meet BS indicators (annually, completed 2023) | Records of discussions with beneficiaries, endorsement decision Annual progress and performance reports of ministries and agencies BS monitoring mission reports | Beneficiaries accept the need to further develop their capacities for policy development, implementation and monitoring Institutions will optimise their use of newly acquired skills and knowledge of their personnel Institutions will retain their trained staff |
|  |  | 1.2.2 Number of officials trained in all topics covered by the TA capacity building programme, disaggregated by institution, gender | Training needs not yet fully defined and training programme not yet developed at the start of project – to be done by the project (ToR suggested a number of training topics, but this should be reviewed and revised in consultation with beneficiaries) | An agreed number of officials from each beneficiary trained –disaggregated by topic, institution, gender (completed by 2023) (number to be agreed with beneficiaries during development of programme) | Assessment reports of capacity building programme including number of officials trained, disaggregated by institution, gender | Beneficiaries recognise the importance of investing in the training and career development of their personnel, using opportunities provided by the capacity building programme to ensure that key staff are trained |
|  | Output 1.3: Enhanced capacity to provide visibility & communications for sector reform policies and specific services provided by beneficiary institutions | 1.3.1 Status of plans, tools, materials etc. developed for public awareness campaigns supported by the project | 2020 None at start of project – to be developed by the project Public awareness campaigns to be supported by the project not yet planned or implemented | 2023 Public awareness campaigns planned and supported by the project (for implementation by project beneficiaries) on: - Key sector policy developments - VET / LLL opportunities - Career guidance - Youth services - Employment services / SESA regional offices - LMIS/LM issues (completed by 2023) | Records of discussions with beneficiaries, endorsement decision Information and visibility materials prepared for campaigns Press releases, and monitoring of resulting media coverage | Beneficiaries are committed to promote reform policies though PR and media activities supported by the project Media will be interested in providing positive coverage of the reforms and availability of services of beneficiary institutions supported by the project |
|  |  | 1.3.2 Number of stakeholder institutions participating in visibility and communications events supported by the project | None at start of project – events to be planned and organized by, or with support from, the project Visibility and communications events not yet planned or organized at the start of the project | Schedule of visibility events, together with a comprehensive list of the stakeholder institutions targeted by each event, drafted and agreed with EUD and the appropriate beneficiary institutions (updated periodically, completed by 2023) | Records of discussions with beneficiaries, endorsement decision Reports of visibility events, including attendance lists | Commitment of all relevant stakeholders at national and regional level to participate in information and visibility events related to the sector reform policies |
| Component 2: Skills Development & ENTREPRENEURSHIP LEARNING |  |  |  |  |  |  |

|  | Output 2.1: Enhanced capacity of the MoESCS to further develop and modernise skills development and LLL systems | 2.1.1 Status of the project’s situational analysis on access to VET/LLL | 2020 Situational analysis not yet prepared – to be done by the project | 2023 Situational analysis on access to VET/LLL elaborated as a basis for identifying measures to be recommended (2020) | Elaborated situational analysis and measures | Cooperation from private as well as public VET institutions will be forthcoming |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | 2.1.2 Status of measures to improve access to VET and LLL for targeted groups, incl. females, NEETs, vulnerable groups | Measures to increase access to VET/LLL and combat early school leaving not yet defined – to be done by the project | Measures to increase access to VET/LLL and combat early school leaving elaborated and discussed with beneficiary (2020) and advisory support provided to implementation (to 2023) | Records of discussions with beneficiaries, endorsement decision Annual progress reports of MoESCS on VET Strategy Implementation, incl. implementation of the specific measures EMIS participation data | The necessary policy and budgetary decisions are made to enable expansion of VET and LLL provision, including provision in areas where there is currently none Proposed measures are implemented by VET institutions |
|  | Output 2.2: Enhanced capacity of educational institutions to provide professional orientation and career guidance for learners in general, vocational and higher education | 2.2.1 Status of the situational analysis and action plan for career education and guidance provision in educational institutions at all levels of education | 2020 Situational analysis not yet developed at beginning of project – to be done by the project Previous situational analysis (by MCA-G in 2015) showed that existing careers information and guidance provision is extremely limited, especially in schools | 2023 Situational analysis and draft action plan (in line with proposed National Career Guidance Strategy) elaborated (2020) and advisory support provided to implementation (to 2023) | Situational analysis on career guidance provision Records of discussions with beneficiaries, endorsement decision | Cooperation between all actors (MoESCS and educational institutions, Youth Agency, SESA) in developing compatible approaches in career education and guidance Cooperation from stakeholders incl. employers in the provision of career information materials and career events |
|  |  | 2.2.2 Status of TPDC career education and guidance modules for general education teachers and VET college career managers | Only very basic career guidance training is currently available for teachers – more advanced training to be developed by the project | Training courses and materials for teachers and career managers developed (2021) and piloted (to 2023) | Records of discussions with beneficiaries, endorsement decision Developed training programmes for career managers and counsellors, and assessment reports of piloting | Capacity of TPDC to provide the necessary training programmes for school and college personnel Adequate budget and resources allocated to support career guidance implementation by trained personnel in educational institutions |
|  | Output 2.3: Enhanced capacity to deliver entrepreneurship education in general, vocational and higher education and lifelong learning | 2.3.1 Status of new entrepreneurship key competence training modules for school teachers and VET teachers | 2020: Introductory module already available, and 50% of VET teachers trained, but a comprehensive entrepreneurship key competence training package including more advanced training not yet developed – to be done by the project | 2023 A 2-stage training package for teachers in general education and VET in entrepreneurship key competences developed (2021) and piloted (with more advanced module building on the existing introductory module) (by 2023) | Training modules and materials, and report on piloting Records of discussions with beneficiaries, endorsement decision | TPDC has the capacity and resources to deliver training in career counselling and in entrepreneurship to a sufficient number of teachers VET and general education institutions are operationally capable of delivering entrepreneurship key competence learning to their students |
|  |  | 2.3.2 Status of review of entrepreneurship key competence development and good practice case studies in universities | Not yet started – to be done by the project | Elaborated report on entrepreneurship key competence development in higher education (by 2022) Two good practice case studies (by 2022) | Report on entrepreneurship key competence development in universities, with 2 good practice case studies Assessment report of consultation workshop | Universities agree to deliver entrepreneurship key competences in their programmes |

COMPONENT 3: YOUTH

|  | Output 3.1 Enhanced capacity of Youth Agency to develop and deliver effective youth services | 3.1.1 Status of Youth Agency institutional capacity building plan | 2020 No TA capacity building plan yet defined – to be done by the project TA capacity building plan for Youth Agency not yet defined | 2023 Capacity building plan developed (2020) and delivered (completed by 2023) | Agreed capacity building programme Records of discussions with beneficiaries, endorsement decision Annual progress reports of Youth Agency documenting capacity development | Effective coordination and cooperation arrangements between the Youth Agency and other stakeholders, including municipalities and other regional interests, VET colleges and SESA |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | 3.1.2 Number of Youth Agency staff trained, disaggregated by gender | No training yet provided by the TA project – to be done by the project Training programme not yet developed | Approx. 20 key YA staff trained, including training in each of the specified youth services to be developed / delivered (completed by 2023) | Assessment report on training for YA staff, incl. participation disaggregated by gender Assessment report of study visit for Youth Agency staff | Enhanced capacities of trained staff will be utilized in the improvement and delivery of youth services, and trained staff will be retained |
|  |  | 3.1.3 Status of drafts of Youth Agency Action Plan, and Law on Youth | Not yet started – to be supported by the project | Drafts of Action Plan and Law on Youth elaborated and presented to the Youth Agency (2020) | Draft action plan of Youth Agency Draft Law on Youth Records of discussions with beneficiaries, endorsement decisions | The Law on Youth will provide a firm legal basis youth services and operations of the Youth Agency, and will be adopted by Parliament The Youth Agency has sufficient budget and resources to implement the Action Plan |
|  |  | 3.1.4 Status of drafts of youth services proposals and materials | No proposals yet formulated or drafted – to be supported by the project Existing youth services provision is considered to be weak and not universally available | The range of elaborated draft youth services proposals and materials elaborated and resented to the Youth Agency include those relating to: - non-formal short courses in key competences - career guidance - youth entrepreneur-ship (completed by2023) | Records of discussions with beneficiaries, endorsement decisions Details of the youth services materials disseminated by the YA to municipalities and youth centres | A firm legal basis for the provision of specified youth services is provided by the Law on Youth The Youth Agency and municipalities have sufficient budget and resources to implement the developed youth services |
|  | Output 3.2: Improved organizational and human capacities to deliver youth services at local level | 3.2.1 Status of draft improvement and development plans for youth centres / local providers of youth services | 2020 None yet developed – to be supported by the project | 2023 Draft improvement and development plans drafted for local providers of youth services (number and locations to be agreed with Youth Agency) (by 2023) | Survey report of YA on current situation of youth centres and youth services provision in the regions (to be done by mid-2020) Proposed development plans for identified youth service providers (to be agreed with the YA) Records of discussions with beneficiaries, endorsement decisions | The municipalities are committed to supporting youth centres in the delivery of the improved portfolio of youth services Availability of sufficient personnel and funding resources in the Municipalities to support effective provision of youth services Disadvantaged youth and NEETs in particular will participate in activities organized by Youth Centres |
|  |  | 3.2.2 Number of youth workers provided with basic training in delivery of youth services, disaggregated by gender and region | None at start of project – training to be provided by the project TA capacity building training for youth workers not yet developed by the TA project | At least 80 youth workers provided with basic training to deliver specified youth services, disaggregated by gender (2021-2023) | Assessment report on basic training of youth workers, disaggregated by gender | The identified youth centres will utilise the skills and knowledge of trained personnel to deliver youth services in their municipalities |
|  |  | 3.2.3 Status of draft occupational standards for youth workers | Development not yet started – to be supported by the project | Occupational standards for youth work developed and proposed for authorisation (by 2022) | Records of discussions with beneficiaries, endorsement decisions Authorization request/ documentation | Occupational standards will be accepted as a basis for developing a modular framework programme / qualification for youth workers in the formal VET system |
|  |  | 3.2.4 Status of draft qualification for youth workers | Development not yet started – to be supported by the project | A draft modular qualification is elaborated, based on developed occupational standards (by 2023) | Records of discussions with beneficiaries, endorsement decisions | Suitable VET provider(s) will collaborate in development of a qualification/programme for youth workers with a view to seeking authorisation in the formal VET system and inclusion in the NQF |

| COMPONENT 4: EMPLOYMENT SERVICES |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | Output 4.1: State Employment Support Agency (SESA) supported in its implementation of the Revised New Service Model (NSM) | 4.1.1 Status of draft revisions to the NSM | 2020 NSM not yet revised – to be supported by the project | 2021 Draft NSM revisions and implementation recommendations, with methodology handbook and guidance materials elaborated and discussed with SESA 2020: NSM assessment 2021: NSM recommendations, methodology handbook(s), guidance materials | Assessment and recommendation reports on NSM implementation Handbooks and NSM procedural guidelines | NSM will be implemented through all SESA regional offices immediately upon their establishment |
|  |  | 4.1.2 Status of proposals for SESA institutional development | SESA not yet fully staffed - institutional development plan to be developed and supported by the project | Draft SESA institutional development plan elaborated and discussed with SESA, providing a basis for NSM implementation by all SESA offices 2020: Outline staffing plan, allocation of functions, draft institutional development plan 2021: Draft customised plans for inclusion of remote areas | Institutional development plan SESA public awareness strategy Annual reports of MoIDPLHSA and SESA | All necessary SESA staff will be appointed Budget and available resources are sufficient to meet NSM objectives Visibility of SESA regional offices |
|  |  | 4.1.3 Status of proposals for local employment policies | Service provision at local level not yet improved – to be supported by the project | Proposals for local employment policies elaborated and discussed with SESA, aimed at providing all citizens with access to full range of SESA services (by 2021) | SRPC "Skills Development and Matching for Labour Market Needs" Review Reports | Effective cooperation obtained with stakeholders in all regions Unemployed and job seekers from remote areas will continue to have access to the regionalised SESA services |
|  | Output 4.2: SESA supported in designing and delivering more accessible, effective and comprehensive ALMP measures for all job seekers | 4.2.1 Status of recommendations on improved ALMP measures | 2020 Assessment and recommendation reports not yet prepared – to be done by the project Currently available ALMP measures: - Training/retraining - Internships - Wage subsidies . | 2023 Comprehensive set of effective ALMP measures elaborated and discussed with SESA, designed to additionally include: - Public works (direct job creation) - Self-employment and entrepreneurship programmes (start-up incentives) 2021: ALMP measures assessment 2021: Recommendations on full set of ALMP measures 2022: ALMP manuals, guidelines 2023: Recommendations on ALMP pilot measures | Assessment and recommendation reports on improved ALMP measures Handbooks and ALMP procedural guidelines SRPC "Skills Development and Matching for Labour Market Needs" Review Reports | Regionalisation does not disadvantage unemployed and job seekers from remote areas Visibility of SESA regional offices Budget and available resources are sufficient to meet ALMP objectives Effective cooperation obtained with stakeholders in all regions Improved ALMP measures will lead to increased participation |
|  | Output 4.3: Capacity (knowledge and expertise) developed within the SESA staff to provide more effective employment services for jobseekers and employers | 4.3.1 Number of SESA staff at different levels trained in the application of: - NSM - ALMP measures - Career guidance - Support to vulnerable groups - LMIMS monitoring / analysis - Institutional development / management | 2020 Capacity building is barely started – capacity building programme to be provided by the project Training in NSM for 11 staff was so far provided in January 2020 | 2023 All current (102) and future SESA staff trained and capable of applying all aspects of the NSM effectively in relation to their job descriptions 2020: Induction training and TNA for all staff 2021: Advanced customised training conducted | Training assessment reports / tests results, including participation disaggregated by level of responsibility, gender Report of study visit Relevant information from annual reports of MoIDPLHSA and SESA | Trained personnel retained at SESA SESA uses the provided capacity building materials for its internal training programmes on an on-going basis |
| COMPONENT 5: INFORMATION SYSTEMS AND ANALYSIS |  |  |  |  |  |  |
|  | Output 5.1: Improved integrity and compatibility of data and information systems for evidence-based policy making and implementation | 5.1.1 Status of proposal for enhanced employment statistics resource | 2020 Concept note for employment statistics resource already drafted by the project, but not yet agreed with beneficiaries or implemented Note: The objective is to include employment statistics from different sources within a single shared resource (referred to in the concept note as a data warehouse) | 2023 Elaborated proposals for employment statistics resource discussed with beneficiaries (2020) Technical specifications elaborated, taking account of results of consultation with beneficiaries (by 2021) If proposal is accepted, advisory support to implementation has been provided (by 2023) Staff of beneficiary institutions have been trained in using the data resource, including its use in making evidence-based recommendations (by 2023) | Finalised concept note/ proposal for employment statistics resource Technical specifications and Implementation plan for employment statistics resource Records of discussions with beneficiaries, endorsement decision Handbooks and operating procedures Assessment reports on the training provided, including participation by institution, gender | Agreements on data sharing between involved institutions will be forthcoming An appropriate institution agrees to host an employment statistics resource (possibly as component of an existing database) Sufficient resources for implementation will be available in the medium term Source databases will be upgraded as necessary to provide required data Trained personnel are retained by the relevant authorities |
|  | Output 5.2: Technical revision and upgrading of Labour Market Information Management System (LMIMS) supported | 5.2.1 Status of the recommendations for technical upgrading of the LMIMS | 2020 Not yet started – to be prepared by the project Note: Only two WorkNet modules so far implemented (Vacancy and Job Seeker portals) | 2023 Recommendations for upgrading elaborated and discussed with MoIDPLHSA/SESA, with implementation proposal for remaining WorkNet modules (by 2021) (Including Enterprise portal with upgraded Vacancy and Job Seeker sub-portals including differentiation of categories of jobseeker -unemployed, employed, social clients | Report on LMIMS upgrade recommendations | Beneficiary institutions remain committed to upgrading the LMIMS Sufficient financial and technical resources are available for implementation of the enterprise portal |
|  |  | 5.2.2 Status of the guidelines on analytical usage of LMIMS | None yet prepared – to be prepared by the project | Draft guidelines elaborated and capacity building activities elaborated and discussed with MoIDPLHA /SESA (2022) | Guideline on using LMIMS for analytical purposes Report on training LMIMS/WorkNet users | LMIMS will be upgraded according to the recommendations |
|  | Output 5.3: Capacity of LMIS team enhanced in analysis, survey and anticipation methods | 5.3.1 Level of capacity of LMIS team in labour market analyses and forecasting | 2020 LMIS team has already some capacity (e.g. LM analyses 2018 and 2019, 2 sector analyses, survey on business demand for skills) | 2023 LMIS team has capacity to undertake different type of surveys (capacity building support started 2020, completed by 2023) | Information on implemented training on the LMIS web portal Training assessment report | Trained personnel will be retained |
|  |  | 5.3.2 Status of draft guidelines on skills anticipation surveys and analysis | None existing – to be supported by the project | Guidelines are used in the generation of LMIS reports (Draft sector skills anticipation guideline; and Draft guideline for all sectors with 5-year perspective: both in 2020) (Other guidelines may be developed on request, 2021, 2022, 2023) | Delivered survey/analysis reports based on the guidelines | Efficient cooperation with relevant industry representatives and GEOSTAT |
|  |  | 5.3.3 Status of concept notes for further developing the LMIS and the LMIS web portal | Concept note for upgrading LMIS and the LMIS web portal not yet elaborated by the project | Concept note for upgrading LMIS to provide new functional opportunities elaborated and presented to MoESD (2020) Proposals for upgrading LMIS web portal elaborated and presented to the beneficiary (2021) If accepted, advisory and technical support has been provided to upgrades of LMIS and LMIS web portal (by 2023) | Finalised concept notes for further developing the LMIS and the LMIS web portal, providing new modules and updating opportunities Technical specifications and Implementation plan for upgrading the LMIS web portal Records of discussions with the beneficiary, endorsement decision | Efficient cooperation with relevant industry representatives and GEOSTAT Sufficient resources will be provided to enable the recommendations to be implemented |
|  | Output 5.4: Enhanced capacity of EMIS to support evidence-based education and training policy making | 5.4.1 Status of review report on content and capacity of EMIS | 2020 Review report not yet prepared | 2023 Review report elaborated, incl. recommendations for filling identified data gaps, and discussed / agreed with EMIS and MoESCS (completed by 2021) | Records of discussions with beneficiaries, endorsement decision Annual progress reports of EMIS | EMIS data coverage is sufficient to meet the needs of education and training policy making without major changes Data from LMIMS and LMIS etc. is shared and available to EMIS analysists Sufficient resources are available for EMIS upgrade |
|  |  | 5.4.2 Status of TA capacity building plan for using EMIS data in evidence-based policy-making | Capacity building plan not yet prepared – to be prepared and implemented by the project | TA capacity building plan developed, agreed and implemented (completed by 2023) | Training assessment report | Trained specialists are retained by beneficiaries Policy-related reports will be generated by EMIS (e.g. incl. socio-economic backgrounds of VET students, VET students with special needs, annual completion rates of VET programmes, etc.) |

|  | Output 5.5 Enhanced capacity of institutions using LMIS, LMIMS and EMIS data in evidence-based policy-making | 5.5.1 Status of capacity assessment report and training plan | 2020 Capacity building assessment/training plan not yet available – to be done by the project | 2023 Capacity of data users (all beneficiary ministries, agencies) assessed, and training plan implemented, with all relevant personnel nominated by the relevant institutions trained (completed 2023) | Records of discussions with beneficiaries, endorsement decision Training assessment reports | Developed methodologies and protocols are incorporated into the internal arrangements of the ministries and agencies, and are actively used in evidence-based policy making Trained personnel are retained by the relevant stakeholders |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | 5.5.2 Status of the survey methodology and pilot surveys proposed for Enterprise Georgia | Survey methodology not yet prepared – to be done by the project | Survey methodology elaborated, presented to Enterprise Georgia and used in the implementation of 2 pilot surveys (completed 2022) | Survey methodology document Records of discussions with beneficiary, endorsement decision Reports of pilot surveys | Trained personnel are retained by Enterprise Georgia |
| COMPONENT 6: GRANT SCHEME MONITORING |  |  |  |  |  |  |

|  | Output 6.1: Grant scheme implementation supported through the monitoring of grant projects | 6.1.1 Status of monitoring reports / recommendations | 2020 None: grant scheme applications are still under evaluation, with selection expected by mid-2020 – contracted projects will be monitored by the project | 2023 6-monthly monitoring reports produced following evaluation of progress reports and monitoring visits (completed by 2023) | Monitoring reports and other feedback provided to EUD | Grantees have the necessary capacity to manage and implement their projects according to contractual requirements Monitoring reports and recommendations are followed up by the EUD with project implementors |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | 6.1.2 Status of the compendium of grant project results and good practices | None: will be compiled towards the end of the grant scheme (2023) – to be done by the project | Compendium produced at the end of the grant scheme according to structure/format agreed with the EUD (2023) | Records of discussions with EUD and formal confirmation of acceptance of monitoring reports and compendium | Compendium is used to inform programming and further interventions |

## Activity Matrix

COMPONENT 1: NATIONAL SECTOR REFORM POLICIES

Output 1.1: Updated national sector reform policies drafted

1.1.1 Analyse policies, strategies and action plans of the MoESCS, MoIDPLHSA, MoESD (incl. their subordinate bodies), and the Youth Agency in the areas of skills development and skills matching to identify gaps and propose areas for improvement

1.1.2 Support updating and/or improvement of policies, strategies and/or action plans in line with national policy planning framework requirements

1.1.3 Assist MoESCS in surveying the geographical coverage of VET provision by municipality, identifying gaps, and recommending solutions and priorities for expanding availability of VET provision through existing institutions and existing or new programmes

1.1.4 Organize annual thematic workshops/events related to sector reform policy development to present/ discuss relevant Georgian and international experiences and practices

1.1.5 Support the strengthening of co-ordinating mechanisms between beneficiary ministries and institutions related to sector reform policy development, implementation and monitoring

1.1.6 Support implementation and further development of monitoring arrangements for sector strategies and action plans, including annual reviews and advisory support to the beneficiary ministries and institutions on achieving targets/performance indicators of the SRPC

1.1.7 Provide administrative and logistical support to EU missions and expert visits to Georgia related to the SRPC

1.1.8 Provide short update and progress reports to the EU Delegation related to the SRPC and its implementation

Output 1.2: Capacities in sector reform policy development, implementation and monitoring enhanced

1.2.1 Develop a comprehensive capacity building programme for the beneficiary ministries and institutions for the whole project duration, related to the requirements of national sector policy development, implementation and monitoring

1.2.2 Monitor and evaluate progress in capacity building for the project beneficiaries and periodically adjust the programme according to emerging needs

Output 1.3: Enhanced capacity to provide vvisibility and communications for sector reform policies and specific services provided by beneficiary institutions

1.3.1 Develop and implement a project communications and visibility plan including measures and related tools and events to promote active stakeholder engagement and raise public awareness in compliance with EU visibility requirements

1.3.2 Prepare communications and visibility materials to support the project communications and visibility plan

1.3.3 Support and monitor communications between project beneficiaries and key stakeholders to ensure effective coordination of sector reform policy-related activities

1.3.4 Coordinate, support and monitor external communications across all components of the TA, in order to raise awareness of sector reform policies and project results among stakeholders and the general public

COMPONENT 2: SKILLS DEVELOPMENT AND ENTREPREEURSHIP LEARNING

Output 2.1: Enhanced capacity of the MoESCS to further develop and modernise skills development and LLL systems

2.1.1 Assist MoESCS in further developing the legal, regulatory and funding framework for VET and LLL

2.1.2 Assist MoESCS in improving access to, and participation in, VET and LLL

Output 2.2: Enhanced capacity of educational institutions to provide professional orientation and career guidance for learners in general, vocational and higher education

2.2.1 Assist MoESCS in developing and improving arrangements for career education and guidance by reviewing current situation, practices and quality in career education, guidance and counselling, and the capacity of institutions in general (upper secondary), vocational and higher education to deliver effective services to students

2.2.2 Develop capacities of schools and colleges in career education and guidance

Output 2.3: Enhanced capacity to deliver entrepreneurship education in general, vocational and higher education and lifelong learning

2.3.1 Support MoESCS in developing a concept note on innovative learning practices in VET in the context of the lifelong entrepreneurial learning strategy

2.3.2 In cooperation with TPDC, design and pilot an in-service training programme for upper secondary teachers on entrepreneurship key competence development within the National Curriculum, based on the relevant EU key competence framework and experience

2.3.3 In cooperation with TPDC, design and pilot an in-service training programme for VET teachers and managers on entrepreneurship key competence development in VET programmes, based on the relevant EU key competence framework and experience

2.3.4 Prepare guidance materials for teachers on new learning methods and approaches to enhance entrepreneurship key competence development

2.3.5 Pilot entrepreneurial experience for students from at least 10 general secondary education schools and VET colleges, and develop a model for replication in the education system

2.3.6 Review the quality and availability of entrepreneurship learning provision in universities/ higher education institutions based on a sample survey, using e.g. online/self-assessment, interviews, focus groups

2.3.7 Organize at least 2 pilots to enhance entrepreneurship learning in universities to identify good practices that work in the Georgian context, and disseminate results to the higher education community

COMPONENT 3: YOUTH

Output 3.1: Enhanced capacity of Youth Agency to develop and deliver effective youth services

3.1.1 Assist the Youth Agency in organizational development, national youth law drafting, national strategy and action planning, for improvement and delivery of youth services in the regions

3.1.2 Assess capacity building and support needs of Youth Agency staff and design and deliver a training plan and coaching scheme

3.1.3 Organize a study visit to EU member state(s) to observe best practices in the field of youth policy and youth services delivery

3.1.4 Support the Youth Agency in Improving coordination and cooperation arrangements with other agencies and stakeholders including local government and organizations in the regions

3.1.5 Review current youth activation services delivery and support the Agency in revising/updating, implementing and monitoring youth activation measures across the regions in cooperation with relevant stakeholders

3.1.6 Review career orientation and guidance services provision for youth across the regions, and support the Agency in revising/developing and piloting more effective services, with guidance materials for planning, implementing, monitoring and evaluating provision

- Review non-formal education and training provision for youth, and support the Youth Agency in developing high quality training courses targeting employability/social needs and improving access, supported by manuals and materials for planning, developing delivering and monitoring/evaluating training provision

3.1.8 Review social entrepreneurship measures for youth and support the Youth Agency in developing and piloting innovative approaches to youth entrepreneurship

3.1.9 Assist the Youth Agency and youth centres in selected regions to increase public awareness of youth services including youth activation measures and social entrepreneurship (linked with Result 1.3)

Output 3.2: Improved organizational and human capacities to deliver youth services at local level

3.2.1 Assess the organizational capacities of selected youth services providers in targeted regions, and support preparation of institutional development/improvement plans to help them in action planning, self-assessment and increasing the effectiveness of youth services delivery

3.2.2 Assess the capacity building and training needs of youth workers (from youth services providers in the regions), and with appropriate arrangements put in place to ensure their training, qualifications and professionalization

COMPONENT 4: EMPLOYMENT SERVICES

Output 4.1: State Employment Agency (SESA) supported in its implementation of the Revised New Service Model (NSM)

4.1.1 Assess how the current system of the NSM has functioned within the local offices and regional centres of the previous SSA/ESS, identifying main lessons learnt and issues for improvement, in order to upgrade, revise and support the implementation of the New Service Model (NSM)

4.1.2 Advise MoIDPLHSA on the institutional development of the new Legal Entity of Public Law (LEPL) Employment Support Agency (ESA)

4.1.3 Develop detailed instructional materials for NSM work methodology

4.1.4 Develop an implementation strategy for improving links with local employers/companies as well as local government institutions in the regions

4.1.5 Develop procedures and guidance materials for planning, implementing, monitoring and evaluation of employment services provided

4.1.6 Develop proposals for increasing public awareness of employment services (linked with Result 1.3 above)

Output 4.2: SESA supported in designing and delivering more accessible, effective and comprehensive ALMP measures available for all job seekers

4.2.1 Assess how the current system of ALMP measures functions within the different regional centres and local offices of ESA, main lessons learnt and issues for improvement

4.2.2 Develop a detailed proposal for the upgrade and revision of all types of ALMP

4.2.3 Develop procedures and guidance materials for planning, implementation, monitoring and evaluation of all types of ALMP measures

4.2.4 Develop a detailed proposal for revised/redesigned career guidance/ counselling for jobseekers both in terms of content and delivery methods, including linkages with institutions which provide similar services

4.2.5 Propose and organize 1-2 pilot programmes of new ALMP measures for jobseekers, to review the pilots and, based on the experience, to develop a model that can be replicated in the employment support services in the regions

Output 4.3: Capacity (knowledge and expertise) developed within the ESA staff to provide more effective employment services for jobseekers and employers

4.3.1 Carry out an induction training and assess training needs of the ESA staff in the field of NSM, implementation of all types of ALMP measures, provision of career guidance and counselling services for jobseekers, and the use of upgraded LMIMS portal

4.3.2 Design a training plan (short and long term) on all the issues above for the staff of ESA and other relevant institutions

4.3.3 Organize training measures based on training plan

4.3.4 Organize a study visit to EU member state(s) to observe best practices in the fields of public employment services

4.3.5 Facilitate the exchange of experience and good practice on delivery of modern public employment services with European peers and nationally

4.3.6 Develop a coaching scheme for the staff of ESA and other relevant institutions and pilot it after the provision of training programmes

COMPONENT 5: INFORMATION SYSTEMS AND ANALYSIS

Output 5.1: Improved integrity and compatibility of data and information systems for evidence-based policy making and implementation

5.1.1 Analyse the specifications (technical and content-related) of the main information systems (EMIS, LMIS, LMIMS, job search portals), assess their scope for inter-connectivity, and prepare detailed proposals for sharing data between them

5.1.2 Provide advisory technical support to the up-grading of data systems to achieve the necessary linking of main data systems

Output 5.2: Technical revision and upgrading of the Labour Market Information Management System (LMIMS) supported

5.2.1 Develop detailed proposals to upgrade the LMIMS portal (software and hardware) including increased information content and enabling the unemployed to be distinguished from job-seekers

5.2.2 Develop procedure and guidance manuals for use of LMIMS as intranet, as well as for analysis of public employment services data

Output 5.3: Capacity of Labour Market Information System (LMIS) team enhanced in analysis, survey and anticipation methods

5.3.1 Provide Guidelines and related capacity building to the LMIS team to collect, analyze and disseminate labour market information and monitor labour market developments

5.3.2 Increase public awareness and visibility of the LMIS (linked with Result 1.3)

Output 5.4: Enhanced capacity of EMIS to support evidence-based education and training policy making

5.4.1 Assess the capacity of the EMIS database to meet the requirements of evidence-based policy making

5.4.2 Develop capacity of EMIS staff to support evidence-based policy making

Output 5.5: Enhanced capacity of institutions using LMIS, LMIMS and EMIS data in evidence-based policy making

5.5.1 Assess the capacity of potential data users to effectively use data in evidence-based policy

5.5.2 Develop and implement training and coaching programme for data users

5.5.3 Disseminate the results of data analyses to relevant stakeholders, through information workshops on use of data in evidence-based policy making

5.5.4 Support Enterprise Georgia in analysing skill needs for SME development in selected sectors and link them with relevant training provision

5.5.5 Support MoIDPLHSA in surveying the health care sector, including the numbers of people qualified and employed in primary health care and hospitals, to identify skills needs and capacity of potential training providers

COMPONENT 6: MONITOR GRANT SCHEME IMPLEMENTATION

Output 6.1: Grant scheme implementation supported through the monitoring of grant projects

6.1.1 Provide technical, implementation and monitoring support to the Grant Scheme

6.1.2 Support preparation of a compendium of grant projects’ results, including good practices identified for possible replication

# Revised Implementation Timetable

See the table provided at ANNEX 2.

# Project Management issues

## Resource utilisation

As noted in various places in this report, the available resources are very tight for implementation of such a large and complex TA project, and the scope of some of the Outputs and Activities has been increased as a result of Inception Phase consultations. (See, for example, the table at the beginning of Chapter 3). The following paragraphs set out our estimates of how best to utilise the available resources.

### Deployment of Key Experts and Long-term Non-Key Experts by Component

Our provisional deployment of key and long-term non-key experts by component is as follows:

| Position | Name | IP/PM | C1 | C2 | C3 | C4 | C5 | C6 | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| TL/ KE1 | D. Handley | 100 | 170 | 220 | 206 | 37 | 37 | 30 | 800 |
| KE2 | H. Duffner | 70 | 50 | 40 | 40 | 460 | 60 | 50 | 770 |
| KE3 | C. Møller | 22 | 46 | 0 | 0 | 32 | 200 | 0 | 300 |

Abbreviation: IP/PM = Inception Phase, Project Management (incl. reporting and closure)

### Non-key Experts

The Consortium’s proposal provided for:

- Senior experts: 850 working days (WD)

- Junior experts:  1,250 working days (WD)

The following have already been appointed during the Inception Period:

- Long-term Junior Non-Key Expert in Skills matching: 520 WD

- Long-term Junior Non-Key Expert in Skills Development: 420 WD

- Long-term Junior Non-Key Expert in Communications and Visibility: 80 WD

The remaining balance of Junior Non-Key Expert working days available for allocation is 230.

We are not yet in a position to precisely allocate working days for Non-Key Experts. However, we consider that the following senior short-term positions may be required:

| Position | Est. W/D |
| --- | --- |
| - Senior NKE for entrepreneurship learning, incl. training and capacity building (Comp. 2 / 3) - Senior NKE(s) for career orientation, guidance and counselling, incl. training and capacity building (Components 2, 3 and 4) - Senior NKE for advisory and capacity building support to youth services development and delivery (Component 3) - Senior NKE for capacity building and training for employment services (Component 4) - Senior NKE for local employment partnerships development (Component 4) - Senior NKE for database development and networking of data (Component 5) - Senior NKE in survey methodology and analysis (Component 5) - Senior NKE for grant scheme monitoring (Component 6) | 130 150 120 120 80 100 50 100 |

We also estimate the following need for junior NKEs:

| Position | Est. W/D |
| --- | --- |
| - Junior NKE for checking legal terminology in drafted by-laws/regulations (Components 1 / 2) - Junior NKE for entrepreneurship teacher and trainer training (Component 2) - Junior NKE in youth work, and support to youth centres (Component 3) - Junior NKE for grant scheme monitoring (Component 6) | 20 80 80 50 |

It should be noted that the increased scope of some of the Results and Activities in the project log frame (detailed above) has some implications for the allocation of working days for some of these positions, and the estimated numbers of days represent the bare minimum that may be necessary.

### Incidental Expenditures

The provision for incidental expenditure for this contract is EUR 850.000. It covers ancillary and exceptional eligible expenditure incurred under this contract. The following table sets out our proposals for provisional allocation of the incidentals budget.

| Category | Comment | Provisional amount |
| --- | --- | --- |
| - Travel costs and subsistence allowances for missions outside the normal place of posting | Experts’ travel to regions in Georgia Estimated average costs/month (over 40 months): 150 person/trips @ 130 euro/person/trip (Travel, Per diems) | 20,000 euro |
| - Training, seminars, workshops and conferences costs. | Estimate: C1: 14 events, 235 person/days C2: 24 events, 500 person/days C3: 21 events, 420 person/days C4: 18 events, 680 person/days C5: 8 events, 130 person/days C6: 1 event, 15 person/days Unallocated: 20 person/days Total: 107 events, 2000 person/days Average cost/person = 20 euro (incl. both events in Tbilisi and in the regions) | 470,000 euro |
| - Participation fees or travel costs of beneficiary ministry staff or other relevant stakeholders in international events | Nothing planned – contingency amount | 10,000 euro |
| - Study tours, including the cost of training services to be provided to Georgian participants by the host organisations. | Estimate assumes: No. of study tours:2 Duration of each: 1 week (5 working days) Destination: Riga or alternative location No. of participants on each: 10, total 20 (Incl. flights, transfers, per diems, interpretation, materials, charges by organizations visited) | 60,000 euro |
| - Publication and dissemination of different kinds of manuals, methodological and guidance materials (incl. survey results), as well as brochures and promotional materials for the services produced within the project. | Publications: Leaflets/info. materials: Manuals/guidance materials: Banners: | 30,000 euro |
| - Costs related to communication and project visibility: media activities, products. The possibility of sub-contracting some activities to an appropriate PR company may also be considered. | Website/soc. Media, Events, campaigns, (All components) – see Communications Plan | 250,000 euro |
| - Translation/proof-reading of English/Georgian of official EU documents | Needs not yet assessed | 10,000 euro |
|  | Total | 850,000 euro |

## Project Steering Committee

The Steering Committee shall be set up to oversee and validate the overall direction and policy of the project. The Steering Committee shall meet at least twice a year and may be chaired by a Deputy Minister from the MoESCS or the MoIDPLHSA on a rotating basis.

Members of the Steering Committee:

The project Steering Committee will be made up of representatives of the main project stakeholders as follows:

MoESCS:

Ms T. Kitiashvili (Deputy Minister)

Ms I. Tserodze (Head of VET Department)

Ms L. Kalandadze (Head of General Education Department)

Ms N. Tsereteli (Head of Higher Education Department)

Mr K. Khandolishvili (Head of International Relations Department and overall project coordinator)

Youth Agency:

Mr R. Charkviani (Head)

Ms K. Kapanadze (Deputy Head)

MoIDPLHSA:

Ms T. Barkalaia (Deputy Minister)

Ms L. Klimiashvili (Head of Labour Relations & Social Partnership Division, Labour & Employment Policy Dept.)

Employment Support Agency (ESA);

Ms N. Veltauri (Deputy Director)

MoESD:

Ms E. Mikabadze (Deputy Minister)

Ms T. Sabadze (Head of Economic Policy Department)

Mr G. Gamkrelidze (Hear of Labour Market Analysis Division, Economic Policy Department)

EMIS:

Mr. D. Beridze (Director)

TPDC:

Ms B. Shukakidze (Director)

GEA:

Mr. E. Meladze (President)

GTUC:

Mr I. Petriashvili (President)

GCCI:

Mr G. Pertaia (President)

EUD

Ms C. de Mercey (Attaché - Team Leader, Governance and Human Capital)

Ms N. Kochishvili (Programme Officer - Task Manager)

Ms. J. Juodsnukyte (Attaché- Programme Officer)

Ms. N. Samvelidze (Programme Officer)

Technical Assistance Team:

The Team Leader (Mr D. Handley), Key Experts (Mr H. Duffner and Mr C. Møller), and (if required) long-term Non-Key Experts (Ms A. Kitiashvili and Ms A. Diakonidze), will attend Steering Committee meetings to report on, and answer questions on, their respective activities. The Technical Assistance Team will also provide the Secretariat and administrative support to meetings of the Steering Committee including preparation of agendas and minutes and the issuing of invitations to meetings.

Observers:

In addition, the following may attend meetings of the Steering Committee as Observers:

ETF: Mr T. Kuusela, Ms U. Bardak, Ms O. Bekh

EU PAR TA: Mr J. Wisniewski

Resident Twinning Adviser, NCEQE: Mr. C. Etzold

Resident Twinning Adviser, MoIDPLHSA: Ms. V. Kubalova

GOPA: Mr N. Sapundzhiev (Project Director), Ms Elena Friesen (Project Manager)

Various international organisations and donors in the areas of education & training, youth and employment will also be invited to nominate an Observer by agreement between the Contracting Authority, Contractor and Beneficiary.

## Reporting

The following reports are required under the ToR:

| Name of report | Content | Time of submission |
| --- | --- | --- |
| Inception Report | Review of project purpose, anticipated results and planned activities to ensure that the project design remains relevant and to suggest a refocusing of activities where appropriate. A detailed explication of the project implementation and management strategy. An overall and Annual Work Plan. A revised resource utilization chart, results schedules and an updated Project Log frame. Work Plan for the next reporting period. | No later than 3 months after the start of implementation |
| 6-month Progress Report | A description of overall project progress to date measured against the previous, Annual, Overall and reporting Period Work Plans, and against the Objectively verifiable Indicators. Deviations from the Work Plan with explanations, if any. Resource utilization charts indicating inputs (volume and value) and measures against outputs and results. Problems encountered likely to inhibit achievement of project results/solutions adopted. Identification of factors likely inhibit achievement of Project Purpose /proposed solutions. The Interim Progress Reports will include as Annexes all technical reports, trainings’, workshops’, seminars’ study visits’ programmes, presentations, signed list of participants and participants’ evaluations, public awareness and dissemination materials etc. produced during the reporting period. Period invoice and/or final report. | No later than 1 month after the end of each 6-month implementation period. |
| Draft Final Report | Content – see below. | No later than 1 month before the end of the implementation period. |
| Final Report | Description of the activities carried out and outputs delivered measured against the time/input plan. An analysis of results achieved, measured against the ToR and the Objectively Verifiable Indicators of Achievement contained in the project Log frame. An analysis of the achievement of the Project Purpose measured against the objectively verifiable Indicators of Achievement contained in the project Log frame. An assessment of the sustainability and probable impact of the assistance provided. A detailed description of the resource utilization against results. Copies of all project outputs. An updated financial report containing details of the time inputs of the experts and of the incidental expenditures. Final invoice and expenditure verification report. | Within 1 month of receiving comments on the draft final report from the Project Manager identified in the contract. |

# Annex 1: List of Inception Period Consultation Meetings and Events

Consultation meetings during the Inception Phases

| Date | Institution, persons met | Issues discussed | Attended |
| --- | --- | --- | --- |
| 07.10.2019 | EUD (N. KOCHISHVILI, J. Juodsnukyte, K. Gvatadze) | Kick-off meeting- full range of administrative and financial issues | TL, KE2, KE3, GOPA/PEM project managers, auditor |
| 08.10.2019 | MoIDPLHSA (L. Klimiashvili, T.Rurua) | Introductory meeting with project coordinator and reps of MoIDPLHSA | TL, KE2, KE3, GOPA Project Managers |
| 08.10.2019 | MoESCS (K. Kahdolisvhili, T. Samkharadze, N. Tsereteli) | Introductory meeting with project coordinator and reps of MoESCS VET and HE departments | TL, KE2, KE3, GOPA Project Managers |
| 09.10.2019 | MoESD (T. Sabadze, G. Gamkrelidze) | Introductory meeting with counterparts in MoESD | TL, KE2, KE3, GOPA Project Managers |
| 15.10.2019 | MoIDPLHSA (DM T, Barkalaia with L. Klimiashvili, T. Rurua, P. Chiviashvili, N. Agashenashvili, B. Lortkianidze, M. Bezarashvili, I. Gelashvili, and N. Kochishvili EUD | First meeting with DM, and presentation of project | TL, KE2, KE3 |
| 16.10.2019 | MoESD (T. Sabadze, G. Gamkrelidze, G. Kapanadze | Meeting to discuss further development of LMIS | TL, KE2, KE3 |
| 17.10.2019 | Meeting with M. Jajanidze, Parliamentary Gender Commission, at EUD | Meeting to discuss gender issues in Skills4Jobs Programme | TL |
| 24.10.2019 | MoESCS (I. Tserodze, T. Samkharadze) | Discussion re project ToR and MoESCS expectations | TL, KE2, KE3 |
| 25.10.2019 | MoESD (First DM E. Mikabadze, T. Sabadze, G. Gamkrelidze) and N. Kochishvili EUD | First meeting with DM and presentation on LMIS development issues | TL, KE2, KE3 |
| 28.10.2019 | ETF (T. Kuusela, U. Bardak, T. Siprashvili) and EUD (N. Kochishvili, N. Samvelidze) | Discussion re. state of play regarding VET and labour market issues | TL, KE2, KE3 |
| 29.10.2019 | GCCI (M. Bolotashvili) during Launch event | Discussion re. role of GCCI and business interests, social partne5rship | KE3 |
| 31.10.2019 | Youth Agency (R. Charkviani, K. Kapanadze, K. Karumitze, S. Shiukashvili) and N. Samvelidze EUD | Introductory meeting with Youth Agency management, and exchange of information | TL, KE2 |
| 01.11.2019 | UNIDO (G. Todua, T. Lomitashvili) | Discussion about youth employment issues | TL, KE2 |
| 01.11.2019 | GIZ (J. Strittmatter) | Exchange of information re. projects | TL, KE2 |
| 11.11.2019 | Meeting with R. Chanturia, consultant to ADB and USAID | Briefing on ADB project preparation and on USAID PITA program | TL |
| 05.11.2019 | Youth Agency (K. Karumitze, S. Shiukashvili) | Discussion about youth centres, youth work | TL, KE2 |
| 08.11.2019 | SSA/ESS (M. Bezarashvili HoD, and B. Lortkipanidze, N. Agashenashvili, P. Chiviashvili, M. Chochitashvili, L. Galumashvili) | Fact-finding about existing employment services, LMIMS etc.) | KE2 |
| 08.11.2019 | MoIDPLHSA (T. Barkalaia, T. Rurua) | Follow-up meeting with DM re MoIDPLHSA expectations | KE2 |
| 13.11.2019 | TA to GCCI (K. Gerber) | Exchange re. business involvement in VET | TL, KE2 |
| 21.11.2019 | EU Twinning Project (C. Etzold), NCEQE, K. Kahdolisvhili MoESCS), N. Kochishvili EUD | Exchange of information about developments incl. update on NCEQE and change of DM | TL |
| 25.11.2019 | EU Twinning Project – MoIDPLHSA (V. Kubalova) | Exchange of information | KE2 |
| 27.11.2019 | MoESCS (DM T. Kitiashvili, I. Tserodze, M. Zakareishvili) & N. Kochishvili (EUD) | First discussion with new DM re priorities | TL |
| 03.12 2019 | EU Agencies (N. Zakareishvili UNFPA, N. Pruidze UNICEF, G. Todua UNIDO) | Briefing and discussion about the UN’s support to Youth Policy development | TL |
| 04.12.2019 | Meeting with N. Dvalidze, independent consultant | Briefing on previous entrepreneurship education initiatives | TL |
| 10.12.2019 | Meeting with EU Review Team (P. Tasker, Y. Sofianopoulos, Y. Danbakli) | Discussion re. progress on Budget Support OVIs | TL, KE2 |
| 10.12.2019 | Meeting with both EU Twinning Projects (C. Erzold, V. Kubalova), N. Kochishvili, N. Samvelidze) at EUD | Sharing of information about projects | TL |
| 10.12.2019 | Meeting with M. Kuchuloria, European Business Association | Provision of information about the project, discussion about business involvement in VET | TL, KE2 |
| 10.12.2019 | ADB Planning Team (H. Sonneveld, R. Chanturia) | Detailed exchange of information | TL, LTNKE Skills Devt. |
| 16.12.2019 | Meeting with J. Juodsnukyte EUD | Progress discussion on labour market issues | TL, KE2 |
| 17.12.2019 | Meeting with EMIS (D. Beridze, M. Simonidze and project managers) | Introductory meeting and discussion about EMIS-related activities | TL, LTNKE Skills Devt. |
| 18.12.2019 | Meeting – MoESCS General Education Dept. (K. Chkhobadze) | Discussion re. entrepreneurship, key competences and career education and guidance in general education | TL, LTNKE Skills Devt. |
| 18.12.2019 | Meeting – MoESCS VET Dept. (G. Lomiashvili) | Briefing on MoESCS expectations for study on extending VET provision across all municipalities | TL, LTNKE Skills Devt. |
| 19.12.2019 | Meeting with ILO (K. Albahnasi) | Fact-finding about LM issues and relevant activities of ILO | KE2 |
| 19.12.2019 | Meeting with GITA – Mariam Lashki | Discussion re. entrepreneurship learning | TL, LTNKE Skills Devt. |
| 19.12.2019 | Meeting with T. Gabunia, DM for Health (with N. Kochishvili EUD) | Meeting re. medical education – need for sector survey to identify numbers of qualified personnel, geographical distribution, training needs | TL, LTNKE Skills Devt. |
| 19.12.2019 | Meeting with TPDC (N. Elbakidze, M. Ghambashidze) | Discussion on training of VET teachers, career managers etc. on career education and guidance, entrepreneurship learning | TL |
| 20.12.2019 | Meeting with J. Wisniewski, PAR programme expert | Discussion re. education strategy and overall situation in VET and employment | TL, KE2 |
| 24.12.2019 | Meeting with UN Women (Nani Bendeliani) | Briefing on women’s employment issues | KE2 |
| 25.12.2019 | Meeting with Friedrich Ebert Stiftung (FES) | Fact-finding visit to pilot model employment office in Nadzaladevi District, Tbilisi | KE2, LTNKE Skills Matching |
| 15.01.2020 | Meeting at Spektri Community College, Tbilisi | Briefing about VET marketing events/ activities including school “VET clubs” | TL |
| 16.01.2020 | Follow-up meeting with F. Hett, local director of FES | Exchange of information and discussion about possible cooperation | KE2 |
| 16.01.2020 | Meeting with full ADB project team | Exchange of information | TL, KE2, LTNKE Skills Development |
| 17.01.2020 | Meeting with IOM (N. Kvitsiani) | Briefing on migration, employment information and training, discussion on cooperation opportunities | KE2 |
| 20.01.2020 | Meeting with deputy head of SESA (N. Veltauri) | Initial information exchange | TL, KE2 |
| 22.02.2020 | Meeting with R. Javeladze, TL Youth Engagement (RDFG) | Discussion about youth work, youth services in Georgia | TL, LTNKE Skills Development |
| 22.01.2020 | Meeting with MoESCS (DM T. Kitiashvili, I. Tserodze and G. Lomiashvili) | Discussion about proposed survey/ mapping of VET institutions in all regions | TL, LTNKE Skills Development |
| 30.01.2020 | Meeting with USAID (M. Kutateladze) | Discussion about upcoming programme | TL, LTNKE Skills Development |

In addition to the meetings listed above, project representatives attended the following events in Tbilisi during the Inception period, as follows:

Related Events attended during the Inception Phase

| Date | Event | Attended |
| --- | --- | --- |
| 29.10.2019 | Skills4Jobs Launch Event at Gldani College (incl. presentation by TL) | TL, KE2, KE3 |
| 30.10.2019 | ETF Torino Process Workshop at Radisson Blu, Tbilisi | TL, KE2, KE3 |
| 04.11.2019 | EU4Youth Programme Presentation of Labour Market Analysis, Holiday Inn | KE2 |
| 18.11.2019 | UNDP Workshop on Sector Skills Organization proposals, Lolita Rooms | TL |
| 25.11.2019 | EUD Visibility Training Session, Biltmore Hotel | TL |
| 26.11.2019 | Life-Long Entrepreneurship Learning (LLEPL) Working Group at MoESCS | TL |
| 05.12.2019 | DC dVET Workshop on Work-based Learning at GIZ | TL |
| 06.12.2019 | Skills4Jobs Steering Committee at MoESCS | KE2 |
| 10.12.2019 | ETF Workshop: Entrepreneurial VET, Radisson Blu, Tbilisi | TL |
| 13.12.2019 | PAR Key Competences Workshop and presentation at EUD | TL |
| 15.12.2019 | VET Donors meeting at GIZ | TL |
| 19.12.2019 | World Bank/GGF consultation meeting of draft teaching standards | LTNKE Skills Devt. |
| 24.12.2019 | Information event about establishment of the SESA, Wyndham Grand, Tbilisi | KE2, LTNKE Skills Matching |

# Annex 2: Revised Implementation Timetable

The term “Output” is preferred to “Result” in the latest EU log frame methodology

Recommendations and capacity building will include gender-sensitising strategic/policy documents (by including gender-disaggregated data etc.) and the training provided should therefore include relevant gender aspects, as well as other cross-cutting themes (human rights etc.)

2017 amendment to the ministerial decree No. 141 dated 20 May 2010 on the Establishment of Rules for Assessing the Socio-Economic status of the socially vulnerable families

One candidate could be the Local Economy Forecasting Model (LEFM) developed by Cambridge Econometrics and the Warwick Institute for Employment Research (https://warwick.ac.uk/fac/soc/ier/software/lefm/) (see Result 5.3).

https://ec.europa.eu/eurostat/documents/3859598/5935673/KS-GQ-13-002-EN.PDF

ETF WP 2014 Country Project Georgia; Concept note on Labour Market Information System in Georgia.

EU EVET project: ’Proposal of an IT LMIS System’ and ‘Proposal for Forecasting the Labour Market’ 2018

https://www.nbg.gov.ge/uploads/publications/fpas/FPAS%20Documentation.pdf

https://warwick.ac.uk/fac/soc/ier/software/lefm/

See ETF: ‘Developing skills foresights, scenarios and forecasts’, Volume 2

www.worknet.gov.ge

# Review report of the current WorkNet information system, 2015

https://agenda.ge/en/news/2019/13. from 2020 all formally employed persons (Personal Identification code and ISCO), employers for these employees (VAT and NACE code) plus the state will pay a small contribution to this this fund, which will enable tracer studies on the employment rate of graduates.

ISCO 08 is already implemented

EVET report on Existing Data in Georgian Vocational Education, 2019

State targeted assistance is sometimes considered to be a barrier for some people accessing labour market, and the ILO is conducting a study/survey and will advise the GoG on this question.