Report on implementation of the indicator of 2019

Goal N2:  Increase of career development and counseling, mediation services and labour market integration services.

Indicator 2.1:  Distribution of a New Employment Service Model in the territorial units of the Social Service Agency.

Aim of Indicator:  The New Employment Service Model covers at least 30% of SSA / ESS territorial units (requires the involvement of 21 territorial units).

Baseline: In 2017, The New Employment Service Model was implemented in 15 (21%) territorial units out of 70 (Tbilisi - 5, Kakheti - 3, Imereti - 4 and Samegrelo-Zemo Svaneti - 3 Service Centers)

In 2019, the Employment Programs Department carried out the following activities for the introduction of the New Service Model in the territorial units and for the implementation of the indicator:

I - Allocation /redistribution of human resources at the regional and district level:

By the end of 2018 and in July 2019, in order to ensure fulfillment of obligations and provision employment support services, several reports on strengthening the human resources in charge of the employment component and expanding staff units in 7 regional centers of the Agency were presented to the Director of the Agency.

II - Organizing trainings for employees at the regional and district level:

In order to develop employment support services, in 2019, trainings and workshops were conducted for the employees working on the employment component.

In particular:

- A working meeting with supportive employment consultants to improve and develop professional skills was held.

- Training for professionals with continuous professional counseling and career planning to improve service delivery and provide more efficient delivery was conducted.

- Two days training for territorial unit employees working on the employment component was conducted in order to effectively implement the state program of vocational training and retraining and raising qualifications.

- A training seminar for consultants working with job seekers to provide services and development of services within the framework of the new service model in order to facilitate employment was held.

- A working meeting / seminar for employees working with employers on the implementation of the Employment Promotion Services Development Program for 2019 and the action plans for 2019 was held.

- A working meeting with the specialists working on the employment component (within the framework of the New Service Model) to discuss the problematic issues raised in the process and to issue appropriate recommendations was held. Also, for those territorial units where the New Service Model is not being implemented, were presented with primary information and new service model manuals to better understand the methodology.

III - Approval of new service model manuals:

From December 2019, in 6 service centers of the Agency (Kakheti - Akhmeta Service Center, Imereti – Tskaltubo, Tkibuli and Sachkhere Service Centers, Samegrelo-Zemo Svaneti -Martvili Service Center and Guria - Ozurgeti Service Center) employees working on employment component were identified and trained by the relevant regions.

Also, according to the order N04-2412 /ო 03.12.19 of the Director of the LEPL - Social Service Agency in order to introduce a new methodology for employment support services, the following manuals/guides were approved:

a) Methodological manual for providing services to job seekers;

b) Methodological guide and accompanying procedures for providing services to employers;

c) Methodological guide for group consultation session.

As a result, the service manuals approved by the New Service Model are implemented in the service centers of Tbilisi, Imereti, Samegrelo-Zemo Svaneti, Kakheti and Guria regional centers, as well as Samtredia, Zestaponi, Khoni, Tskaltubo, Tkibuli, Sachkhere, Poti, Senaki , Sagarejo, Sighnaghi and Akhmeta Regional departments.