UPDATED LOGICAL FRAMEWORK, Project title: Improving the standards of employment conditions/relations as well as health and safety at work in Georgia

| Intervention logic | Description | Indicators (with relevant baseline and target data) | Sources of verification | Risks | Assumptions (external to project) |
| --- | --- | --- | --- | --- | --- |
| Overall Objective | The overall objective of the project is to support higher standards in employment relationship and working conditions in Georgia through improving legal framework and enforcing implementation. | - Improved employment relations and health and safety standards at work for Georgian employees and enterprises | - Reports, including the EC Progress reports - Comparative international studies - National statistics and reports |  |  |
| Specific (Project) Objective(s) | The specific objective of the project is to assist the MoIDPLHSA, together with other relevant stakeholders, to draft the legal and administrative provisions and establish the institutional mechanisms to improve employment conditions/ relations and Occupational Safety and Health, including a labour inspection system. Additionally, to strengthen the capacity of the national institutions to implement and adopt the best European practices. | - Degree of compliance of the relevant Georgian legislation with the Union acquis; - Legal, administrative and institutional mechanisms for improved employment relations and health and safety standards at work are in place and operational. | Project documentation (list of various meetings, list of participants from various meetings, training programmes, training materials, list of trainees, interim project reports, etc.); Project documentation: legal analysis reports, administrative/ institutional analysis reports, quality and cost assessment reports, training needs assessments, recommendations, etc.); Translated Georgian versions of the all labour legislation acquis covered by the project; Operational plans and procedures, implementation manuals and guidelines; Promotional materials, links to public information tools; Mission reports, participants’ list, and/or training lists; Project interim and final reports. | L/M Decrease of commitment and support of all governmental bodies of the Georgia and other involved stakeholders to the process of fulfilment of AA/DCFTA requirement | Government commitment on the fulfilment of AA/ DCFTA requirements continued; Strong support and commitment from the senior management of the MoIDPLHSA; Strong support and commitment from twinning partner(s); Relevant staff of the MoIDPLHSA and other stakeholder representatives available and involved in the process. |
| Mandatory results/outputs by Components |  |  |  |  |  |
|  | Mandatory result 1: Approximation of primary and secondary legislation related to labour law, gender equality and OSH in accordance with the Union acquis | - The legal basis allowing for a labour inspection system covering standard labour rights and working conditions elaborated; - Legal amendments prepared in the field of Labour Law, Gender Equality, and Occupational Safety and Health as per Union acquis, with an inclusive and evidence-based approach. | Reports of the MoIDPLHSA; Monitoring/assessment reports by international organisations such as ILO; EU-Georgia Association Agenda implementation report. | Inadequate commitment and support from decision making level in particular with regard to adoption of amended legislation, draft acts, guidelines and procedures | Government commitment on the fulfilment of AA/ DCFTA requirements continued; Strong support and commitment from the senior management of the MoLHSA; Availability of local staff; Good communication between the Beneficiary and other stakeholders; Twinning MS partner(s) commitment; All relevant national documentation available. |
|  | Mandatory result 2: Capacity building, inter-institutional cooperation, and awareness raising of relevant state authorities and private sector for full implementation of amended legislation in labour law, gender equality and OSH | - Operational plans and administrative procedures of the MoIDPLHSA and other relevant stakeholders amended in accordance with the new requirements; - The relevant staff of the MoIDPLHSA and other stakeholder representatives trained for the implementation of new legal framework. | Reports of the MoIDPLHSA; Monitoring/assessment reports by international organisations such as ILO; EU-Georgia Association Agenda implementation report. | L/M No sufficient cooperation among all involved Georgian stakeholders | Government commitment on the fulfilment of AA/ DCFTA requirements continued; Strong support and commitment from the senior management of the MoLHSA; Availability of local staff; Good communication between the Beneficiary and other stakeholders; Twinning MS partner(s) commitment; All relevant national documentation available. |
| Sub-results per component (optional and indicative | Sub-result 1.1: Legal framework on labour law, including aspects of labour inspection system, amended in compliance with the Union acquis Sub-result 1.2: Legal framework on non-discrimination and gender equality, including aspects of labour inspection system, amended in compliance with the Union acquis Sub-result 1.3: Legal framework on OSH, including aspects of labour inspection system, amended in compliance with the Union acquis Sub-result 2.1: Analysis for strengthening state authorities’ capacity for implementation of the EU best practices performed and required strategies developed Sub-result 2.2: Implementation of the EU best practices regarding the amended legislation piloted and awareness of the citizens and private sector on the topic increased Sub-result 2.3: Organisation of working group(s) on labour law, gender equality and OSH comprising line ministries and social partners completed and functional | Number of the Tables of Concordance prepared for the Labour Law acquis, including aspects of labour inspection system Baseline: 4 Target: 8 Directives List of amendments to be made in the Georgian primary and secondary labour legislation specified with explanatory notes Baseline: 3 Target: 8 Directives List of amendments to be made in the Georgian primary and secondary legislation on Gender Equality acquis specified with explanatory notes Baseline: 3 Target: 3 Directives Share of staff from relevant public institutions who are fully informed on regulatory and fiscal impact of changes in labour law and gender equality acquis Baseline: 0 Target: 90% of staff in LCID and LEPD Availability of quality checked translation of the OSH acquis with clear technical terminology (if necessary) Baseline: 9 Target: 15 Directives Availability of the Tables of Concordance prepared for the OSH acquis, including aspects of labour inspection system Baseline: 5 Target: 15 Directives Availability of the list of amendments to be made in the Georgian primary and secondary OSH legislation specified with explanatory notes Baseline: 2 Target: 15 Directives Share of staff from relevant public institutions who are fully informed on regulatory and fiscal impact of changes in OSH acquis Baseline: 0 Target: 90% of staff in LCID and LEPD Functional review of the relevant state authorities to implement changes, including human and financial resources, administrative structures and equipment needed Baseline: 0 Target: 1 Training needs analysis and plan of the whole staff of beneficiary department and representatives from other relevant institutions listed Baseline: 0 Target: 1 Share of BA staff who received training to implement necessary changes and the representatives from other relevant institutions listed Baseline: 10% Target: 90% of staff in BA and others Number of labour inspectors who are trained more to become ‘trainers’ with full knowledge and competency in implementing new laws Baseline: 0 Target: 5 Plan for improving institutional operations and procedures of the relevant state authorities to support their pilot implementation, each with clear competences and coordination roles Baseline: 0 Target: 1 Number of written operational guidelines, manuals and procedures required to implement all changes, explaining all steps of implementation to the relevant staff Baseline: 0 Target: At least 15 documents(*) Number of OSH online Glossary and Risk Assessment checklists and their dissemination to relevant parties Baseline: 0 Target: At least 20 (*) Number of elaborated promotional materials and public information campaigns in printed and online media, TV and other tools Baseline: 5 Target: 30 short written materials + 2 public campaigns (*) Share of private companies (i.e. both employers and workers) which are informed and number of citizens reached out on the new rules and changes made in labour legislation Baseline: 50 Target: 90% of registered companies Proposal for a structure of inter-institutional cooperation and working procedures, with a review of existing options Baseline: 0 Target: 1 Working groups operational with team members from relevant institutions with a clear mandate and their continuous involvement in the ‘Technical Working Group’ and ‘Coordination Group’ Baseline: 0 Target: 2 (*) Number of meetings facilitated for effective functioning of working groups through team building, training and expert inputs Baseline: 0 Target: at least 4 meetings a year (*) | Project documentation (list of meetings, training programs and materials, list of participants, recommendations etc); Translated Georgian versions of the all labour law acquis covered by the project; Translated Georgian versions of the all OSH acquis covered by the project; Analysis reports of the relevant Georgian legislation (including by-laws, amendments and administrative regulations); Reports on regulatory and fiscal impact assessments of the legal amendments; Tables of concordance in both areas (labour law, gender equality and OSH acquis); Reports on administrative/ institutional assessments, including legal basis for a modern labour inspection system; Meeting notes and decisions on the topic from the technical working group and/or the Tripartite Social Partnership Commission (TSPC); Legislative amendments made in labour law, gender equality, and OSH; STE mission reports. Project documentation (training programmes and materials, list of participants, recommendations etc); Translated Georgian versions of the all relevant EU Directives; Analysis reports of the relevant Georgian legislation (including by-laws, amendments and administrative regulations); Reports on regulatory and fiscal impact assessments of the legal amendments; Meeting notes and decisions on the topic from the technical working group and/or the Tripartite Social Partnership Commission (TSPC); Legislative amendments in labour law, non-discrimination and gender equality, and OSH); Analysis reports on the training needs of the BA (LCID and LEPD staff) as well as other relevant institutions listed; Short and long-term training plans, training programs and materials; The names and numbers of training participants from all institutions; Study visits’ and mission reports; Plans for improvement of administrative structure and resources; Operational plans and procedures, implementation manuals and guidelines (in English and Georgian); Promotional materials, links to public information campaigns. | L/M Inadequate commitment and support from decision making level in particular with regard to adoption of amended legislation, draft acts, guidelines and procedures | Government commitment on the fulfilment of AA/ DCFTA requirements continued; Strong support and commitment from the senior management of the MoLHSA; Availability of local staff; Good communication between the Beneficiary and other stakeholders; Twinning MS partner(s) commitment; All relevant national documentation available. |
| Activities |  | Objectively Verifiable Indicators | Source of verification |  |  |
|  | 1.1.1 Aligning Georgian legal framework on labour law, including aspects of labour inspection system, amended in compliance with the Union acquis | - Number of the Tables of Concordance prepared for the Labour Law acquis, including aspects of labour inspection system; - List of amendments to be made in the Georgian primary and secondary labour legislation specified with explanatory notes - Share of staff from relevant public institutions who are fully informed on regulatory and fiscal impact of changes in OSH acquis | - Project documentation (list of meetings, training programs and materials, list of participants, recommendations etc); - Translated Georgian versions of the all labour law acquis covered by the project; - Analysis reports of the relevant Georgian legislation (including by-laws, amendments and administrative regulations); - Reports on regulatory and fiscal impact assessments of the legal amendments; - Tables of concordance in both areas (labour law, gender equality and OSH acquis); | Different approaches of the Georgian stakeholders to legislative proposals. Inadequate commitment and support from decision making level in particular with regard to adoption of amended legislation, draft acts, guidelines and procedures | Government commitment on the fulfilment of AA/ DCFTA requirements continued; Strong support and commitment from the senior management of the MoLHSA; Availability of local staff; Good communication between the Beneficiary and other stakeholders; Twinning MS partner(s) commitment; All relevant national documentation available. |
|  | 1.2.1 Aligning Georgian legal framework on non-discrimination and gender equality, including aspects of labour inspection system, amended in compliance with the Union acquis | - List of amendments to be made in the Georgian primary and secondary legislation on Gender Equality acquis specified with explanatory notes; - Share of staff from relevant public institutions who are fully informed on regulatory and fiscal impact of changes in labour law and gender equality acquis. - Share of staff from relevant public institutions who are fully informed on regulatory and fiscal impact of changes in OSH acquis | - Project documentation (list of meetings, training programs and materials, list of participants, recommendations etc); - Translated Georgian versions of the all non-discrimination and gender equality acquis covered by the project; - Analysis reports of the relevant Georgian legislation (including by-laws, amendments and administrative regulations); - Reports on regulatory and fiscal impact assessments of the legal amendments; | Different approaches of the Georgian stakeholders to legislative proposals. Inadequate commitment and support from decision making level in particular with regard to adoption of amended legislation, draft acts, guidelines and procedures | Government commitment on the fulfilment of AA/ DCFTA requirements continued; Strong support and commitment from the senior management of the MoLHSA; Availability of local staff; Good communication between the Beneficiary and other stakeholders; Twinning MS partner(s) commitment; All relevant national documentation available. |
|  | 1.3.1. Aligning Georgian legal framework on Occupational Safety and Health, including aspects of labour inspection system, amended in compliance with the Union acquis | - Availability of quality checked translation of the OSH acquis with clear technical terminology (if necessary); - Availability of the Tables of Concordance prepared for the OSH acquis, including aspects of labour inspection system; - Available list of amendments to be made in the Georgian primary and secondary OSH legislation specified with explanatory notes; - Share of staff from relevant public institutions who are fully informed on regulatory and fiscal impact of changes in OSH acquis. | - Translated Georgian versions of the all OSH acquis covered by the project; - Reports on regulatory and fiscal impact assessments of the legal amendments; - Tables of concordance in both areas (labour law, gender equality and OSH acquis); - Analysis reports of the relevant Georgian legislation (including by-laws, amendments and administrative regulations); - Reports on regulatory and fiscal impact assessments of the legal amendments; | Different approaches of the Georgian stakeholders to legislative proposals. Inadequate commitment and support from decision making level in particular with regard to adoption of amended legislation, draft acts, guidelines and procedures | Government commitment on the fulfilment of AA/ DCFTA requirements continued; Strong support and commitment from the senior management of the MoLHSA; Availability of local staff; Good communication between the Beneficiary and other stakeholders; Twinning MS partner(s) commitment; All relevant national documentation available. |
|  | 2.1.1. Assessment of the administrative structures and institutional capacities of the beneficiary and relevant stakeholders and improvement of their inter-institutional operations | - Functional review of the relevant state authorities to implement changes, including human and financial resources, administrative structures and equipment needed; - Plan (a set of recommendations) for improving institutional operations and procedures of the relevant state authorities to support their pilot implementation, each with clear competences and coordination roles. | - Analysis reports on the training needs of the BA (LCID and LEPD staff) as well as other relevant institutions listed; - Plans for improvement of administrative structure and resources; | No sufficient cooperation among all involved Georgian stakeholders | Government commitment on the fulfilment of AA/ DCFTA requirements continued; Strong support and commitment from the senior management of the MoLHSA; Availability of local staff; Good communication between the Beneficiary and other stakeholders; Twinning MS partner(s) commitment; All relevant national documentation available. |
|  | 2.1.2. Training needs analysis and strengthening the institutional capacity of the beneficiary and relevant stakeholders | - Training needs analysis and plan of the whole staff of beneficiary department and representatives from other relevant institutions listed; | - Short and long-term training plans, training programs and materials; - The names and numbers of training participants from all institutions; | No sufficient cooperation among all involved Georgian stakeholders | Availability of local staff |
|  | 2.1.3. Delivery of the Training of Trainers of the labour inspectors | - 90% of BA staff who received training to implement necessary changes and the representatives from other relevant institutions listed; | The names and numbers of training participants from all institutions; | No sufficient cooperation among all involved Georgian stakeholders | Availability of local staff; Good communication between the Beneficiary and other stakeholders; Twinning MS partner(s) commitment; |
|  | 2.1.4. Delivery of comprehensive training programmes to improve the institutional capacities of the beneficiary and relevant stakeholders | - Number of labour inspectors who are trained more to become ‘trainers’ with full knowledge and competency in implementing new laws; | The names and numbers of training participants from all institutions; | No sufficient cooperation among all involved Georgian stakeholders Unsuccessful beneficiary administration´s reorganization | Availability of local staff; Good communication between the Beneficiary and other stakeholders; Twinning MS partner(s) commitment; |
|  | 2.2.1. Development of the relevant guidelines, labour inspection manuals, checklists and other tools to improve the institutional operations and procedures focused on precise implementation of newly adopted legislation | - At least 20 written operational guidelines, manuals and procedures required to implement all changes, explaining all steps of implementation to the relevant staff; - At least 20 OSH online Glossary and Risk Assessment checklists and their dissemination to relevant parties; | Operational plans and procedures, implementation manuals and guidelines (in English and Georgian); | No sufficient cooperation among all involved Georgian stakeholders Unsuccessful beneficiary administration´s reorganization | Availability of local staff; Good communication between the Beneficiary and other stakeholders; Twinning MS partner(s) commitment; |
|  | 2.2.2. Preparing and implementing public information campaign aiming to raise awareness among the project among key stakeholders, public, private sector and civil society | - At least 30 elaborated promotional materials and 2 public information campaigns in printed and online media, TV and other tools; - 90% of private companies (i.e. both employers and workers) which are informed and number of citizens reached out on the new rules and changes made in labour legislation. | Promotional materials, links to public information campaigns. | No sufficient cooperation among all involved Georgian stakeholders Unsuccessful beneficiary administration´s reorganization | Government commitment on the fulfilment of AA/ DCFTA requirements continued; Good communication between the Beneficiary and other stakeholders; Twinning MS partner(s) commitment; |
|  | 2.2.3. Conducting study visits to Member states, focused for transfer of good practices on organisation and management of labour inspection | - 3 x 5 days Study visit for 20 participants in total accomplished - Study Visit Reports prepared | Study visits’ and mission reports; | No sufficient cooperation among all involved Georgian stakeholders Unsuccessful beneficiary administration´s reorganization | Good communication between the Beneficiary and other stakeholders; Twinning MS partner(s) commitment; |
|  | 2.3.1. Supporting inter-institutional cooperation in the process of approximation and implementation of the relevant EU acquis | - Proposal for a structure of inter-institutional cooperation and working procedures, with a review of existing options; - 2 Working groups operational with team members from relevant institutions with a clear mandate and their continuous involvement in the “Technical Working Group” and “Coordination Group”; - At least 4 meetings per year facilitated for effective functioning of working groups through team building, training and expert inputs. | - Meeting notes and decisions on the topic from the technical working group and/or the Tripartite Social Partnership Commission (TSPC); | No sufficient cooperation among all involved Georgian stakeholders Unsuccessful beneficiary administration´s reorganization | Government commitment on the fulfilment of AA/ DCFTA requirements continued; Good communication between the Beneficiary and other stakeholders; Twinning MS partner(s) commitment; |

Please consult Annex 5 – “Action Document for Skills Development and Matching for Labour Market Needs” under which this Twinning Project will be operating