## Slide 1
განათლება დასაქმებისთვის
Skills4Jobs
Technical Assistance to Skills Development for
Matching Labour Market Needs in Georgia
Second Project Steering Committee Meeting
29.05.2020
Technical Assistance to Skills Development for Matching Labour Market Needs in Georgia

## Slide 2: Activities before March 2020
განათლება დასაქმებისთვის
Skills4Jobs
Technical Assistance to Skills Development for Matching Labour Market Needs in Georgia
27th August 2019: Contract date
October 2019 to January 2020: Inception Phase
Project started: 03.10.2019
Draft Inception Report submitted to EUD, 15.01.2020
Inception Report presented to Steering Committee, 14.02.2020
Revised Inception Report submitted to EUD, 28.02.2020
Other Activities:
Thematic Workshop on Youth Policy, 12.02.2020 (Activity 1.1.4)
Thematic Workshop on Key Competences, 14.02.2020 (Activity 1.1.4)
Project leaflet, banner developed (Output 1.3)
Advice to MoIDPLSA on SESA job descriptions (Activity 4.1.2)
International Senior NKE for PES Capacity Building recruited but not yet deployed (Component 4)

## Slide 3: Six-monthly Implementation Period: March to August 2020
განათლება დასაქმებისთვის
Skills4Jobs
Technical Assistance to Skills Development for Matching Labour Market Needs in Georgia
Now at half-way stage, with 3 months completed (March to May 2020)
Covid-19 lockdown started mid-March
Planned events not involving tele-working were cancelled, including workshop on linking LM data sources and induction training for SESA staff
TL and KE2 remained in Georgia, KE3 returned to home country
All activities since 16.03.2020 carried out through tele-working
Log Frame/Inception Report shared with EU ROM EaP QA team – Outputs/Indicators revised (March/April)
Beneficiaries consulted on changes to project planning/implementation (April/May)
Some activities carried out so far in Components 1, 4 and 5

## Slide 4
განათლება დასაქმებისთვის
Skills4Jobs
Technical Assistance to Skills Development for Matching Labour Market Needs in Georgia
Component 1
Output 1.1: Updated national sector reform policies drafted
1.1.2: Support updating/improvement of policies, strategies, action plans
Strategy/Action Plan for Career Guidance: Situational analysis started, first online meeting with stakeholders (linked with Component 2)
VET Strategy/Action Plan: Methodology agreed, situational analysis drafted, jointly cooperated with PAR project in workshop for MoESCS (linked with Component 2)
Strategy/Action Plan for Youth Services: International Senior NKE in Youth Policy recruited to support strategy development and drafting of Law on Youth; advice provided on survey methodology (linked with Component3)
1.1.3: Survey of geographical coverage of VET provision: Supply side analysis drafted, demand side analysis started
1.1.6: Advisory support on performance indicators of the SRPC: Comments provided to EUD on preliminary and full information relating to BS Indicators
1.1.8: Short update and progress reports to the EUD on sector reform policies: comments provided on Draft Employment Law, situation paper on VET updated

## Slide 5
განათლება დასაქმებისთვის
Skills4Jobs
Technical Assistance to Skills Development for Matching Labour Market Needs in Georgia
Components 2 and 3
Current activities in VET and Youth are mainly related to Strategy development under Component 1
Component 4
Output 4.1 SESA supported in implementing the NSM
4.1.1 Assess functioning of NSM: Comments provided on handbook for employment counsellors and proposals for refinement of NSM, proposals on working with local employers drafted
4.1.2: Advise on institutional development of SESA: Organizational chart drafted, recommendations drafted on provision of local services, work started on drafting proposals for institutional development plan
Output 4.3: Capacity of SESA staff developed
4.3.2: Design a training plan for SESA staff: Initial training plan developed

## Slide 6
განათლება დასაქმებისთვის
Skills4Jobs
Technical Assistance to Skills Development for Matching Labour Market Needs in Georgia
Component 5
Output 5.1: Improved integrity and compatibility of data systems
5.1.1: Assess main information systems and prepare proposals for data sharing: Concept paper prepared on developing an Employment Statistics Resource based on data sharing between main data providers
Output 5.2: LMIMS
5.2.1: Develop proposals for upgrading the LMIMS portal: Functioning of LMIMS/WorkNet assessed (as section of the Concept Paper) and proposals drafted
Output 5.3: Capacity of LMIS Team enhanced
5.3.1: Provide guidelines and related capacity building: LMAD advised on choice of sectors, options for sector analysis, work started on drafting guidelines
Component 6
Not yet started

## Slide 7
განათლება დასაქმებისთვის
Skills4Jobs
Technical Assistance to Skills Development for Matching Labour Market Needs in Georgia
Consultations with beneficiary institutions on Covid-19 pandemic
General: Tele-working continues during reporting period, with some restrictions remaining during the gradual easing of lockdown. Officials/staff have had extra demands on their time resulting from pandemic. MoESCS, MoIDPLHA and MoESD all reported Covid-related difficulties in meeting one or more BS Indicator requirements
MoESCS: Student enrolment, especially in VET, will be greatly reduced in 2020 - one of two enrolments cancelled, distancing requirements for students after reopening of colleges etc.
MoIDPLHSA: Full establishment of SESA, particularly in the regions slowed down, some delay in staff recruitment, reduced registration of vacancies
MoESD: Cannot implement sector surveys using the usual survey methods, online survey alternatives not considered appropriate
Youth Agency: Opportunities for direct contacts with local providers adversely affected

## Slide 8
განათლება დასაქმებისთვის
Skills4Jobs
Technical Assistance to Skills Development for Matching Labour Market Needs in Georgia
Project planning changes resulting from Covid-19 pandemic
General:
Focus mainly on documentary outputs during pandemic
Capacity building training, large workshops, site visits etc. postponed, at least until the autumn and mainly until next year
Tele-working continues for remainder of the six-monthly period, perhaps longer
Use of international experts will be very limited until travel restrictions across Europe are lifted unless tele-working is possible: SNKE for youth policy can do tele-working, not possible for SNKE for PES capacity building; recruitment process for SNKE for career guidance is started
The time resources of key experts and long-term NKEs are stretched to the limit at the moment, and the situation especially requires inputs from the two long-term NKEs beyond what was expected before the pandemic began

## Slide 9
განათლება დასაქმებისთვის
Skills4Jobs
Technical Assistance to Skills Development for Matching Labour Market Needs in Georgia
Project planning changes resulting from Covid-19 pandemic
Component 1:
Focus on drafting the 3 urgently required national strategies (which are the priorities for MoESCS and Youth Agency) supported by online meetings of working groups wherever possible (Output 1.1)
Geographical survey of VET s being implemented albeit with limited local data gathering (Output 1.1)
Most capacity building training deferred until next year (Output 1.2)
Most communications activities beyond online information delayed (1.3)
Component 2:
Most support to MoESCS is being provided through Component 1 because key Component 2 activities are dependent on the strategies being developed
Component 2 activities that are document based - e.g. situational analyses, concept papers - can be started
Start of development of training packages and pilot trainings deferred to 2021
Flexible approach – delayed activities to be kept under review in the light of MoESCS priorities and upcoming projects of other donors

## Slide 10
განათლება დასაქმებისთვის
Skills4Jobs
Technical Assistance to Skills Development for Matching Labour Market Needs in Georgia
Component 3:
All support from international SNKE in his first assignment will be through tele-working
The most urgent need of the Youth Agency is the Youth Strategy (Component 1)
Support to drafting Youth Law (3.3.1) will also start in the current reporting period
Other institutional development support related to Strategy (also in 3.1) may also be started
Capacity development training and all support in the regions is deferred until 2021 (Outputs 3.1, 3.2)
Component 4:
Support mainly focused on desk research and drafting/revision of handbooks/guidelines (mainly under Output 4.1)
Assessment of NSM implementation deferred until field visits are possible (4.1.1)
Support to SESA institutional development at regional level beyond documentary support is limited until visits can be organized (4.1.2)
Although some materials can be developed, induction training for SESA staff deferred until face-to-face training is possible and trainer can travel (4.3.1)

## Slide 11
განათლება დასაქმებისთვის
Skills4Jobs
Technical Assistance to Skills Development for Matching Labour Market Needs in Georgia
Component 5:
Inputs from KE3 limited, e.g. on data sharing (Output 5.1) and capacity building for LMIS team (Output 5.3), until he can return
LT NKE has to undertake a larger share of the work until his return
Support to sector survey implementation pending the ability of MoESD to commence them (5.3)
Drafting of guidelines started (5.3.1)
Drafting of capacity building materials can be started
Recommendations on technical upgrading of data systems deferred until an expert can come (5.1.2, 5.2.1)
Component 6:
Support to monitoring grant scheme implementation deferred until at least September 2020

## Slide 12
განათლება დასაქმებისთვის
Skills4Jobs
Technical Assistance to Skills Development for Matching Labour Market Needs in Georgia
Contingency planning has sought to take full account of the views, circumstances and priorities of project beneficiaries At this early stage in the project, implementation has not been too badly impacted by the pandemic as there are many activities that can be carried out through tele-working We have assumed that there will be a gradual easing of Covid-19 restrictions with a return to near-normal by the end of the year A return of the pandemic during the winter months could cause further disruption to project implementation, especially capacity building activities that have been deferred until late 2020 or early 2021 The progress report at the end of this six-monthly implementation period will provide an opportunity to take stock of developments and make appropriate adjustments to project implementation planning
Points to consider

## Slide 13
განათლება დასაქმებისთვის
Skills4Jobs
Thank You!
David.Handley@gopa.de
Technical Assistance to Skills Development for Matching Labour Market Needs in Georgia