## Slide 1: Quarterly progress report: achievements, challenges and opportunities
Joint SDG Programme
“Transforming the Social Protection System for People with Disabilities in Georgia”

## Slide 2: Outcome 1: By 2022, persons with disabilities, especially those from vulnerable groups, benefit from enabling environment through disability inclusive legislation, evidence-based policy, decreased stigma on disability and expanded employment opportunities.
Output 1.1. Legislative framework and evidence-based policy environment strengthened, and non-discriminatory social norms promoted to enable all PwDs effectively enjoy their rights:
A preliminary study of Georgian legislation on persons with disabilities and its compatibility with UNCRPD was conducted
The UN agencies contributed to the development of a draft Law on the Rights of Persons with Disabilities and submitted to the Parliament of Georgia and HRS
Parliament of Georgia was supported to conduct wide public discussions on the draft law together with organizations of persons with disabilities (OPDs) and NGOs to ensure participatory principles in policy making
Establishing a Coordination Commission to facilitate implementation of UNCRPD was supported, and the draft decree on the creation of an inter-agency commission on the rights of PwDs and its regulation was reviewed through UNCRPD lenses
Elaboration of National Accessibility Plan and National Human Rights Strategy with an emphasis on the Rights of PwDs started
Planning underway for the forthcoming implementation of the WHO Model Disability Survey (MDS)

## Slide 3: Outcome 1: By 2022, persons with disabilities, especially those from vulnerable groups, benefit from enabling environment through disability inclusive legislation, evidence-based policy, decreased stigma on disability and expanded employment opportunities.
Output 1.2. Capacities for data collection, monitoring and advocacy improved for the implementation of CRPD, ICPD PoA, CEDAW, BFPA, UPR, CSW
A Call for Proposals (CfP) for CSOs with expertise and proven experience in working on the rights of women and girls with disabilities was announced. The selected CSO will capacitate organizations to lobby the implementation of UNCRPD in the context of national and international commitments to gender equality and women's empowerment.
Consultations and discussions with MoIDPOTLHSA representatives to support development of an electronic data management system for PwDs in the frame of new disability assessment and status determination system was organized. Electronic data collection and analysis tools are currently being refined and finalized.
Output 1.3 - Equal employment opportunities promoted and expanded for all PwDs regardless of age and sex
Pharmaceutical and banking sector companies were selected to support them implementing reasonable accommodation principles in the services and infrastructure . Trainings on service provision to PwDs was conducted for two pharmaceutical companies.

## Slide 4: Outcome 2 - By 2022, the social protection system, health and social services are transformed in line with the social model of disability to ensure social inclusion and equal rights for people with disabilities
Three State Universities (Ivane Javakhishvili Tbilisi State University, Ilia State University and Batumi Shota Rustaveli State University) agreed to explore embedding capacity building of frontline professionals within the frame of a new disability assessment and status determination system.
Selection and recruitment of an international consultant to develop assessment of the current pilot of the social model of disability assessment and status determination system in Adjara, in line with International Classification of Functioning, Disability and Health (ICF) and/or UNCRPD has been started.
Output 2.1 - Gender-sensitive disability assessment and status determination system transformed based on social model

## Slide 5: challenges and opportunities
In response to the COVID-19 pandemic, restrictions on gatherings and mobility were put in place and further enforced through a nationwide state of emergency.
These limitations influenced timely implementation of activities of most of the agencies, including the official launch of the project.
The COVID-19 outbreak redirected the focus of Government of Georgia to pandemic-related issues hence some of the strategic decisions regarding the SDG programme have been delayed.
Since PwDs are one of the most vulnerable groups in the COVID-19 related crisis, the implementing agencies are reprogramming some of the activities within the current Joint Programme and will be submitted to the Steering Committee for approval.
The UN agencies continue to work online on the issues that do not require intensive in-country travels or face-to-face communication. As the situation normalizes in the country, the SDG programme activities will be continued as planned.