Quality Assurance Plan

version 2.0

25-11-2016

Activity 2.8

The content of this report does not reflect the official opinion of the European Union. Responsibility for the information and views expressed in the report therein lies entirely with the twinning partners.

Content

1.	Purpose	3

1.1.	Objective and scope	3

1.2.	Target group	3

1.3.	Context	3

1.4.	Preparation and status of this document	3

1.5.	Timeline	3

1.6.	Quality function deployment and structure	4

1.7.	Connections with other systems in the SSA	4

1.8.	Dissemination	4

2.	Quality goals and criteria	4

2.1.	Customers	4

2.2.	Definition of quality and metrics	6

3.	Quality assurance and control	8

3.1.	Quality planning	8

3.2.	Quality documentation	8

3.3.	Quality assurance measures	9

3.4.	Error proofing	9

3.5.	Inspection	9

3.6.	Quality monitoring and reporting	10

3.7.	Internal quality audit	10

3.8.	Quality survey	10

4.	Audit trail	11

5.	Roles and tasks of quality assurance	11

# Purpose

# Objective and scope

The objective of the present Quality Assurance Plan (QAP) is to ensure that

- quality requirements are defined

- process documentation and tools provide for the observation of these requirements

- quality is measured and if necessary corrective steps are taken

The scope of this plan is to define quality and how it is measured, to identify the core processes that bring about quality and the documentation and tools that support the observation of quality requirements and finally to define how quality is ensured and what roles and tasks are necessary for this purpose.

It is not the scope of this QAP to regulate how the ESS works or to produce documents and tools that are used in the processes and to explore or correct errors.

# Target group

The indirect or final target group of the QAP are the customers of ESS, i.e. the jobseekers and the employers. The purpose of the QAP is to promote that the quality requirements of these target groups are observed.

The direct target groups are the management and employees of the ESS, whose task is to supervise and implement the QAP and the operation of the ESS in order to reach the quality criteria.

# Context

The present QAP is prepared as part of the Twinning project and in a period, when the New Service Model is being implemented at a pilot level and face labour-market related challenges. In this context, the aim of the QAP is to introduce basic quality instruments with a view of evaluating the use of these instruments in one year after the launching of the New Service Model.

Also, because of the transitory or pilot character of the operation of the ESS, the goals, criteria, metrics, tools are kept as simple as possible to avoid requiring more than it is realistic and necessary at this stage and what might be ideal at a full-fledged ESS operation.

# Preparation and status of this document

This document has been produced as a draft of or as a proposal for the QAP. Once it is approved the language has to be revised in a way that it reflects that it is an approved document and not a proposal.

It is noted that the QAP was prepared with a view to the context described and in a timeframe justified by this context. For this reason, the preparation of the QAP focused on the identification of the processes and process-related errors with the assistance of the staff during two workshops, as these were regarded as key instruments to ensure quality.

# Timeline

It is proposed that quality functions are introduced gradually in the organisation. The present QAP lists the preconditions that ought to take place before its introduction and it is recommended that these steps take place until 30 November 2016. It is recommended that quality measures as laid down in this plan are implemented in 3 months after the preconditions are fulfilled. It is foreseen that the QAP is evaluated one year after the launch of the New Service Model.

# Quality function deployment and structure

In order to reach its purpose, the QAP follows the basic structure of quality functions deployment: first we define quality goals and criteria from the point of view of the ‘customers’ of the ESS, then we define how quality is measured, then we translate the requirements into process and operations requirements that ensure the observation of the requirements at the level of processes and quality control.

# Connections with other systems in the SSA

Quality requirements are ensured at the level of the quality system, such as processes and tools, but they also have to be built in the performance requirements of the ESS staff. This is achieved through defining at job description and individual level how each employee will contribute to the achievement of quality targets and this has to be evaluated as part of the performance evaluation. The present QAP doesn’t provide any arrangement in this respect, this aspect has to be taken into account at the planning and evaluation of individual performance.

# Dissemination

It is important that the QAP will remain in obsolesce if it is not disseminated properly. it is recommended that

- The essential elements are shared with the management and the employees when the plan is introduced in the form of a presentation

- The quality goals and targets are displayed at each office at visible places

- The processes are displayed in large size at each office in the actual rooms where employees work

- The critical checklists are also displayed at the actual places of work and at the workstations of the employees

# Quality goals and criteria

Quality for the purpose of this QAP is defined as the basic characteristics of the service provided as derived from the requirements of the customers.

# Customers

The two groups of customers of the ESS are jobseekers and employers. These customers generally speaking set two types of requirements:

- Requirements related to the output and outcome of the service

- Requirements related to the service process

Below, we list the key requirements by target groups.

Jobseekers

Group 1

- A wide offer of skilled jobs matching their profile and offering competitive remuneration

- Up-to-date job announcements

- State-of-the-art web-based user support and functions in order to easily apply for jobs

- Seamless, reliable processes and functions

Group 2 and 3

- An up-to-date and wide selection of jobs that both match their basic skillset and experience and offer an acceptable remuneration

- Great chance of receiving a suitable job offer in a short time

- More accessible job opportunities than those offered at fee-based private providers

- High chance of getting a job in an acceptable time-period

- Availability of assistance that help them get a job

- Accessible customer service personally and by phone

- Helpful, attentive, understanding, professional staff

- Availability of personal help throughout the process and especially as regards any electronic surface

- Straightforward language and forms

- Clear information on where to go, what to do and what to expect when asking for services

- Very clear and easy-to-understand processes

- A physical place that has a clear access, provides space for waiting, radiates openness, provides for an intimate customer service place

- Opening hours after working time

- Easy-to-use Internet functions if relevant

Group 4

- A selection of jobs that match their basic skillset and a remuneration that is better than it is achievable under their current circumstances

- Availability of assistance that help them get a job

- Possibly availability of travel reimbursement or discount  and/or other incentives

- Chance of receiving a suitable job in an acceptable timeframe

- Accessible customer service personally

- Helpful, attentive, understanding, professional staff

- Availability of personal help throughout the process and especially as regards any electronic surface

- Straightforward language and forms

- Clear information on where to go, what to do and what to expect when asking for services

- Very clear and easy-to-understand processes

- A physical place that has a clear access, provides space for waiting, radiates openness, provides for an intimate customer service place

Employers

- Reliable offer of suitable candidates to job announcements with a significant success rate and in the given timeframe

- Professional, time-efficient, professionally looking, well-communicating staff who easily understand job requirements

- Easy-to-use web-based services

- Accessible customer service by phone with reliable and prompt replies

# Definition of quality and metrics

| # | Quality criteria | Definition | Measurement | Process |
| --- | --- | --- | --- | --- |
|  | A wide offer of skilled jobs matching their profile and offering competitive remuneration |  |  |  |
|  | A selection of jobs that match their basic skillset and a remuneration that is better than it is achievable under their current circumstances |  |  |  |
|  | An up-to-date and wide selection of jobs that both match their basic skillset and experience and offer an acceptable remuneration |  |  |  |
|  | State-of-the-art web-based user support and functions in order to easily apply for jobs |  |  |  |
|  | Seamless, reliable processes and functions |  |  |  |
|  | Great chance of receiving a suitable job offer in a short time |  |  |  |
|  | More accessible job opportunities than those offered at fee-based private providers |  |  |  |
|  | High chance of getting a job in an acceptable time-period |  |  |  |
|  | Availability of assistance that help them get a job |  |  |  |
|  | Accessible customer service personally and by phone |  |  |  |
|  | Helpful, attentive, understanding, professional staff |  |  |  |
|  | Availability of personal help throughout the process and especially as regards any electronic surface |  |  |  |
|  | Straightforward language and forms |  |  |  |
|  | Clear information on where to go, what to do and what to expect when asking for services |  |  |  |
|  | Very clear and easy-to-understand processes |  |  |  |
|  | A physical place that has a clear access, provides space for waiting, radiates openness, provides for an intimate customer service place |  |  |  |
|  | Opening hours after working time |  |  |  |
|  | Easy-to-use Internet functions if relevant |  |  |  |
|  | Reliable offer of suitable candidates to job announcements with a significant success rate and in the given timeframe |  |  |  |
|  | Professional, time-efficient, professionally looking, well-communicating staff who easily understand job requirements |  |  |  |
|  | Easy-to-use web-based services |  |  |  |
|  | Accessible customer service by phone with reliable and prompt replies |  |  |  |

# Quality assurance and control

# Quality planning

Quality plans

For the purpose of quality assurance in the ESS we define two plans:

- The present QAP as an overall guidance document in relation to quality

- The quality inspection and audit plan (Annex)

Failure and risk analysis

The failure mode and effect and risk analysis identifies

- the possible types of failure along the core processes

- the estimated effect of the failure on the operation and on the fulfilment quality criteria

- the probability of the event

- the score of the event based on its effect and probability

The result of the analysis is part of the planning of audits.

# Quality documentation

Quality documentation has to be stored in hard copy in a separate folder as prescribed by the documentation rules of the SSA and on the shared drive of ESS. The QAP and the management system documents are accessible by all employees, the other documents are accessible only by the Quality Manager and by the management. The components of the quality documentation:

Quality plans

- QAP and the inspection and audit plan as annex to it

Inspection and audit documents

- This contains the documentation of the planning and delivery of audits and inspections and the action plan proposed and approved.

- The quality inspection and audit plans are prepared in a simple textual format. They contain the exact objective of the inspection / audit, the name of the auditors, the duration of the audit, the failure and risk analysis, the areas to be investigated with the exact indication of the process elements, geographical locations, documents and if relevant participatory observations, the required resources and venues and the applied methodology.

- The delivery documents contain the authorisation letter of the inspectors / auditors, the declaration of confidence signed by the auditors, the attendance sheet of any meetings held during an inspection or audit, a textual description of the findings, a separate report on any irregularity found.

- The action plan is the result of the inspection / audit. It is prepared in a table format and contains the finding, the proposed action, the person responsible, any cost/resource associated, the commencement and deadline of the action, the reporting back deadline and the date of the repeated inspection.

Quality management system documents

The quality management system documentation at the ESS at present contains the following:

- Handbooks: Services to Employers, Job Counselling (annex II).

- Process charts: to be prepared. At present: audit trails (annex I.)

- Templates: as part of the handbooks (Annex III.)

- Checklists: as part of the handbooks. (Annex IV.)

The quality management system documents have to be accessible in hard copy and in electronic form to the employees all the time.

In case of an up-date, the version in force has to be accessible and the quality manager has to inform all employees on the scope of change and on the date of entry into force.

# Quality assurance measures

Quality is ensured through the following means:

- Error proofing: error proofing serves the prevention of or removal of errors along the process. This is achieved by providing templates, model texts, visual aids, short printed instructions, checklists to the employees.

- Regular inspection: regular inspection serves to find out if processes are done as they are laid down and according to the quality criteria. Inspection takes places at regular intervals and is aimed at the in-depth investigation of the process.

- Continuous monitoring and reporting: monitoring and reporting provides data on a daily, weekly and monthly basis. While it primarily serves controlling purposes, deviations may also reflect quality problems and these have to be investigated.

- Audit: at present one overall audit is recommended to take place in one year. Audit is performed by an internal auditor (either staff member or contracted). The audit is directed at the in-depth investigation of the delivery of processes and the quality of outputs and outcome.

- Surveys: two customer surveys are conducted each year, one among jobseekers and one among employers. Further to that, a continuously applied feedback questionnaire is applied among both target groups on a voluntary basis.

- Job shadowing and peer review: peer review is an action whereby trained and more experienced / senior staff monitors the work of other staff members in a given process step to ensure they are performing as expected by the processes. Peer review is necessary every time a colleague performs a task for the first time and may comprise a peer monitoring several times during a week. The monitoring person discusses performance with the colleague concerned and they define action if necessary. The results of the peer review should be monitored weekly by the unit manager. The peer review is recommended to be complemented in advance by job shadowing, where the colleague who will perform a task for the first time shadows an experienced colleague during a few days to learn the expected behaviour.

- Management control: the unit managers should also check on a weekly basis in group and individual discussion as well as through the investigation of documents if processes are observed.

# Error proofing

Error proofing serves the purpose of preventing possible human errors caused by forgetting, negligence, lack of proper training, lack of attention, etc. This is achieved by applying throughout the process templates, checklists and other types of aids that are used by the staff on a mandatory basis and the use of these documents provide a uniform service approach and level, as well as ensure that staff members have performed all operations required or conveyed all necessary information. The list of these documents are found in the Annex. Regular inspections and audits must check the use of these documents.

# Inspection

Inspection is a process where a process or task performed is investigated to establish to what extent processes are regular. We define the following inspection types:

- Self-inspection: self-inspection is performed by the employee on the basis of checklists as indicated in the audit trail and in the annex.

- Successive inspection: successive inspection is performed by a workmate or by a co-ordinator/manager as indicated in the audit trail and in the annex. Successive inspection entails the full inspection of the preceeding step/incoming document in the process and serves as a mandatory gate to the next process step.

- Source inspection: source inspection entails the inspection of external sources in terms of their quality, credibility, reliability. This covers primarily three sources:

  - Data input in the Worknet in terms of reliability and consistency. This has to occur after the registration of a jobseeker or an employer.

  - Information provided by jobseekers in terms of the content of their CVs and statement of skills and experience, as corruption of this information is detrimental to the credibility of services towards employers.

  - Job announcement provided by employers in terms of the completeness and correctness of the data provided.

- Ex-post sample-based inspection: ex-post inspections have to take place at monthly intervals, performed by the quality manager and/or other independent staff member and is directed at the investigation if the processes are operating according to the rules. The inspection may be sample-based and the sample should contain at least 10% of the cases but not less than 20 cases overall and be representative in terms of representing the distribution of all cases. The cases should be selected on a random basis in each segment.

# Internal quality audit

Internal quality audits take place on a regular and ad-hoc basis. At the present one regular audit shall take place after one year of the launch of the New Service Model and then before the end of each calendar year.

Internal audits are performed by contracted or regular staff member auditors. The audits are conducted along the following steps:

- The audit is organised one month before the start of the audit activities according to the audit plan.

- First the leader and members of the auditing team are selected, which include the quality manager, a skilled auditor and selected members of the staff. The team members sign the authorisation letter and the declaration of confidence.

- The quality manager and the team leader prepare the team members in the methodology and process of the audit as well as in audit ethical and professional principles in a one or two-day training.

- The audit team with the direction of the team leader and quality manager prepares the plan of the actual audit. It specifies the members of the audit team, the exact objective and subject of the audit with the exact indication of the process elements, the duration of the audit, geographical locations, documents to be investigated, the required resources and venues and the applied methodology.

- The audit starts with a kick-off meeting where the auditing team and the line managers of the audited area discuss the schedule and tasks of the audit, the availability of documents and interviewees.

- The audit is performed according to the plan, attendance sheets of any meetings held during the audit have to be produced and kept.

- The audit team prepares an audit report, that contains a textual summary description of the findings, a table-format description of all items investigated and the findings, a separate report on any irregularity found and an action plan in a table format that contains the findings, the proposed actions, the persons responsible, any cost/resource associated, the commencement and deadline of the action, the reporting back deadline and the date of the repeated inspection.

- The report is shared with the manager of the audited unit and with the head of department, who may comment on it and propose corrections. In case of disagreement the audit team leader and the quality manager discuss the discrepancies with the managers. If disagreement persists, it has to be noted on the audit report but the report need not to be changed.

- The final report is submitted to the responsible deputy director general of the SSA.

- After the report is approved, the head of department of ESS and the manager of the audited unit(s) prepare a schedule specifying the steps to be taken to implement the actions described in the report. The managers distribute tasks accordingly and create an alert to remind about the deadline of the actions.

# Quality survey

Four surveys are recommended:

- Annual survey among jobseekers (phone-based among jobseekers who effectively used the service). This survey takes place in the last two months of each calendar year on the basis of the same questionnaire. The survey must be representative in terms of the jobseekers who used the services of ESS. It is recommended to commission a professional survey provider to conduct the survey.

- Annual survey among employers (phone-based): This survey takes place in the last two months of each calendar year on the basis of the same questionnaire. The survey must be representative in terms of the employers who used the services of ESS. It is recommended to commission a professional survey provider to conduct the survey.

- The results of the two surveys are presented to the ESS management not later than the 31 January of the following year.

- Continuously applied questionnaires: two short questionnaires are made available to both target groups after the use of the services. The questionnaire for jobseekers have to be available as jobseekers leave the place of the service and there should be a closed box where they drop in the anonymous questionnaire. The questionnaires have to be collected after the end of each month and analysed and presented to the management by the controller/quality manager by the middle of next month.

# Audit trail and process control

The audit trail contains in a table format all process steps, their input and output (where relevant), the associated documents and systems, the types of error envisaged, the means of managing/preventing that error. One audit trail covers the services for jobseekers and one the services for employers.

The audit trail provides for means to ensure that processes follow the prescribed rules in the respective handbooks. This is ensured by providing

- checklists that are used by the employees during the process

- document templates

- model, template information texts to ensure standardized information is conveyed

- suggestions for simple electronic tools – such as meeting organizer, task manager in Outlook or other programmes – to prevent backlogs, losing or forgetting information

- identifying the points where data clarity and consistency should be ensured in the Worknet or other It system used

- inspection to be carried out on a monthly or different basis with the purpose of

  - checking whether every document, information or action was carried out as they should have been and whether every document or information can be found at its place of storage – i.e. in the file of the client or in the Worknet,

  - discussing a selected number of cases in the previous month with the employees to find out possible problems, different practices and ensure coherence and consistency of service

A list of chekclists, model texts, templates and preventive actions are listed in the Annex.

# Roles and tasks of quality assurance

For the purpose of the introduction of the QAP a Quality Manager role has to be established either as full- or part-time role.  The role of Quality Manager can be performed by a current employee as well. The role of the Quality Manager is:

- The elaboration and maintenance of the quality plans and proposing quality plans for approval for the management

- Maintenance of the quality system documentation

  - Storing the quality system documentation at a dedicated physical place (folder) and on the electronic storage

  - Revise the documents when any change is made to the process or process-related documents

  - Revise the documents based on the results of the annual audits

  - Indicate on a cover sheet the actual version and version number of the document, the changes made to the previous version and the date of the next revision (audit)

- Planning, co-ordination and delivery of inspection and audit

    - Perform regular inspections

    - Organise and supervise annual audits

- Report to the management on the findings of inspections, audits, surveys as well as proposed changes.

Every employee has a task in the operation of the quality management system. Their task is to perform their job according to the agreed processes and quality targets (criteria) and participate in the inspections, audits, surveys as team members under the supervision of the quality manager.

Management has three roles in the quality system:

- Approve (or ask modifications to) quality system documents and quality plans as proposed by the quality manager. The approval of the quality documents and plans is in the authority of the deputy director general of the SSA responsible for ESS.

- Provide for the observance of quality targets and documentations during daily work as part of distributing and checking the status of tasks

- Request, receive and interpret monitoring reports, audit, inspection and survey reports from a quality point of view, make sure causes of deviations are explored and proper actions are elaborated and approve corrective actions. As regards the whole operation of ESS it is the task of the head of department, while every head of unit has to perform this task in relation to the work of its own unit.

Annex

Audit and inspection plan

| # | Name | Responsible | Participants | Coverage | Period audited | Timing | Purpose | Sample | Means |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Annual internal audit | QM | One person from each central office unit | ESS Department and local units | Calendar year | January each year | To assess compliance with focus on selected areas based on risk-analysis and policy priority | 5% of documents produced in the selected processes, but not less than 20 cases covering each process step | Inspection and compliance assessment of randomly selected cases |
| 2 | Annual customer survey | QM | One person from the units for jobseeker and employer services respectively | Services to jobseekers Services to employers | Once in a year connected to the annual audit | January each year | To assess the satisfaction and expectations of both jobseekers and employers and draw service-improvement conclusions | Jobseekers: version A) assess the continuous customer survey results for the given year B) Conduct a survey of at least 200 valid responses based on contact data in the worknet and with returning clients Employers: conduct a survey covering ALL clients | Survey based on two questionnaires attached |
| 3 | Bi-annual source inspection | QM / Statistical officer | One person from each unit | Worknet / other databases Client files (archives) | Half-year period | July and January each year | To assess the completeness, clarity and consistency of data | Total worknet database | Specific algorithms to detect: a) missing data b) data with irregular format c) data out of specified value limits. |
| 4 | Monthly ex-post inspection and customer survey | QM | One person from each unit | ESS Department and local units | Given month | First week following a given month | To find out if a) all documents and information are properly produced and stored, b) compliance of documents based on a selection of documents – 20 cases, c) group discussion of cases and prcatices | Jobseeker and employer services: - compliance: completeness of all personal files - inspection of 20 cases in the given month in terms of full compliance | - document analysis - Continuous customer survey |

Quality assurance tools  - Services for jobseekers

| Quality assurance tool | Process number | Process step |
| --- | --- | --- |
| Model text about Worknet registration | 1.2.1 | Info about Worknet registration |
| CV template for jobseekers | 1.2.6 2.8.6 | Jobseekers upload CV EC collects their profiles/CVs |
| Contact list template of jobseekers | 2.1.2 | Identifying newly registered in the Worknet |
| Standard text and checklist on information on ESS services | 2.3.1 2.4.8 3.1.3 | Provision of information about ESS services and Worknet functions Inform the unemployed persons at the event Determining what kind of support is needed and what can be offered |
| Written / electronic labour market summary | 2.3.2 | Information on labour market situation and job offers |
| Request for provision of employment services | 2.3.5 2.5.5 | The jobseeker signs a Request for provision of employment services The unemployed person signs a Request for provision of employment services |
| Checklist for EC to go through during each meeting when requesting services | 2.3.5 2.5.5 | The jobseeker signs a Request for provision of employment service The unemployed person signs a Request for provision of employment services |
| Letter template (e-mail) that contains all data fields necessary for the approval of an information event | 2.4.1.1 | Write a letter to the Central Office on the need of an information event |
| Invitation template for an information event for participants | 2.4.3 | Prepare invitation text and book venue |
| List of human and physical resources for events | 2.4.3 | Prepare invitation text and book venue |
| Attendance sheet template for information events | 2.4.8 | Inform the unemployed persons at the event |
| Vacancy list template for informational purposes at information events | 2.4.9 | Provide information about suitable vacancies |
| Interview list template - List of interviews with jobseekers and dates | 2.4.13 | Agreement on interview |
| Standardized interview checklist and preparation note | 2.5.1 | Preparation for the first interview with jobseekers |
| Annotated (hints) interview questionnaire (in:Handbook on Counselling annexes) | 2.5.2 | First interview - Filling questionnaires and administrative files |
| Checklist of services matching particular profiles (support ECs in advising services for jobseekers) | 2.5.3 | Determination of possible services |
| Checklist and question list to assign registered jobseekers to service during phone conversation | 2.6.2 | Approaching the registered jobseeker by phone or SMS |
| Job announcement based candidate job profile checklist (identification of suitable candidates) | 2.6.4 2.8.1 | Employment counsellor investigates all information on conditions of offered employment at personal meeting Employment counsellors receive an information on upcoming mass interview organised for an employer |
| Interview preparatory checklist for preparing candidates for interviews | 2.6.2 | Preparing the client for the interview and informs client on documents he/she have to bring to an interview |
| Referral (to employers) template | 2.6.3 | Issuing of the Referral to the interview to a jobseeker |
| Text template – standardized information and advice on job searching options | 2.7.2 | Provides information and advice about job searching |
| Agreement template on inclusion in the employment mediation process | 2.7.3 | Agrees with the client that he/she will be included in the employment mediation process |
| Standardized form for vacancies to be announced by the ESS | 2.8.1 2.9.3 | Employment counsellors receive an information on upcoming mass interview organised for an employer Track employers who enrolled to participate at a job fair |
| Job fair standardized information sheet (standard information on the job fairs) | 2.9.1 | Referral of suitable jobseekers to visit a job fair |
| Standardized information sheet for ECs to follow during information provision through phone | 2.9.5 | Actively engages with these jobseekers by phone or email, informing them on job fair |
| IAP | 3.1.5-3.1.10 |  |
| Model annotated IAP | 3.1.5-3.1.10 |  |

Quality assurance tools  - Services for employers

| Quality assurance tool | Process number | Process step |
| --- | --- | --- |
| Selection method and checklist for choosing adequate employers (based on the vacancy database to avoid pontless contacts) | 1.1 | Searching for employers |
| Daily tasks checklist for job agents | 2.1.1 2.1.2 | Checking WN newly registered vacancies Checking WN employers if they asked for SSA assistance |
| regular labour market data and analysis (national, regional, local level) provided by analyst expert | 2.1.3 | Local or regional labour market mapping if there are not enough new vacancies |
| Preparatory checklist before contacting employer first | 3.1.1 3.1.3 3.1.4 | Studying vacancies posted by the employer Preparing basic offer to the employer by checking the quality and quantity of potentially suitable candidates from WN |
| Structured company profile template | 3.1.2 | Collecting basic info about the company (profile, size, seat, contact level, needs) |
| First call draft (text template) | 3.1.5 | Preparing the draft structure of the first call |
| Preparatory checklist before visiting the employer | 3.2.1 3.2.2 3.2.3 3.2.4 | Planning the logistics of the visit (travel, address) Preparing background doc folder (leaflets, business card, template of visit) Prefill the visit template Thinking on the set of services to be provided |
| Employer visit checklist for job agent | 3.2.5 3.2.6 3.2.7 3.2.8 3.2.10 | open an account for the employer Identifing contact point Helping in defining the realistic profile of candidates Set a deadline and a target amount Recording the visit |
| “Request of employer for provision of SSA services” template | 3.2.9 | Employer signs written Request of employer for provision of SSA services |
| Checklist to maintain communication and partnership to employer | 3.3.2 | Active and regular communication with the employer during the process of collecting candidates |
| Process description and checklist of conducting pre-selection services to employers | 4.1.1 4.1.2 4.1.3 4.1.4 | Job agent (JA) announces the new vacancy by email to employment counsellors with the direct link in WN Employment counsellor collects and sends candidates profiles ASAP to job agent Job agent collects the automated matches from WN and if job agent assigned as a contact point in the WN, checks the jobseekers CVs directly come to them Job agent sends the preselected CV-s to the employer |
| Satisfaction questionnaire form to measure the employer’s feedback | 4.2.6 4.2.7 | Collecting feedback from employers about the result of the selection process Sending a form of satisfaction survey by the client |
| Task checklist for organizing mass interview | 4.2.1 4.2.2 4.2.3 4.2.4 | Offering contribution to the organisation of mass interviews Job agent informs the candidates come from automatic matching and other resources Job agent informs the employm. counsellors about the result of the interview Employment counsellors inform the unsuccessful candidates |
| Task checklists for organizing working meetings and information sessions to employers | 5.1 5.2 | Organising working meetings Organising information sessions |

Process list for services to jobseekers

| Process number in the audit trail | Process name |
| --- | --- |
| 1.1 | Obtaining information on ESS services |
| 1.2 | Registering as client |
| 2.1 | Identifying and approaching newly registered jobseekers |
| 2.2 | Registering jobseekers personally |
| 2.3 | Provision of information on ESS services and request for services |
| 2.4 | Organising information event |
| 2.5 | Conducting first interview with jobseekers |
| 2.6 | Information provision on job offers and preparation for job interview |
| 2.7 | Inclusion of clients in employment mediation service |
| 2.8 | Mass interview |
| 2.9 | Organisation of job fair |
| 3.1 | Job counselling |

Process list for services to employers

| Process number in the audit trail | Process name |
| --- | --- |
| 1.1 | Searching for and selecting employers to provide them ESS services |
| 2.1 | Checking WorkNet communication related to employers using the WN system |
| 3.1 | Preparation for contacting the employer |
| 3.2 | Visiting the employer |
| 3.3 | Communication with the employer |
| 4.1 | Conducting pre-selection services with the collaboration of the employment counsellors (EC) |
| 4.2 | Organisation of mass interview |
| 5.1 | Organising working meetings |
| 5.2 | Organising information sessions |
| 6.1 | Organisation of job fair (engagement of employers to participate) |

Risk analysis template  (services to jobseekers)

| Process number in the audit trail | Process name | Risk factor description | Impact | Probability | Summarized risk | Control points |
| --- | --- | --- | --- | --- | --- | --- |
| 1.1 | Obtaining information on ESS services |  |  |  |  |  |
| 1.2 | Registering as client |  |  |  |  |  |
| 2.1 | Identifying and approaching newly registered jobseekers |  |  |  |  |  |
| 2.2 | Registering jobseekers personally |  |  |  |  |  |
| 2.3 | Provision of information on ESS services and request for services |  |  |  |  |  |
| 2.4 | Organising information event |  |  |  |  |  |
| 2.5 | Conducting first interview with jobseekers |  |  |  |  |  |
| 2.6 | Information provision on job offers and preparation for job interview |  |  |  |  |  |
| 2.7 | Inclusion of clients in employment mediation service |  |  |  |  |  |
| 2.8 | Mass interview |  |  |  |  |  |
| 2.9 | Organisation of job fair |  |  |  |  |  |
| 3.1 | Job counselling |  |  |  |  |  |

Risk analysis  template (services to employers)

| Process number in the audit trail | Process name | Risk factor description | Impact | Probability | Summarized risk | Control points |
| --- | --- | --- | --- | --- | --- | --- |
| 1.1 | Searching for and selecting employers to provide them ESS services |  |  |  |  |  |
| 2.1 | Checking WorkNet communication related to employers already using the WN system |  |  |  |  |  |
| 3.1 | Preparation for contacting the employer |  |  |  |  |  |
| 3.2 | Visiting the employer |  |  |  |  |  |
| 3.3 | Communication with the employer |  |  |  |  |  |
| 4.1 | Conducting pre-selection services with the collaboration of the employment counsellors (EC) |  |  |  |  |  |
| 4.2 | Organisation of mass interview |  |  |  |  |  |
| 5.1 | Organising working meetings |  |  |  |  |  |
| 5.2 | Organising information sessions |  |  |  |  |  |
| 6.1 | Organisation of job fair |  |  |  |  |  |

Audit report

Audit report structure

- The auditing organisational unit and team

- The objectives and tasks of the audit

- The audited unit

- The responsible managers in office during the audit period

- The content of the audit

- The type of the audit

- Applied methodology and procedures

- Legal background

- Audited period

- The start and end of the on-the-spot audit

- The lead auditor

- The audit team

- Duration

Audit report – statements, consequences and proposed actions

| Audit statement | Ranking | Consequence | Proposal and action | Impact | Action needed (Y/N) |
| --- | --- | --- | --- | --- | --- |