Revised Logframe Component 4

| COMPONENT 4: EMPLOYMENT SERVICES |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | Output 4.1: State Employment Support Agency (SESA) supported in its implementation of the Revised New Service Model (NSM) | 4.1.1 Status of draft revisions to the NSM | 2020 NSM not yet revised – to be supported by the project | 2021 Draft NSM revisions and implementation recommendations, with methodology handbook and guidance materials elaborated and discussed with SESA 2020: NSM assessment 2021: NSM recommendations, methodology handbook(s), guidance materials | Assessment and recommendation reports on NSM implementation Handbooks and NSM procedural guidelines | NSM will be implemented through all SESA regional offices immediately upon their establishment |
|  |  | 4.1.2 Status of proposals for SESA institutional development | SESA not yet fully staffed - institutional development plan to be developed and supported by the project | Draft SESA institutional development plan elaborated and discussed with SESA, providing a basis for NSM implementation by all SESA offices 2020: Outline staffing plan, allocation of functions, draft institutional development plan 2021: Draft customised plans for inclusion of remote areas | Institutional development plan SESA public awareness strategy Annual reports of MoIDPLHSA and SESA | All necessary SESA staff will be appointed Budget and available resources are sufficient to meet NSM objectives Visibility of SESA regional offices |
|  |  | 4.1.3 Status of proposals for local employment policies | Service provision at local level not yet improved – to be supported by the project | Proposals for local employment policies elaborated and discussed with SESA, aimed at providing all citizens with access to full range of SESA services (by 2021) | SRPC "Skills Development and Matching for Labour Market Needs" Review Reports | Effective cooperation obtained with stakeholders in all regions Unemployed and job seekers from remote areas will continue to have access to the regionalised SESA services |
|  | Output 4.2: SESA supported in designing and delivering more accessible, effective and comprehensive ALMP measures for all job seekers | 4.2.1 Status of recommendations on improved ALMP measures | 2020 Assessment and recommendation reports not yet prepared – to be done by the project Currently available ALMP measures: - Training/retraining - Internships - Wage subsidies . | 2023 Comprehensive set of effective ALMP measures elaborated and discussed with SESA, designed to additionally include: - Public works (direct job creation) - Self-employment and entrepreneurship programmes (start-up incentives) 2021: ALMP measures assessment 2021: Recommendations on full set of ALMP measures 2022: ALMP manuals, guidelines 2023: Recommendations on ALMP pilot measures | Assessment and recommendation reports on improved ALMP measures Handbooks and ALMP procedural guidelines SRPC "Skills Development and Matching for Labour Market Needs" Review Reports | Regionalisation does not disadvantage unemployed and job seekers from remote areas Visibility of SESA regional offices Budget and available resources are sufficient to meet ALMP objectives Effective cooperation obtained with stakeholders in all regions Improved ALMP measures will lead to increased participation |
|  | Output 4.3: Capacity (knowledge and expertise) developed within the SESA staff to provide more effective employment services for jobseekers and employers | 4.3.1 Number of SESA staff at different levels trained in the application of: - NSM - ALMP measures - Career guidance - Support to vulnerable groups - LMIMS monitoring / analysis - Institutional development / management | 2020 Capacity building is barely started – capacity building programme to be provided by the project Training in NSM for 11 staff was so far provided in January 2020 | 2023 All current (102) and future SESA staff trained and capable of applying all aspects of the NSM effectively in relation to their job descriptions 2020: Induction training and TNA for all staff 2021: Advanced customised training conducted | Training assessment reports / tests results, including participation disaggregated by level of responsibility, gender Report of study visit Relevant information from annual reports of MoIDPLHSA and SESA | Trained personnel retained at SESA SESA uses the provided capacity building materials for its internal training programmes on an on-going basis |