|  | Result chain | Indicator(s) | Baseline | Target | Source and means of verification | Assumptions |
| --- | --- | --- | --- | --- | --- | --- |
| Impact: Overall objective | OVERALL OBJECTIVE: (Contribute to) Improved employability of women and men in the selected regions of Georgia | - Proportion of NEETs in the population | 2020 Proportion of NEETs 15-24: 26.9% (male 23.2%, female 31.0%) in 2018 | 2023 Target for proportion of NEETs 15-24, in 2023: <22.8% | GEOSTAT LFS survey (Baseline and targets from Labour & Employment Strategy 2019-2023) | Not applicable |
|  |  | - Women of working age employed / total working age female population | Women’s participation rate: 55.6% in 2019 | Target for women’s participation rate: >63% in 2023 | GEOSTAT LFS (Baseline and targets from Labour & Employment Strategy 2019-2023) |  |
|  |  | - Lifelong learning rate by gender | 0.61% (M 0.68%, F 1.55%) in 2015 | 0.8% (2020), 1.5% with at least 0.5 percentage point increase for women (2022) | GEOSTAT LFS, EMIS (Baseline and targets from Action Document for Annual Action Programme 2017) |  |
|  |  | - Youth drop-out rate from VET | 14% in 2016 | 13% (2020), 11% (2022) | EMIS (Baseline and targets from Action Document for Annual Action Programme 2017) |  |
| Outcome: Specific objective | SPECIFIC OBJECTIVE: (Contribute to) Enhanced capacity of the beneficiary ministries and agencies, as well as local communities, to develop, implement, monitor and review skills development and matching policies | - Status of TA capacity building plans for MoESCS, MoESD, MoIDPLHSA (incl. SESA) and Youth Agency (YA) | 2020 TA capacity building plans not yet defined for the MoESCS, MoESD, MoIDPLHSA/SESA, Youth Agency – to be done by the project | 2023 TA capacity building plans defined, agreed with each beneficiary and fully implemented | Assessment reports of TA capacity building plans for MoESCS, MoESD, MoIDPLHSA (incl. SESA), YA, disaggregated by gender | The enhanced capacities of trained personnel will be effectively utilized in sector reform policy development, implementation and monitoring, and the trained personnel will be retained by the respective institutions |
|  |  | - Status of TA proposals for improving the coordination of policy development, implementation and monitoring for skills development & matching | TA proposals for improved policy coordination not yet defined – to be done by the project (Inter-agency cooperation, apart from consultations on developed policies is now mainly ad hoc) | Improved policy coordination mechanism for skills development/ matching policy development, implementation and monitoring skills development agreed and launched with the responsible institutions | MoUs or other formal agreements for inter-agency cooperation | The Government further maintains and improves the efficiency of inter-agency policy dialogue mechanisms Beneficiaries and targeted stakeholders are prepared to cooperate more closely in the revision/updating of policies, strategies etc. |
|  |  | - Development and implementation status of draft strategies and action plans of the MoESCS, MoIDPLHSA, MoESD and the Youth Agency related to skills development & matching | Current status of existing strategies/ action plans (VET Strategy, CG Strategy, Youth Strategy (all 2021-26) not yet prepared; Labour/Employment Strategy 2019-23 approved but not yet implemented) | VET Strategy/AP, CG Strategy/AP, Youth Strategy/AP and Labour/Employment Strategy have been launched and are annually monitored and reported on by the responsible institutions | Annual reports of MoESCS, MoESD, MoIDPLHA/SESA, YA Monitoring reports of implementation of VET Strategy/AP, CG Strategy/AP, Youth Strategy/AP and Labour/Employment Strategy | The respective roles and responsibilities of beneficiaries and other stakeholders are appropriate for sector reform policy development, implementation and monitoring Appropriate budget and resource allocation provided for Strategy/AP implementation |

| COMPONENT 1: NATIONAL SECTOR REFORM POLICIES |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Outputs – Results | Output 1.1: Updated national sector reform policies drafted | 1.1.1 Status of drafts of updated sector reform policies, strategies and action plans | 2020 Current status of the sector reform strategies that will be supported by the project: - Only the Labour/ Employment Strategy (2019-23) was developed in compliance with the Government’s development and monitoring guidelines - VET strategy (2021-26), CG Strategy (2021-26) and Youth Strategy (2020-25) not yet drafted | 2023 Drafts developed/ updated in compliance with Government development and monitoring guidelines include: - National VET Strategy (2021-26), and Action Plans (2020, with AP updated as necessary) - National Career Guidance Strategy (2021-26) and Action Plan (2020, with AP updated as necessary) - Youth Strategy (2020-25) and Action Plan (2020, with AP updated as necessary) - Labour/Employment Strategy (2019-23) (AP updated as necessary and Strategy updated 2023) | Draft policy documents, Annual progress and performance reports of ministries and agencies BS mission reports | Ministries, agencies and stakeholders including social partners and regional players actively cooperating in development, implementation and monitoring of sector reform policy-related activities The policies are properly funded and resourced |
|  |  | 1.1.2 Status of proposals for improved policy coordination and monitoring | Proposals for improved policy coordination and monitoring have not yet been drafted – to be done by the project | Proposals for improved policy coordination and monitoring have been elaborated and discussed with the beneficiary institutions (2020), with further advice provided as necessary (by 2023) | Records of discussions with beneficiaries, endorsement decision Minutes/reports of inter-agency cooperation meetings related to sector reform policy development, implementation and monitoring | Beneficiary institutions agree to further consider and institutionalise policy coordination proposals |
|  | Output 1.2: Capacities in sector reform policy development, implementation and monitoring enhanced | 1.2.1 Implementation status of TA capacity building programme of the project | 2020 TA capacity building programme not yet existing at start of project – to be developed by the project | 2023 Comprehensive TA capacity building programme developed and agreed (2020), and completed (by 2023) Beneficiaries advised and supported to help them to meet BS indicators (annually, completed 2023) | Records of discussions with beneficiaries, endorsement decision Annual progress and performance reports of ministries and agencies BS monitoring mission reports | Beneficiaries accept the need to further develop their capacities for policy development, implementation and monitoring Institutions will optimise their use of newly acquired skills and knowledge of their personnel Institutions will retain their trained staff |
|  |  | 1.2.2 Number of officials trained in all topics covered by the TA capacity building programme, disaggregated by institution, gender | Training needs not yet fully defined and training programme not yet developed at the start of project – to be done by the project (ToR suggested a number of training topics, but this should be reviewed and revised in consultation with beneficiaries) | An agreed number of officials from each beneficiary trained –disaggregated by topic, institution, gender (completed by 2023) (number to be agreed with beneficiaries during development of programme) | Assessment reports of capacity building programme including number of officials trained, disaggregated by institution, gender | Beneficiaries recognise the importance of investing in the training and career development of their personnel, using opportunities provided by the capacity building programme to ensure that key staff are trained |
|  | Output 1.3: Enhanced capacity to provide visibility & communications for sector reform policies and specific services provided by beneficiary institutions | 1.3.1 Status of plans, tools, materials etc. developed for public awareness campaigns supported by the project | 2020 None at start of project – to be developed by the project Public awareness campaigns to be supported by the project not yet planned or implemented | 2023 Public awareness campaigns planned and supported by the project (for implementation by project beneficiaries) on: - Key sector policy developments - VET / LLL opportunities - Career guidance - Youth services - Employment services / SESA regional offices - LMIS/LM issues (completed by 2023) | Records of discussions with beneficiaries, endorsement decision Information and visibility materials prepared for campaigns Press releases, and monitoring of resulting media coverage | Beneficiaries are committed to promote reform policies though PR and media activities supported by the project Media will be interested in providing positive coverage of the reforms and availability of services of beneficiary institutions supported by the project |
|  |  | 1.3.2 Number of stakeholder institutions participating in visibility and communications events supported by the project | None at start of project – events to be planned and organized by, or with support from, the project Visibility and communications events not yet planned or organized at the start of the project | Schedule of visibility events, together with a comprehensive list of the stakeholder institutions targeted by each event, drafted and agreed with EUD and the appropriate beneficiary institutions (updated periodically, completed by 2023) | Records of discussions with beneficiaries, endorsement decision Reports of visibility events, including attendance lists | Commitment of all relevant stakeholders at national and regional level to participate in information and visibility events related to the sector reform policies |
| Component 2: Skills Development & ENTREPRENEURSHIP LEARNING |  |  |  |  |  |  |

|  | Output 2.1: Enhanced capacity of the MoESCS to further develop and modernise skills development and LLL systems | 2.1.1 Status of the project’s situational analysis on access to VET/LLL | 2020 Situational analysis not yet prepared – to be done by the project |  | 2023 Situational analysis on access to VET/LLL elaborated as a basis for identifying measures to be recommended (2020) | Elaborated situational analysis and measures | Cooperation from private as well as public VET institutions will be forthcoming |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 2.1.2 Status of measures to improve access to VET and LLL for targeted groups, incl. females, NEETs, vulnerable groups | Measures to increase access to VET/LLL and combat early school leaving not yet defined – to be done by the project |  | Measures to increase access to VET/LLL and combat early school leaving elaborated and discussed with beneficiary (2020) and advisory support provided to implementation (to 2023) | Records of discussions with beneficiaries, endorsement decision Annual progress reports of MoESCS on VET Strategy Implementation, incl. implementation of the specific measures EMIS participation data | The necessary policy and budgetary decisions are made to enable expansion of VET and LLL provision, including provision in areas where there is currently none Proposed measures are implemented by VET institutions |
|  | Output 2.2: Enhanced capacity of educational institutions to provide professional orientation and career guidance for learners in general, vocational and higher education | 2.2.1 Status of the situational analysis and action plan for career education and guidance provision in educational institutions at all levels of education |  | 2020 Situational analysis not yet developed at beginning of project – to be done by the project Previous situational analysis (by MCA-G in 2015) showed that existing careers information and guidance provision is extremely limited, especially in schools | 2023 Situational analysis and draft action plan (in line with proposed National Career Guidance Strategy) elaborated (2020) and advisory support provided to implementation (to 2023) | Situational analysis on career guidance provision Records of discussions with beneficiaries, endorsement decision | Cooperation between all actors (MoESCS and educational institutions, Youth Agency, SESA) in developing compatible approaches in career education and guidance Cooperation from stakeholders incl. employers in the provision of career information materials and career events |
|  |  | 2.2.2 Status of TPDC career education and guidance modules for general education teachers and VET college career managers |  | Only very basic career guidance training is currently available for teachers – more advanced training to be developed by the project | Training courses and materials for teachers and career managers developed (2021) and piloted (to 2023) | Records of discussions with beneficiaries, endorsement decision Developed training programmes for career managers and counsellors, and assessment reports of piloting | Capacity of TPDC to provide the necessary training programmes for school and college personnel Adequate budget and resources allocated to support career guidance implementation by trained personnel in educational institutions |
|  | Output 2.3: Enhanced capacity to deliver entrepreneurship education in general, vocational and higher education and lifelong learning | 2.3.1 Status of new entrepreneurship key competence training modules for school teachers and VET teachers |  | 2020: Introductory module already available, and 50% of VET teachers trained, but a comprehensive entrepreneurship key competence training package including more advanced training not yet developed – to be done by the project | 2023 A 2-stage training package for teachers in general education and VET in entrepreneurship key competences developed (2021) and piloted (with more advanced module building on the existing introductory module) (by 2023) | Training modules and materials, and report on piloting Records of discussions with beneficiaries, endorsement decision | TPDC has the capacity and resources to deliver training in career counselling and in entrepreneurship to a sufficient number of teachers VET and general education institutions are operationally capable of delivering entrepreneurship key competence learning to their students |
|  |  | 2.3.2 Status of review of entrepreneurship key competence development and good practice case studies in universities |  | Not yet started – to be done by the project | Elaborated report on entrepreneurship key competence development in higher education (by 2022) Two good practice case studies (by 2022) | Report on entrepreneurship key competence development in universities, with 2 good practice case studies Assessment report of consultation workshop | Universities agree to deliver entrepreneurship key competences in their programmes |

COMPONENT 3: YOUTH

|  | Output 3.1 Enhanced capacity of Youth Agency to develop and deliver effective youth services | 3.1.1 Status of Youth Agency institutional capacity building plan | 2020 No TA capacity building plan yet defined – to be done by the project TA capacity building plan for Youth Agency not yet defined | 2023 Capacity building plan developed (2020) and delivered (completed by 2023) | Agreed capacity building programme Records of discussions with beneficiaries, endorsement decision Annual progress reports of Youth Agency documenting capacity development | Effective coordination and cooperation arrangements between the Youth Agency and other stakeholders, including municipalities and other regional interests, VET colleges and SESA |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | 3.1.2 Number of Youth Agency staff trained, disaggregated by gender | No training yet provided by the TA project – to be done by the project Training programme not yet developed | Approx. 20 key YA staff trained, including training in each of the specified youth services to be developed / delivered (completed by 2023) | Assessment report on training for YA staff, incl. participation disaggregated by gender Assessment report of study visit for Youth Agency staff | Enhanced capacities of trained staff will be utilized in the improvement and delivery of youth services, and trained staff will be retained |
|  |  | 3.1.3 Status of drafts of Youth Agency Action Plan, and Law on Youth | Not yet started – to be supported by the project | Drafts of Action Plan and Law on Youth elaborated and presented to the Youth Agency (2020) | Draft action plan of Youth Agency Draft Law on Youth Records of discussions with beneficiaries, endorsement decisions | The Law on Youth will provide a firm legal basis youth services and operations of the Youth Agency, and will be adopted by Parliament The Youth Agency has sufficient budget and resources to implement the Action Plan |
|  |  | 3.1.4 Status of drafts of youth services proposals and materials | No proposals yet formulated or drafted – to be supported by the project Existing youth services provision is considered to be weak and not universally available | The range of elaborated draft youth services proposals and materials elaborated and resented to the Youth Agency include those relating to: - non-formal short courses in key competences - career guidance - youth entrepreneur-ship (completed by2023) | Records of discussions with beneficiaries, endorsement decisions Details of the youth services materials disseminated by the YA to municipalities and youth centres | A firm legal basis for the provision of specified youth services is provided by the Law on Youth The Youth Agency and municipalities have sufficient budget and resources to implement the developed youth services |
|  | Output 3.2: Improved organizational and human capacities to deliver youth services at local level | 3.2.1 Status of draft improvement and development plans for youth centres / local providers of youth services | 2020 None yet developed – to be supported by the project | 2023 Draft improvement and development plans drafted for local providers of youth services (number and locations to be agreed with Youth Agency) (by 2023) | Survey report of YA on current situation of youth centres and youth services provision in the regions (to be done by mid-2020) Proposed development plans for identified youth service providers (to be agreed with the YA) Records of discussions with beneficiaries, endorsement decisions | The municipalities are committed to supporting youth centres in the delivery of the improved portfolio of youth services Availability of sufficient personnel and funding resources in the Municipalities to support effective provision of youth services Disadvantaged youth and NEETs in particular will participate in activities organized by Youth Centres |
|  |  | 3.2.2 Number of youth workers provided with basic training in delivery of youth services, disaggregated by gender and region | None at start of project – training to be provided by the project TA capacity building training for youth workers not yet developed by the TA project | At least 80 youth workers provided with basic training to deliver specified youth services, disaggregated by gender (2021-2023) | Assessment report on basic training of youth workers, disaggregated by gender | The identified youth centres will utilise the skills and knowledge of trained personnel to deliver youth services in their municipalities |
|  |  | 3.2.3 Status of draft occupational standards for youth workers | Development not yet started – to be supported by the project | Occupational standards for youth work developed and proposed for authorisation (by 2022) | Records of discussions with beneficiaries, endorsement decisions Authorization request/ documentation | Occupational standards will be accepted as a basis for developing a modular framework programme / qualification for youth workers in the formal VET system |
|  |  | 3.2.4 Status of draft qualification for youth workers | Development not yet started – to be supported by the project | A draft modular qualification is elaborated, based on developed occupational standards (by 2023) | Records of discussions with beneficiaries, endorsement decisions | Suitable VET provider(s) will collaborate in development of a qualification/programme for youth workers with a view to seeking authorisation in the formal VET system and inclusion in the NQF |

| COMPONENT 4: EMPLOYMENT SERVICES |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | Output 4.1: State Employment Support Agency (SESA) supported in its implementation of the Revised New Service Model (NSM) | 4.1.1 Status of draft revisions to the NSM | 2020 NSM not yet revised – to be supported by the project | 2021 Draft NSM revisions and implementation recommendations, with methodology handbook and guidance materials elaborated and discussed with SESA 2020: NSM assessment 2021: NSM recommendations, methodology handbook(s), guidance materials | Assessment and recommendation reports on NSM implementation Handbooks and NSM procedural guidelines | NSM will be implemented through all SESA regional offices immediately upon their establishment |
|  |  | 4.1.2 Status of proposals for SESA institutional development | SESA not yet fully staffed - institutional development plan to be developed and supported by the project | Draft SESA institutional development plan elaborated and discussed with SESA, providing a basis for NSM implementation by all SESA offices 2020: Outline staffing plan, allocation of functions, draft institutional development plan 2021: Draft customised plans for inclusion of remote areas | Institutional development plan SESA public awareness strategy Annual reports of MoIDPLHSA and SESA | All necessary SESA staff will be appointed Budget and available resources are sufficient to meet NSM objectives Visibility of SESA regional offices |
|  |  | 4.1.3 Status of proposals for local employment policies | Service provision at local level not yet improved – to be supported by the project | Proposals for local employment policies elaborated and discussed with SESA, aimed at providing all citizens with access to full range of SESA services (by 2021) | SRPC "Skills Development and Matching for Labour Market Needs" Review Reports | Effective cooperation obtained with stakeholders in all regions Unemployed and job seekers from remote areas will continue to have access to the regionalised SESA services |
|  | Output 4.2: SESA supported in designing and delivering more accessible, effective and comprehensive ALMP measures for all job seekers | 4.2.1 Status of recommendations on improved ALMP measures | 2020 Assessment and recommendation reports not yet prepared – to be done by the project Currently available ALMP measures: - Training/retraining - Internships - Wage subsidies . | 2023 Comprehensive set of effective ALMP measures elaborated and discussed with SESA, designed to additionally include: - Public works (direct job creation) - Self-employment and entrepreneurship programmes (start-up incentives) 2021: ALMP measures assessment 2021: Recommendations on full set of ALMP measures 2022: ALMP manuals, guidelines 2023: Recommendations on ALMP pilot measures | Assessment and recommendation reports on improved ALMP measures Handbooks and ALMP procedural guidelines SRPC "Skills Development and Matching for Labour Market Needs" Review Reports | Regionalisation does not disadvantage unemployed and job seekers from remote areas Visibility of SESA regional offices Budget and available resources are sufficient to meet ALMP objectives Effective cooperation obtained with stakeholders in all regions Improved ALMP measures will lead to increased participation |
|  | Output 4.3: Capacity (knowledge and expertise) developed within the SESA staff to provide more effective employment services for jobseekers and employers | 4.3.1 Number of SESA staff at different levels trained in the application of: - NSM - ALMP measures - Career guidance - Support to vulnerable groups - LMIMS monitoring / analysis - Institutional development / management | 2020 Capacity building is barely started – capacity building programme to be provided by the project Training in NSM for 11 staff was so far provided in January 2020 | 2023 All current (102) and future SESA staff trained and capable of applying all aspects of the NSM effectively in relation to their job descriptions 2020: Induction training and TNA for all staff 2021: Advanced customised training conducted | Training assessment reports / tests results, including participation disaggregated by level of responsibility, gender Report of study visit Relevant information from annual reports of MoIDPLHSA and SESA | Trained personnel retained at SESA SESA uses the provided capacity building materials for its internal training programmes on an on-going basis |
| COMPONENT 5: INFORMATION SYSTEMS AND ANALYSIS |  |  |  |  |  |  |
|  | Output 5.1: Improved integrity and compatibility of data and information systems for evidence-based policy making and implementation | 5.1.1 Status of proposal for enhanced employment statistics resource | 2020 Concept note for employment statistics resource already drafted by the project, but not yet agreed with beneficiaries or implemented Note: The objective is to include employment statistics from different sources within a single shared resource (referred to in the concept note as a data warehouse) | 2023 Elaborated proposals for employment statistics resource discussed with beneficiaries (2020) Technical specifications elaborated, taking account of results of consultation with beneficiaries (by 2021) If proposal is accepted, advisory support to implementation has been provided (by 2023) Staff of beneficiary institutions have been trained in using the data resource, including its use in making evidence-based recommendations (by 2023) | Finalised concept note/ proposal for employment statistics resource Technical specifications and Implementation plan for employment statistics resource Records of discussions with beneficiaries, endorsement decision Handbooks and operating procedures Assessment reports on the training provided, including participation by institution, gender | Agreements on data sharing between involved institutions will be forthcoming An appropriate institution agrees to host an employment statistics resource (possibly as component of an existing database) Sufficient resources for implementation will be available in the medium term Source databases will be upgraded as necessary to provide required data Trained personnel are retained by the relevant authorities |
|  | Output 5.2: Labour Market Information Management System (LMIMS) portal technically revised and upgraded | 5.2.1 Status of the recommendations for technical upgrading of the LMIMS | 2020 Not yet started – to be prepared by the project Note: Only two WorkNet modules so far implemented (Vacancy and Job Seeker portals) | 2023 Recommendations for upgrading elaborated and discussed with MoIDPLHSA/SESA, with implementation proposal for remaining WorkNet modules (by 2021) (Including Enterprise portal with upgraded Vacancy and Job Seeker sub-portals including differentiation of categories of jobseeker -unemployed, employed, social clients | Report on LMIMS upgrade recommendations | Beneficiary institutions remain committed to upgrading the LMIMS Sufficient financial and technical resources are available for implementation of the enterprise portal |
|  |  | 5.2.2 Status of the guidelines on analytical usage of LMIMS | None yet prepared – to be prepared by the project | Draft guidelines elaborated and capacity building activities elaborated and discussed with MoIDPLHA /SESA (2022) | Guideline on using LMIMS for analytical purposes Report on training LMIMS/WorkNet users | LMIMS will be upgraded according to the recommendations |
|  | Output 5.3: Capacity of LMIS team enhanced in analysis, survey and anticipation methods | 5.3.1 Level of capacity of LMIS team in labour market analyses and forecasting | 2020 LMIS team has already some capacity (e.g. LM analyses 2018 and 2019, 2 sector analyses, survey on business demand for skills) | 2023 LMIS team has capacity to undertake different type of surveys (capacity building support started 2020, completed by 2023) | Information on implemented training on the LMIS web portal Training assessment report | Trained personnel will be retained |
|  |  | 5.3.2 Status of draft guidelines on skills anticipation surveys and analysis | None existing – to be supported by the project | Guidelines are used in the generation of LMIS reports (Draft sector skills anticipation guideline; and Draft guideline for all sectors with 5-year perspective: both in 2020) (Other guidelines may be developed on request, 2021, 2022, 2023) | Delivered survey/analysis reports based on the guidelines | Efficient cooperation with relevant industry representatives and GEOSTAT |
|  |  | 5.3.3 Status of concept notes for further developing the LMIS and the LMIS web portal | Concept note for upgrading LMIS and the LMIS web portal not yet elaborated by the project | Concept note for upgrading LMIS to provide new functional opportunities elaborated and presented to MoESD (2020) Proposals for upgrading LMIS web portal elaborated and presented to the beneficiary (2021) If accepted, advisory and technical support has been provided to upgrades of LMIS and LMIS web portal (by 2023) | Finalised concept notes for further developing the LMIS and the LMIS web portal, providing new modules and updating opportunities Technical specifications and Implementation plan for upgrading the LMIS web portal Records of discussions with the beneficiary, endorsement decision | Efficient cooperation with relevant industry representatives and GEOSTAT Sufficient resources will be provided to enable the recommendations to be implemented |
|  | Output 5.4: Enhanced capacity of EMIS to support evidence-based education and training policy making | 5.4.1 Status of review report on content and capacity of EMIS | 2020 Review report not yet prepared | 2023 Review report elaborated, incl. recommendations for filling identified data gaps, and discussed / agreed with EMIS and MoESCS (completed by 2021) | Records of discussions with beneficiaries, endorsement decision Annual progress reports of EMIS | EMIS data coverage is sufficient to meet the needs of education and training policy making without major changes Data from LMIMS and LMIS etc. is shared and available to EMIS analysists Sufficient resources are available for EMIS upgrade |
|  |  | 5.4.2 Status of TA capacity building plan for using EMIS data in evidence-based policy-making | Capacity building plan not yet prepared – to be prepared and implemented by the project | TA capacity building plan developed, agreed and implemented (completed by 2023) | Training assessment report | Trained specialists are retained by beneficiaries Policy-related reports will be generated by EMIS (e.g. incl. socio-economic backgrounds of VET students, VET students with special needs, annual completion rates of VET programmes, etc.) |

|  | Output 5.5 Enhanced capacity of institutions using LMIS, LMIMS and EMIS data in evidence-based policy-making | 5.5.1 Status of capacity assessment report and training plan | 2020 Capacity building assessment/training plan not yet available – to be done by the project | 2023 Capacity of data users (all beneficiary ministries, agencies) assessed, and training plan implemented, with all relevant personnel nominated by the relevant institutions trained (completed 2023) | Records of discussions with beneficiaries, endorsement decision Training assessment reports | Developed methodologies and protocols are incorporated into the internal arrangements of the ministries and agencies, and are actively used in evidence-based policy making Trained personnel are retained by the relevant stakeholders |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | 5.5.2 Status of the survey methodology and pilot surveys proposed for Enterprise Georgia | Survey methodology not yet prepared – to be done by the project | Survey methodology elaborated, presented to Enterprise Georgia and used in the implementation of 2 pilot surveys (completed 2022) | Survey methodology document Records of discussions with beneficiary, endorsement decision Reports of pilot surveys | Trained personnel are retained by Enterprise Georgia |
| OMPONENT 6: GRANT SCHEME MONITORING |  |  |  |  |  |  |

|  | Output 6.1: Grant scheme implementation supported through the monitoring of grant projects | 6.1.1 Status of monitoring reports / recommendations | 2020 None: grant scheme applications are still under evaluation, with selection expected by mid-2020 – contracted projects will be monitored by the project | 2023 6-monthly monitoring reports produced following evaluation of progress reports and monitoring visits (completed by 2023) | Monitoring reports and other feedback provided to EUD | Grantees have the necessary capacity to manage and implement their projects according to contractual requirements Monitoring reports and recommendations are followed up by the EUD with project implementors |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | 6.1.2 Status of the compendium of grant project results and good practices | None: will be compiled towards the end of the grant scheme (2023) – to be done by the project | Compendium produced at the end of the grant scheme according to structure/format agreed with the EUD (2023) | Records of discussions with EUD and formal confirmation of acceptance of monitoring reports and compendium | Compendium is used to inform programming and further interventions |