| Project/Activities | Description | timeframe |
| --- | --- | --- |
| USAID Project Social model of Disability Assessment and Status Determination System |  |  |
| Meetings with the Disability Community |  |  |
| First Informational meeting within the existing working group on social model under the Ministry | - Update on the recent development to the WG; - Introducing a standardized Children’s Functional Assessment Instrument; - Introducing new ways to engage the disability community. | First meeting to be held in June – - Facilitated by the Ministry - Supported by UNICEF |
| Setting up the new mechanism to engage the disability community at large to ensure their higher representation: Council with various thematic groups within | - Creation of the ToR of the council and thematic groups | TOR to be created in June. First Meeting of the council in July. Meetings continue throughout the USAID and SDG project. - Facilitated by the Ministry - Supported by UNICEF |
| EPRA- Additional validation of the Children’s Functional Assessment Instrument |  |  |
| Additional validity studies for the Children’s Functional Assessment Instrument | Agreement has been reached and the validity studies will take place during June-September | June - September |
| Other Pilot Related issues |  |  |
| - “Winner-Loser” analysis, Cost-benefit analysis, Final Report of the GASW - External analysis of the pilot by an International Consultant (Under the SDG project) | Internal and External Analysis of the pilot results in relation to institutionalization of the model; | June-August |
| - Discussions on merging existing electronic application and database with the Ministry’s data systems (Under the SDG project) | - Transitioning from Application to the Web settings - Merging pilot data with the Ministry’s data | Initial Meetings/discussions to be held in July |
| SDG project Rollout |  |  |
| Legislative changes to ensure institutionalization of a social model of disability assessment and status determination system | Revisions and changes within the law on social-medical expertise – When to start working on the amendment of the law? | TBD |
| Identification of a second region for testing of disability status determination system – selection criteria and a context of the activity. | - Which region/s - Which groups - Which medical facilities (psyco-neurological facility to be included) - Other criteria - Sustainability – still a pilot or part of the official rollout? | TBD |
| Capacity development and institutionalization of the supervision and inspection systems of the NEW disability assessment system | - Work with the Medical Care Agency under the ministry - External supervision opportunities | Initial discussions to start in July |
| Identification of relevant educational institutions, development of curriculum to ensure sustainability of capacity building of frontline professionals of the disability assessment | - Mapping of educational institutions - Development of Curriculum/Certification programme | June – September |