## Activités
Technical Assistance to Welfare modernization and social inclusion in Georgia |  | Working days - 24 months |  |  |  | Working days - First year
|  | International |  |  | Local | International |  |  | Local
|  | Total | CdE | ECT |  | Total | CdE | ECT
Inception phase |  | 15 | 10 | 5 |  | 10 | 10 |  |  |  | Inception report | June 2019
Launch event |  | 10 | 5 | 5 |  | 15 | 5 | 10 | 10 |  | Launch event involving 100 persons is organised | September 2019
Pillar 1 | Enhancing social support to vulnerable groups | [8 empty] | Partners | Delivrables | Period
Component 1.1 | Improving the support to peoples with disabilities (PWD) by developing functional/social model of assessing and granting disability status in line with the UN Convention on the Rights of Persons with disabilities | [8 empty] | UNICEF, WHO, USAIDS
A111 | Development of methodology for piloting of disability assessment in Samtskhe Javakheti region | 35 | 10 | 25 |  | 35 | 10 | 25 |  |  |  Methodology for piloting the disability assessment in Samtskhe Javakheti region is drafted and approved by the beneficiary;  Electronic versions of administration of the instrument's scores are is ready for implementation  Database for data treatment is established  1 day workshop is organised in Borjomi in order to discuss the methodology with local authorities | April 2019
A112 | Piloting of assessment instruments in Samtskhe Javakheti region | 100 | 40 | 60 | 245 | 60 | 20 | 40 | 215 |  |  Trainings are organised involving XXX persons;  XXX PWD are evaluated according to new assessment instruments  Report on piloting is drafted;  Anonymous database is established | September 2020
A113 | Policy impact assessment based on the results of piloting in two Georgian regions and best international practices in implementing the functional/ social model for evaluation of disability | 75 | 20 | 55 | 60 | 10 | 5 | 5 | 15 |  |  Public policy impact assessment report (including gender dimension) is drafted;  Simulation model is developed based on pilot data of two regions;  Analysis of connection between the results of social/functional assessment, environmental assessment and health condition / medical diagnosis (proof of functional limitation, disability etc.). | December 2020
A114 | Proposal for minimum support package for people/children with disabilities | 80 | 20 | 60 | 100 | 10 | 5 | 5 | 10 |  |  Different options for minimum support package for people/children with disabilities including their pricing  Recommendations on involvement of different stakeholders (Ministry, other public institutions, local authorities, SCOs) with clear distribution of roles;  Development of methodology of assessment of capacities of different service providers | December 2020
A115 | Support in drafting a realistic Action Plan for implementation of functional/social model in Georgia | 55 | 25 | 30 | 60 | 0 | 0 | 0 | 0 |  |  Proposal of Action Plan for implementation of functional/social model in Georgia including cost of the scale up and the reform;  Organisation of debates involving professionals and PWD | April 2021
A116 | Support in Implementation of awareness raising compaigns and consultations about implementation of functional/social model in Georgia | 45 | 15 | 30 | 60 | 30 | 10 | 20 | 40 |  |  Organisation of 3 thematic round tables involving different stakeholders  Communication strategy about difference between medical and social models of disability | April 2021
A117 | Study Visit | 20 | 10 | 10 |  | 0 | 0 | 0 |  |  |  Organisation of study visit for 6 officials to France  Report of study visit | April 2021
necessary information : - Report (translated in English) explaining the adaptation and the rationale behind these adaptations - methodology of Adjara A.R Pilot project to test the new assessment methodology
Component 1.2 | Support to the implementation of the second phase of deinstitutionalization | [8 empty] | UNICEF
A121 | Development of methodology for monitoring of standards for children under state care with severe disabilities | [9 empty] |  Methodology is drafted for pilot implementation of standards for children under state care with severe disabilities and monitoring of quality of delivered services  Workshop to discuss the methodology of piloting  Selection of 2 pilot regions | July 2019
A122 | Support in implementation of monitoring of standards for children under state care with severe disabilities | [9 empty] | 2 monitoring missions are organised in 2 pilot regions 3 training sessions are organised for potential services providers | July 2019 - July 2020
A123 | Drafting of recommendations to generalise specialised home care service for children with severe disabilities under the state care | [9 empty] | Report on recommendations to generalise specialised home care service for children with severe disabilities under the state care | December 2020
necessary information : - standards for children under state care with severe disabilities approved by MOLHSA (translated in English) -
Component 1.3 | Establish new services for children in street situation to protect their rights and promote their integration. | [8 empty] | UNICEF
A131 | Support in development of new standards for services provided to children in street situation | [9 empty] |  Workshop for identification of best practices in service delivery for children in street situation  Proposal of new standards for services provided to children in street situation is drafted  Validation workshop involving different stakeholders is organised | December 2019
A132 | Development of methodology for monitoring of standards for services provided to children in street situation | [9 empty] | Methodology is drafted for monitoring of standards for services provided to children in street situation | March 2020
A133 | Drafting of recommendations to mainstream services provided to children in street situation | [9 empty] | Report on recommendations to generalise specialised home care service for children with severe disabilities under the state care | December 2020
necessary information : - ??? -
Pillar 2 | Ensure affordable and quality healthcare and promote of a healthy lifestyle | [8 empty] | Partners | Delivrables | Period
Component 2.1 | Improve the effectiveness and efficiency of universal healthcare and other programs | [8 empty] | WHO
A211 | Recommendations of common approaches to be used to address high cost of services, drugs and consumables | [9 empty] | Recomendations on regulation of drug market, medical services and consumables | July 2019
A212 | Analysis of introduction of efficient remuneration models | [9 empty] | Recomendations on introduction of efficient remuneration models | July 2019
A213 | Support in elaboration of strategic purchasing mechanisms | [9 empty] | Report presenting the strategic purchasing mechanisms (including principles of contracting for purchasing services, continue selective contracting ) in order to improve the effectiveness and efficiency of universal healthcare and other related health programs; Road map for implementation of strategic purchasing mechanisms | September 2019
A214 | Piloting of proposed strategic purchasing mechanisms | [9 empty] | Piloting methodology in 2 regions is developed; piloting is implemented; Report on actions to be taken to improve the effectiveness and efficiency of universal healthcare, with a particular attention to quality of care and cost containment methods | December 2020
A211 | Define standard operating procedures for the implementation of performance-based contracting, especially to primary health care | 30 | 5 | 25 | 20 | 20 | 5 | 15 | 10 |  | Standard operating procedures for the implementation of performance-based contracting, especially to primary health care are drafted | December 2019
A212 | Analyse the functioning of IT in the health sector (E health) | 35 | 5 | 30 | 40 | 15 | 5 | 10 | 20 |  | Report of functioning of IT in the health sector (E health) and recomendations for improvement | July 2020
A213 | Study Visit | 20 | 10 | 10 |  | 20 | 10 | 10 |  |  |  Organisation of study visit for 6 officials to France  Report of study visit
necessary information : - Results of external survey to identity groups of population that are not adequately covered and the main gaps of the existing health care system (e.g. geographical disparities, access to drugs and services, increasing costs, challenge in payment mechanisms, diverse quality of treatment, etc.) -
|  | Working days - 24 months |  |  |  | Working days - First year
|  | International |  |  | Local | International |  |  | Local
|  | Total | CdE | ECT |  | Total | CdE | ECT
Component 2.2 | Strengthen the Mental Health Services | [8 empty] | WHO
A221 | Development of the roadmap for implementation of deinstitutionalization and the development of community based services in line with recomendations of WHO report | 50 | 20 | 30 | 50 | 50 | 20 | 30 | 50 |  | Development of the roadmap for implementation of deinstitutionalization and the development of community based services in line with recomendations of WHO report | September 2019
A222 | Elaboration of monitoring mechanisms for protection of Human rights is mental health institutions (public and private) | 50 | 20 | 30 | 30 | 40 | 10 | 30 | 30 |  | Elaboration of monitoring mechanisms for protection of Human rights is mental health institutions (public and private) | June 2020
A223 | Formulation of recomendations for improving of legal framework for mental health care in line with best EU practices | 40 | 20 | 20 | 70 | 0 |  |  |  |  | Formulation of recomendations for improving of legal framework for mental health care in line with best EU practices | December 2020
A224 | Study Visit | 20 | 10 | 10 |  | 20 | 10 | 10
necessary information : - national strategy of mental health adopted in 2014 by the Decree of Government of Georgia N762). (translated in English) - Report WHO -
Pillar 3 | To optimise the ressources allocated to IDP needs | [8 empty] | Partners | Delivrables | Period
Component 3.1 | Reinforce the efficiency of ressources allocated to IDP needs | [8 empty] | NGOs and CSOs
A31 | Proposal of different innovative solutions for housing and livelihood problems of vulnerable IDPs (vulnerability score between 100, 001 and 200, 000) | 40 | 25 | 15 | 35 | 10 | 5 | 5 | 10 |  | Report and recommendations on i ) the resettlement providing information on the number of people/ families resettled and resettlement solution ; ii) livelihood issues (socio-economic integration) | April 2020
A32 | Analysis of budgetary impact of different solutions for reform of IDP benefits (from a status-based government benefit to a needs-based benefit) | 35 | 25 | 10 | 35 | 0 | 0 |  | 35 |  | Report and recommendations with different budgeted scenarii | June 2020
A33 | Organisation of workshop about best options for Georgia, including an benchmark of other countries' experiences in management of IDP issues | 40 | 25 | 15 | 35 | 0 | 0 |  |  |  | 1-day conference with benchmark presentations of relevant experiences (Balkanic countries? Turkey?) and mediation with the different stakeholders | December 2020
A34 | Study Visit | 0 | 0 | 0 | [6 empty] |  Organisation of study visit for 6 officials to France  Report of study visit
| Cross cuting issues | [8 empty] | Partners | Delivrables | Period
Component 4 | Improve the evidence-based monitoring and evaluation of social policies
A411 | Establishment of a working group for statistical analysis and projections | [9 empty] | 3-5 specialists of the Ministry and SSA are mobilised; working group officially estabished | June 2019
A412 | Presentation of best practices in monitoring of social benefits (case of TSA) | [9 empty] | simulation of existing data (TSA oand/or other benefits) provided; French experience in intoduction of active measures for TSA beneficiaies presented | May 2019
A413 | Analysis of existing data sources and reporting obligations | [9 empty] | Report on existing data sources | September 2019
A414 | Preparation of a demogaphic model of projection of i) the global population and ii) the beneficiaries of different social benefits and services | [9 empty] | Model of projection for different types of beneficiaries (PWD, Children, TSA); 3 thematic studues are devemoped | December 2019
A415 | Development of M&E guidelines for social policies | [9 empty] | M&E guideliines for social policies | December 2020
Closing conference |  | 20 | 10 | 10 | [7 empty] | December 2020
Closing phase |  | 20 | 15 | 5 | [7 empty] | November - December 2020
490
TOTAL |  | 835 | 345 | 490 | 840 | 345 | 130 | 215 | 445