## ENG - WP
Tasks | Activity | Duration (man/days) | Start Date | End Date | Responsible Individuals | Milestone/Output
Development of a work plan (this document) | Development of a workplan | 1 | 2019-02-01 | 2019-02-01 | Consultant (SS) | Draft work plan
| Discussion of a work plan (with Ministry working group (WG)) and approval |  | 2019-02-15 | 2019-02-15 | Consultant (SS) | Work plan (final)
Review of existing legislative base in Georgia regarding housing (residential, household fund) | Searching for and familizarizing with the legislative and normative documents covering the rights against housing | 2 | 2019-02-02 | 2019-02-14 | Consultant (SS), Assistant (LV) | Review of local legislative base; recommending working terminology
Definition of homeless and vulnerable social groups
Review of existing legilative and normative base and analysis with regard to homeless and vulnerable social groups. Defining strengths and weaknesses
Determining working terminology/developing
Review of international practice/experience of solution of housing problems | General review of foreign experience and assessment of its relevance | 3 | 2019-02-15 | 2019-02-28 | Consultant (SS), Assistant (LV) | Review of foreign experience
Selection of countries acceptable/examplery/suitable for Georgia (presumably 2-3 countries from post-Soviet sphere and/or East European region, e.g. Estonia)
Generalization of foreign experience and outlining acceptable/desirable aspects for Georgia
Defining guiding principles of housing policy in Georgia | Development of guiding principles of housing policy (on the basis of the two previous tasks/activities) | 2 | 2019-03-01 | 2019-03-08 | Consultant (SS), Assistant (LV) | Guiding principles document
Discussion, correction and agreement of the guiding principles with the Ministry working group
Development of housing policy vision | Identification of relevant interest-groups/stakeholders in housing policy sphere (state, civi sectors, professional society) together with the Ministry working group | 10 | 2019-03-09 | 2019-03-29 | Consultant (SS), Assistant (LV), working group | Vision document
Preparation of inquiry of interest-groups and experts (questionnaires/dialogu scenario) and interviewing with participation of working group members (presumably, focus group interviews and deep/qualitative interviews with experts will also be used)
Formulating interview analysis and main directions/principles of vision (in cooperation with the working group)
Development of approaches/principles to be carried out against homeless and vulnerable social groups
Defining financial mechanisms for housing policy implementation | Defining possible financial model (s) of providing homeless and vulnerable social groups with housing | 3 | 2019-03-30 | 2019-04-10 | Consultant (SS), Financial expert (ISET?) | Financial model/approach document
Development of draft housing policy strategy | Writing draft housing policy strategy with working group involvement | 5 | 2019-04-11 | 2019-04-21 | Consultant (SS) | Draft housing policy
| Discussion, correction and final formulation of draft strategy (together with the working group and involvement of relevant institutions) | 1 | 2019-04-22 | 2019-04-30 | Consultant (SS), Assistant (LV)
Deliverable 1: Work plan | [5 empty] | Deliverable #1 submitted
Deliverable 2: Review of legislative base in Georgia | [5 empty] | Deliverable #2 submitted
Deliverable 3: Review of international practice and selected samples (cases) | [5 empty] | Deliverable #3 submitted
Deliverable 4: Drawing up policy development guiding principles for the WG | [5 empty] | Deliverable #4 submitted
Deliverable 5: Stakeholder interview plan/questionnaires | [5 empty] | Deliverable #5 submitted
Delivarable 6: Review-analysis of stakeholder interviews; main findings | [5 empty] | Deliverable #6 submitted
Delivarable 7: Housing policy vision document | [5 empty] | Deliverable #7 submitted
Deliverable 8: Financial models/approaches' document of housing policy | [5 empty] | Deliverable #8 submitted
Deliverable 9: Dpreliminary draft housing policy and strategy document | [5 empty] | Deliverable #9 submitted
Deliverable 10: Final draft/report of housing policy and strategy | [5 empty] | Deliverable #10 submitted
Deliverable 11: Mid-term report |  | presumably 01/04/2019 |  |  |  | Deliverable #11 submitted
Deliverable 12: Bi-weekly reports* | [5 empty] | Deliverable #12 submitted
* I think it will be better to substitute bi-weekly reports with monthly reports (this is less formal against the background of big number of deliverables)

## ISET
Tasks | Activity | Duration (man/days) | Start Date | End Date | Responsible Individuals | Milestone/Output | ISET COMMENTS
Development of a work plan (this document) | Development of a workplan | 1 | 2019-02-01 | 2019-02-01 | Consultant (SS) | Draft work plan
| Discussion of a work plan (with Ministry working group (WG)) and approval |  | 2019-02-15 | 2019-02-15 | Consultant (SS) | Work plan (final)
Review of existing legislative base in Georgia regarding housing (residential, household fund) | Searching for and familizarizing with the legislative and normative documents covering the rights against housing | 2 | 2019-02-02 | 2019-02-14 | Consultant (SS), Assistant (LV) | Review of local legislative base; recommending working terminology | ISET team will review the material produced by SS and LV as soon as it will be ready, ask for clarifications and provide comments/request additional information
Definition of homeless and vulnerable social groups
Review of existing legilative and normative base and analysis with regard to homeless and vulnerable social groups. Defining strengths and weaknesses
Determining working terminology/developing
Review of international practice/experience of solution of housing problems | General review of foreign experience and assessment of its relevance | 3 | 2019-02-15 | 2019-02-28 | Consultant (SS), Assistant (LV) | Review of foreign experience | ISET team will review the bulk of economic (and other relevant) literature over the period 7th Feb - 28th Feb (some additional reading might take place afterwards)
Selection of countries acceptable/examplery/suitable for Georgia (presumably 2-3 countries from post-Soviet sphere and/or East European region, e.g. Estonia)
Generalization of foreign experience and outlining acceptable/desirable aspects for Georgia
Defining guiding principles of housing policy in Georgia | Development of guiding principles of housing policy (on the basis of the two previous tasks/activities) | 2 | 2019-03-01 | 2019-03-08 | Consultant (SS), Assistant (LV) | Guiding principles document | ISET team will participate to the discussion with the Ministry, to identify the guiding principles and - preliminarly - define both the problem and the general objectives of the Ministry. Period 01/03-08/03
Discussion, correction and agreement of the guiding principles with the Ministry working group
Development of housing policy vision | Identification of relevant interest-groups/stakeholders in housing policy sphere (state, civi sectors, professional society) together with the Ministry working group | 10 | 2019-03-09 | 2019-03-29 | Consultant (SS), Assistant (LV), working group | Vision document | ISET team will actively participate to the activities in connection with consultations, conduct data collection, preliminary data analysis and use this phase to finalize the definition of the problem and of the objectives by March 29
Preparation of inquiry of interest-groups and experts (questionnaires/dialogu scenario) and interviewing with participation of working group members (presumably, focus group interviews and deep/qualitative interviews with experts will also be used)
Formulating interview analysis and main directions/principles of vision (in cooperation with the working group)
Development of approaches/principles to be carried out against homeless and vulnerable social groups
Defining financial mechanisms for housing policy implementation | Defining possible financial model (s) of providing homeless and vulnerable social groups with housing | 3 | 2019-03-30 | 2019-04-10 | Consultant (SS), Financial expert (ISET?) | Financial model/approach document | ISET team will lead the process to define the alternatives over the period 30/03-05/04 (and continue data collection activities)
ISET team will be working from 8th of April to the10th of May to provide its quantitative/qualitative analysis. On the 10th there will be a workshop for a presentation of the results. We suggest the Development of the draft housing policy strategy starts only then.
Development of draft housing policy strategy | Writing draft housing policy strategy with working group involvement | 5 | 2019-05-11 | 2019-05-21 | Consultant (SS) | Draft housing policy | ISET team incorporates the feedback and performs additional analysis as agreed during the workshop, providing the data to the Consultant. ISET team finalizes its background paper by the 24th of May. Ministry personnel finalizes the RIA report (under ISET team's supervision) by the 7th of June.
| Discussion, correction and final formulation of draft strategy (together with the working group and involvement of relevant institutions) | 1 | 2019-05-22 | 2019-05-31 | Consultant (SS), Assistant (LV)
Deliverable 1: Work plan | [5 empty] | Deliverable #1 submitted
Deliverable 2: Review of legislative base in Georgia | [5 empty] | Deliverable #2 submitted
Deliverable 3: Review of international practice and selected samples (cases) | [5 empty] | Deliverable #3 submitted
Deliverable 4: Drawing up policy development guiding principles for the WG | [5 empty] | Deliverable #4 submitted
Deliverable 5: Stakeholder interview plan/questionnaires | [5 empty] | Deliverable #5 submitted
Delivarable 6: Review-analysis of stakeholder interviews; main findings | [5 empty] | Deliverable #6 submitted
Delivarable 7: Housing policy vision document | [5 empty] | Deliverable #7 submitted
Deliverable 8: Financial models/approaches' document of housing policy | [5 empty] | Deliverable #8 submitted
Deliverable 9: Dpreliminary draft housing policy and strategy document | [5 empty] | Deliverable #9 submitted
Deliverable 10: Final draft/report of housing policy and strategy | [5 empty] | Deliverable #10 submitted
Deliverable 11: Mid-term report |  | presumably 01/04/2019 |  |  |  | Deliverable #11 submitted
Deliverable 12: Bi-weekly reports* | [5 empty] | Deliverable #12 submitted
* I think it will be better to substitute bi-weekly reports with monthly reports (this is less formal against the background of big number of deliverables)

## Geo - WP
შესასრულებელი სამუშაოები | აქტივობა | ხანგრძლივობა (კაც/დღე) | დაწყება | დასრულება | პასუხისმგებელი პირი | შედეგი
Deliverable 1: | [5 empty] | Deliverable #1 წარმოდგენილია
Deliverable 2: | [5 empty] | Deliverable #2 წარმოდგენილია
Deliverable 3: | [5 empty] | Deliverable #3 წარმოდგენილია
Deliverable 4: | [5 empty] | Deliverable #4 წარმოდგენილია
Deliverable 5: | [5 empty] | Deliverable #5 წარმოდგენილია
Delivarable 6: | [5 empty] | Deliverable #6 წარმოდგენილია
Delivarable 7: | [5 empty] | Deliverable #7 წარმოდგენილია
Deliverable 8: | [5 empty] | Deliverable #8 წარმოდგენილია
Deliverable 9: | [5 empty] | Deliverable #9 წარმოდგენილია
Deliverable 10: | [5 empty] | Deliverable #10 წარმოდგენილია