- Outline of Proposed Interventions

Output 1: The child-friendly city initiative is better understood and conceptualized in targeted areas

Activity 1.1: Awareness raising on the child-friendly city initiative

Together with local partners, UNICEF will develop and carry out an awareness raising campaign to raise awareness, improve the understanding and mobilize support among key community representatives, service providers, professionals, parents, youth and children, as well as the wider community on the CFCI and the positive impact it would have on realization of child rights and the general livability in their city/area. Awareness will also be raised about the various elements of the CFCI, including violence against children, positive parenting, child participation, youth development etc.

Activity 1.2: Conceptualization of the child-friendly approach

In Georgia proper, UNICEF will support the selected municipalities in understanding and conceptualizing the CFCI approaches and their role in the development and provision of the decentralized social services and social programs within the exclusive as well as delegated rights as per the Code on the Rights of the Child and the decentralization strategy. UNICEF will support the select municipalities to develop and apply the methodology for a needs assessment of the capacities at the municipality level to be able to respond to the framework of the decentralization strategy.  Work in Georgia will be largely based on the newly adopted Code on the Rights of the Child and the roles of the local municipalities as defined in the Code.

Output 2: Local capacities to apply the CFCI approach are strengthened

Activity 2.1: Needs assessment and local strategy/action plan development

UNICEF will support the development and application of the methodology for the needs assessment of children, young people and vulnerable families within each municipality.

In Georgia proper UNICEF will support the targeted municipalities in developing local strategies and action plans based on the findings of the needs assessment and will develop a training programme focused on management, provision and monitoring of social services and the children and family programmes at municipal level defined by the Code on the Rights of the Child. UNICEF will deliver training in the target municipalities. While doing that, UNICEF will also work with relevant national authorities in Tbilisi to develop sustainability mechanisms for roll out in other municipalities in the country. UNICEF will also support capacity building on Public Finance for Children (PF4C) in the targeted municipalities, including program budgeting for effective allocation and use of resources.

Activity 2.2: Capacity building and technical assistance for relevant local stakeholders in selected fields

A capacity building programme will be developed for local stakeholders in relevant fields in Georgia proper. The specific stakeholders and areas of capacity building will depend on the results of the needs assessment and thus might vary between municipalities. The target groups will include as a minimum, and as far as possible in the different communities, municipal officials and other local professionals (e.g. teachers, social workers, healthcare workers, judges, etc.) working in direct contact with children, as well as with service providers, NGOs, parents, youth and children. The target areas will include, as far as possible, planning of local budgets and programmes for children and vulnerable families, as well as provision of child and family support programmes (social, educational, health), various local social services, including preschools, health, WASH, services for children with disabilities, multi-disciplinary approach to child protection, etc.

UNICEF will support development of a concept of a minimum package of social services/benefits to be delivered at the municipal level. This will include clearly defining the main types of regular and one-time allowances, community-based services, family-based and alternative care services, together with the list of documents and eligibility criteria that are required to receive such assistance.

Furthermore, the capacity of non-governmental service providers will be strengthened to maintain quality of services in their areas of work, coordination on local level, as well as between local and central levels, people and assets management, application of child-friendly and rights-based approaches etc.

Activity 2.3: Development of a social protection and social services monitoring system and improved coordination at national and municipal levels

While municipalities provide certain health and social assistance benefits to the population in form of direct financial aid, indirect financial aid and services, it is often difficult for them to identify recipients of social benefits at the municipal level. This causes duplication in receipt of different benefits at national and local levels, as well as gaps in coverage for other potential beneficiaries. Therefore, UNICEF will support the selected municipalities in Georgia proper in developing an information management system for social programmes through standardizing data collection and reporting; standardizing indicators that should be derived from such information management system, as well as developing the standard analytical tools for further analysis. The information management system will allow the central and municipal authorities to receive, process, and analyze data on preschool education, WASH conditions in preschools, healthcare and social assistance programs in a more efficient, accurate, and timely manner and thus identify beneficiary groups and categories, facilitate financial and budgetary decision-making, and improve accountability and governance.

Activity 2.4: Creation of child-friendly spaces and services

The Code on the Rights of the Child requires application of a child-friendly approach for all children participating in judicial and administrative proceedings. The Code also stipulates that children will be provided with free legal aid by the Legal Aid Service. UNICEF will provide training, technical assistance and materials to local offices of the Legal Aid Service to understand the provisions of the Code and child-friendly justice. Support will be provided for outreach to most vulnerable children and informational sessions on child rights and mechanisms for obtaining justice in cases of infringements. UNICEF will also work with the relevant partners in the courts in Gori, Batumi and Zugdidi cities.  Child sensitive and age-appropriate internal guidelines and methodology for specialized professionals will be developed and staff of relevant agencies will be trained on application of child-friendly approach in the justice system.

Output 3: A supportive environment for children, young people and local communities to participate in local decision-making processes and to demand quality and inclusive services

Activity 3.1: Promoting a supportive environment for participation of children, young people and local communities

UNICEF will provide technical assistance to municipalities in influencing harmful social norms and behaviors and engaging the most marginalized communities and groups, including children, youth and adolescents, in the decision-making process, increasing knowledge and demand for quality and inclusive services; as well as adopting healthy and protective behaviors, including parenting, family and community practices.

Through service delivery platforms UNICEF will work with social services (i.e. clinics, health centers, child protection centers, etc.) and social service providers (i.e. community health workers, social workers, preschool educators) to enhance their skills in community engagement and interpersonal communication. At the same time, through community-based platforms, UNICEF will work with faith-based organizations, family and parenting organizations, women’s support groups, youth organizations and support them in raising awareness of the existing services and building their skills in advocacy and social change communication.  In addition, through engagement with adolescent and youth networks, UNICEF will work with children and youth to promote child and adolescent participation across government structures, communities, schools, service providers and families; and to support children and young people in building their skills in advocacy and participation.

As part of its global strategy, UNICEF works with religious communities throughout the world to promote and protect children’s rights. Religious leaders have deep and trusted relationships with their communities and often have strong linkages with the most disadvantaged and vulnerable members. They are well positioned to support the poorest, most vulnerable and hard to reach children and families. UNICEF Georgia initiated cooperation with the Orthodox Church and Administration of All Muslims of Georgia and conducted various workshops on children’s rights for the religious leaders in 2019. As a continuation of this initiative, UNICEF will partner with the religious organizations in Batumi, Zugdidi and Gori and conduct seminars on children’s rights for the religious leaders of the respective cities. Workshops will cover a variety of topics related to situation of children in Georgia, international and national legal framework, existing mechanisms, and will aim to strengthen the role of religious leaders in promotion and protection of child rights.

In Georgia proper, UNICEF will also support the Public Defender’s Office to engage with stakeholders and children from pilot municipalities to share results from child rights monitoring, recommendations to local authorities and reach out to children to increase their awareness on child rights and the role of PDO.