Skills for Jobs Programme 2020 indicator 2.2 and their possible fulfilment by the Ministry of IDPs, Labour, Health and Social Affairs of Georgia and State Employment Support Agency.

Indicator number 2.2 (Number of job intermediations provided by employment offices nationwide) refers to the number of jobseeker beneficiaries who received support from SESA to find a job. Target for full achievement was determined as “at least 10% increase in the total number of job intermediations provided by  SESA offices nationwide compared to the baseline of 2017”, while partial achievement was- at least 7% increase in the total number of job intermediations provided by SESA

SESA i.e. the State Employment Support Agency was established in October 2019 and started operation on January 1, 2020. In order for the Agency to be operational, work on institutional and human resources development started in January and vacancies were announced in February. In the midst of the process, the world was hit by the outbreak of COVID-19 i.e. novel coronavirus. Due to the said pandemics, the Governments of the countries use quarantines to stop spread of the disease that is highly contagious. Georgia was not an exception and state institutions started work remotely.

Considering the above-mentioned situation, all the work described above was suspended for the period of the state of emergency. Currently, the Ministry and accordingly SESA are working in an emergency mode within the Anti-Crisis Action Plan of the Government of Georgia. The plan envisages temporary unemployment benefits for people who were affected by the crisis. The program targets officially employed workers who lost their jobs/got unpaid leave, TSA beneficiaries, PWDs and self-employed workers who lost their income.

Possibility of achieving a full target is highly unlikely considering the reasons, such as economic situation in Georgia, preparedness of the business and related other reasons despite the Agency’s readiness.  The Ministry considers important and necessary to make a reservation and preliminary inform the Commission that fulfilment of the indicator does not solely depend on the work of the Agency. In this case, we do commit to start work and achieving the target next year.